## A1 register
A1 Obligations and compliance register — WORKING DRAFT
WORKING DRAFT, full register: 206 rows (review status: proposed 206; amendment ops: proposed 65). Rows and ops count as accepted only with a named person's decision bound to their current content. Image readings pending the owner's review: VOL-II-p3-r1, VOL-IV-p6-r1. Validated state: ADD-03.
Requirement ID | Clause group | Scope tags | Requirement (summary) | Text as issued (original document; never assembled) | Effective text at the validated state (ASSEMBLED by applying the addenda; not a printed text) | Quoted words relied on | Latest reference for the quoted words (document clause page; amending provision) | Pass/fail or scored | Discipline | Owner (role) | Evidence needed | Status after BASE | Status after ADD-01 | Status after ADD-02 | Status after ADD-03 | Stated consequence (quoted) | Consequence source | Dates (planning reading; all readings in Dates sheet) | Confidence | Image reading status | Interpretation review | Amendment ops review | Evidence chain (original -> ops) | Issues
VOL-I-6.1-01 | VOL-I:6.1 | bid_submission; deadline | Deliver the Proposal to the Authority by the Proposal Due Date and time, at the Appendix 3 address | Proposals shall be received by the Authority not later than 14:00 hours Riyadh time on Thursday 12 November 2026 at the address given in Appendix 3. | Proposals shall be received by the Authority not later than 14:00 hours Riyadh time on Thursday 10 December 2026 at the address given in Appendix 3. | not later than 14:00 hours Riyadh time on Thursday 10 December 2026 | VOL-I 6.1 p3 as amended by ADD-03 2.1 p1 | pass_fail | Bid management | Bid manager | EV-DELIVERY | ACTIVE | AMENDED (ADD-01/2.1) | ACTIVE (as amended by ADD-01/2.1) | AMENDED (ADD-03/2.1) | rejection: "will be rejected unopened and returned to the Bidder" | VOL-I 6.6 p3 | PDD: 2026-12-10 (as_stated) | high: verbatim text-layer clause; the consequence is stated in VOL-I 6.6 | n/a (text layer) | proposed (not reviewed) | ADD-01/2.1: proposed; ADD-03/2.1: proposed | VOL-I:6.1 (VOL-I p3; text layer); ADD-01/2.1 [proposed] <- ADD-01:2.1 (ADD-01 p1); ADD-03/2.1 [proposed] <- ADD-03:2.1 (ADD-03 p1)
VOL-I-5.2-01 | VOL-I:5.2 | clarification; deadline | Submit any clarification requests no later than ten Working Days before the Proposal Due Date | Requests for clarification shall be submitted no later than ten (10) Working Days before the Proposal Due Date. Requests received after that time will not be answered. | Requests for clarification shall be submitted no later than fifteen (15) Working Days before the Proposal Due Date. Requests received after 14:00 Riyadh time on the last day for submission will not be answered. | no later than fifteen (15) Working Days before the Proposal Due Date | VOL-I 5.2 p3 as amended by ADD-03 3.1 p1 | procedural | Bid management | Bid manager | EV-CLARIFICATIONS | ACTIVE | ACTIVE | ACTIVE | AMENDED (ADD-03/3.1, ADD-03/3.2) | lesser consequence: "Requests received after 14:00 Riyadh time on the last day for submission will not be answered." | ADD-03 3.2 p1 (amending VOL-I 5.2) | CLARIFICATION-CUTOFF: 2026-11-19 (stated_date_excluded) | high: backward Working Day counting is defined in VOL-I 2.4 | n/a (text layer) | proposed (not reviewed) | ADD-03/3.1: proposed; ADD-03/3.2: proposed | VOL-I:5.2 (VOL-I p3; text layer); ADD-03/3.1 [proposed] <- ADD-03:3.1 (ADD-03 p1); ADD-03/3.2 [proposed] <- ADD-03:3.2 (ADD-03 p1)
VOL-I-6.3-01 | VOL-I:6.3 | envelope_A; bid_security; validity | Bid Bond valid for 180 days from the Proposal Due Date (extendable on demand) | Envelope A shall be accompanied by a Bid Bond which shall remain valid for one hundred and eighty (180) days from the Proposal Due Date and shall be extended on demand where the Authority extends the period of Proposal validity. | Envelope A shall be accompanied by a Bid Bond which shall remain valid for one hundred and eighty (180) days from the Proposal Due Date and shall be extended on demand where the Authority extends the period of Proposal validity. | valid for one hundred and eighty (180) days from the Proposal Due Date | VOL-I 6.3 p3 | pass_fail | Commercial | Commercial lead | EV-BID-BOND | ACTIVE | ACTIVE | ACTIVE | ACTIVE — STALE | none stated in the documents |  | BID-BOND-VALIDITY: 2027-06-08 (day0) | medium: no consequence is stated; whether day 0 or day 1 is the PDD is not stated (two readings) | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:6.3 (VOL-I p3; text layer) | I-NO-CONSEQUENCE
VOL-I-6.4-01 | VOL-I:6.4 | envelope_A; bid_security | Bid Bond of SAR 4,500,000, unconditional and payable on first written demand | The Bid Bond shall be in the amount of SAR 4,500,000 (four million five hundred thousand Saudi Riyals), shall be unconditional and payable on first written demand, and shall be issued by a bank licensed to operate in the Kingdom holding a long-term credit rating of not lower than A- from a recognised international rating agency. | The Bid Bond shall be in the amount of SAR 6,000,000 (six million Saudi Riyals), shall be unconditional and payable on first written demand, and shall be issued by a bank licensed to operate in the Kingdom holding a long-term credit rating of not lower than A- from a recognised international rating agency. | in the amount of SAR 6,000,000 | VOL-I 6.4 p3 as amended by ADD-03 4.1 p1 | pass_fail | Commercial | Commercial lead | EV-BID-BOND | ACTIVE | ACTIVE | ACTIVE | AMENDED (ADD-03/4.1) | none stated in the documents |  |  | high: verbatim; confirmed by ADD-02 Q8 (no consequence stated) | n/a (text layer) | proposed (not reviewed) | ADD-03/4.1: proposed | VOL-I:6.4 (VOL-I p3; text layer); ADD-03/4.1 [proposed] <- ADD-03:4.1 (ADD-03 p1) | I-NO-CONSEQUENCE
VOL-I-6.4-02 | VOL-I:6.4 | envelope_A; bid_security | Bid Bond issued by a bank licensed in the Kingdom with a long-term rating not lower than A- | The Bid Bond shall be in the amount of SAR 4,500,000 (four million five hundred thousand Saudi Riyals), shall be unconditional and payable on first written demand, and shall be issued by a bank licensed to operate in the Kingdom holding a long-term credit rating of not lower than A- from a recognised international rating agency. | The Bid Bond shall be in the amount of SAR 6,000,000 (six million Saudi Riyals), shall be unconditional and payable on first written demand, and shall be issued by a bank licensed to operate in the Kingdom holding a long-term credit rating of not lower than A- from a recognised international rating agency. | issued by a bank licensed to operate in the Kingdom holding a long-term credit rating of not lower than A- | VOL-I 6.4 p3 as amended by ADD-03 4.1 p1 | pass_fail | Commercial | Commercial lead | EV-BID-BOND | ACTIVE | ACTIVE | ACTIVE | AMENDED (ADD-03/4.1) — STALE | none stated in the documents |  |  | high: verbatim; clarified by ADD-01 Q3 (no consequence stated) | n/a (text layer) | proposed (not reviewed) | ADD-03/4.1: proposed | VOL-I:6.4 (VOL-I p3; text layer); ADD-03/4.1 [proposed] <- ADD-03:4.1 (ADD-03 p1) | I-NO-CONSEQUENCE
VOL-I-7.1-01 | VOL-I:7.1 | validity | Proposal open for acceptance for 150 days from the Proposal Due Date | Each Proposal shall remain open for acceptance for one hundred and fifty (150) days from the Proposal Due Date. | Each Proposal shall remain open for acceptance for one hundred and fifty (150) days from the Proposal Due Date. | one hundred and fifty (150) days from the Proposal Due Date | VOL-I 7.1 p4 | pass_fail | Commercial | Commercial lead | EV-FORM-4A | ACTIVE | ACTIVE | ACTIVE | ACTIVE — STALE | none stated in the documents |  | PROPOSAL-VALIDITY: 2027-05-09 (day0) | medium: no consequence stated; day 0 / day 1 not stated | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:7.1 (VOL-I p4; text layer) | I-NO-CONSEQUENCE
VOL-I-8.3-01 | VOL-I:8.3 | qualification; envelope_A | EPC Contractor ISO 9001:2015 certificate, current as at the Proposal Due Date, copy in Envelope A | The proposed EPC Contractor shall hold a valid ISO 9001:2015 quality management certificate, current as at the Proposal Due Date, issued by an accredited certification body. A copy of the certificate shall be submitted with Envelope A. | The proposed EPC Contractor shall hold a valid ISO 9001:2015 quality management certificate, current as at the Proposal Due Date, issued by an accredited certification body. A copy of the certificate shall be submitted with Envelope A. | current as at the Proposal Due Date | VOL-I 8.3 p4 | pass_fail | Technical | Technical lead | EV-ISO | ACTIVE | ACTIVE — STALE | ACTIVE — STALE | ACTIVE — STALE | none stated in the documents |  | ISO-CURRENT-AT: 2026-12-10 (as_stated) | medium: no consequence stated; this period is not named in ADD-01 §2.2 (whose list is non-exhaustive) | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:8.3 (VOL-I p4; text layer) | I-NO-CONSEQUENCE
VOL-I-8.5-01 | VOL-I:8.5 | qualification; references | Evidence two reference sewage treatment plants of at least the capacity footnote 12 states, each in commercial operation within the ten years before the Proposal Due Date | For the avoidance of doubt, a Bidder that does not evidence at least two (2) reference sewage treatment plants, each of nominal capacity not less than 80,000 m³/day and each having achieved commercial operation within the ten (10) years preceding the Proposal Due Date, shall be rejected without further evaluation. | For the avoidance of doubt, a Bidder that does not evidence at least two (2) reference sewage treatment plants, each of nominal capacity not less than 60,000 m3/day and each having achieved commercial operation within the ten (10) years preceding the Proposal Due Date, shall be rejected without further evaluation. | at least two (2) reference sewage treatment plants, each of nominal capacity not less than 60,000 | VOL-I 8.5#fn12 p4 as amended by ADD-03 6.1 p1 | pass_fail | Technical | Technical lead | EV-REFERENCES | ACTIVE | ACTIVE | ACTIVE | AMENDED (ADD-03/6.1) | rejection: "shall be rejected without further evaluation" | VOL-I 8.5#fn12 p4 as amended by ADD-03 6.1 p1 | REFERENCE-LOOKBACK: 2016-12-11 (boundary_exclusive) | high: verbatim footnote; boundary of the look-back not stated (two readings) | n/a (text layer) | proposed (not reviewed) | ADD-03/6.1: proposed | VOL-I:8.5#fn12 (VOL-I p4; text layer); ADD-03/6.1 [proposed] <- ADD-03:6.1 (ADD-03 p1)
VOL-I-8.6-01 | VOL-I:8.6 | qualification; envelope_A | Local Content Certificate from the competent authority showing the minimum construction-phase local content ratio | The Bidder shall submit a Local Content Certificate issued by the competent authority evidencing a local content ratio of not less than thirty per cent (30%) for the construction phase. | The Bidder shall submit a Local Content Certificate issued by the competent authority evidencing a local content ratio of not less than thirty per cent (30%) for the construction phase. Failure to submit the certificate shall render the Proposal non-responsive. | not less than thirty per cent (30%) for the construction phase | VOL-I 8.6 p4 as amended by ADD-03 7.1 p2 | pass_fail | Commercial | Commercial lead | EV-LCC | ACTIVE | DELETED (ADD-01/4.1) | REINSTATED-AMENDED (ADD-02/9.1) | AMENDED (ADD-03/7.1) | non-responsive: "Failure to submit the certificate shall render the Proposal non-responsive." | ADD-02 9.1 p3 (reinstating VOL-I 8.6) |  | high: verbatim at every stage; the issuing authority is not named and the lead time is unknown | n/a (text layer) | proposed (not reviewed) | ADD-01/4.1: proposed; ADD-02/9.1: proposed; ADD-03/7.1: proposed | VOL-I:8.6 (VOL-I p4; text layer); ADD-01/4.1 [proposed] <- ADD-01:4.1 (ADD-01 p1); ADD-02/9.1 [proposed] <- ADD-02:9.1 (ADD-02 p3); ADD-03/7.1 [proposed] <- ADD-03:7.1 (ADD-03 p2) | I-LCC-ISSUER
VOL-I-5.4-01 | VOL-I:5.4 | pre_bid; fixed_date | Be represented at the Pre-Bid Conference on 30 September 2026 | A Pre-Bid Conference will be held on Wednesday 30 September 2026 at 10:00 Riyadh time at the Authority's offices. Attendance by at least one authorised representative of each Bidder is mandatory. A Bidder that is not represented at the Pre-Bid Conference shall be disqualified. | A Pre-Bid Conference will be held on Wednesday 30 September 2026 at 10:00 Riyadh time at the Authority's offices. Attendance by at least one authorised representative of each Bidder is mandatory. A Bidder that is not represented at the Pre-Bid Conference shall be disqualified. | Attendance by at least one authorised representative of each Bidder is mandatory. | VOL-I 5.4 p3 | pass_fail | Bid management | Bid manager | EV-ATTENDANCE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | disqualification: "A Bidder that is not represented at the Pre-Bid Conference shall be disqualified." | VOL-I 5.4 p3 | PRE-BID: 2026-09-30 (as_stated) | high: verbatim; a fixed past date (does not move with the PDD); attendance is a bidder fact | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:5.4 (VOL-I p3; text layer) | I-BIDDER-FACTS
ADD-01-3.1-01 | ADD-01:3.1 | pre_bid; deadline | If the attendance record is wrong, notify the Authority within five Working Days of Addendum No. 1 | The attendance record is held by the Authority. A Bidder that considers its attendance to have been incorrectly recorded shall notify the Authority through the Portal within five (5) Working Days of this Addendum. | The attendance record is held by the Authority. A Bidder that considers its attendance to have been incorrectly recorded shall notify the Authority through the Portal within five (5) Working Days of this Addendum. | shall notify the Authority through the Portal within five (5) Working Days of this Addendum | ADD-01 3.1 p1 | procedural | Bid management | Bid manager | EV-ATTENDANCE | NOT ISSUED | NEW | ACTIVE | ACTIVE | none stated in the documents |  | ATTENDANCE-NOTICE: 2026-10-14 (event_day_counted) | medium: forward Working Day counting is not defined (two readings) | n/a (text layer) | proposed (not reviewed) | n/a | ADD-01:3.1 (ADD-01 p1; text layer)
VOL-I-9.3-01 | VOL-I:9.3 | envelope_A; forms | Form 4-A signed by a person holding a notarised Power of Attorney from the lead member | Form 4-A shall be signed by a person holding a notarised Power of Attorney from the lead member of the Bidder. An unsigned or improperly executed Form 4-A shall render the Proposal non-responsive. | Form 4-A shall be signed by a person holding a notarised Power of Attorney from the lead member of the Bidder. An unsigned or improperly executed Form 4-A shall render the Proposal non-responsive. | Form 4-A shall be signed by a person holding a notarised Power of Attorney from the lead member of the Bidder. | VOL-I 9.3 p5 | pass_fail | Legal | Legal counsel | EV-FORM-4A; EV-POA | ACTIVE | ACTIVE | ACTIVE | ACTIVE | non-responsive: "An unsigned or improperly executed Form 4-A shall render the Proposal non-responsive." | VOL-I 9.3 p5 |  | high: verbatim | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:9.3 (VOL-I p5; text layer) | I-F4A-FIELDS
VOL-IV-F4A-01 | VOL-IV:F4-A | forms; printed_date | Use the Form 4-A as issued (reissued by ADD-01 App A: 'Bidders shall use this version'); its printed Proposal Due Date | Proposal Due Date: 12 November 2026, 14:00 Riyadh time | Proposal Due Date: 10 December 2026, 14:00 Riyadh time | Proposal Due Date: 12 November 2026, 14:00 Riyadh time | ADD-01 AppA/proposal-due-date p3 (replacing VOL-IV F4-A/proposal-due-date p3, ADD-01/AppA/para1) | procedural | Legal | Legal counsel | EV-FORM-4A | ACTIVE | AMENDED (ADD-01/AppA/para1) | ACTIVE (as amended by ADD-01/AppA/para1) | AMENDED (ADD-03/2.3) — STALE | none stated in the documents |  |  | high: verbatim printed field; the conflict with the amended PDD is shown, not resolved | n/a (text layer) | proposed (not reviewed) | ADD-01/AppA/para1: proposed; ADD-03/2.3: proposed | VOL-IV:F4-A/proposal-due-date (VOL-IV p3; text layer); ADD-01/AppA/para1 [proposed] <- ADD-01:AppA/para1 (ADD-01 p3); ADD-03/2.3 [proposed] <- ADD-03:2.3 (ADD-03 p1) | I-F4A-FIELDS
VOL-I-9.4-01 | VOL-I:9.4 | envelope_A; forms; arabic | Form 4-C completed in Arabic, signed and stamped by an authorised signatory of each member | Form 4-C shall be completed in the Arabic language, signed and stamped by an authorised signatory of each member of the Bidder. A translation may be attached for convenience but the Arabic text shall govern. Failure to submit a complete and properly executed Form 4-C for each member shall render the Proposal non-responsive. | Form 4-C shall be completed in the Arabic language, signed and stamped by an authorised signatory of each member of the Bidder. A translation may be attached for convenience but the Arabic text shall govern. Failure to submit a complete and properly executed Form 4-C for each member shall render the Proposal non-responsive. | Form 4-C shall be completed in the Arabic language, signed and stamped by an authorised signatory of each member of the Bidder. | VOL-I 9.4 p5 | pass_fail | Legal | Legal counsel | EV-FORM-4C | ACTIVE | ACTIVE | ACTIVE | ACTIVE — STALE | non-responsive: "Failure to submit a complete and properly executed Form 4-C for each member shall render the Proposal non-responsive." | VOL-I 9.4 p5 |  | high: text-layer clause; the form itself is an image whose reading is pending | pending | proposed (not reviewed) | n/a | VOL-I:9.4 (VOL-I p5; text layer) | I-BIDDER-FACTS
VOL-IV-F4C-04 | VOL-IV:F4-C | forms; arabic; declaration | Form 4-C declaration 4 (Arabic only): all information in the Proposal is true and complete | رابعاً: أن جميع المعلومات المقدمة في هذا العرض صحيحة وكاملة، وندرك أن أي بيان غير صحيح يؤدي إلى استبعاد العرض. | رابعاً: أن جميع المعلومات المقدمة في هذا العرض صحيحة وكاملة، وندرك أن أي بيان غير صحيح يؤدي إلى استبعاد العرض. | أن جميع المعلومات المقدمة في هذا العرض صحيحة وكاملة | VOL-IV F4-C/image/decl4 p6 | pass_fail | Legal | Legal counsel | EV-FORM-4C | ACTIVE | ACTIVE | ACTIVE | ACTIVE | exclusion: "يؤدي إلى استبعاد العرض" (proposed translation, not reviewed: 'leads to the exclusion of the proposal') | VOL-IV F4-C/image/decl4 p6 |  | medium: from an image reading still pending the owner's review; Arabic-only consequence | pending | proposed (not reviewed) | n/a | VOL-IV:F4-C/image/decl4 (VOL-IV p6; image reading) | I-READING-F4C
VOL-IV-F4C-N1 | VOL-IV:F4-C | forms; arabic | Form 4-C note (Arabic): submit the form in Arabic for each consortium member | ملاحظة: يجب تقديم هذا النموذج باللغة العربية عن كل عضو من أعضاء الائتلاف. عدم تقديمه كاملاً يجعل العرض غير مستجيب. | ملاحظة: يجب تقديم هذا النموذج باللغة العربية عن كل عضو من أعضاء الائتلاف. عدم تقديمه كاملاً يجعل العرض غير مستجيب. | يجب تقديم هذا النموذج باللغة العربية عن كل عضو من أعضاء الائتلاف | VOL-IV F4-C/image/note p6 | pass_fail | Legal | Legal counsel | EV-FORM-4C | ACTIVE | ACTIVE | ACTIVE | ACTIVE | non-responsive: "عدم تقديمه كاملاً يجعل العرض غير مستجيب" (proposed translation, not reviewed: 'failure to submit it complete renders the proposal non-responsive') | VOL-IV F4-C/image/note p6 |  | medium: from an image reading still pending the owner's review | pending | proposed (not reviewed) | n/a | VOL-IV:F4-C/image/note (VOL-IV p6; image reading) | I-READING-F4C
ADD-02-7.2-01 | ADD-02:7 | envelope_A; forms; new_in_addendum | Complete and submit the new Form 4-G (cybersecurity undertaking) with Envelope A | Form 4-G shall be completed and submitted with Envelope A. Failure to submit Form 4-G shall render the Proposal non-responsive. | Form 4-G shall be completed and submitted with Envelope A. Failure to submit Form 4-G shall render the Proposal non-responsive. | Form 4-G shall be completed and submitted with Envelope A. | ADD-02 7.2 p3 | pass_fail | Technical | Technical lead | EV-FORM-4G | NOT ISSUED | NOT ISSUED | NEW | ACTIVE — STALE | non-responsive: "Failure to submit Form 4-G shall render the Proposal non-responsive." | ADD-02 7.2 p3 |  | high: verbatim; the re-lettering of the Envelope A list after item (e) is not stated | n/a (text layer) | proposed (not reviewed) | n/a | ADD-02:7.2 (ADD-02 p3; text layer) | I-F4G-LETTERING
ADD-02-F4G-01 | ADD-02:F4-G | forms; post_award; new_in_addendum | Form 4-G undertakings 1-6, each confirmed Yes or No (3-6 are new obligations not in VOL-II 6) | Item: 3 ¦ Undertaking: A named accountable security officer will be appointed for the concession period. ¦ Confirmed: Yes / No | Item: 3 ¦ Undertaking: A named accountable security officer will be appointed for the concession period. ¦ Confirmed: Yes / No | A named accountable security officer will be appointed for the concession period. | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/3) | contractual_post_award | Technical | Technical lead | EV-FORM-4G | NOT ISSUED | NOT ISSUED | NEW | ACTIVE (as amended by ADD-02/7.1) | none stated in the documents |  |  | medium: verbatim; the effect of answering 'No' is not stated | n/a (text layer) | proposed (not reviewed) | ADD-02/7.1: proposed | ADD-02:F4-G/T1/3 (ADD-02 p3; text layer); ADD-02/7.1 [proposed] <- ADD-02:7.1 (ADD-02 p3) | I-F4G-NO
VOL-II-4.4-01 | VOL-II:4.4 | technical_design; repeated_wording | Standby power sized to carry the inlet works, disinfection and effluent pumping for the stated duration | Standby provision for all rotating equipment shall be N+1. Standby power shall be sized to carry the full inlet works, the disinfection stage and the effluent pumping station for not less than seventy-two (72) hours. | Standby provision for all rotating equipment shall be N+1. Standby power shall be sized to carry the full inlet works, the disinfection stage and the effluent pumping station for not less than ninety-six (96) hours. | for not less than ninety-six (96) hours | VOL-II 4.4 p4 as amended by ADD-02 4.1 p1 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | AMENDED (ADD-02/4.1) | ACTIVE (as amended by ADD-02/4.1) | none stated in the documents |  |  | high: verbatim; how non-compliance in the technical proposal is treated is not stated | n/a (text layer) | proposed (not reviewed) | ADD-02/4.1: proposed | VOL-II:4.4 (VOL-II p4; text layer); ADD-02/4.1 [proposed] <- ADD-02:4.1 (ADD-02 p1)
VOL-V-31.3-01 | VOL-V:31.3 | contract; post_award; repeated_wording | Cure period of 72 hours for an Unavailability Event under VOL-V 31.1(c) (unchanged by the addenda) | A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a) and of seventy-two (72) hours to an event under Clause 31.1(c). No cure period applies to an event under Clause 31.1(b). | A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a) and of seventy-two (72) hours to an event under Clause 31.1(c). No cure period applies to an event under Clause 31.1(b). | of seventy-two (72) hours to an event under Clause 31.1(c) | VOL-V 31.3 p3 | contractual_post_award | Legal | Legal counsel |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim; must not change when VOL-II 4.4's identical words do | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:31.3 (VOL-V p3; text layer)
VOL-I-11.2-01 | VOL-I:11.2 | evaluation; weighting; repeated_wording | Combined score weighting, technical / commercial | Proposals reaching stage (iii) will be ranked on a combined score calculated on a weighting of sixty per cent (60%) technical and forty per cent (40%) commercial. | Proposals reaching stage (iii) will be ranked on a combined score calculated on a weighting of sixty-five per cent (65%) technical and thirty-five per cent (35%) commercial. | sixty-five per cent (65%) technical and thirty-five per cent (35%) commercial | ADD-02 T1-1-rev/note(2) p1 (amending VOL-I 11.2) | scored | Bid management | Bid manager | none: an evaluation rule the Authority applies; what it weighs are the Technical Proposal and the commercial proposal, required by their own rows | ACTIVE | ACTIVE | AMENDED (ADD-02/T1-1-rev/note(2)) | ACTIVE (as amended by ADD-02/T1-1-rev/note(2)) | none stated in the documents |  |  | medium: the amendment is in a small-print table note and does not quote the words it replaces | n/a (text layer) | proposed (not reviewed) | ADD-02/T1-1-rev/note(2): proposed | VOL-I:11.2 (VOL-I p5; text layer); ADD-02/T1-1-rev/note(2) [proposed] <- ADD-02:T1-1-rev/note(2) (ADD-02 p1)
VOL-V-29.2-01 | VOL-V:29.2 | contract; payment; repeated_wording | Availability Payment indexation: 60% indexed to CPI, 40% fixed (unchanged by the addenda) | The Availability Payment shall be indexed annually in accordance with Schedule 9, with sixty per cent (60%) of the payment indexed to the published consumer price index and forty per cent (40%) remaining fixed. | The Availability Payment shall be indexed annually in accordance with Schedule 9, with sixty per cent (60%) of the payment indexed to the published consumer price index and forty per cent (40%) remaining fixed. | sixty per cent (60%) of the payment indexed to the published consumer price index and forty per cent (40%) remaining fixed | VOL-V 29.2 p3 | contractual_post_award | Commercial | Commercial lead |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim; must not change when VOL-I 11.2's similar words do | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:29.2 (VOL-V p3; text layer)
VOL-I-11.3-01 | VOL-I:11.3 | evaluation; threshold | Technical score of at least 70 out of 100 to proceed to commercial evaluation | A Proposal scoring less than seventy (70) marks out of one hundred (100) at the technical evaluation shall not proceed to commercial evaluation and its Envelope B shall be returned unopened. | A Proposal scoring less than seventy (70) marks out of one hundred (100) at the technical evaluation shall not proceed to commercial evaluation and its Envelope B shall be returned unopened. | scoring less than seventy (70) marks out of one hundred (100) | VOL-I 11.3 p5 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | Envelope B returned unopened: "its Envelope B shall be returned unopened" | VOL-I 11.3 p5 |  | high: verbatim; confirmed unchanged by ADD-02 note (1) | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:11.3 (VOL-I p5; text layer)
VOL-I-T1-1-B | VOL-I:T1-1 | evaluation; weighting | Marks available for criterion B (construction methodology, programme and interfaces) | Ref: B ¦ Criterion: Construction methodology, programme and interface management ¦ Marks: 20 | Ref: B ¦ Criterion: Construction methodology, programme and interface management ¦ Marks: 15 | Marks: 15 | ADD-02 T1-1-rev/B p1 (replacing VOL-I T1-1/B p6, ADD-02/3.1) | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | AMENDED (ADD-02/3.1) | ACTIVE (as amended by ADD-02/3.1) | none stated in the documents |  |  | high: verbatim table rows | n/a (text layer) | proposed (not reviewed) | ADD-02/3.1: proposed | VOL-I:T1-1/B (VOL-I p6; text layer); ADD-02/3.1 [proposed] <- ADD-02:3.1 (ADD-02 p1)
VOL-I-T1-1-D | VOL-I:T1-1 | evaluation; weighting | Marks available for criterion D (environmental and social management) | Ref: D ¦ Criterion: Environmental and social management ¦ Marks: 15 | Ref: D ¦ Criterion: Environmental and social management ¦ Marks: 20 | Marks: 20 | ADD-02 T1-1-rev/D p1 (replacing VOL-I T1-1/D p6, ADD-02/3.1) | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | AMENDED (ADD-02/3.1) | ACTIVE (as amended by ADD-02/3.1) | none stated in the documents |  |  | high: verbatim table rows | n/a (text layer) | proposed (not reviewed) | ADD-02/3.1: proposed | VOL-I:T1-1/D (VOL-I p6; text layer); ADD-02/3.1 [proposed] <- ADD-02:3.1 (ADD-02 p1)
VOL-II-T2-4-TN | VOL-II:T2-4 | technical_design; effluent; image | Treated effluent Total Nitrogen (TN): value shown in Table 2-4, unit and basis of assessment | Parameter: Total Nitrogen (TN) ¦ Unit: mg/l ¦ Limit: 5 ¦ Basis of assessment: 30-day rolling average | Parameter: Total Nitrogen (TN) ¦ Unit: mg/l ¦ Limit: 3 ¦ Basis of assessment: 30-day rolling average | Limit: 3 | VOL-II T2-4/TN p3 as amended by ADD-02 5.1 p1 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | AMENDED (ADD-02/5.1) | ACTIVE (as amended by ADD-02/5.1) | none stated in the documents |  |  | medium: base value and basis come from an image reading still pending review; the Permit is not supplied | pending | proposed (not reviewed) | ADD-02/5.1: proposed | VOL-II:T2-4/TN (VOL-II p3; image reading); ADD-02/5.1 [proposed] <- ADD-02:5.1 (ADD-02 p1) | I-PERMIT; I-READING-T24
ADD-03-8.1-01 | VOL-I:10.5 (new; ADD-03 8.1) | financial_proposal; envelope_B; price_cap; new_in_addendum | Quote in Form 4-F an Availability Payment of no more than SAR 210,000,000 per annum (year 1 of operations, excluding VAT) |  | The Availability Payment quoted in Form 4-F shall not exceed SAR 210,000,000 per annum (year 1 of operations, exclusive of value added tax). A Proposal that quotes an Availability Payment exceeding this amount shall be rejected. | The Availability Payment quoted in Form 4-F shall not exceed SAR 210,000,000 per annum (year 1 of operations, exclusive of value added tax). | ADD-03 8.1 p2 (amending VOL-I 10.4+ADD-03) | pass_fail | Commercial | Commercial lead | EV-FORM-4F | NOT ISSUED | NOT ISSUED | NOT ISSUED | NEW | rejection: "A Proposal that quotes an Availability Payment exceeding this amount shall be rejected." | ADD-03 8.1 p2 (amending VOL-I 10.4+ADD-03) |  | high: verbatim; how 'year 1 of operations' relates to the indexed payment profile is for the financial model | n/a (text layer) | proposed (not reviewed) | ADD-03/8.1: proposed | VOL-I:10.4+ADD-03 (VOL-I p2; addendum op); ADD-03/8.1 [proposed] <- ADD-03:8.1 (ADD-03 p2) | I-BLIND-CAP
VOL-IV-F4C-06 | VOL-IV:F4-C | envelope_A; forms; integrity; new_in_addendum | Each member's Form 4-C gives the sixth declaration: no conviction of the member or its directors in the Kingdom for fraud, bribery or corruption in the preceding five years |  | Sixth: that neither the member nor any of its directors has, within the preceding five (5) years, been convicted in the Kingdom of an offence involving fraud, bribery or corruption. | neither the member nor any of its directors has, within the preceding five (5) years, been convicted in the Kingdom of an offence involving fraud, bribery or corruption | ADD-03 12.1 p2 (amending VOL-IV F4-C/image/decl5+ADD-03) | pass_fail | Legal | Legal counsel | EV-FORM-4C | NOT ISSUED | NOT ISSUED | NOT ISSUED | NEW | non-responsive: "Failure to submit a complete and properly executed Form 4-C for each member shall render the Proposal non-responsive." | VOL-I 9.4 p5 | F4C-SIXTH-LOOKBACK: None (unknown_anchor) | medium: verbatim; the language of the declaration and its look-back start (the signing date is assumed) are for a person | n/a (text layer) | proposed (not reviewed) | ADD-03/12.1: proposed | VOL-IV:F4-C/image/decl5+ADD-03 (VOL-IV p2; addendum op); ADD-03/12.1 [proposed] <- ADD-03:12.1 (ADD-03 p2) | I-BLIND-F4C-LANG
ADD-03-11.2-01 | ADD-03:11 | technical_design; hydraulics; new_in_addendum | Hydraulic design (Volume II Section 4) reflects the amended peak hourly flow of 9,000 m3/h (Table 2-6 row 2-6.2) | Bidders shall reflect the amended flow in the hydraulic design submitted under Volume II Section 4. | Bidders shall reflect the amended flow in the hydraulic design submitted under Volume II Section 4. | Bidders shall reflect the amended flow in the hydraulic design submitted under Volume II Section 4. | ADD-03 11.2 p2 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | NOT ISSUED | NOT ISSUED | NOT ISSUED | NEW | none stated in the documents |  |  | high: verbatim | n/a (text layer) | proposed (not reviewed) | n/a | ADD-03:11.2 (ADD-03 p2; text layer) | I-FLOWS
ADD-03-Q17-01 | ADD-03:Q17 | qualification; references; new_in_addendum | Count only reference projects for which the consortium member itself was responsible for design, construction or operation; an affiliate's reference is disregarded | No: 17 ¦ Bidder question: May a consortium member rely on a reference project delivered by its parent company or another affiliate for the purposes of Volume I Clause 8.5? ¦ Authority response: No. Only a reference project for which the consortium member itself was responsible for design, construction or operation will be considered. A reference project of an affiliate will be disregarded. | No: 17 ¦ Bidder question: May a consortium member rely on a reference project delivered by its parent company or another affiliate for the purposes of Volume I Clause 8.5? ¦ Authority response: No. Only a reference project for which the consortium member itself was responsible for design, construction or operation will be considered. A reference project of an affiliate will be disregarded. | Only a reference project for which the consortium member itself was responsible for design, construction or operation will be considered. | ADD-03 Q17 p2 | pass_fail | Technical | Technical lead | EV-REFERENCES | NOT ISSUED | NOT ISSUED | NOT ISSUED | NEW | lesser consequence: "A reference project of an affiliate will be disregarded." | ADD-03 Q17 p2 |  | high: verbatim | n/a (text layer) | proposed (not reviewed) | n/a | ADD-03:Q17 (ADD-03 p2; text layer)
ADD-01-AppA-01 | ADD-01:AppA | envelope_A; forms; addenda_acknowledgement; reissued_form; new_in_addendum | Acknowledge receipt of each Addendum in Form 4-A (reissued form field 'Addenda acknowledged (numbers)') | This Addendum amends the Proposal Due Date, deletes one qualification requirement, amends Volume II Clause 5.3, publishes the minutes of the Pre-Bid Conference, and responds to clarification requests 1 to 6. This Addendum forms part of the RFP Documents and takes precedence in accordance with Volume I Clause 3.2. Bidders shall acknowledge receipt in Form 4-A. All other terms of the RFP Documents remain unchanged. | This Addendum amends the Proposal Due Date, deletes one qualification requirement, amends Volume II Clause 5.3, publishes the minutes of the Pre-Bid Conference, and responds to clarification requests 1 to 6. This Addendum forms part of the RFP Documents and takes precedence in accordance with Volume I Clause 3.2. Bidders shall acknowledge receipt in Form 4-A. All other terms of the RFP Documents remain unchanged. | Bidders shall acknowledge receipt in Form 4-A. | ADD-01 cover/para3 p1 | pass_fail | Bid management | Bid manager | EV-FORM-4A | NOT ISSUED | NEW — STALE | ACTIVE — STALE | ACTIVE | none stated in the documents |  |  | medium: verbatim; the reissued form's stated purpose ('paragraph 1') does not match its layout | n/a (text layer) | proposed (not reviewed) | n/a | ADD-01:cover/para3 (ADD-01 p1; text layer) | I-F4A-FIELDS; I-NO-CONSEQUENCE
ADD-01-Q4-01 | ADD-01:Q4 | site_conditions; risk; data_gap; new_in_addendum | Satisfy yourselves as to ground conditions (asked for the wadi crossing); the data-room geotechnical report is for information | No: 4 ¦ Bidder question: Can the Authority confirm the ground conditions at the wadi crossing? ¦ Authority response: The geotechnical report in the data room is provided for information. Bidders shall satisfy themselves as to ground conditions. | No: 4 ¦ Bidder question: Can the Authority confirm the ground conditions at the wadi crossing? ¦ Authority response: The geotechnical report in the data room is provided for information. Bidders shall satisfy themselves as to ground conditions. | Bidders shall satisfy themselves as to ground conditions. | ADD-01 Q4 p2 | procedural | Technical | Technical lead | EV-GROUND-DD | NOT ISSUED | NEW | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim answer; the report it refers to and the drawings are not in the pack | n/a (text layer) | proposed (not reviewed) | n/a | ADD-01:Q4 (ADD-01 p2; text layer) | I-VOL-III
ADD-02-5.2-01 | ADD-02:5.2 | technical_design; effluent; new_in_addendum | Reflect the amended Total Nitrogen limit (3 mg/l, ADD-02 5.1) in the process design submitted under Volume II Section 3 | Bidders shall reflect the amended limit in the process design submitted under Volume II Section 3. | Bidders shall reflect the amended limit in the process design submitted under Volume II Section 3. | Bidders shall reflect the amended limit in the process design submitted under Volume II Section 3. | ADD-02 5.2 p1 | pass_fail | Technical | Technical lead | EV-TECH-PROPOSAL | NOT ISSUED | NOT ISSUED | NEW | ACTIVE | none stated in the documents |  |  | medium: verbatim; the basis of assessment rests on a pending image reading and the Permit is not supplied | n/a (text layer) | proposed (not reviewed) | n/a | ADD-02:5.2 (ADD-02 p1; text layer) | I-NO-CONSEQUENCE; I-PERMIT; I-READING-T24
ADD-02-T1-1-N3-01 | ADD-02:T1-1-rev | evaluation; scoring; new_in_addendum | Technical marks awarded on the Authority's 'standard five-point scale' and multiplied by the weight shown (reissued Table 1-1) | (3) Marks are awarded on the Authority's standard five-point scale and multiplied by the weight shown. | (3) Marks are awarded on the Authority's standard five-point scale and multiplied by the weight shown. | Marks are awarded on the Authority's standard five-point scale and multiplied by the weight shown. | ADD-02 T1-1-rev/note(3) p1 | scored | Bid management | Bid manager | EV-TECH-PROPOSAL | NOT ISSUED | NOT ISSUED | NEW | ACTIVE | none stated in the documents |  |  | medium: verbatim; the method it states cannot be applied from the pack | n/a (text layer) | proposed (not reviewed) | n/a | ADD-02:T1-1-rev/note(3) (ADD-02 p1; text layer) | I-VOL-IV-SCALE
ADD-02-F4G-02 | ADD-02:F4-G | forms; post_award; cybersecurity; new_in_addendum | Form 4-G undertaking 1: segregate the OT environment from any business network per VOL-II 6.2 (confirmed Yes or No) | Item: 1 ¦ Undertaking: The operational technology environment will be segregated from any business network in accordance with Volume II Clause 6.2. ¦ Confirmed: Yes / No | Item: 1 ¦ Undertaking: The operational technology environment will be segregated from any business network in accordance with Volume II Clause 6.2. ¦ Confirmed: Yes / No | The operational technology environment will be segregated from any business network in accordance with Volume II Clause 6.2. | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/1) | contractual_post_award | Technical | Technical lead | EV-FORM-4G | NOT ISSUED | NOT ISSUED | NEW | ACTIVE (as amended by ADD-02/7.1) | none stated in the documents |  |  | medium: verbatim; the effect of answering 'No' is not stated | n/a (text layer) | proposed (not reviewed) | ADD-02/7.1: proposed | ADD-02:F4-G/T1/1 (ADD-02 p3; text layer); ADD-02/7.1 [proposed] <- ADD-02:7.1 (ADD-02 p3) | I-F4G-NO
ADD-02-F4G-03 | ADD-02:F4-G | forms; post_award; cybersecurity; new_in_addendum | Form 4-G undertaking 2: implement an information security management system covering the OT environment before commissioning | Item: 2 ¦ Undertaking: An information security management system covering the operational technology environment will be implemented before commissioning. ¦ Confirmed: Yes / No | Item: 2 ¦ Undertaking: An information security management system covering the operational technology environment will be implemented before commissioning. ¦ Confirmed: Yes / No | An information security management system covering the operational technology environment will be implemented before commissioning. | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/2) | contractual_post_award | Technical | Technical lead | EV-FORM-4G | NOT ISSUED | NOT ISSUED | NEW | ACTIVE (as amended by ADD-02/7.1) | none stated in the documents |  |  | medium: verbatim; the effect of answering 'No' is not stated | n/a (text layer) | proposed (not reviewed) | ADD-02/7.1: proposed | ADD-02:F4-G/T1/2 (ADD-02 p3; text layer); ADD-02/7.1 [proposed] <- ADD-02:7.1 (ADD-02 p3) | I-F4G-NO
ADD-02-F4G-04 | ADD-02:F4-G | envelope_A; forms; new_in_addendum | Sign Form 4-G for and on behalf of the Bidder, with name and date | Signed for and on behalf of the Bidder: _______________________ Name: _______________________ Date: ____________ | Signed for and on behalf of the Bidder: _______________________ Name: _______________________ Date: ____________ | Signed for and on behalf of the Bidder | ADD-02 7.1 p3 (amending ADD-02 F4-G/para1) | pass_fail | Technical | Bid manager | EV-FORM-4G | NOT ISSUED | NOT ISSUED | NEW | ACTIVE (as amended by ADD-02/7.1) | none stated in the documents |  |  | high: verbatim signature line | n/a (text layer) | proposed (not reviewed) | ADD-02/7.1: proposed | ADD-02:F4-G/para1 (ADD-02 p3; text layer); ADD-02/7.1 [proposed] <- ADD-02:7.1 (ADD-02 p3) | I-NO-CONSEQUENCE
VOL-I-1.4-01 | VOL-I:1.4 | eligibility; qualification | Only a Bidder prequalified under RFQ NUPA/ISTP/2025/031 and named in Appendix 1 may submit a Proposal | Only Bidders prequalified under Request for Qualification NUPA/ISTP/2025/031 and named in Appendix 1 to this Volume are eligible to submit a Proposal. A Proposal received from any other person shall be rejected without evaluation. | Only Bidders prequalified under Request for Qualification NUPA/ISTP/2025/031 and named in Appendix 1 to this Volume are eligible to submit a Proposal. A Proposal received from any other person shall be rejected without evaluation. | Only Bidders prequalified under Request for Qualification NUPA/ISTP/2025/031 and named in Appendix 1 to this Volume are eligible to submit a Proposal. | VOL-I 1.4 p2 | pass_fail | Bid management | Bid manager | none: an eligibility status (prequalified and named in Appendix 1), not a document; the Bidder submits in its prequalified name | ACTIVE | ACTIVE | ACTIVE | ACTIVE | rejection: "A Proposal received from any other person shall be rejected without evaluation." | VOL-I 1.4 p2 |  | high: verbatim; the Bidder's identity is an assumption, not a fact from the pack | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:1.4 (VOL-I p2; text layer) | I-BIDDER-FACTS
VOL-I-3.3-01 | VOL-I:3.3 | clarification; conflicts | Raise any conflict, ambiguity or discrepancy found in the RFP Documents as a clarification request under Section 5 | A Bidder that identifies a conflict, ambiguity or discrepancy shall raise it as a request for clarification under Section 5. A Bidder that resolves such a conflict unilaterally does so at its own risk, and the Authority shall not be bound by the Bidder's interpretation. | A Bidder that identifies a conflict, ambiguity or discrepancy shall raise it as a request for clarification under Section 5. A Bidder that resolves such a conflict unilaterally does so at its own risk, and the Authority shall not be bound by the Bidder's interpretation. | A Bidder that identifies a conflict, ambiguity or discrepancy shall raise it as a request for clarification under Section 5. | VOL-I 3.3 p2 | procedural | Bid management | Bid manager | EV-CLARIFICATIONS | ACTIVE | ACTIVE | ACTIVE | ACTIVE | lesser consequence: "A Bidder that resolves such a conflict unilaterally does so at its own risk, and the Authority shall not be bound by the Bidder's interpretation." | VOL-I 3.3 p2 |  | high: verbatim; the consequence ('at its own risk') is stated in the same clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:3.3 (VOL-I p2; text layer) | I-VOL-I-ENV-B; I-VOL-I-ENV-A-PRICES; I-CONCESSION
VOL-I-3.4-01 | VOL-I:3.4 | clarification; completeness; deadline | Check the completeness of the RFP Documents downloaded from the Portal; omission claims are not entertained after the Proposal Due Date | Bidders shall satisfy themselves as to the completeness of the RFP Documents downloaded from the Portal. No claim arising from an alleged omission shall be entertained after the Proposal Due Date. | Bidders shall satisfy themselves as to the completeness of the RFP Documents downloaded from the Portal. No claim arising from an alleged omission shall be entertained after the Proposal Due Date. | Bidders shall satisfy themselves as to the completeness of the RFP Documents downloaded from the Portal. | VOL-I 3.4 p3 | procedural | Bid management | Bid manager | EV-CLARIFICATIONS | ACTIVE | ACTIVE — STALE | ACTIVE — STALE | ACTIVE — STALE | lesser consequence: "No claim arising from an alleged omission shall be entertained after the Proposal Due Date." | VOL-I 3.4 p3 | OMISSION-CLAIM-CUTOFF: 2026-12-10 (as_stated) | medium: verbatim; the cut-off moves with the PDD but this clause is not named in ADD-01 §2.2 (non-exhaustive list) | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:3.4 (VOL-I p3; text layer) | I-VOL-III
VOL-I-4.1-01 | VOL-I:4.1 | communications; conduct | Make all communications with the Authority through the Portal, in English unless Volume I expressly requires Arabic | All communications between a Bidder and the Authority shall be made exclusively through the Portal and shall be in the English language, save where this Volume expressly requires Arabic. | All communications between a Bidder and the Authority shall be made exclusively through the Portal and shall be in the English language, save where this Volume expressly requires Arabic. | All communications between a Bidder and the Authority shall be made exclusively through the Portal and shall be in the English language, save where this Volume expressly requires Arabic. | VOL-I 4.1 p3 | procedural | Bid management | Bid manager | none: a rule on how every communication is made; no deliverable of its own | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim; no consequence stated (a procedural rule) | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:4.1 (VOL-I p3; text layer)
VOL-I-4.2-01 | VOL-I:4.2 | communications; conduct; blackout | Blackout: no contact with the Authority's board, staff, consultants or advisors about the Project other than through the Portal, until the PBN | From the date of issue of this Volume until the issue of the Preferred Bidder Notification, no Bidder, and no person acting for a Bidder, shall contact any board member, officer, employee, consultant or advisor of the Authority in relation to the Project other than through the Portal. Breach of this Clause shall result in the disqualification of the Bidder. | From the date of issue of this Volume until the issue of the Preferred Bidder Notification, no Bidder, and no person acting for a Bidder, shall contact any board member, officer, employee, consultant or advisor of the Authority in relation to the Project other than through the Portal. Breach of this Clause shall result in the disqualification of the Bidder. | no Bidder, and no person acting for a Bidder, shall contact any board member, officer, employee, consultant or advisor of the Authority in relation to the Project other than through the Portal | VOL-I 4.2 p3 | procedural | Bid management | Bid manager | none: a conduct rule binding the Bidder and anyone acting for it; nothing to submit | ACTIVE | ACTIVE | ACTIVE | ACTIVE | disqualification: "Breach of this Clause shall result in the disqualification of the Bidder." | VOL-I 4.2 p3 | BLACKOUT-START: 2026-09-14 (as_stated); BLACKOUT-END: None (unknown_anchor) | high: verbatim; the window's end date depends on an event not yet known | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:4.2 (VOL-I p3; text layer)
VOL-I-4.3-01 | VOL-I:4.3 | communications | Nominate a single point of contact and notify the Authority of any change within two Working Days | Each Bidder shall nominate a single point of contact and shall notify the Authority of any change within two (2) Working Days. | Each Bidder shall nominate a single point of contact and shall notify the Authority of any change within two (2) Working Days. | Each Bidder shall nominate a single point of contact and shall notify the Authority of any change within two (2) Working Days. | VOL-I 4.3 p3 | procedural | Bid management | Bid manager | EV-SPOC | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  | SPOC-CHANGE-NOTICE: None (unknown_anchor) | high: verbatim; the period runs from a change (an event), and forward Working Day counting is not defined | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:4.3 (VOL-I p3; text layer)
VOL-I-5.1-01 | VOL-I:5.1 | clarification | Submit clarification requests through the Portal, each citing the Volume, Clause and page it relates to | A Bidder may submit requests for clarification of the RFP Documents through the Portal. Each request shall cite the Volume, Clause and page to which it relates. | A Bidder may submit requests for clarification of the RFP Documents through the Portal. Each request shall cite the Volume, Clause and page to which it relates. | Each request shall cite the Volume, Clause and page to which it relates. | VOL-I 5.1 p3 | procedural | Bid management | Bid manager | EV-CLARIFICATIONS | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim; no consequence stated (a procedural rule) | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:5.1 (VOL-I p3; text layer)
VOL-I-5.5-01 | VOL-I:5.5 | site; risk | The Bidder must satisfy itself as to site conditions; attending the site visit is optional and does not relieve it of this | A site visit will be offered on the day following the Pre-Bid Conference. Attendance at the site visit is optional and does not relieve a Bidder of its obligation to satisfy itself as to site conditions. | A site visit will be offered on the day following the Pre-Bid Conference. Attendance at the site visit is optional and does not relieve a Bidder of its obligation to satisfy itself as to site conditions. | Attendance at the site visit is optional and does not relieve a Bidder of its obligation to satisfy itself as to site conditions. | VOL-I 5.5 p3 | procedural | Technical | Technical lead | none: a risk the Bidder carries; the site visit (the day after the Pre-Bid Conference) was optional | ACTIVE | ACTIVE | ACTIVE | ACTIVE — STALE | none stated in the documents |  |  | medium: the clause refers to the obligation rather than stating it; no consequence stated | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:5.5 (VOL-I p3; text layer) | I-VOL-III
VOL-I-6.2-01 | VOL-I:6.2 | bid_submission; envelopes | Submit the Proposal in two separately sealed, clearly marked envelopes: A (Technical Proposal) and B (Commercial Proposal) | Each Proposal shall be submitted in two separately sealed and clearly marked envelopes: Envelope A (Technical Proposal) and Envelope B (Commercial Proposal). The appearance of any price, rate, or other commercial information within Envelope A shall render the Proposal non-responsive. | Each Proposal shall be submitted in two separately sealed and clearly marked envelopes: Envelope A (Technical Proposal) and Envelope B (Commercial Proposal). The appearance of any price, rate, or other commercial information within Envelope A shall render the Proposal non-responsive. | Each Proposal shall be submitted in two separately sealed and clearly marked envelopes: Envelope A (Technical Proposal) and Envelope B (Commercial Proposal). | VOL-I 6.2 p3 | pass_fail | Bid management | Bid manager | EV-DELIVERY | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim; no consequence stated for the envelopes themselves | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:6.2 (VOL-I p3; text layer) | I-NO-CONSEQUENCE
VOL-I-6.2-02 | VOL-I:6.2 | envelope_A; commercial_separation | No price, rate or other commercial information anywhere in Envelope A | Each Proposal shall be submitted in two separately sealed and clearly marked envelopes: Envelope A (Technical Proposal) and Envelope B (Commercial Proposal). The appearance of any price, rate, or other commercial information within Envelope A shall render the Proposal non-responsive. | Each Proposal shall be submitted in two separately sealed and clearly marked envelopes: Envelope A (Technical Proposal) and Envelope B (Commercial Proposal). The appearance of any price, rate, or other commercial information within Envelope A shall render the Proposal non-responsive. | The appearance of any price, rate, or other commercial information within Envelope A | VOL-I 6.2 p3 | pass_fail | Commercial | Commercial lead | none: a check on the content of every Envelope A document, not a deliverable of its own | ACTIVE | ACTIVE | ACTIVE | ACTIVE | non-responsive: "The appearance of any price, rate, or other commercial information within Envelope A shall render the Proposal non-responsive." | VOL-I 6.2 p3 |  | medium: verbatim consequence; the scope of 'other commercial information' is not defined and Form 4-B conflicts | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:6.2 (VOL-I p3; text layer) | I-VOL-I-ENV-A-PRICES
VOL-I-6.5-01 | VOL-I:6.5 | bid_submission; copies | Submit one marked original, three hard copies and one searchable electronic copy on encrypted USB media | Each Proposal shall be submitted as one (1) marked original, three (3) hard copies, and one (1) searchable electronic copy on encrypted USB media. Electronic files shall be named strictly in accordance with the convention at Appendix 2. A Proposal whose electronic copy materially differs from the marked original shall be evaluated on the basis of the marked original. | Each Proposal shall be submitted as one (1) marked original and one (1) searchable electronic copy on encrypted USB media. Electronic files shall be named strictly in accordance with the convention at Appendix 2. A Proposal whose electronic copy materially differs from the marked original shall be evaluated on the basis of the marked original. | Each Proposal shall be submitted as one (1) marked original and one (1) searchable electronic copy on encrypted USB media. | ADD-03 5.1 p1 (amending VOL-I 6.5) | pass_fail | Bid management | Bid manager | EV-COPIES | ACTIVE | ACTIVE | ACTIVE | AMENDED (ADD-03/5.1) | none stated in the documents |  |  | medium: verbatim; whether the copies are per envelope or per Proposal is not stated; no consequence stated | n/a (text layer) | proposed (not reviewed) | ADD-03/5.1: proposed | VOL-I:6.5 (VOL-I p3; text layer); ADD-03/5.1 [proposed] <- ADD-03:5.1 (ADD-03 p1) | I-NO-CONSEQUENCE; I-VOL-I-COPIES
VOL-I-6.5-02 | VOL-I:6.5 | bid_submission; electronic_copy; file_naming | Name electronic files per the Appendix 2 convention (pattern, folder depth up to 3 levels, names up to 120 characters) | Each Proposal shall be submitted as one (1) marked original, three (3) hard copies, and one (1) searchable electronic copy on encrypted USB media. Electronic files shall be named strictly in accordance with the convention at Appendix 2. A Proposal whose electronic copy materially differs from the marked original shall be evaluated on the basis of the marked original. | Each Proposal shall be submitted as one (1) marked original and one (1) searchable electronic copy on encrypted USB media. Electronic files shall be named strictly in accordance with the convention at Appendix 2. A Proposal whose electronic copy materially differs from the marked original shall be evaluated on the basis of the marked original. | Electronic files shall be named strictly in accordance with the convention at Appendix 2. | VOL-I 6.5 p3 as amended by ADD-03 5.1 p1 | procedural | Bid management | Bid manager | EV-COPIES | ACTIVE | ACTIVE | ACTIVE | AMENDED (ADD-03/5.1) — STALE | lesser consequence: "Non-conforming file names will be corrected by the Authority at the Bidder's risk." | VOL-I App2/para1 p7 |  | medium: verbatim; the '.pdf' pattern cannot fit the Excel Financial Model and [YYYYMMDD] is not explained | n/a (text layer) | proposed (not reviewed) | ADD-03/5.1: proposed | VOL-I:6.5 (VOL-I p3; text layer); ADD-03/5.1 [proposed] <- ADD-03:5.1 (ADD-03 p1) | I-VOL-I-FILE-NAMES
VOL-I-6.7-01 | VOL-I:6.7 | bid_submission; deadline | Withdraw or modify the Proposal only before the Proposal Due Date, by written notice through the Portal | A Bidder may withdraw or modify its Proposal at any time before the Proposal Due Date by written notice through the Portal. No modification will be accepted thereafter. | A Bidder may withdraw or modify its Proposal at any time before the Proposal Due Date by written notice through the Portal. No modification will be accepted thereafter. | A Bidder may withdraw or modify its Proposal at any time before the Proposal Due Date by written notice through the Portal. | VOL-I 6.7 p3 | procedural | Bid management | Bid manager | none: an option: arises only if the Bidder withdraws or modifies its Proposal | ACTIVE | ACTIVE — STALE | ACTIVE — STALE | ACTIVE — STALE | lesser consequence: "No modification will be accepted thereafter." | VOL-I 6.7 p3 | MODIFY-CUTOFF: 2026-12-10 (as_stated) | high: verbatim; the cut-off moves with the PDD although ADD-01 §2.2 does not name this clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:6.7 (VOL-I p3; text layer)
VOL-I-7.2-01 | VOL-I:7.2 | validity; bid_security | If the Bidder agrees to an Authority request to extend validity, procure a corresponding extension of its Bid Bond | The Authority may, before expiry of the validity period, request Bidders to extend validity. A Bidder may refuse without forfeiting its Bid Bond; a Bidder that agrees shall procure a corresponding extension of its Bid Bond. | The Authority may, before expiry of the validity period, request Bidders to extend validity. A Bidder may refuse without forfeiting its Bid Bond; a Bidder that agrees shall procure a corresponding extension of its Bid Bond. | a Bidder that agrees shall procure a corresponding extension of its Bid Bond | VOL-I 7.2 p4 | procedural | Commercial | Commercial lead | none: conditional: arises only if the Authority requests an extension and the Bidder agrees (refusal is allowed) | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim; no consequence stated for failing to procure the extension | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:7.2 (VOL-I p4; text layer)
VOL-I-8.1-01 | VOL-I:8.1 | qualification; consortium | Bid as the prequalified entity or consortium; no change to composition, shareholding or lead member without the Authority's prior written consent | A Bidder shall be either a single entity or a consortium, in each case prequalified under the RFQ. No change to the composition, shareholding or lead member of a prequalified consortium shall be effective without the prior written consent of the Authority. An unapproved change shall result in rejection of the Proposal. | A Bidder shall be either a single entity or a consortium, in each case prequalified under the RFQ. No change to the composition, shareholding or lead member of a prequalified consortium shall be effective without the prior written consent of the Authority. An unapproved change shall result in rejection of the Proposal. | No change to the composition, shareholding or lead member of a prequalified consortium shall be effective without the prior written consent of the Authority. | VOL-I 8.1 p4 | pass_fail | Legal | Legal counsel | none: a status (the consortium as prequalified); the Authority's written consent is needed only before any change | ACTIVE | ACTIVE | ACTIVE | ACTIVE | rejection: "An unapproved change shall result in rejection of the Proposal." | VOL-I 8.1 p4 |  | high: verbatim; the consortium's composition is a bidder fact | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:8.1 (VOL-I p4; text layer) | I-BIDDER-FACTS
VOL-I-8.2-01 | VOL-I:8.2 | qualification; conduct; multiple_participation | No firm or affiliate of a member may participate in more than one Proposal | No firm, and no affiliate of a firm, shall participate in more than one Proposal. Participation in more than one Proposal shall cause every Proposal in which that firm or affiliate participates to be rejected. | No firm, and no affiliate of a firm, shall participate in more than one Proposal. Participation in more than one Proposal shall cause every Proposal in which that firm or affiliate participates to be rejected. | No firm, and no affiliate of a firm, shall participate in more than one Proposal. | VOL-I 8.2 p4 | pass_fail | Legal | Legal counsel | EV-FORM-4C | ACTIVE | ACTIVE | ACTIVE | ACTIVE | rejection: "Participation in more than one Proposal shall cause every Proposal in which that firm or affiliate participates to be rejected." | VOL-I 8.2 p4 |  | high: verbatim; 'affiliate' is not defined | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:8.2 (VOL-I p4; text layer) | I-BIDDER-FACTS
VOL-I-8.4-01 | VOL-I:8.4 | qualification; financial; envelope_A | Combined tangible net worth (weighted by shareholding) of at least SAR 800,000,000 per the most recent audited statements | The Bidder shall demonstrate, on a combined basis across consortium members weighted by shareholding, (a) a consolidated tangible net worth of not less than SAR 800,000,000 as at the most recent audited financial statements, and (b) an average annual turnover over the last three (3) audited financial years of not less than SAR 1,200,000,000. | The Bidder shall demonstrate, on a combined basis across consortium members weighted by shareholding, (a) a consolidated tangible net worth of not less than SAR 800,000,000 as at the most recent audited financial statements, and (b) an average annual turnover over the last three (3) audited financial years of not less than SAR 1,200,000,000. | (a) a consolidated tangible net worth of not less than SAR 800,000,000 as at the most recent audited financial statements | VOL-I 8.4 p4 | pass_fail | Finance | Financial modeller | EV-FIN-STANDING | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim; how the shareholding weighting is applied and which statements count as most recent are not stated | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:8.4 (VOL-I p4; text layer) | I-NO-CONSEQUENCE; I-BIDDER-FACTS
VOL-I-8.4-02 | VOL-I:8.4 | qualification; financial; envelope_A | Combined average annual turnover (weighted by shareholding) over the last three audited years of at least SAR 1,200,000,000 | The Bidder shall demonstrate, on a combined basis across consortium members weighted by shareholding, (a) a consolidated tangible net worth of not less than SAR 800,000,000 as at the most recent audited financial statements, and (b) an average annual turnover over the last three (3) audited financial years of not less than SAR 1,200,000,000. | The Bidder shall demonstrate, on a combined basis across consortium members weighted by shareholding, (a) a consolidated tangible net worth of not less than SAR 800,000,000 as at the most recent audited financial statements, and (b) an average annual turnover over the last three (3) audited financial years of not less than SAR 1,200,000,000. | (b) an average annual turnover over the last three (3) audited financial years of not less than SAR 1,200,000,000 | VOL-I 8.4 p4 | pass_fail | Finance | Financial modeller | EV-FIN-STANDING | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim; how the shareholding weighting is applied is not stated | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:8.4 (VOL-I p4; text layer) | I-NO-CONSEQUENCE; I-BIDDER-FACTS
VOL-I-8.7-01 | VOL-I:8.7 | qualification; guarantee; envelope_A | Executed Parent Company Guarantee from the EPC Contractor's ultimate parent, substantially in Form 4-D, unconditional for the construction period | The Bidder shall submit an executed Parent Company Guarantee from the ultimate parent company of the proposed EPC Contractor, substantially in the form set out in Form 4-D, unconditional as to the EPC Contractor's obligations during the construction period. | The Bidder shall submit an executed Parent Company Guarantee from the ultimate parent company of the proposed EPC Contractor, substantially in the form set out in Form 4-D, unconditional as to the EPC Contractor's obligations during the construction period. | The Bidder shall submit an executed Parent Company Guarantee from the ultimate parent company of the proposed EPC Contractor, substantially in the form set out in Form 4-D | VOL-I 8.7 p4 | pass_fail | Legal | Legal counsel | EV-FORM-4D | ACTIVE | ACTIVE | ACTIVE | ACTIVE — STALE | none stated in the documents |  |  | high: verbatim; confirmed by ADD-02 Q10 (no consequence stated) | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:8.7 (VOL-I p4; text layer) | I-NO-CONSEQUENCE
VOL-I-8.8-01 | VOL-I:8.8 | qualification; operations; envelope_A | O&M Operator: at least five years' continuous operation of a wastewater treatment facility of at least 50,000 m3/day | The proposed O&M Operator shall evidence not less than five (5) years of continuous operation of at least one (1) wastewater treatment facility of nominal capacity not less than 50,000 m³/day. | The proposed O&M Operator shall evidence not less than five (5) years of continuous operation of at least one (1) wastewater treatment facility of nominal capacity not less than 50,000 m³/day. | shall evidence not less than five (5) years of continuous operation of at least one (1) wastewater treatment facility of nominal capacity not less than 50,000 | VOL-I 8.8 p4 | pass_fail | Operations | O&M lead | EV-OM-EXPERIENCE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim; no consequence stated; the period's end date is not stated | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:8.8 (VOL-I p4; text layer) | I-NO-CONSEQUENCE; I-BIDDER-FACTS
VOL-I-8.9-01 | VOL-I:8.9 | qualification; licensing; envelope_A | For each foreign member: a current investment licence, or a signed undertaking to obtain one before Financial Close | The Bidder shall submit either evidence of a current investment licence for each foreign consortium member, or a signed undertaking to obtain such licence prior to Financial Close. | The Bidder shall submit either evidence of a current investment licence for each foreign consortium member, or a signed undertaking to obtain such licence prior to Financial Close. | The Bidder shall submit either evidence of a current investment licence for each foreign consortium member, or a signed undertaking to obtain such licence prior to Financial Close. | VOL-I 8.9 p4 | pass_fail | Legal | Legal counsel | EV-INVESTMENT-LICENCE | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  | INVESTMENT-LICENCE-BY-FC: None (unknown_anchor) | high: verbatim; which members are foreign is a bidder fact; no consequence stated | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:8.9 (VOL-I p4; text layer) | I-NO-CONSEQUENCE; I-BIDDER-FACTS
VOL-I-8.10-01 | VOL-I:8.10 | qualification; debarment; envelope_A | No member debarred by a public authority in the Kingdom now or in the preceding five years; declared in Form 4-C | No member of the Bidder shall be the subject of, or have been the subject of within the preceding five (5) years, any debarment by a public authority in the Kingdom. A declaration to this effect shall be given in Form 4-C. | No member of the Bidder shall be the subject of, or have been the subject of within the preceding five (5) years, any debarment by a public authority in the Kingdom. A declaration to this effect shall be given in Form 4-C. | No member of the Bidder shall be the subject of, or have been the subject of within the preceding five (5) years, any debarment by a public authority in the Kingdom. | VOL-I 8.10 p4 | pass_fail | Legal | Legal counsel | EV-FORM-4C | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  | DEBARMENT-LOOKBACK: None (unknown_anchor) | medium: verbatim; the look-back's reference date is not stated; no consequence stated in this clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:8.10 (VOL-I p4; text layer) | I-NO-CONSEQUENCE; I-BIDDER-FACTS
VOL-I-9.1-01 | VOL-I:9.1 | envelope_A; order | Envelope A contains items (a) to (i) in the stated order, separated by numbered dividers | Envelope A shall contain, in the following order and separated by numbered dividers: | Envelope A shall contain, in the following order and separated by numbered dividers: | Envelope A shall contain, in the following order and separated by numbered dividers | VOL-I 9.1 p4 | pass_fail | Bid management | Bid manager | EV-DELIVERY | ACTIVE | ACTIVE | ACTIVE | ACTIVE — STALE | none stated in the documents |  |  | medium: verbatim; no consequence stated; the lettering after ADD-02's insertion is not stated | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:9.1 (VOL-I p4; text layer) | I-NO-CONSEQUENCE; I-F4G-LETTERING
VOL-I-9.1h-01 | VOL-I:9.1 | envelope_A; authority_to_sign | Include a notarised Power of Attorney for each signatory in Envelope A | (h) notarised Powers of Attorney for each signatory; | (h) notarised Powers of Attorney for each signatory; | notarised Powers of Attorney for each signatory | VOL-I 9.1(h) p4 | pass_fail | Legal | Legal counsel | EV-POA | ACTIVE | ACTIVE | ACTIVE | ACTIVE — STALE | none stated in the documents |  |  | medium: verbatim list item; 'each signatory' is not defined; no consequence stated | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:9.1(h) (VOL-I p4; text layer) | I-NO-CONSEQUENCE; I-BIDDER-FACTS
VOL-I-9.2-01 | VOL-I:9.2 | envelope_A; technical_proposal; page_limit | Technical Proposal narrative within the A4 page limit (Form Sheets and Volume II-permitted appendices excluded) | The Technical Proposal narrative shall not exceed one hundred and twenty (120) pages of A4, excluding the Form Sheets and the appendices expressly permitted by Volume II. Pages in excess of the limit will be removed before evaluation and will not be scored. | The Technical Proposal narrative shall not exceed one hundred and fifty (150) pages of A4, excluding the Form Sheets and the appendices expressly permitted by Volume II. Pages in excess of the limit will be removed before evaluation and will not be scored. | The Technical Proposal narrative shall not exceed one hundred and fifty (150) pages of A4, excluding the Form Sheets and the appendices expressly permitted by Volume II. | VOL-I 9.2 p5 as amended by ADD-02 2.1 p1 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | AMENDED (ADD-02/2.1) | ACTIVE (as amended by ADD-02/2.1) — STALE | lesser consequence: "Pages in excess of the limit will be removed before evaluation and will not be scored." | VOL-I 9.2 p5 as amended by ADD-02 2.1 p1 |  | high: verbatim at every stage; the 'appendices expressly permitted by Volume II' were not found in the extract | n/a (text layer) | proposed (not reviewed) | ADD-02/2.1: proposed | VOL-I:9.2 (VOL-I p5; text layer); ADD-02/2.1 [proposed] <- ADD-02:2.1 (ADD-02 p1) | I-VOL-I-APPENDICES
VOL-I-9.5-01 | VOL-I:9.5 | envelope_A; references; forms | A separate Form 4-B for each reference project relied on under 8.5, each with a client completion certificate | A separate Form 4-B shall be submitted for each reference project relied upon under Clause 8.5, accompanied by a client completion certificate. A reference project not evidenced by a completion certificate will be disregarded. | A separate Form 4-B shall be submitted for each reference project relied upon under Clause 8.5, accompanied by a client completion certificate. A reference project not evidenced by a completion certificate will be disregarded. | A separate Form 4-B shall be submitted for each reference project relied upon under Clause 8.5, accompanied by a client completion certificate. | VOL-I 9.5 p5 | pass_fail | Technical | Technical lead | EV-FORM-4B; EV-COMPLETION-CERT | ACTIVE | ACTIVE | ACTIVE | ACTIVE — STALE | lesser consequence: "A reference project not evidenced by a completion certificate will be disregarded." | VOL-I 9.5 p5 |  | high: verbatim; Form 4-B also asks for a contract value in SAR (Envelope A), see I-VOL-I-ENV-A-PRICES | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:9.5 (VOL-I p5; text layer) | I-VOL-I-ENV-A-PRICES; I-BIDDER-FACTS
VOL-I-9.6-01 | VOL-I:9.6 | envelope_A; deviations; forms | Form 4-E lists every deviation, qualification or reservation to Volume V; never 'no deviations' with a qualification elsewhere | Form 4-E shall list every deviation, qualification or reservation to Volume V. A Proposal that states ‘no deviations’ in Form 4-E while containing a qualification elsewhere in the Proposal shall be treated as non-responsive. | Form 4-E shall list every deviation, qualification or reservation to Volume V. A Proposal that states ‘no deviations’ in Form 4-E while containing a qualification elsewhere in the Proposal shall be treated as non-responsive. | Form 4-E shall list every deviation, qualification or reservation to Volume V. | VOL-I 9.6 p5 | pass_fail | Legal | Legal counsel | EV-FORM-4E | ACTIVE | ACTIVE | ACTIVE | ACTIVE — STALE | non-responsive: "A Proposal that states ‘no deviations’ in Form 4-E while containing a qualification elsewhere in the Proposal shall be treated as non-responsive." | VOL-I 9.6 p5 |  | high: verbatim | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:9.6 (VOL-I p5; text layer) | I-CONCESSION
VOL-I-9.7-01 | VOL-I:9.7 | envelope_A; technical_proposal | Technical Proposal narrative (Envelope A item (f)) addressing at least the six listed topics | The Technical Proposal shall address, as a minimum, the process design, the construction methodology and programme, the operations and maintenance philosophy, the health and safety plan, the environmental and social management approach, and the organisation and key personnel. | The Technical Proposal shall address, as a minimum, the process design, the construction methodology and programme, the operations and maintenance philosophy, the health and safety plan, the environmental and social management approach, and the organisation and key personnel. | The Technical Proposal shall address, as a minimum, the process design, the construction methodology and programme, the operations and maintenance philosophy, the health and safety plan, the environmental and social management approach, and the organisation and key personnel. | VOL-I 9.7 p5 | pass_fail | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE — STALE | none stated in the documents |  |  | high: verbatim; no consequence stated for a missing topic | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:9.7 (VOL-I p5; text layer) | I-NO-CONSEQUENCE
VOL-I-10.1-01 | VOL-I:10.1 | envelope_B; commercial | Envelope B contains only Form 4-F and the Financial Model; no other document | Envelope B shall contain only (a) Form 4-F (Financial Proposal Schedule) and (b) the Financial Model. No other document shall be placed in Envelope B. | Envelope B shall contain only (a) Form 4-F (Financial Proposal Schedule) and (b) the Financial Model. No other document shall be placed in Envelope B. | Envelope B shall contain only (a) Form 4-F (Financial Proposal Schedule) and (b) the Financial Model. No other document shall be placed in Envelope B. | VOL-I 10.1 p5 | pass_fail | Commercial | Commercial lead | EV-FORM-4F; EV-FIN-MODEL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim; conflicts with VOL-I 10.3 and 10.6; no consequence stated | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:10.1 (VOL-I p5; text layer) | I-NO-CONSEQUENCE; I-VOL-I-ENV-B
VOL-I-10.2-01 | VOL-I:10.2 | envelope_B; price | Quote a single Availability Payment in SAR per annum, calculated per the Volume V Clause 29 payment mechanism | The Bidder shall quote a single Availability Payment expressed in Saudi Riyals per annum, calculated in accordance with the payment mechanism at Volume V Clause 29. | The Bidder shall quote a single Availability Payment expressed in Saudi Riyals per annum, calculated in accordance with the payment mechanism at Volume V Clause 29. | The Bidder shall quote a single Availability Payment expressed in Saudi Riyals per annum, calculated in accordance with the payment mechanism at Volume V Clause 29. | VOL-I 10.2 p5 | pass_fail | Commercial | Commercial lead | EV-FORM-4F | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim; no consequence stated (VOL-I 10.5 covers conditional or alternative prices) | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:10.2 (VOL-I p5; text layer) | I-NO-CONSEQUENCE
VOL-I-10.3-01 | VOL-I:10.3 | envelope_B; financial_model | Financial Model in unlocked, fully formula-linked Excel, with no macros and no hard-coded values in calculation cells | The Financial Model shall be submitted in unlocked, fully formula-linked Microsoft Excel format, without macros and without hard-coded values in calculation cells, and shall be accompanied by an opinion from an independent model auditor addressed to the Authority. | The Financial Model shall be submitted in unlocked, fully formula-linked Microsoft Excel format, without macros and without hard-coded values in calculation cells, and shall be accompanied by an opinion from an independent model auditor addressed to the Authority. | The Financial Model shall be submitted in unlocked, fully formula-linked Microsoft Excel format, without macros and without hard-coded values in calculation cells | VOL-I 10.3 p5 | pass_fail | Finance | Financial modeller | EV-FIN-MODEL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim; no consequence stated; Appendix 2 names files '.pdf' | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:10.3 (VOL-I p5; text layer) | I-NO-CONSEQUENCE; I-VOL-I-FILE-NAMES
VOL-I-10.3-02 | VOL-I:10.3 | envelope_B; financial_model; model_audit | Financial Model accompanied by an independent model auditor's opinion addressed to the Authority | The Financial Model shall be submitted in unlocked, fully formula-linked Microsoft Excel format, without macros and without hard-coded values in calculation cells, and shall be accompanied by an opinion from an independent model auditor addressed to the Authority. | The Financial Model shall be submitted in unlocked, fully formula-linked Microsoft Excel format, without macros and without hard-coded values in calculation cells, and shall be accompanied by an opinion from an independent model auditor addressed to the Authority. | shall be accompanied by an opinion from an independent model auditor addressed to the Authority | VOL-I 10.3 p5 | pass_fail | Finance | Financial modeller | EV-MODEL-AUDIT | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim; conflicts with VOL-I 10.1; no consequence stated | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:10.3 (VOL-I p5; text layer) | I-NO-CONSEQUENCE; I-VOL-I-ENV-B
VOL-I-10.4-01 | VOL-I:10.4 | envelope_B; price | All prices exclusive of VAT and stated in Saudi Riyals | All prices shall be exclusive of value added tax and shall be stated in Saudi Riyals. | All prices shall be exclusive of value added tax and shall be stated in Saudi Riyals. | All prices shall be exclusive of value added tax and shall be stated in Saudi Riyals. | VOL-I 10.4 p5 | pass_fail | Commercial | Commercial lead | EV-FORM-4F | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim; no consequence stated | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:10.4 (VOL-I p5; text layer) | I-NO-CONSEQUENCE
VOL-I-10.5-01 | VOL-I:10.5 | envelope_B; price | No conditional price, alternative price, or price subject to adjustment other than as provided in Volume V | Any conditional price, price subject to adjustment other than as provided in Volume V, or alternative price shall render the Proposal non-responsive. An alternative technical solution may be submitted only as a supplement to a fully compliant base Proposal and will be considered at the Authority's sole discretion. | Any conditional price, price subject to adjustment other than as provided in Volume V, or alternative price shall render the Proposal non-responsive. An alternative technical solution may be submitted only as a supplement to a fully compliant base Proposal and will be considered at the Authority's sole discretion. | Any conditional price, price subject to adjustment other than as provided in Volume V, or alternative price | VOL-I 10.6 (issued as 10.5) p5 | pass_fail | Commercial | Commercial lead | EV-FORM-4F | ACTIVE | ACTIVE | ACTIVE | ACTIVE — STALE | non-responsive: "Any conditional price, price subject to adjustment other than as provided in Volume V, or alternative price shall render the Proposal non-responsive." | VOL-I 10.6 (issued as 10.5) p5 |  | high: verbatim | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:10.5 (VOL-I p5; text layer)
VOL-I-10.5-02 | VOL-I:10.5 | alternative_solution | An alternative technical solution only as a supplement to a fully compliant base Proposal (considered at the Authority's discretion) | Any conditional price, price subject to adjustment other than as provided in Volume V, or alternative price shall render the Proposal non-responsive. An alternative technical solution may be submitted only as a supplement to a fully compliant base Proposal and will be considered at the Authority's sole discretion. | Any conditional price, price subject to adjustment other than as provided in Volume V, or alternative price shall render the Proposal non-responsive. An alternative technical solution may be submitted only as a supplement to a fully compliant base Proposal and will be considered at the Authority's sole discretion. | An alternative technical solution may be submitted only as a supplement to a fully compliant base Proposal and will be considered at the Authority's sole discretion. | VOL-I 10.6 (issued as 10.5) p5 | pass_fail | Technical | Technical lead | none: applies only if the Bidder offers an alternative technical solution; nothing to submit otherwise | ACTIVE | ACTIVE | ACTIVE | ACTIVE — STALE | none stated in the documents |  |  | medium: verbatim; what happens to an alternative submitted without a compliant base is not stated | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:10.5 (VOL-I p5; text layer) | I-NO-CONSEQUENCE
VOL-I-10.6-01 | VOL-I:10.6 | envelope_B; financing | With Form 4-F, a schedule of the principal financing assumptions (debt tenor, margin, gearing) | The Bidder shall submit with Form 4-F a schedule of the principal financing assumptions underlying the Availability Payment, including the assumed debt tenor, margin and gearing. | The Bidder shall submit with Form 4-F a schedule of the principal financing assumptions underlying the Availability Payment, including the assumed debt tenor, margin and gearing. | The Bidder shall submit with Form 4-F a schedule of the principal financing assumptions underlying the Availability Payment, including the assumed debt tenor, margin and gearing. | VOL-I 10.7 (issued as 10.6) p5 | pass_fail | Finance | Financial modeller | EV-FIN-ASSUMPTIONS | ACTIVE | ACTIVE | ACTIVE | ACTIVE — STALE | none stated in the documents |  |  | medium: verbatim; conflicts with VOL-I 10.1; no consequence stated | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:10.6 (VOL-I p5; text layer) | I-NO-CONSEQUENCE; I-VOL-I-ENV-B
VOL-I-11.5-01 | VOL-I:11.5 | clarification; post_submission; price | A response to an Authority clarification request must not change the Availability Payment quoted | The Authority may seek written clarification of any Proposal. A response to a clarification shall not change the Availability Payment quoted; any response that does so shall render the Proposal non-responsive. | The Authority may seek written clarification of any Proposal. A response to a clarification shall not change the Availability Payment quoted; any response that does so shall render the Proposal non-responsive. | A response to a clarification shall not change the Availability Payment quoted | VOL-I 11.5 p5 | procedural | Commercial | Commercial lead | none: arises only after submission, if the Authority seeks a written clarification | ACTIVE | ACTIVE | ACTIVE | ACTIVE | non-responsive: "any response that does so shall render the Proposal non-responsive" | VOL-I 11.5 p5 |  | high: verbatim | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:11.5 (VOL-I p5; text layer)
VOL-I-T1-1-A | VOL-I:T1-1 | evaluation; weighting | Marks available for criterion A (process design, treatment performance and compliance with Volume II) | Ref: A ¦ Criterion: Process design, treatment performance and compliance with Volume II ¦ Marks: 25 | Ref: A ¦ Criterion: Process design, treatment performance and compliance with Volume II ¦ Marks: 25 | Marks: 25 | ADD-02 T1-1-rev/A p1 (replacing VOL-I T1-1/A p6, ADD-02/3.1) | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | AMENDED (ADD-02/3.1) | ACTIVE (as amended by ADD-02/3.1) | none stated in the documents |  |  | high: verbatim table rows | n/a (text layer) | proposed (not reviewed) | ADD-02/3.1: proposed | VOL-I:T1-1/A (VOL-I p6; text layer); ADD-02/3.1 [proposed] <- ADD-02:3.1 (ADD-02 p1)
VOL-I-T1-1-C | VOL-I:T1-1 | evaluation; weighting | Marks available for criterion C (operations and maintenance philosophy and lifecycle strategy) | Ref: C ¦ Criterion: Operations and maintenance philosophy and lifecycle strategy ¦ Marks: 20 | Ref: C ¦ Criterion: Operations and maintenance philosophy and lifecycle strategy ¦ Marks: 20 | Marks: 20 | ADD-02 T1-1-rev/C p1 (replacing VOL-I T1-1/C p6, ADD-02/3.1) | scored | Operations | O&M lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | AMENDED (ADD-02/3.1) | ACTIVE (as amended by ADD-02/3.1) | none stated in the documents |  |  | high: verbatim table rows | n/a (text layer) | proposed (not reviewed) | ADD-02/3.1: proposed | VOL-I:T1-1/C (VOL-I p6; text layer); ADD-02/3.1 [proposed] <- ADD-02:3.1 (ADD-02 p1)
VOL-I-T1-1-E | VOL-I:T1-1 | evaluation; weighting | Marks available for criterion E (organisation, key personnel and consortium governance) | Ref: E ¦ Criterion: Organisation, key personnel and consortium governance ¦ Marks: 10 | Ref: E ¦ Criterion: Organisation, key personnel and consortium governance ¦ Marks: 10 | Marks: 10 | ADD-02 T1-1-rev/E p1 (replacing VOL-I T1-1/E p6, ADD-02/3.1) | scored | Bid management | Bid manager | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | AMENDED (ADD-02/3.1) | ACTIVE (as amended by ADD-02/3.1) | none stated in the documents |  |  | high: verbatim table rows | n/a (text layer) | proposed (not reviewed) | ADD-02/3.1: proposed | VOL-I:T1-1/E (VOL-I p6; text layer); ADD-02/3.1 [proposed] <- ADD-02:3.1 (ADD-02 p1)
VOL-I-T1-1-F | VOL-I:T1-1 | evaluation; weighting | Marks available for criterion F (health, safety and security of supply) | Ref: F ¦ Criterion: Health, safety and security of supply ¦ Marks: 10 | Ref: F ¦ Criterion: Health, safety and security of supply ¦ Marks: 10 | Marks: 10 | ADD-02 T1-1-rev/F p1 (replacing VOL-I T1-1/F p6, ADD-02/3.1) | scored | HSE | HSE lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | AMENDED (ADD-02/3.1) | ACTIVE (as amended by ADD-02/3.1) | none stated in the documents |  |  | high: verbatim table rows | n/a (text layer) | proposed (not reviewed) | ADD-02/3.1: proposed | VOL-I:T1-1/F (VOL-I p6; text layer); ADD-02/3.1 [proposed] <- ADD-02:3.1 (ADD-02 p1)
VOL-I-12.1-01 | VOL-I:12.1 | concession; post_award | Concession period of 25 years from the Project Commercial Operation Date, then transfer of the Project to the Authority per Volume V | The Authority will notify the successful Bidder as Preferred Bidder. The concession period shall be twenty-five (25) years commencing on the Project Commercial Operation Date, following which the Project shall transfer to the Authority in accordance with Volume V. | The Authority will notify the successful Bidder as Preferred Bidder. The concession period shall be twenty-five (25) years commencing on the Project Commercial Operation Date, following which the Project shall transfer to the Authority in accordance with Volume V. | The concession period shall be twenty-five (25) years commencing on the Project Commercial Operation Date, following which the Project shall transfer to the Authority in accordance with Volume V. | VOL-I 12.1 p6 | contractual_post_award | Legal | Legal counsel |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  | CONCESSION-END-PCOD: None (unknown_anchor) | low: verbatim, but conflicts with VOL-V 3.1 and the Authority declined to resolve it (ADD-02 Q7) | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:12.1 (VOL-I p6; text layer) | I-CONCESSION
VOL-I-12.2-01 | VOL-I:12.2 | award; commercial_close; post_award | Preferred Bidder to achieve Commercial Close within 120 days of the Preferred Bidder Notification | The Preferred Bidder shall achieve Commercial Close within one hundred and twenty (120) days, and Financial Close within two hundred and seventy (270) days, of the date of the Preferred Bidder Notification. Failure to achieve Financial Close by the long-stop date entitles the Authority to call the Bid Bond and to proceed with the next ranked Bidder. | The Preferred Bidder shall achieve Commercial Close within one hundred and twenty (120) days, and Financial Close within three hundred (300) days, of the date of the Preferred Bidder Notification. Failure to achieve Financial Close by the long-stop date entitles the Authority to call the Bid Bond and to proceed with the next ranked Bidder. | The Preferred Bidder shall achieve Commercial Close within one hundred and twenty (120) days | VOL-I 12.2 p6 as amended by ADD-03 9.1 p2 | contractual_post_award | Commercial | Commercial lead |  | ACTIVE | ACTIVE | ACTIVE | AMENDED (ADD-03/9.1) — STALE | none stated in the documents |  | PB-COMMERCIAL-CLOSE: None (unknown_anchor) | high: verbatim; anchored to the PBN, an event not in the pack; no consequence stated for Commercial Close | n/a (text layer) | proposed (not reviewed) | ADD-03/9.1: proposed | VOL-I:12.2 (VOL-I p6; text layer); ADD-03/9.1 [proposed] <- ADD-03:9.1 (ADD-03 p2)
VOL-I-12.2-02 | VOL-I:12.2 | award; financial_close; bid_security; post_award | Preferred Bidder to achieve Financial Close within the period VOL-I 12.2 states, from the Preferred Bidder Notification | The Preferred Bidder shall achieve Commercial Close within one hundred and twenty (120) days, and Financial Close within two hundred and seventy (270) days, of the date of the Preferred Bidder Notification. Failure to achieve Financial Close by the long-stop date entitles the Authority to call the Bid Bond and to proceed with the next ranked Bidder. | The Preferred Bidder shall achieve Commercial Close within one hundred and twenty (120) days, and Financial Close within three hundred (300) days, of the date of the Preferred Bidder Notification. Failure to achieve Financial Close by the long-stop date entitles the Authority to call the Bid Bond and to proceed with the next ranked Bidder. | Financial Close within three hundred (300) days | VOL-I 12.2 p6 as amended by ADD-03 9.1 p2 | contractual_post_award | Finance | Financial modeller |  | ACTIVE | ACTIVE | ACTIVE | AMENDED (ADD-03/9.1) | contractual remedy (post-award): "Failure to achieve Financial Close by the long-stop date entitles the Authority to call the Bid Bond and to proceed with the next ranked Bidder." | VOL-I 12.2 p6 as amended by ADD-03 9.1 p2 | PB-FINANCIAL-CLOSE: None (unknown_anchor) | medium: verbatim; 'long-stop date' undefined and the Bid Bond's 180-day validity may not reach it | n/a (text layer) | proposed (not reviewed) | ADD-03/9.1: proposed | VOL-I:12.2 (VOL-I p6; text layer); ADD-03/9.1 [proposed] <- ADD-03:9.1 (ADD-03 p2) | I-VOL-I-BOND-LONGSTOP
VOL-I-13.2-01 | VOL-I:13.2 | confidentiality; conduct | Keep the RFP Documents confidential; disclose only to members, advisors and financiers on a need-to-know basis under equivalent terms | The RFP Documents are confidential and shall not be disclosed other than to a Bidder's members, advisors and financiers on a need-to-know basis and subject to equivalent confidentiality obligations. | The RFP Documents are confidential and shall not be disclosed other than to a Bidder's members, advisors and financiers on a need-to-know basis and subject to equivalent confidentiality obligations. | The RFP Documents are confidential and shall not be disclosed other than to a Bidder's members, advisors and financiers on a need-to-know basis and subject to equivalent confidentiality obligations. | VOL-I 13.2 p6 | procedural | Legal | Legal counsel | none: a conduct rule on handling the RFP Documents; nothing to submit | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim; no consequence stated | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:13.2 (VOL-I p6; text layer)
VOL-I-App3-01 | VOL-I:App3 | bid_submission; address; marking | Deliver to Tender Box 4, Administrative Building C, Sakaka; marking 'NUPA/ISTP/2026/014 — NOT TO BE OPENED BEFORE 14:00 ON THE PROPOSAL DUE DATE' | Tender Box 4, Ground Floor, Northern Utilities Procurement Authority, Administrative Building C, Sakaka. Marked: ‘NUPA/ISTP/2026/014 — NOT TO BE OPENED BEFORE 14:00 ON THE PROPOSAL DUE DATE’. | Tender Box 4, Ground Floor, Northern Utilities Procurement Authority, Administrative Building C, Sakaka. Marked: ‘NUPA/ISTP/2026/014 — NOT TO BE OPENED BEFORE 14:00 ON THE PROPOSAL DUE DATE’. | Tender Box 4, Ground Floor, Northern Utilities Procurement Authority, Administrative Building C, Sakaka. | VOL-I App3/para1 p7 | pass_fail | Bid management | Bid manager | EV-DELIVERY | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim; whether 'Marked:' is the envelope marking required by VOL-I 6.2 is not stated | n/a (text layer) | proposed (not reviewed) | n/a | VOL-I:App3/para1 (VOL-I p7; text layer) | I-NO-CONSEQUENCE
VOL-II-1.1-01 | VOL-II:1.1 | scope_of_works; concession | Design, finance, construct, commission, own, operate and maintain the Facility; transfer it at concession end in the Volume V condition | The Project Company shall design, finance, construct, commission, own, operate and maintain the Wadi Sirhan Independent Sewage Treatment Plant and shall transfer the Facility to the Authority at the end of the concession period in the condition required by Volume V. | The Project Company shall design, finance, construct, commission, own, operate and maintain the Wadi Sirhan Independent Sewage Treatment Plant and shall transfer the Facility to the Authority at the end of the concession period in the condition required by Volume V. | The Project Company shall design, finance, construct, commission, own, operate and maintain the Wadi Sirhan Independent Sewage Treatment Plant | VOL-II 1.1 p2 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause; when the concession period ends depends on the term start (I-CONCESSION) | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:1.1 (VOL-II p2; text layer) | I-CONCESSION
VOL-II-1.2-01 | VOL-II:1.2 | scope_of_works | The Works include every listed element: inlet works to tertiary treatment, disinfection, sludge, odour control, effluent main and reservoir | The Works comprise: the inlet works and screening; primary, secondary and tertiary treatment; disinfection; sludge thickening, digestion and dewatering; odour control; the treated effluent transmission main; the treated effluent storage reservoir; and all associated electrical, control and civil works. | The Works comprise: the inlet works and screening; primary, secondary and tertiary treatment; disinfection; sludge thickening, digestion and dewatering; odour control; the treated effluent transmission main; the treated effluent storage reservoir; and all associated electrical, control and civil works. | The Works comprise: the inlet works and screening; primary, secondary and tertiary treatment; disinfection; sludge thickening, digestion and dewatering; odour control; the treated effluent transmission main; the treated effluent storage reservoir; and all associated electrical, control and civil works. | VOL-II 1.2 p2 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:1.2 (VOL-II p2; text layer)
VOL-II-1.3-01 | VOL-II:1.3 | scope_of_works; interfaces | Manage all interfaces with the existing collection network at the two designated tie-in points, incl. temporary works to keep flows | The Project Company shall be responsible for all interfaces with the existing collection network at the two designated tie-in points, including any temporary works required to maintain flows during construction. | The Project Company shall be responsible for all interfaces with the existing collection network at the two designated tie-in points, including any temporary works required to maintain flows during construction. | shall be responsible for all interfaces with the existing collection network at the two designated tie-in points, including any temporary works required to maintain flows during construction | VOL-II 1.3 p2 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim; the two designated tie-in points are not identified anywhere in the pack | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:1.3 (VOL-II p2; text layer) | I-VOL-II-MISSING
VOL-II-1.4-01 | VOL-II:1.4 | scope_of_works; utilities | Procure all utilities other than the grid connection point at the site boundary (which the Authority provides) | The Authority will provide the site free of encumbrance, together with a grid connection point at the site boundary. All other utilities shall be procured by the Project Company. | The Authority will provide the site free of encumbrance, together with a grid connection point at the site boundary. All other utilities shall be procured by the Project Company. | All other utilities shall be procured by the Project Company. | VOL-II 1.4 p2 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:1.4 (VOL-II p2; text layer)
VOL-II-2.1-01 | VOL-II:2.1 | design_basis; capacity | Design for a nominal capacity of 120,000 m3/day average daily flow at the inlet works, at the Table 2-2 design-year influent | The Facility shall be designed for a nominal treatment capacity of 120,000 m³/day average daily flow, measured at the inlet works, at the design year influent characteristics stated in Table 2-2. | The Facility shall be designed for a nominal treatment capacity of 120,000 m³/day average daily flow, measured at the inlet works, at the design year influent characteristics stated in Table 2-2. | designed for a nominal treatment capacity of 120,000 m³/day average daily flow, measured at the inlet works | VOL-II 2.1 p2 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause and table | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:2.1 (VOL-II p2; text layer)
VOL-II-2.2-01 | VOL-II:2.2 | design_basis; design_life | Design life of all civil structures of at least 50 years | The design life of all civil structures shall be not less than fifty (50) years. The design life of mechanical and electrical equipment shall be not less than twenty (20) years or the manufacturer's rated life, whichever is the shorter, with lifecycle replacement provided for in the Project Company's lifecycle plan. | The design life of all civil structures shall be not less than fifty (50) years. The design life of mechanical and electrical equipment shall be not less than twenty (20) years or the manufacturer's rated life, whichever is the shorter, with lifecycle replacement provided for in the Project Company's lifecycle plan. | The design life of all civil structures shall be not less than fifty (50) years. | VOL-II 2.2 p2 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:2.2 (VOL-II p2; text layer)
VOL-II-2.2-02 | VOL-II:2.2 | design_basis; design_life; lifecycle | M&E design life of at least 20 years or the manufacturer's rated life, whichever is shorter; lifecycle replacement in the lifecycle plan | The design life of all civil structures shall be not less than fifty (50) years. The design life of mechanical and electrical equipment shall be not less than twenty (20) years or the manufacturer's rated life, whichever is the shorter, with lifecycle replacement provided for in the Project Company's lifecycle plan. | The design life of all civil structures shall be not less than fifty (50) years. The design life of mechanical and electrical equipment shall be not less than twenty (20) years or the manufacturer's rated life, whichever is the shorter, with lifecycle replacement provided for in the Project Company's lifecycle plan. | The design life of mechanical and electrical equipment shall be not less than twenty (20) years or the manufacturer's rated life, whichever is the shorter, with lifecycle replacement provided for in the Project Company's lifecycle plan. | VOL-II 2.2 p2 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:2.2 (VOL-II p2; text layer)
VOL-II-2.3-01 | VOL-II:2.3 | design_basis; future_expansion | Space for a future 50% expansion of nominal capacity without demolishing permanent structures (space provision only) | The Facility shall be designed to accommodate a future expansion of 50% of nominal capacity without demolition of permanent structures. Space provision only is required; no expansion works form part of the Works. | The Facility shall be designed to accommodate a future expansion of 50% of nominal capacity without demolition of permanent structures. Space provision only is required; no expansion works form part of the Works. | designed to accommodate a future expansion of 50% of nominal capacity without demolition of permanent structures | VOL-II 2.3 p2 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:2.3 (VOL-II p2; text layer)
VOL-II-2.4-01 | VOL-II:2.4 | technical_design; effluent; permit | Treated effluent to comply at all times with the Table 2-4 parameters (reproduced from the Environmental Permit, which prevails) | The treated effluent shall at all times comply with the parameters set out in Table 2-4. Table 2-4 is reproduced overleaf from the Environmental Permit issued for the site and is incorporated into this Volume by reference. | The treated effluent shall at all times comply with the parameters set out in Table 2-4. Table 2-4 is reproduced overleaf from the Environmental Permit issued for the site and is incorporated into this Volume by reference. | The treated effluent shall at all times comply with the parameters set out in Table 2-4. | VOL-II 2.4 p2 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim text-layer clause; the table it incorporates is an image reading pending review and the Permit that prevails is not supplied | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:2.4 (VOL-II p2; text layer) | I-PERMIT; I-READING-T24; I-VOL-II-T24-TENSIONS
VOL-II-2.5-01 | VOL-II:2.5 | technical_design; monitoring; image | Continuous online monitoring of the Table 2-4 parameters assessed on a continuous basis, with real-time signals to the Authority | The Project Company shall install continuous online monitoring for those parameters identified in Table 2-4 as assessed on a continuous basis, with signals available to the Authority in real time. | The Project Company shall install continuous online monitoring for those parameters identified in Table 2-4 as assessed on a continuous basis, with signals available to the Authority in real time. | shall install continuous online monitoring for those parameters identified in Table 2-4 as assessed on a continuous basis, with signals available to the Authority in real time | VOL-II 2.5 p2 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim clause, but the parameters it selects come from an image reading still pending review | pending | proposed (not reviewed) | n/a | VOL-II:2.5 (VOL-II p2; text layer) | I-READING-T24
VOL-II-T2-4-BOD5 | VOL-II:T2-4 | technical_design; effluent; image | Treated effluent Biochemical Oxygen Demand (BOD5): value shown in Table 2-4, unit and basis of assessment | Parameter: Biochemical Oxygen Demand (BOD5) ¦ Unit: mg/l ¦ Limit: 10 ¦ Basis of assessment: 30-day rolling average | Parameter: Biochemical Oxygen Demand (BOD5) ¦ Unit: mg/l ¦ Limit: 10 ¦ Basis of assessment: 30-day rolling average | Limit: 10 | VOL-II T2-4/BOD5 p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: value and basis come from an image reading still pending review; the Environmental Permit, which prevails, is not supplied | pending | proposed (not reviewed) | n/a | VOL-II:T2-4/BOD5 (VOL-II p3; image reading) | I-PERMIT; I-READING-T24
VOL-II-T2-4-COD | VOL-II:T2-4 | technical_design; effluent; image | Treated effluent Chemical Oxygen Demand (COD): value shown in Table 2-4, unit and basis of assessment | Parameter: Chemical Oxygen Demand (COD) ¦ Unit: mg/l ¦ Limit: 50 ¦ Basis of assessment: 30-day rolling average | Parameter: Chemical Oxygen Demand (COD) ¦ Unit: mg/l ¦ Limit: 50 ¦ Basis of assessment: 30-day rolling average | Limit: 50 | VOL-II T2-4/COD p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: value and basis come from an image reading still pending review; the Environmental Permit, which prevails, is not supplied | pending | proposed (not reviewed) | n/a | VOL-II:T2-4/COD (VOL-II p3; image reading) | I-PERMIT; I-READING-T24
VOL-II-T2-4-TSS | VOL-II:T2-4 | technical_design; effluent; image | Treated effluent Total Suspended Solids (TSS): value shown in Table 2-4, unit and basis of assessment | Parameter: Total Suspended Solids (TSS) ¦ Unit: mg/l ¦ Limit: 10 ¦ Basis of assessment: 30-day rolling average | Parameter: Total Suspended Solids (TSS) ¦ Unit: mg/l ¦ Limit: 15 ¦ Basis of assessment: Maximum, any single sample | Limit: 15 | VOL-II T2-4/TSS p3 as amended by ADD-03 10.1 p2 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | AMENDED (ADD-03/10.1(a), ADD-03/10.1(b)) | none stated in the documents |  |  | medium: value and basis come from an image reading still pending review; the Environmental Permit, which prevails, is not supplied | pending | proposed (not reviewed) | ADD-03/10.1(a): proposed; ADD-03/10.1(b): proposed | VOL-II:T2-4/TSS (VOL-II p3; image reading); ADD-03/10.1(a) [proposed] <- ADD-03:10.1 (ADD-03 p2); ADD-03/10.1(b) [proposed] <- ADD-03:10.1 (ADD-03 p2) | I-PERMIT; I-READING-T24
VOL-II-T2-4-TP | VOL-II:T2-4 | technical_design; effluent; image | Treated effluent Total Phosphorus (TP): value shown in Table 2-4, unit and basis of assessment | Parameter: Total Phosphorus (TP) ¦ Unit: mg/l ¦ Limit: 1 ¦ Basis of assessment: 30-day rolling average | Parameter: Total Phosphorus (TP) ¦ Unit: mg/l ¦ Limit: 1 ¦ Basis of assessment: 30-day rolling average | Limit: 1 | VOL-II T2-4/TP p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: value and basis come from an image reading still pending review; the Environmental Permit, which prevails, is not supplied | pending | proposed (not reviewed) | n/a | VOL-II:T2-4/TP (VOL-II p3; image reading) | I-PERMIT; I-READING-T24
VOL-II-T2-4-Turbidity | VOL-II:T2-4 | technical_design; effluent; image | Treated effluent turbidity: value shown in Table 2-4, unit and basis of assessment | Parameter: Turbidity ¦ Unit: NTU ¦ Limit: 2 ¦ Basis of assessment: Maximum instantaneous | Parameter: Turbidity ¦ Unit: NTU ¦ Limit: 2 ¦ Basis of assessment: Maximum instantaneous | Limit: 2 | VOL-II T2-4/Turbidity p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: value and basis come from an image reading still pending review; the Environmental Permit, which prevails, is not supplied | pending | proposed (not reviewed) | n/a | VOL-II:T2-4/Turbidity (VOL-II p3; image reading) | I-PERMIT; I-READING-T24
VOL-II-T2-4-FaecalColiforms | VOL-II:T2-4 | technical_design; effluent; image | Treated effluent faecal coliforms: value shown in Table 2-4, unit and basis of assessment | Parameter: Faecal Coliforms ¦ Unit: MPN/100 ml ¦ Limit: 2.2 ¦ Basis of assessment: Maximum, any single sample | Parameter: Faecal Coliforms ¦ Unit: MPN/100 ml ¦ Limit: 2.2 ¦ Basis of assessment: Maximum, any single sample | Limit: 2.2 | VOL-II T2-4/FaecalColiforms p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: value and basis come from an image reading still pending review; the Environmental Permit, which prevails, is not supplied | pending | proposed (not reviewed) | n/a | VOL-II:T2-4/FaecalColiforms (VOL-II p3; image reading) | I-PERMIT; I-READING-T24
VOL-II-T2-4-ResidualChlorine | VOL-II:T2-4 | technical_design; effluent; image; disinfection | Treated effluent residual chlorine: range shown in Table 2-4, unit and basis of assessment | Parameter: Residual Chlorine ¦ Unit: mg/l ¦ Limit: 0.5 - 1.0 ¦ Basis of assessment: Continuous at outlet | Parameter: Residual Chlorine ¦ Unit: mg/l ¦ Limit: 0.5 - 1.0 ¦ Basis of assessment: Continuous at outlet | Limit: 0.5 - 1.0 | VOL-II T2-4/ResidualChlorine p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: from an image reading still pending review; the Permit is not supplied; tension with VOL-II 3.3 recorded as an issue | pending | proposed (not reviewed) | n/a | VOL-II:T2-4/ResidualChlorine (VOL-II p3; image reading) | I-PERMIT; I-READING-T24; I-VOL-II-T24-TENSIONS
VOL-II-T2-4-pH | VOL-II:T2-4 | technical_design; effluent; image | Treated effluent pH: range shown in Table 2-4 and basis of assessment | Parameter: pH ¦ Unit: - ¦ Limit: 6.0 - 9.0 ¦ Basis of assessment: Continuous at outlet | Parameter: pH ¦ Unit: - ¦ Limit: 6.0 - 9.0 ¦ Basis of assessment: Continuous at outlet | Limit: 6.0 - 9.0 | VOL-II T2-4/pH p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: from an image reading still pending review; the Environmental Permit, which prevails, is not supplied | pending | proposed (not reviewed) | n/a | VOL-II:T2-4/pH (VOL-II p3; image reading) | I-PERMIT; I-READING-T24; I-VOL-II-T24-TENSIONS
VOL-II-T2-4-OilGrease | VOL-II:T2-4 | technical_design; effluent; image | Treated effluent oil and grease: value shown in Table 2-4, unit and basis of assessment | Parameter: Oil and Grease ¦ Unit: mg/l ¦ Limit: 1 ¦ Basis of assessment: Maximum, any single sample | Parameter: Oil and Grease ¦ Unit: mg/l ¦ Limit: 1 ¦ Basis of assessment: Maximum, any single sample | Limit: 1 | VOL-II T2-4/OilGrease p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: value and basis come from an image reading still pending review; the Environmental Permit, which prevails, is not supplied | pending | proposed (not reviewed) | n/a | VOL-II:T2-4/OilGrease (VOL-II p3; image reading) | I-PERMIT; I-READING-T24
VOL-II-T2-4-NOTE1 | VOL-II:T2-4 | technical_design; effluent; image; permit | Parameters not listed in Table 2-4: the limits stated in the Environmental Permit apply (the Permit is not in the pack) | Note 1: Where a parameter is not listed above, the limit stated in the Environmental Permit shall apply. | Note 1: Where a parameter is not listed above, the limit stated in the Environmental Permit shall apply. | Where a parameter is not listed above, the limit stated in the Environmental Permit shall apply. | VOL-II T2-4/note1 p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | low: image reading pending review; the Permit and its limits are not supplied, so these limits cannot be identified from the pack | pending | proposed (not reviewed) | n/a | VOL-II:T2-4/note1 (VOL-II p3; image reading) | I-PERMIT; I-READING-T24
VOL-II-3.1-01 | VOL-II:3.1 | technical_design; process | Treatment process able to achieve the Table 2-4 effluent quality under all Table 2-2 design influent conditions | The treatment process shall be capable of achieving the effluent quality in Table 2-4 under all design influent conditions in Table 2-2. The Authority does not mandate a particular process train. | The treatment process shall be capable of achieving the effluent quality in Table 2-4 under all design influent conditions in Table 2-2. The Authority does not mandate a particular process train. | The treatment process shall be capable of achieving the effluent quality in Table 2-4 under all design influent conditions in Table 2-2. | VOL-II 3.1 p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim; the effluent quality it refers to is an image reading pending review and the Permit that prevails is not supplied | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:3.1 (VOL-II p3; text layer) | I-READING-T24; I-PERMIT
VOL-II-3.2-01 | VOL-II:3.2 | technical_design; process; membrane; lifecycle | If a membrane process is proposed: show membrane replacement provisions in the lifecycle plan | Where a membrane process is proposed, the Project Company shall demonstrate membrane replacement provisions in the lifecycle plan and shall warrant a membrane life of not less than seven (7) years. | Where a membrane process is proposed, the Project Company shall demonstrate membrane replacement provisions in the lifecycle plan and shall warrant a membrane life of not less than seven (7) years. | Where a membrane process is proposed, the Project Company shall demonstrate membrane replacement provisions in the lifecycle plan | VOL-II 3.2 p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:3.2 (VOL-II p3; text layer)
VOL-II-3.2-02 | VOL-II:3.2 | technical_design; process; membrane; warranty | If a membrane process is proposed: warrant a membrane life of at least 7 years | Where a membrane process is proposed, the Project Company shall demonstrate membrane replacement provisions in the lifecycle plan and shall warrant a membrane life of not less than seven (7) years. | Where a membrane process is proposed, the Project Company shall demonstrate membrane replacement provisions in the lifecycle plan and shall warrant a membrane life of not less than seven (7) years. | shall warrant a membrane life of not less than seven (7) years | VOL-II 3.2 p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:3.2 (VOL-II p3; text layer)
VOL-II-3.3-01 | VOL-II:3.3 | technical_design; process; disinfection | Disinfection by chlorination with dechlorination provision, by UV with a validated dose, or both; ozonation alone not acceptable | Disinfection shall be by chlorination with provision for dechlorination, or by ultraviolet irradiation with a validated dose, or by a combination. Ozonation alone is not acceptable. | Disinfection shall be by chlorination with provision for dechlorination, or by ultraviolet irradiation with a validated dose, or by a combination. Ozonation alone is not acceptable. | Disinfection shall be by chlorination with provision for dechlorination, or by ultraviolet irradiation with a validated dose, or by a combination. | VOL-II 3.3 p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause; the tension with Table 2-4 is recorded as an issue | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:3.3 (VOL-II p3; text layer) | I-VOL-II-T24-TENSIONS
VOL-II-3.4-01 | VOL-II:3.4 | environmental_performance; odour | Odour at the site boundary of no more than 5 OU/m3 as a 98th percentile hourly value | Odour control shall achieve not more than 5 OU/m³ at the site boundary, assessed as a 98th percentile hourly value. | Odour control shall achieve not more than 5 OU/m³ at the site boundary, assessed as a 98th percentile hourly value. | Odour control shall achieve not more than 5 OU/m³ at the site boundary, assessed as a 98th percentile hourly value. | VOL-II 3.4 p3 | scored | Environmental | Environmental lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:3.4 (VOL-II p3; text layer)
VOL-II-3.5-01 | VOL-II:3.5 | environmental_performance; noise | Noise at the nearest sensitive receptor of no more than 55 dB(A) by day and 45 dB(A) by night | Noise at the nearest sensitive receptor shall not exceed 55 dB(A) by day and 45 dB(A) by night. | Noise at the nearest sensitive receptor shall not exceed 55 dB(A) by day and 45 dB(A) by night. | Noise at the nearest sensitive receptor shall not exceed 55 dB(A) by day and 45 dB(A) by night. | VOL-II 3.5 p3 | scored | Environmental | Environmental lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:3.5 (VOL-II p3; text layer)
VOL-II-4.1-01 | VOL-II:4.1 | technical_design; hydraulics | Hydraulic profile to pass the Table 2-6 flows without surcharging any structure or relying on pumped bypass | The hydraulic profile shall accommodate the flows in Table 2-6 without surcharge of any structure and without reliance on pumped bypass. | The hydraulic profile shall accommodate the flows in Table 2-6 without surcharge of any structure and without reliance on pumped bypass. | The hydraulic profile shall accommodate the flows in Table 2-6 without surcharge of any structure and without reliance on pumped bypass. | VOL-II 4.1 p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim; the Table 2-6 peak hourly and storm flows are questioned and ADD-02 Q11 did not resolve them | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:4.1 (VOL-II p3; text layer) | I-FLOWS
VOL-II-T2-6-1 | VOL-II:T2-6 | technical_design; hydraulics; design_flow | Hydraulic design criterion 2-6.1: average daily flow of 120,000 m3/day | Ref: 2-6.1 ¦ Criterion: Average daily flow ¦ Value: 120,000 ¦ Unit: m³/day | Ref: 2-6.1 ¦ Criterion: Average daily flow ¦ Value: 120,000 ¦ Unit: m³/day | Value: 120,000 | VOL-II T2-6/2-6.1 p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim table row; the consistency of the Table 2-6 flows is questioned (I-FLOWS) | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:T2-6/2-6.1 (VOL-II p3; text layer) | I-FLOWS
VOL-II-T2-6-2 | VOL-II:T2-6 | technical_design; hydraulics; design_flow | Hydraulic design criterion 2-6.2: the peak hourly flow (design) Table 2-6 states | Ref: 2-6.2 ¦ Criterion: Peak hourly flow (design) ¦ Value: 7,500 ¦ Unit: m³/h | Ref: 2-6.2 ¦ Criterion: Peak hourly flow (design) ¦ Value: 9,000 ¦ Unit: m³/h | Value: 9,000 | VOL-II T2-6/2-6.2 p3 as amended by ADD-03 11.1 p2 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | AMENDED (ADD-03/11.1) | none stated in the documents |  |  | medium: verbatim table row; questioned in ADD-02 Q11 against the 120,000 m3/day average, and not answered (I-FLOWS) | n/a (text layer) | proposed (not reviewed) | ADD-03/11.1: proposed | VOL-II:T2-6/2-6.2 (VOL-II p3; text layer); ADD-03/11.1 [proposed] <- ADD-03:11.1 (ADD-03 p2) | I-FLOWS
VOL-II-T2-6-3 | VOL-II:T2-6 | technical_design; hydraulics; design_flow | Hydraulic design criterion 2-6.3: minimum night flow of 1,800 m3/h | Ref: 2-6.3 ¦ Criterion: Minimum night flow ¦ Value: 1,800 ¦ Unit: m³/h | Ref: 2-6.3 ¦ Criterion: Minimum night flow ¦ Value: 1,800 ¦ Unit: m³/h | Value: 1,800 | VOL-II T2-6/2-6.3 p4 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim table row | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:T2-6/2-6.3 (VOL-II p4; text layer)
VOL-II-T2-6-4 | VOL-II:T2-6 | technical_design; hydraulics; design_flow; storm | Hydraulic design criterion 2-6.4: pass storm flow of 3 x dry weather flow to full treatment | Ref: 2-6.4 ¦ Criterion: Storm flow to be passed to full treatment ¦ Value: 3 x dry weather flow ¦ Unit: — | Ref: 2-6.4 ¦ Criterion: Storm flow to be passed to full treatment ¦ Value: 3 x dry weather flow ¦ Unit: — | Value: 3 x dry weather flow | VOL-II T2-6/2-6.4 p4 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim table row; dry weather flow is undefined and 3 x DWF may exceed the 7,500 m3/h design peak (I-FLOWS) | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:T2-6/2-6.4 (VOL-II p4; text layer) | I-FLOWS
VOL-II-T2-6-5 | VOL-II:T2-6 | technical_design; hydraulics | Hydraulic design criterion 2-6.5: inlet works design head of 1.8 m | Ref: 2-6.5 ¦ Criterion: Inlet works design head ¦ Value: 1.8 ¦ Unit: m | Ref: 2-6.5 ¦ Criterion: Inlet works design head ¦ Value: 1.8 ¦ Unit: m | Value: 1.8 | VOL-II T2-6/2-6.5 p4 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim table row | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:T2-6/2-6.5 (VOL-II p4; text layer)
VOL-II-T2-6-6 | VOL-II:T2-6 | technical_design; hydraulics | Hydraulic design criterion 2-6.6: maximum velocity in channels of 1.2 m/s | Ref: 2-6.6 ¦ Criterion: Maximum velocity in channels ¦ Value: 1.2 ¦ Unit: m/s | Ref: 2-6.6 ¦ Criterion: Maximum velocity in channels ¦ Value: 1.2 ¦ Unit: m/s | Value: 1.2 | VOL-II T2-6/2-6.6 p4 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim table row | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:T2-6/2-6.6 (VOL-II p4; text layer)
VOL-II-4.2-01 | VOL-II:4.2 | clarification; hydraulics; design_flow | Check the consistency of the Volume II flow figures and raise any inconsistency as a clarification under VOL-I 5.1 | The Project Company shall satisfy itself as to the consistency of the flow figures stated in this Volume and shall raise any inconsistency as a clarification under Volume I Clause 5.1. | The Project Company shall satisfy itself as to the consistency of the flow figures stated in this Volume and shall raise any inconsistency as a clarification under Volume I Clause 5.1. | shall satisfy itself as to the consistency of the flow figures stated in this Volume and shall raise any inconsistency as a clarification under Volume I Clause 5.1 | VOL-II 4.2 p4 | procedural | Technical | Process engineer | EV-CLARIFICATIONS | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim; the ADD-02 Q11 answer refers back to this clause without resolving the figures | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:4.2 (VOL-II p4; text layer) | I-FLOWS
VOL-II-4.3-01 | VOL-II:4.3 | technical_design; reliability; redundancy | Each treatment stage arranged in at least four parallel streams | Each treatment stage shall be arranged in not fewer than four (4) parallel streams, such that the Facility can meet Table 2-4 with any one stream out of service. | Each treatment stage shall be arranged in not fewer than four (4) parallel streams, such that the Facility can meet Table 2-4 with any one stream out of service. | Each treatment stage shall be arranged in not fewer than four (4) parallel streams | VOL-II 4.3 p4 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:4.3 (VOL-II p4; text layer)
VOL-II-4.3-02 | VOL-II:4.3 | technical_design; reliability; redundancy; effluent | Facility able to meet Table 2-4 with any one stream out of service | Each treatment stage shall be arranged in not fewer than four (4) parallel streams, such that the Facility can meet Table 2-4 with any one stream out of service. | Each treatment stage shall be arranged in not fewer than four (4) parallel streams, such that the Facility can meet Table 2-4 with any one stream out of service. | such that the Facility can meet Table 2-4 with any one stream out of service | VOL-II 4.3 p4 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim; the Table 2-4 limits it refers to are an image reading pending review | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:4.3 (VOL-II p4; text layer) | I-READING-T24
VOL-II-4.4-02 | VOL-II:4.4 | technical_design; reliability; redundancy | N+1 standby provision for all rotating equipment | Standby provision for all rotating equipment shall be N+1. Standby power shall be sized to carry the full inlet works, the disinfection stage and the effluent pumping station for not less than seventy-two (72) hours. | Standby provision for all rotating equipment shall be N+1. Standby power shall be sized to carry the full inlet works, the disinfection stage and the effluent pumping station for not less than ninety-six (96) hours. | Standby provision for all rotating equipment shall be N+1. | VOL-II 4.4 p4 as amended by ADD-02 4.1 p1 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | AMENDED (ADD-02/4.1) | ACTIVE (as amended by ADD-02/4.1) | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | ADD-02/4.1: proposed | VOL-II:4.4 (VOL-II p4; text layer); ADD-02/4.1 [proposed] <- ADD-02:4.1 (ADD-02 p1)
VOL-II-4.5-01 | VOL-II:4.5 | technical_design; transmission_main; surge | Surge protection on the transmission main for the full range of operating scenarios, including simultaneous pump trip | The transmission main shall be provided with surge protection designed for the full range of operating scenarios including simultaneous pump trip. | The transmission main shall be provided with surge protection designed for the full range of operating scenarios including simultaneous pump trip. | The transmission main shall be provided with surge protection designed for the full range of operating scenarios including simultaneous pump trip. | VOL-II 4.5 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:4.5 (VOL-II p4; text layer)
VOL-II-5.1-01 | VOL-II:5.1 | technical_design; transmission_main; route | Treated effluent main of about 18 km from the Facility outlet chamber to the delivery point shown on Drawing 03-C-114 | The treated effluent transmission main shall be approximately eighteen (18) kilometres in length between the Facility outlet chamber and the delivery point shown on Drawing 03-C-114. | The treated effluent transmission main shall be approximately eighteen (18) kilometres in length between the Facility outlet chamber and the delivery point shown on Drawing 03-C-114. | approximately eighteen (18) kilometres in length between the Facility outlet chamber and the delivery point shown on Drawing 03-C-114 | VOL-II 5.1 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | low: the delivery point is shown only on Drawing 03-C-114 (Volume III), which is not supplied; route and end point cannot be established | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:5.1 (VOL-II p4; text layer) | I-VOL-III
VOL-II-5.2-01 | VOL-II:5.2 | technical_design; transmission_main; hydraulics | Size the main for the Table 2-6 peak hourly flow at a velocity of no more than 2.0 m/s | The main shall be sized for the peak hourly flow in Table 2-6 with a maximum velocity of 2.0 m/s and a minimum residual head of 15 m at the delivery point. | The main shall be sized for the peak hourly flow in Table 2-6 with a maximum velocity of 2.0 m/s and a minimum residual head of 15 m at the delivery point. | The main shall be sized for the peak hourly flow in Table 2-6 with a maximum velocity of 2.0 m/s | VOL-II 5.2 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE — STALE | none stated in the documents |  |  | medium: verbatim; the peak hourly flow it is sized for is questioned (I-FLOWS) | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:5.2 (VOL-II p4; text layer) | I-FLOWS
VOL-II-5.2-02 | VOL-II:5.2 | technical_design; transmission_main; hydraulics | Minimum residual head of 15 m at the delivery point | The main shall be sized for the peak hourly flow in Table 2-6 with a maximum velocity of 2.0 m/s and a minimum residual head of 15 m at the delivery point. | The main shall be sized for the peak hourly flow in Table 2-6 with a maximum velocity of 2.0 m/s and a minimum residual head of 15 m at the delivery point. | a minimum residual head of 15 m at the delivery point | VOL-II 5.2 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim; the delivery point is shown only on Drawing 03-C-114, which is not supplied | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:5.2 (VOL-II p4; text layer) | I-VOL-III
VOL-II-5.3-01 | VOL-II:5.3 | technical_design; transmission_main; materials | Main of internally lined, externally protected ductile iron; other materials only with a whole-life cost comparison | The main shall be of ductile iron to the relevant international standard, internally lined and externally protected, with a minimum nominal diameter of DN1200. Alternative materials will be considered only where supported by a whole-life cost comparison. | The main shall be of ductile iron to the relevant international standard, internally lined and externally protected, with a minimum nominal diameter of DN1200. Alternative materials will be considered only where supported by a whole-life cost comparison. Glass reinforced plastic pipe of an equivalent pressure class is acceptable for the buried sections of the transmission main, subject to the whole-life cost comparison required by this Clause. | Glass reinforced plastic pipe of an equivalent pressure class is acceptable for the buried sections of the transmission main, subject to the whole-life cost comparison required by this Clause. | ADD-01 5.1 p1 (amending VOL-II 5.3) | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | AMENDED (ADD-01/5.1) | ACTIVE (as amended by ADD-01/5.1) | ACTIVE (as amended by ADD-01/5.1) | none stated in the documents |  |  | high: verbatim at each stage; the applicable international standard is not named | n/a (text layer) | proposed (not reviewed) | ADD-01/5.1: proposed | VOL-II:5.3 (VOL-II p4; text layer); ADD-01/5.1 [proposed] <- ADD-01:5.1 (ADD-01 p1)
VOL-II-5.3-02 | VOL-II:5.3 | technical_design; transmission_main | Main of minimum nominal diameter DN1200 | The main shall be of ductile iron to the relevant international standard, internally lined and externally protected, with a minimum nominal diameter of DN1200. Alternative materials will be considered only where supported by a whole-life cost comparison. | The main shall be of ductile iron to the relevant international standard, internally lined and externally protected, with a minimum nominal diameter of DN1200. Alternative materials will be considered only where supported by a whole-life cost comparison. Glass reinforced plastic pipe of an equivalent pressure class is acceptable for the buried sections of the transmission main, subject to the whole-life cost comparison required by this Clause. | with a minimum nominal diameter of DN1200 | VOL-II 5.3 p4 as amended by ADD-01 5.1 p1 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | AMENDED (ADD-01/5.1) | ACTIVE (as amended by ADD-01/5.1) | ACTIVE (as amended by ADD-01/5.1) | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | ADD-01/5.1: proposed | VOL-II:5.3 (VOL-II p4; text layer); ADD-01/5.1 [proposed] <- ADD-01:5.1 (ADD-01 p1)
VOL-II-5.4-01 | VOL-II:5.4 | technical_design; transmission_main; crossings | Execute the three road crossings and the wadi crossing by trenchless methods | Three (3) road crossings and one (1) wadi crossing shall be executed by trenchless methods. Crossing permits shall be obtained by the Project Company. | Three (3) road crossings and one (1) wadi crossing shall be executed by trenchless methods. Crossing permits shall be obtained by the Project Company. | Three (3) road crossings and one (1) wadi crossing shall be executed by trenchless methods. | VOL-II 5.4 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim; ground conditions at the wadi crossing are the Bidder's risk (ADD-01 Q4) and the geotechnical report is in the data room, not the pack | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:5.4 (VOL-II p4; text layer) | I-VOL-II-MISSING
VOL-II-5.4-02 | VOL-II:5.4 | permits; transmission_main; crossings | Obtain the crossing permits | Three (3) road crossings and one (1) wadi crossing shall be executed by trenchless methods. Crossing permits shall be obtained by the Project Company. | Three (3) road crossings and one (1) wadi crossing shall be executed by trenchless methods. Crossing permits shall be obtained by the Project Company. | Crossing permits shall be obtained by the Project Company. | VOL-II 5.4 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:5.4 (VOL-II p4; text layer)
VOL-II-5.5-01 | VOL-II:5.5 | technical_design; civil; seismic | Design permanent civil structures for a seismic event with a 475-year return period | All permanent civil structures shall be designed for a seismic event with a return period of 475 years and for a flood with a return period of 100 years. | All permanent civil structures shall be designed for a seismic event with a return period of 475 years and for a flood with a return period of 100 years. | designed for a seismic event with a return period of 475 years | VOL-II 5.5 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:5.5 (VOL-II p4; text layer)
VOL-II-5.5-02 | VOL-II:5.5 | technical_design; civil; flood | Design permanent civil structures for a flood with a 100-year return period | All permanent civil structures shall be designed for a seismic event with a return period of 475 years and for a flood with a return period of 100 years. | All permanent civil structures shall be designed for a seismic event with a return period of 475 years and for a flood with a return period of 100 years. | for a flood with a return period of 100 years | VOL-II 5.5 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:5.5 (VOL-II p4; text layer)
VOL-II-6.1-01 | VOL-II:6.1 | technical_design; scada | SCADA system capable of unattended operation of the whole Facility | The Facility shall be provided with a SCADA system capable of unattended operation of the whole Facility, with a permanently manned central control room. | The Facility shall be provided with a SCADA system capable of unattended operation of the whole Facility, with a central control room manned between 06:00 and 22:00 daily. | The Facility shall be provided with a SCADA system capable of unattended operation of the whole Facility | VOL-II 6.1 p4 as amended by ADD-03 Q16 p2 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | AMENDED (ADD-03/Q16) — STALE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | ADD-03/Q16: proposed | VOL-II:6.1 (VOL-II p4; text layer); ADD-03/Q16 [proposed] <- ADD-03:Q16 (ADD-03 p2)
VOL-II-6.1-02 | VOL-II:6.1 | technical_design; scada; staffing | A permanently manned central control room | The Facility shall be provided with a SCADA system capable of unattended operation of the whole Facility, with a permanently manned central control room. | The Facility shall be provided with a SCADA system capable of unattended operation of the whole Facility, with a central control room manned between 06:00 and 22:00 daily. | with a central control room manned between 06:00 and 22:00 daily | VOL-II 6.1 p4 as amended by ADD-03 Q16 p2 | scored | Operations | O&M lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | AMENDED (ADD-03/Q16) | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | ADD-03/Q16: proposed | VOL-II:6.1 (VOL-II p4; text layer); ADD-03/Q16 [proposed] <- ADD-03:Q16 (ADD-03 p2)
VOL-II-6.2-01 | VOL-II:6.2 | technical_design; cyber_security | Control system segregated from any business network by a DMZ, with one-way data flow to the Authority's monitoring interface | The industrial control system shall be segregated from any business network by a demilitarised zone with unidirectional data flow to the Authority's monitoring interface. | The industrial control system shall be segregated from any business network by a demilitarised zone with unidirectional data flow to the Authority's monitoring interface. | The industrial control system shall be segregated from any business network by a demilitarised zone with unidirectional data flow to the Authority's monitoring interface. | VOL-II 6.2 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause; Form 4-G undertaking 1 (ADD-02) restates this segregation | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:6.2 (VOL-II p4; text layer)
VOL-II-6.3-01 | VOL-II:6.3 | technical_design; cyber_security | Implement and maintain an information security management system covering the operational technology environment | The Project Company shall implement and maintain an information security management system covering the operational technology environment, and shall submit its security architecture for the Authority's review prior to commissioning. | The Project Company shall implement and maintain an information security management system covering the operational technology environment, and shall submit its security architecture for the Authority's review prior to commissioning. | shall implement and maintain an information security management system covering the operational technology environment | VOL-II 6.3 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause; Form 4-G undertakings 3-6 (ADD-02) add cyber obligations not in this clause (I-F4G-NO) | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:6.3 (VOL-II p4; text layer)
VOL-II-6.3-02 | VOL-II:6.3 | cyber_security; submission_to_authority | Submit the security architecture for the Authority's review before commissioning | The Project Company shall implement and maintain an information security management system covering the operational technology environment, and shall submit its security architecture for the Authority's review prior to commissioning. | The Project Company shall implement and maintain an information security management system covering the operational technology environment, and shall submit its security architecture for the Authority's review prior to commissioning. | shall submit its security architecture for the Authority's review prior to commissioning | VOL-II 6.3 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  | VOL-II-SECURITY-ARCHITECTURE-DUE: None (unknown_anchor) | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:6.3 (VOL-II p4; text layer)
VOL-II-6.4-01 | VOL-II:6.4 | operations; data_retention | Retain all process data for at least seven years | All process data shall be retained for not less than seven (7) years and shall be made available to the Authority on demand in a non-proprietary format. | All process data shall be retained for not less than seven (7) years and shall be made available to the Authority on demand in a non-proprietary format. | All process data shall be retained for not less than seven (7) years | VOL-II 6.4 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:6.4 (VOL-II p4; text layer)
VOL-II-6.4-02 | VOL-II:6.4 | operations; data_access | Make process data available to the Authority on demand in a non-proprietary format | All process data shall be retained for not less than seven (7) years and shall be made available to the Authority on demand in a non-proprietary format. | All process data shall be retained for not less than seven (7) years and shall be made available to the Authority on demand in a non-proprietary format. | shall be made available to the Authority on demand in a non-proprietary format | VOL-II 6.4 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:6.4 (VOL-II p4; text layer)
VOL-II-7.1-01 | VOL-II:7.1 | commissioning; testing | Carry out FAT, SAT and integrated process commissioning under a commissioning plan approved by the Authority | The Project Company shall carry out factory acceptance testing, site acceptance testing, and integrated process commissioning in accordance with a commissioning plan approved by the Authority. | The Project Company shall carry out factory acceptance testing, site acceptance testing, and integrated process commissioning in accordance with a commissioning plan approved by the Authority. | shall carry out factory acceptance testing, site acceptance testing, and integrated process commissioning in accordance with a commissioning plan approved by the Authority | VOL-II 7.1 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:7.1 (VOL-II p4; text layer)
VOL-II-7.2-01 | VOL-II:7.2 | commissioning; pcod; reliability_run; effluent | Before PCOD: a 30-day continuous reliability run at 90% or more of nominal capacity meeting every Table 2-4 parameter | PCOD shall not be certified until the Facility has completed a continuous reliability run of thirty (30) days at not less than 90% of nominal capacity, during which every parameter in Table 2-4 has been met. | PCOD shall not be certified until the Facility has completed a continuous reliability run of thirty (30) days at not less than 90% of nominal capacity, during which every parameter in Table 2-4 has been met. | PCOD shall not be certified until the Facility has completed a continuous reliability run of thirty (30) days at not less than 90% of nominal capacity, during which every parameter in Table 2-4 has been met. | VOL-II 7.2 p4 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE — STALE | contractual remedy (post-award): "A failure of any Table 2-4 parameter during the reliability run shall restart the run in full." | VOL-II 7.3 p4 |  | medium: verbatim; every Table 2-4 parameter is an image reading pending review, and TN is amended by ADD-02 5.1 (row VOL-II-T2-4-TN) | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:7.2 (VOL-II p4; text layer) | I-READING-T24; I-PERMIT
VOL-II-7.4-01 | VOL-II:7.4 | commissioning; documentation; post_pcod | Provide as-built documents, O&M manuals and an asset register in the Authority's standard format within 60 days after PCOD | The Project Company shall provide as-built documentation, operation and maintenance manuals, and an asset register in the Authority's standard format not later than sixty (60) days after PCOD. | The Project Company shall provide as-built documentation, operation and maintenance manuals, and an asset register in the Authority's standard format not later than sixty (60) days after PCOD. | shall provide as-built documentation, operation and maintenance manuals, and an asset register in the Authority's standard format not later than sixty (60) days after PCOD | VOL-II 7.4 p5 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  | VOL-II-AS-BUILT-DUE: None (unknown_anchor) | medium: verbatim; the Authority's standard format is not in the pack; PCOD is not a pack event | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:7.4 (VOL-II p5; text layer) | I-VOL-II-MISSING
VOL-II-8.1-01 | VOL-II:8.1 | operations; maintenance; spares | Hold spares for two years of normal operation for all items with a lead time over 12 weeks | The Project Company shall hold a spare parts inventory sufficient for two (2) years of normal operation for all items with a lead time exceeding twelve (12) weeks. | The Project Company shall hold a spare parts inventory sufficient for two (2) years of normal operation for all items with a lead time exceeding twelve (12) weeks. | shall hold a spare parts inventory sufficient for two (2) years of normal operation for all items with a lead time exceeding twelve (12) weeks | VOL-II 8.1 p5 | scored | Operations | O&M lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:8.1 (VOL-II p5; text layer)
VOL-II-8.2-01 | VOL-II:8.2 | operations; maintenance; cmms | Implement a computerised maintenance management system before PCOD and keep it in use for the concession period | A computerised maintenance management system shall be implemented before PCOD and shall remain in use for the concession period. | A computerised maintenance management system shall be implemented before PCOD and shall remain in use for the concession period. | A computerised maintenance management system shall be implemented before PCOD and shall remain in use for the concession period. | VOL-II 8.2 p5 | scored | Operations | O&M lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  | VOL-II-CMMS-BY-PCOD: None (unknown_anchor) | high: verbatim text-layer clause; PCOD is not a pack event | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:8.2 (VOL-II p5; text layer)
VOL-II-8.3-01 | VOL-II:8.3 | operations; staffing | Employ a suitably qualified plant manager | The Project Company shall employ a suitably qualified plant manager and shall maintain a minimum of two (2) certified operators on shift at all times. | The Project Company shall employ a suitably qualified plant manager and shall maintain a minimum of two (2) certified operators on shift at all times. | shall employ a suitably qualified plant manager | VOL-II 8.3 p5 | scored | Operations | O&M lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause; 'suitably qualified' is not defined | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:8.3 (VOL-II p5; text layer)
VOL-II-8.3-02 | VOL-II:8.3 | operations; staffing | At least two certified operators on shift at all times | The Project Company shall employ a suitably qualified plant manager and shall maintain a minimum of two (2) certified operators on shift at all times. | The Project Company shall employ a suitably qualified plant manager and shall maintain a minimum of two (2) certified operators on shift at all times. | shall maintain a minimum of two (2) certified operators on shift at all times | VOL-II 8.3 p5 | scored | Operations | O&M lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:8.3 (VOL-II p5; text layer)
VOL-II-8.4-01 | VOL-II:8.4 | operations; sludge | Dewater sludge to at least 22% dry solids | Sludge shall be dewatered to not less than 22% dry solids and shall be disposed of or reused in accordance with the applicable regulations. Disposal to landfill of sludge exceeding 500 tonnes per annum shall require the Authority's prior written consent. | Sludge shall be dewatered to not less than 22% dry solids and shall be disposed of or reused in accordance with the applicable regulations. Disposal to landfill of sludge exceeding 500 tonnes per annum shall require the Authority's prior written consent. | Sludge shall be dewatered to not less than 22% dry solids | VOL-II 8.4 p5 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:8.4 (VOL-II p5; text layer)
VOL-II-8.4-02 | VOL-II:8.4 | operations; sludge; environmental_compliance | Dispose of or reuse sludge under the applicable regulations; landfill over 500 t/a only with the Authority's prior written consent | Sludge shall be dewatered to not less than 22% dry solids and shall be disposed of or reused in accordance with the applicable regulations. Disposal to landfill of sludge exceeding 500 tonnes per annum shall require the Authority's prior written consent. | Sludge shall be dewatered to not less than 22% dry solids and shall be disposed of or reused in accordance with the applicable regulations. Disposal to landfill of sludge exceeding 500 tonnes per annum shall require the Authority's prior written consent. | shall be disposed of or reused in accordance with the applicable regulations | VOL-II 8.4 p5 | scored | Environmental | Environmental lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:8.4 (VOL-II p5; text layer)
VOL-II-8.5-01 | VOL-II:8.5 | handback; survey | Carry out a handback condition survey in the final two years of the concession | A handback condition survey shall be carried out in the final two (2) years of the concession, and any remedial works identified shall be completed before transfer. | A handback condition survey shall be carried out in the final two (2) years of the concession, and any remedial works identified shall be completed before transfer. | A handback condition survey shall be carried out in the final two (2) years of the concession | VOL-II 8.5 p5 | scored | Operations | O&M lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  | VOL-II-HANDBACK-SURVEY-WINDOW: None (unknown_anchor) | medium: verbatim; when the concession ends depends on whether the term runs from the Effective Date or PCOD | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:8.5 (VOL-II p5; text layer) | I-CONCESSION
VOL-II-8.5-02 | VOL-II:8.5 | handback; remedial_works | Complete the remedial works the handback survey identifies before transfer | A handback condition survey shall be carried out in the final two (2) years of the concession, and any remedial works identified shall be completed before transfer. | A handback condition survey shall be carried out in the final two (2) years of the concession, and any remedial works identified shall be completed before transfer. | any remedial works identified shall be completed before transfer | VOL-II 8.5 p5 | scored | Operations | O&M lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  | VOL-II-HANDBACK-REMEDIALS-DUE: None (unknown_anchor) | medium: verbatim; the transfer date depends on the concession term start | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:8.5 (VOL-II p5; text layer) | I-CONCESSION
VOL-II-9.1-01 | VOL-II:9.1 | environmental_social; esia | Comply with the Environmental and Social Impact Assessment for the site (in the data room) | The Project Company shall comply with the Environmental and Social Impact Assessment prepared for the site and available in the data room, and shall prepare an Environmental and Social Management Plan aligned with the International Finance Corporation Performance Standards. | The Project Company shall comply with the Environmental and Social Impact Assessment prepared for the site and available in the data room, and shall prepare an Environmental and Social Management Plan aligned with the International Finance Corporation Performance Standards. | shall comply with the Environmental and Social Impact Assessment prepared for the site and available in the data room | VOL-II 9.1 p5 | scored | Environmental | Environmental lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim; the ESIA is in the data room, not in the pack, so what compliance requires cannot be read here | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:9.1 (VOL-II p5; text layer) | I-VOL-II-MISSING
VOL-II-9.1-02 | VOL-II:9.1 | environmental_social; esmp | Prepare an Environmental and Social Management Plan aligned with the IFC Performance Standards | The Project Company shall comply with the Environmental and Social Impact Assessment prepared for the site and available in the data room, and shall prepare an Environmental and Social Management Plan aligned with the International Finance Corporation Performance Standards. | The Project Company shall comply with the Environmental and Social Impact Assessment prepared for the site and available in the data room, and shall prepare an Environmental and Social Management Plan aligned with the International Finance Corporation Performance Standards. | shall prepare an Environmental and Social Management Plan aligned with the International Finance Corporation Performance Standards | VOL-II 9.1 p5 | scored | Environmental | Environmental lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:9.1 (VOL-II p5; text layer)
VOL-II-9.2-01 | VOL-II:9.2 | environmental_social; permits | Obtain environmental clearance from the national environmental regulator before construction starts | Environmental clearance shall be obtained from the competent national environmental regulator before commencement of construction. | Environmental clearance shall be obtained from the competent national environmental regulator before commencement of construction. | Environmental clearance shall be obtained from the competent national environmental regulator before commencement of construction. | VOL-II 9.2 p5 | scored | Environmental | Environmental lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  | VOL-II-ENV-CLEARANCE-DUE: None (unknown_anchor) | high: verbatim text-layer clause; the regulator is not named | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:9.2 (VOL-II p5; text layer)
VOL-II-9.3-01 | VOL-II:9.3 | environmental_social; grievance | Set up a grievance mechanism for the affected community before construction and keep it for the concession period | A grievance mechanism accessible to the affected community shall be established before construction and maintained for the concession period. | A grievance mechanism accessible to the affected community shall be established before construction and maintained for the concession period. | A grievance mechanism accessible to the affected community shall be established before construction and maintained for the concession period. | VOL-II 9.3 p5 | scored | Environmental | Environmental lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  | VOL-II-GRIEVANCE-DUE: None (unknown_anchor) | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:9.3 (VOL-II p5; text layer)
VOL-II-9.4-01 | VOL-II:9.4 | environmental_social; water | Do not abstract construction water from the local aquifer; use tankered supply or treated effluent | Construction water shall not be abstracted from the local aquifer. The Project Company shall source construction water from tankered supply or treated effluent. | Construction water shall not be abstracted from the local aquifer. The Project Company shall source construction water from tankered supply or treated effluent. | Construction water shall not be abstracted from the local aquifer. | VOL-II 9.4 p5 | scored | Environmental | Environmental lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:9.4 (VOL-II p5; text layer)
VOL-II-9.5-01 | VOL-II:9.5 | environmental_social; reporting | Report environmental and social performance to the Authority quarterly during construction and annually after | The Project Company shall report environmental and social performance to the Authority quarterly during construction and annually thereafter. | The Project Company shall report environmental and social performance to the Authority quarterly during construction and annually thereafter. | shall report environmental and social performance to the Authority quarterly during construction and annually thereafter | VOL-II 9.5 p5 | scored | Environmental | Environmental lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-II:9.5 (VOL-II p5; text layer)
VOL-IV-FORMS-01 | VOL-IV:cover/para5 | forms; wording | Reproduce every Form without alteration to its wording | Forms shall be reproduced without alteration to their wording. A Bidder that alters the wording of a Form does so at its own risk. | Forms shall be reproduced without alteration to their wording. A Bidder that alters the wording of a Form does so at its own risk. | Forms shall be reproduced without alteration to their wording. | VOL-IV cover/para5 p2 | procedural | Bid management | Bid manager | none: a rule on how each Form is reproduced; the Forms themselves are the deliverables of their own rows | ACTIVE | ACTIVE | ACTIVE | ACTIVE | lesser consequence: "A Bidder that alters the wording of a Form does so at its own risk." | VOL-IV cover/para5 p2 |  | high: verbatim; 'at its own risk' does not say what the Authority will do | n/a (text layer) | proposed (not reviewed) | n/a | VOL-IV:cover/para5 (VOL-IV p2; text layer) | I-F4A-FIELDS
VOL-IV-F4A-02 | VOL-IV:F4-A | envelope_A; forms; reissued_form | Complete and execute Form 4-A (Envelope A, mandatory): fill every field and sign; continues in the form reissued by ADD-01 App A | Name of Bidder / lead member: | Name of Bidder / lead member: | Name of Bidder / lead member: | ADD-01 AppA/name-of-bidder-lead-member p3 (replacing VOL-IV F4-A/name-of-bidder-lead-member p3, ADD-01/AppA/para1) | pass_fail | Legal | Bid manager | EV-FORM-4A | ACTIVE | AMENDED (ADD-01/AppA/para1) | ACTIVE (as amended by ADD-01/AppA/para1) | ACTIVE (as amended by ADD-01/AppA/para1) — STALE | non-responsive: "An unsigned or improperly executed Form 4-A shall render the Proposal non-responsive." | VOL-I 9.3 p5 |  | medium: verbatim fields; the reissued form drops fields and still prints the old PDD (a decision for a person) | n/a (text layer) | proposed (not reviewed) | ADD-01/AppA/para1: proposed | VOL-IV:F4-A/name-of-bidder-lead-member (VOL-IV p3; text layer); ADD-01/AppA/para1 [proposed] <- ADD-01:AppA/para1 (ADD-01 p3) | I-F4A-FIELDS
VOL-IV-F4A-03 | VOL-IV:F4-A | envelope_A; forms; confirmation; addenda_acknowledgement; dropped_in_reissue | Form 4-A para 1: acknowledge receipt of the Addenda by number and offer the Project in conformity with the RFP Documents | 1. Having examined the RFP Documents, including Addenda numbered ______ to ______, the receipt of which is hereby acknowledged, we offer to design, finance, construct, own, operate, maintain and transfer the Project in conformity with the RFP Documents. | 1. Having examined the RFP Documents, including Addenda numbered ______ to ______, the receipt of which is hereby acknowledged, we offer to design, finance, construct, own, operate, maintain and transfer the Project in conformity with the RFP Documents. | the receipt of which is hereby acknowledged, we offer to design, finance, construct, own, operate, maintain and transfer the Project in conformity with the RFP Documents | VOL-IV F4-A/item1 p3 | pass_fail | Legal | Bid manager | EV-FORM-4A | ACTIVE | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | none stated in the documents |  |  | medium: verbatim; dropped by the reissued form from ADD-01 (whether to give it anyway is for a person) | n/a (text layer) | proposed (not reviewed) | ADD-01/AppA/para1: proposed | VOL-IV:F4-A/item1 (VOL-IV p3; text layer); ADD-01/AppA/para1 [proposed] <- ADD-01:AppA/para1 (ADD-01 p3) | I-F4A-FIELDS; I-NO-CONSEQUENCE
VOL-IV-F4A-04 | VOL-IV:F4-A | envelope_A; forms; confirmation; validity; dropped_in_reissue | Form 4-A para 2: confirm the Proposal is valid for 150 days from the Proposal Due Date | 2. We confirm that this Proposal is valid for one hundred and fifty (150) days from the Proposal Due Date. | 2. We confirm that this Proposal is valid for one hundred and fifty (150) days from the Proposal Due Date. | We confirm that this Proposal is valid for one hundred and fifty (150) days from the Proposal Due Date. | VOL-IV F4-A/item2 p3 | pass_fail | Commercial | Bid manager | EV-FORM-4A | ACTIVE | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | none stated in the documents |  | PROPOSAL-VALIDITY-F4A: 2027-05-09 (day0) | medium: verbatim; dropped by the reissued form from ADD-01; day 0 / day 1 not stated | n/a (text layer) | proposed (not reviewed) | ADD-01/AppA/para1: proposed | VOL-IV:F4-A/item2 (VOL-IV p3; text layer); ADD-01/AppA/para1 [proposed] <- ADD-01:AppA/para1 (ADD-01 p3) | I-F4A-FIELDS; I-NO-CONSEQUENCE
VOL-IV-F4A-05 | VOL-IV:F4-A | envelope_A; forms; confirmation; bid_security; dropped_in_reissue | Form 4-A para 3: confirm the Bid Bond required by VOL-I 6.4 accompanies the Proposal | 3. We confirm that the Bid Bond required by Volume I Clause 6.4 accompanies this Proposal. | 3. We confirm that the Bid Bond required by Volume I Clause 6.4 accompanies this Proposal. | We confirm that the Bid Bond required by Volume I Clause 6.4 accompanies this Proposal. | VOL-IV F4-A/item3 p3 | pass_fail | Commercial | Bid manager | EV-FORM-4A | ACTIVE | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | none stated in the documents |  |  | medium: verbatim; dropped by the reissued form from ADD-01 | n/a (text layer) | proposed (not reviewed) | ADD-01/AppA/para1: proposed | VOL-IV:F4-A/item3 (VOL-IV p3; text layer); ADD-01/AppA/para1 [proposed] <- ADD-01:AppA/para1 (ADD-01 p3) | I-F4A-FIELDS; I-NO-CONSEQUENCE
VOL-IV-F4A-06 | VOL-IV:F4-A | envelope_A; forms; confirmation; multiple_participation; dropped_in_reissue | Form 4-A para 4: confirm no consortium member participates in any other Proposal for the Project | 4. We confirm that no member of our consortium participates in any other Proposal for this Project. | 4. We confirm that no member of our consortium participates in any other Proposal for this Project. | We confirm that no member of our consortium participates in any other Proposal for this Project. | VOL-IV F4-A/item4 p3 | pass_fail | Legal | Bid manager | EV-FORM-4A | ACTIVE | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | none stated in the documents |  |  | medium: verbatim; dropped by the reissued form from ADD-01; the confirmation rests on bidder facts | n/a (text layer) | proposed (not reviewed) | ADD-01/AppA/para1: proposed | VOL-IV:F4-A/item4 (VOL-IV p3; text layer); ADD-01/AppA/para1 [proposed] <- ADD-01:AppA/para1 (ADD-01 p3) | I-F4A-FIELDS; I-NO-CONSEQUENCE; I-BIDDER-FACTS
VOL-IV-F4A-07 | VOL-IV:F4-A | envelope_A; forms; confirmation; pre_bid; dropped_in_reissue | Form 4-A para 5: confirm attendance at the Pre-Bid Conference held under VOL-I 5.4 | 5. We confirm that we attended the Pre-Bid Conference held under Volume I Clause 5.4. | 5. We confirm that we attended the Pre-Bid Conference held under Volume I Clause 5.4. | We confirm that we attended the Pre-Bid Conference held under Volume I Clause 5.4. | VOL-IV F4-A/item5 p3 | pass_fail | Bid management | Bid manager | EV-FORM-4A | ACTIVE | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | none stated in the documents |  |  | medium: verbatim; dropped by the reissued form from ADD-01; attendance is a bidder fact | n/a (text layer) | proposed (not reviewed) | ADD-01/AppA/para1: proposed | VOL-IV:F4-A/item5 (VOL-IV p3; text layer); ADD-01/AppA/para1 [proposed] <- ADD-01:AppA/para1 (ADD-01 p3) | I-F4A-FIELDS; I-NO-CONSEQUENCE; I-BIDDER-FACTS
VOL-IV-F4B-01 | VOL-IV:F4-B | envelope_A; forms; references | Form 4-B, one per reference project (Envelope A): complete every field, incl. the completion certificate question | Form: 4-B ¦ Title: Reference Projects Schedule ¦ Envelope: A ¦ Status: Mandatory (one per project) | Form: 4-B ¦ Title: Reference Projects Schedule ¦ Envelope: A ¦ Status: Mandatory (one per project) | Envelope: A ¦ Status: Mandatory (one per project) | VOL-IV cover/T1/4-B p2 | pass_fail | Technical | Technical lead | EV-FORM-4B | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim fields; the contract value field conflicts with VOL-I 6.2 (no commercial information in Envelope A) | n/a (text layer) | proposed (not reviewed) | n/a | VOL-IV:cover/T1/4-B (VOL-IV p2; text layer) | I-NO-CONSEQUENCE; I-VOL-I-ENV-A-PRICES; I-BIDDER-FACTS
VOL-IV-F4C-01 | VOL-IV:F4-C | envelope_A; forms; arabic; declaration; image | Form 4-C declaration 1 (Arabic only): no actual or potential conflict of interest with the Authority or its advisers on this project | أولاً: أنه لا يوجد أي تضارب في المصالح، فعلي أو محتمل، بيننا وبين الهيئة أو أي من مستشاريها فيما يتعلق بهذا المشروع. | أولاً: أنه لا يوجد أي تضارب في المصالح، فعلي أو محتمل، بيننا وبين الهيئة أو أي من مستشاريها فيما يتعلق بهذا المشروع. | أنه لا يوجد أي تضارب في المصالح، فعلي أو محتمل، بيننا وبين الهيئة أو أي من مستشاريها فيما يتعلق بهذا المشروع | VOL-IV F4-C/image/decl1 p6 | pass_fail | Legal | Legal counsel | EV-FORM-4C | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: from an image reading still pending the owner's review; translation proposed | pending | proposed (not reviewed) | n/a | VOL-IV:F4-C/image/decl1 (VOL-IV p6; image reading) | I-READING-F4C; I-NO-CONSEQUENCE; I-BIDDER-FACTS
VOL-IV-F4C-02 | VOL-IV:F4-C | envelope_A; forms; arabic; declaration; image; multiple_participation | Form 4-C declaration 2 (Arabic): the member has not taken part, directly or indirectly, in more than one proposal for this tender | ثانياً: أن الشركة لم تشارك، بصورة مباشرة أو غير مباشرة، في أكثر من عرض واحد لهذه المناقصة. | ثانياً: أن الشركة لم تشارك، بصورة مباشرة أو غير مباشرة، في أكثر من عرض واحد لهذه المناقصة. | أن الشركة لم تشارك، بصورة مباشرة أو غير مباشرة، في أكثر من عرض واحد لهذه المناقصة | VOL-IV F4-C/image/decl2 p6 | pass_fail | Legal | Legal counsel | EV-FORM-4C | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: from an image reading still pending the owner's review; translation proposed | pending | proposed (not reviewed) | n/a | VOL-IV:F4-C/image/decl2 (VOL-IV p6; image reading) | I-READING-F4C; I-NO-CONSEQUENCE; I-BIDDER-FACTS
VOL-IV-F4C-03 | VOL-IV:F4-C | envelope_A; forms; arabic; declaration; image; debarment | Form 4-C declaration 3 (Arabic): the member is not, and in the previous five years was not, on any Kingdom government debarment list | ثالثاً: أن الشركة غير مدرجة، ولم تكن مدرجة خلال الخمس سنوات السابقة، في أي قائمة حظر صادرة عن جهة حكومية في المملكة. | ثالثاً: أن الشركة غير مدرجة، ولم تكن مدرجة خلال الخمس سنوات السابقة، في أي قائمة حظر صادرة عن جهة حكومية في المملكة. | أن الشركة غير مدرجة، ولم تكن مدرجة خلال الخمس سنوات السابقة، في أي قائمة حظر صادرة عن جهة حكومية في المملكة | VOL-IV F4-C/image/decl3 p6 | pass_fail | Legal | Legal counsel | EV-FORM-4C | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: from an image reading still pending the owner's review; wording differs from VOL-I 8.10 | pending | proposed (not reviewed) | n/a | VOL-IV:F4-C/image/decl3 (VOL-IV p6; image reading) | I-READING-F4C; I-NO-CONSEQUENCE; I-BIDDER-FACTS
VOL-IV-F4C-05 | VOL-IV:F4-C | envelope_A; forms; arabic; declaration; image; communications | Form 4-C declaration 5 (Arabic): undertake to comply with the communication rules of Volume I clause 4-2 (digit uncertain) | خامساً: نلتزم بقواعد الاتصال المنصوص عليها في البند ٤-٢ من المجلد الأول. | خامساً: نلتزم بقواعد الاتصال المنصوص عليها في البند ٤-٢ من المجلد الأول. | نلتزم بقواعد الاتصال المنصوص عليها في البند ٤-٢ من المجلد الأول | VOL-IV F4-C/image/decl5 p6 | pass_fail | Legal | Legal counsel | EV-FORM-4C | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | low: image reading pending; which Volume I clause is referenced (4.2 or 4.3) is an open reading decision | pending | proposed (not reviewed) | n/a | VOL-IV:F4-C/image/decl5 (VOL-IV p6; image reading) | I-READING-F4C; I-NO-CONSEQUENCE
VOL-IV-F4D-01 | VOL-IV:F4-D | envelope_A; forms; guarantee | Form 4-D (Envelope A, EPC parent): name guarantor, jurisdiction and EPC Contractor; execute with name, capacity, date, authority reference | Form: 4-D ¦ Title: Parent Company Guarantee — pro forma ¦ Envelope: A ¦ Status: Mandatory (EPC parent) | Form: 4-D ¦ Title: Parent Company Guarantee — pro forma ¦ Envelope: A ¦ Status: Mandatory (EPC parent) | Envelope: A ¦ Status: Mandatory (EPC parent) | VOL-IV cover/T1/4-D p2 | pass_fail | Legal | Legal counsel | EV-FORM-4D | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim fields; no consequence stated | n/a (text layer) | proposed (not reviewed) | n/a | VOL-IV:cover/T1/4-D (VOL-IV p2; text layer) | I-NO-CONSEQUENCE
VOL-IV-F4D-02 | VOL-IV:F4-D | forms; guarantee; post_award | Guarantee covers all EPC Contractor obligations under the EPC Contract during construction, incl. payment of liquidated damages | Guaranteed obligations: All obligations of the EPC Contractor under the EPC Contract during the construction period, including the payment of liquidated damages. | Guaranteed obligations: All obligations of the EPC Contractor under the EPC Contract during the construction period, including the payment of liquidated damages. | All obligations of the EPC Contractor under the EPC Contract during the construction period, including the payment of liquidated damages. | VOL-IV F4-D/guaranteed-obligations p7 | contractual_post_award | Legal | Legal counsel | EV-FORM-4D | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim pre-printed term | n/a (text layer) | proposed (not reviewed) | n/a | VOL-IV:F4-D/guaranteed-obligations (VOL-IV p7; text layer)
VOL-IV-F4D-03 | VOL-IV:F4-D | forms; guarantee; post_award; liability | Guarantor's liability unlimited as to the guaranteed obligations | Limit of liability: Unlimited as to the guaranteed obligations | Limit of liability: Unlimited as to the guaranteed obligations | Limit of liability: Unlimited as to the guaranteed obligations | VOL-IV F4-D/limit-of-liability p7 | contractual_post_award | Legal | Legal counsel | EV-FORM-4D | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim pre-printed term | n/a (text layer) | proposed (not reviewed) | n/a | VOL-IV:F4-D/limit-of-liability (VOL-IV p7; text layer)
VOL-IV-F4D-04 | VOL-IV:F4-D | forms; guarantee; post_award; expiry | Guarantee expires at the later of the final completion certificate and the end of the defects notification period | Expiry: The later of the issue of the final completion certificate under the EPC Contract and the expiry of the defects notification period | Expiry: The later of the issue of the final completion certificate under the EPC Contract and the expiry of the defects notification period | The later of the issue of the final completion certificate under the EPC Contract and the expiry of the defects notification period | VOL-IV F4-D/expiry p7 | contractual_post_award | Legal | Legal counsel | EV-FORM-4D | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim pre-printed term | n/a (text layer) | proposed (not reviewed) | n/a | VOL-IV:F4-D/expiry (VOL-IV p7; text layer)
VOL-IV-F4D-05 | VOL-IV:F4-D | forms; guarantee; post_award; governing_law | Guarantee governed by the laws of the Kingdom | Governing law: Laws of the Kingdom | Governing law: Laws of the Kingdom | Governing law: Laws of the Kingdom | VOL-IV F4-D/governing-law p7 | contractual_post_award | Legal | Legal counsel | EV-FORM-4D | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim pre-printed term | n/a (text layer) | proposed (not reviewed) | n/a | VOL-IV:F4-D/governing-law (VOL-IV p7; text layer)
VOL-IV-F4D-06 | VOL-IV:F4-D | forms; guarantee; post_award | Irrevocable, unconditional guarantee of the EPC Contractor's performance to the Project Company and, by collateral warranty, the Authority | 1. The Guarantor irrevocably and unconditionally guarantees to the Project Company and, by way of collateral warranty, to the Authority, the due and punctual performance by the EPC Contractor of the guaranteed obligations. | 1. The Guarantor irrevocably and unconditionally guarantees to the Project Company and, by way of collateral warranty, to the Authority, the due and punctual performance by the EPC Contractor of the guaranteed obligations. | The Guarantor irrevocably and unconditionally guarantees to the Project Company and, by way of collateral warranty, to the Authority, the due and punctual performance by the EPC Contractor of the guaranteed obligations. | VOL-IV F4-D/item1 p7 | contractual_post_award | Legal | Legal counsel | EV-FORM-4D | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim pre-printed term | n/a (text layer) | proposed (not reviewed) | n/a | VOL-IV:F4-D/item1 (VOL-IV p7; text layer)
VOL-IV-F4D-07 | VOL-IV:F4-D | forms; guarantee; post_award | Guarantor liable as primary obligor; not discharged by any amendment, indulgence or waiver granted to the EPC Contractor | 2. The Guarantor's liability is that of a primary obligor and is not discharged by any amendment, indulgence or waiver granted to the EPC Contractor. | 2. The Guarantor's liability is that of a primary obligor and is not discharged by any amendment, indulgence or waiver granted to the EPC Contractor. | The Guarantor's liability is that of a primary obligor and is not discharged by any amendment, indulgence or waiver granted to the EPC Contractor. | VOL-IV F4-D/item2 p7 | contractual_post_award | Legal | Legal counsel | EV-FORM-4D | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim pre-printed term | n/a (text layer) | proposed (not reviewed) | n/a | VOL-IV:F4-D/item2 (VOL-IV p7; text layer)
VOL-IV-F4D-08 | VOL-IV:F4-D | forms; guarantee; post_award | Guarantee not conditional on any demand first being made of the EPC Contractor | 3. This guarantee is not conditional on any demand first being made of the EPC Contractor. | 3. This guarantee is not conditional on any demand first being made of the EPC Contractor. | This guarantee is not conditional on any demand first being made of the EPC Contractor. | VOL-IV F4-D/item3 p7 | contractual_post_award | Legal | Legal counsel | EV-FORM-4D | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim pre-printed term | n/a (text layer) | proposed (not reviewed) | n/a | VOL-IV:F4-D/item3 (VOL-IV p7; text layer)
VOL-IV-F4E-01 | VOL-IV:F4-E | envelope_A; forms; deviations | Form 4-E (Envelope A, mandatory): one line per deviation (Volume/Clause, nature, proposed wording, rationale), total declared, signed, dated | Form: 4-E ¦ Title: Schedule of Deviations ¦ Envelope: A ¦ Status: Mandatory | Form: 4-E ¦ Title: Schedule of Deviations ¦ Envelope: A ¦ Status: Mandatory | Title: Schedule of Deviations ¦ Envelope: A ¦ Status: Mandatory | VOL-IV cover/T1/4-E p2 | pass_fail | Legal | Legal counsel | EV-FORM-4E | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim; no consequence stated for the form itself | n/a (text layer) | proposed (not reviewed) | n/a | VOL-IV:cover/T1/4-E (VOL-IV p2; text layer) | I-NO-CONSEQUENCE
VOL-IV-F4F-01 | VOL-IV:F4-F | envelope_B; forms; commercial | Form 4-F (Envelope B, mandatory): complete every field (Availability Payment in figures and words, cost, financing, IRRs, model audit) and sign | Form: 4-F ¦ Title: Financial Proposal Schedule ¦ Envelope: B ¦ Status: Mandatory | Form: 4-F ¦ Title: Financial Proposal Schedule ¦ Envelope: B ¦ Status: Mandatory | Title: Financial Proposal Schedule ¦ Envelope: B ¦ Status: Mandatory | VOL-IV cover/T1/4-F p2 | pass_fail | Commercial | Commercial lead | EV-FORM-4F | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim fields; where the 10.3 and 10.6 documents go is an open issue | n/a (text layer) | proposed (not reviewed) | n/a | VOL-IV:cover/T1/4-F (VOL-IV p2; text layer) | I-NO-CONSEQUENCE; I-VOL-I-ENV-B
VOL-IV-F4F-02 | VOL-IV:F4-F | envelope_B; forms; confirmation; commercial | Form 4-F: confirm the Availability Payment is unconditional, unqualified and derived from the Financial Model submitted with the Form | We confirm that the Availability Payment stated above is unconditional, is not subject to any qualification, and has been derived from the Financial Model submitted with this Form. | We confirm that the Availability Payment stated above is unconditional, is not subject to any qualification, and has been derived from the Financial Model submitted with this Form. | We confirm that the Availability Payment stated above is unconditional, is not subject to any qualification, and has been derived from the Financial Model submitted with this Form. | VOL-IV F4-F/para1 p9 | pass_fail | Commercial | Commercial lead | EV-FORM-4F; EV-FIN-MODEL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim | n/a (text layer) | proposed (not reviewed) | n/a | VOL-IV:F4-F/para1 (VOL-IV p9; text layer) | I-NO-CONSEQUENCE
VOL-V-NOTE-01 | VOL-V:cover/note-to-bidders | contract; deviations; bid_submission | List every deviation from the Volume V clauses in Form 4-E; a deviation not listed is taken as accepted | Note to Bidders. This extract contains the clauses of the draft Project Agreement on which the Authority invites comment through Form 4-E. Clause numbering follows the full draft; omitted clauses are not reproduced. A deviation not listed in Form 4-E will be taken as accepted. | Note to Bidders. This extract contains the clauses of the draft Project Agreement on which the Authority invites comment through Form 4-E. Clause numbering follows the full draft; omitted clauses are not reproduced. A deviation not listed in Form 4-E will be taken as accepted. | This extract contains the clauses of the draft Project Agreement on which the Authority invites comment through Form 4-E. | VOL-V cover/note-to-bidders p2 | procedural | Legal | Legal counsel | EV-FORM-4E | ACTIVE | ACTIVE | ACTIVE | ACTIVE | lesser consequence: "A deviation not listed in Form 4-E will be taken as accepted." | VOL-V cover/note-to-bidders p2 |  | high: verbatim text-layer note | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:cover/note-to-bidders (VOL-V p2; text layer) | I-VOL-V-MISSING; I-CONCESSION
VOL-V-3.1-01 | VOL-V:3.1 | contract; post_award; term | Agreement in force from the Effective Date for 25 years from the Effective Date, unless terminated earlier | This Agreement shall come into force on the Effective Date and shall continue for a period of twenty-five (25) years from the Effective Date, unless terminated earlier in accordance with its terms. | This Agreement shall come into force on the Effective Date and shall continue for a period of twenty-five (25) years from the Effective Date, unless terminated earlier in accordance with its terms. | shall continue for a period of twenty-five (25) years from the Effective Date | VOL-V 3.1 p2 | contractual_post_award | Legal | Legal counsel |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  | VOL-V-TERM-END: None (unknown_anchor) | medium: verbatim, but conflicts with VOL-I 12.1 and the Authority declined to resolve it; the Effective Date is not a pack event | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:3.1 (VOL-V p2; text layer) | I-CONCESSION
VOL-V-3.2-01 | VOL-V:3.2 | contract; post_award; handback | On expiry, transfer the Facility to the Authority under Clause 42 for nil consideration | On expiry, the Facility shall transfer to the Authority in accordance with Clause 42 for nil consideration. | On expiry, the Facility shall transfer to the Authority in accordance with Clause 42 for nil consideration. | On expiry, the Facility shall transfer to the Authority in accordance with Clause 42 for nil consideration. | VOL-V 3.2 p2 | contractual_post_award | Legal | Legal counsel |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim; the expiry date depends on the term start (I-CONCESSION) | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:3.2 (VOL-V p2; text layer) | I-CONCESSION
VOL-V-12.1-01 | VOL-V:12.1 | contract; post_award; programme; pcod | Achieve PCOD within 36 months of the Notice to Proceed (the Scheduled PCOD) | The Project Company shall achieve PCOD within thirty-six (36) months of the Notice to Proceed (the Scheduled PCOD). | The Project Company shall achieve PCOD within thirty-six (36) months of the Notice to Proceed (the Scheduled PCOD). | shall achieve PCOD within thirty-six (36) months of the Notice to Proceed (the Scheduled PCOD) | VOL-V 12.1 p2 | contractual_post_award | Technical | Technical lead |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | contractual remedy (post-award): "the Project Company shall pay to the Authority delay liquidated damages at the rate of SAR 180,000 for each day of delay" | VOL-V 18.1 p2 | VOL-V-SCHEDULED-PCOD: None (unknown_anchor) | high: verbatim; the Notice to Proceed is not a pack event, so the Scheduled PCOD cannot be dated | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:12.1 (VOL-V p2; text layer)
VOL-V-18.3-01 | VOL-V:18.3 | contract; post_award; programme; pcod; termination | Achieve PCOD within 365 days after the Scheduled PCOD, failing which the Authority may terminate under Clause 39.2 | If PCOD has not been achieved within three hundred and sixty-five (365) days after the Scheduled PCOD, the Authority may terminate under Clause 39.2. | If PCOD has not been achieved within three hundred and sixty-five (365) days after the Scheduled PCOD, the Authority may terminate under Clause 39.2. | If PCOD has not been achieved within three hundred and sixty-five (365) days after the Scheduled PCOD | VOL-V 18.3 p2 | contractual_post_award | Legal | Legal counsel |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | contractual remedy (post-award): "the Authority may terminate under Clause 39.2" | VOL-V 18.3 p2 | VOL-V-PCOD-LONG-STOP: None (unknown_anchor) | high: verbatim; the Scheduled PCOD depends on the Notice to Proceed, not a pack event | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:18.3 (VOL-V p2; text layer)
VOL-V-12.2-01 | VOL-V:12.2 | contract; post_award; epc | Have the EPC Contractor build on a fixed price, lump sum, date certain, turnkey basis with single point responsibility | The Project Company shall procure that the EPC Contractor performs the construction works on a fixed price, lump sum, date certain, turnkey basis with single point responsibility. | The Project Company shall procure that the EPC Contractor performs the construction works on a fixed price, lump sum, date certain, turnkey basis with single point responsibility. | shall procure that the EPC Contractor performs the construction works on a fixed price, lump sum, date certain, turnkey basis with single point responsibility | VOL-V 12.2 p2 | contractual_post_award | Commercial | Commercial lead |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:12.2 (VOL-V p2; text layer)
VOL-V-12.3-01 | VOL-V:12.3 | contract; post_award; independent_engineer; cost | Bear half of the Independent Engineer's reasonable costs (the Authority appoints the Independent Engineer) | The Authority shall appoint an Independent Engineer whose reasonable costs shall be borne equally by the parties. | The Authority shall appoint an Independent Engineer whose reasonable costs shall be borne equally by the parties. | whose reasonable costs shall be borne equally by the parties | VOL-V 12.3 p2 | contractual_post_award | Commercial | Commercial lead |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:12.3 (VOL-V p2; text layer)
VOL-V-12.4-01 | VOL-V:12.4 | contract; post_award; reporting | Submit monthly progress reports | The Project Company shall submit monthly progress reports and shall permit the Authority access to the site at all reasonable times. | The Project Company shall submit monthly progress reports and shall permit the Authority access to the site at all reasonable times. | shall submit monthly progress reports | VOL-V 12.4 p2 | contractual_post_award | Technical | Technical lead |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:12.4 (VOL-V p2; text layer)
VOL-V-12.4-02 | VOL-V:12.4 | contract; post_award; site_access | Permit the Authority access to the site at all reasonable times | The Project Company shall submit monthly progress reports and shall permit the Authority access to the site at all reasonable times. | The Project Company shall submit monthly progress reports and shall permit the Authority access to the site at all reasonable times. | shall permit the Authority access to the site at all reasonable times | VOL-V 12.4 p2 | contractual_post_award | Technical | Technical lead |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:12.4 (VOL-V p2; text layer)
VOL-V-24.1-01 | VOL-V:24.1 | contract; post_award; finance; accounts | Open and keep the project accounts the Financing Documents require, with an account bank acceptable to the Senior Lenders | The Project Company shall open and maintain the project accounts required by the Financing Documents with an account bank acceptable to the Senior Lenders. | The Project Company shall open and maintain the project accounts required by the Financing Documents with an account bank acceptable to the Senior Lenders. | shall open and maintain the project accounts required by the Financing Documents with an account bank acceptable to the Senior Lenders | VOL-V 24.1 p2 | contractual_post_award | Finance | Financial modeller |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:24.1 (VOL-V p2; text layer)
VOL-V-24.2-01 | VOL-V:24.2 | contract; post_award; finance; reserves | Establish, maintain and fund the reserve accounts the Financing Documents require | The Project Company shall establish and maintain such reserve accounts, and shall fund them to such levels and at such times, as are required under the Financing Documents. The Authority takes no position on the sizing of any reserve account. | The Project Company shall establish and maintain such reserve accounts, and shall fund them to such levels and at such times, as are required under the Financing Documents. The Authority takes no position on the sizing of any reserve account. | shall establish and maintain such reserve accounts, and shall fund them to such levels and at such times, as are required under the Financing Documents | VOL-V 24.2 p3 | contractual_post_award | Finance | Financial modeller |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:24.2 (VOL-V p3; text layer)
VOL-V-24.3-01 | VOL-V:24.3 | contract; post_award; finance; distributions | No shareholder distribution unless the Financing Documents' conditions are met and no Unavailability Event is continuing | The Project Company shall not make a distribution to its shareholders unless the conditions to distribution in the Financing Documents are satisfied and no Unavailability Event is continuing. | The Project Company shall not make a distribution to its shareholders unless the conditions to distribution in the Financing Documents are satisfied and no Unavailability Event is continuing. | shall not make a distribution to its shareholders unless the conditions to distribution in the Financing Documents are satisfied and no Unavailability Event is continuing | VOL-V 24.3 p3 | contractual_post_award | Finance | Financial modeller |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:24.3 (VOL-V p3; text layer)
VOL-V-24.4-01 | VOL-V:24.4 | contract; post_award; finance; reporting | Give the Authority quarterly statements of each project account | The Project Company shall provide the Authority with quarterly statements of each project account. | The Project Company shall provide the Authority with quarterly statements of each project account. | shall provide the Authority with quarterly statements of each project account | VOL-V 24.4 p3 | contractual_post_award | Finance | Financial modeller |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:24.4 (VOL-V p3; text layer)
VOL-V-29.3-01 | VOL-V:29.3 | contract; post_award; payment; ramp_up; image | Ramp-Up Period (12 months after PCOD): payment at 90%; no deduction for Table 2-4 parameters assessed on a rolling average | During the first twelve (12) months after PCOD (the Ramp-Up Period) the Availability Payment shall be paid at ninety per cent (90%) of the full rate, and no availability deduction shall apply to a parameter listed in Table 2-4 as assessed on a rolling average basis. | During the first twelve (12) months after PCOD (the Ramp-Up Period) the Availability Payment shall be paid at ninety per cent (90%) of the full rate, and no availability deduction shall apply to a parameter listed in Table 2-4 as assessed on a rolling average basis. | During the first twelve (12) months after PCOD (the Ramp-Up Period) the Availability Payment shall be paid at ninety per cent (90%) of the full rate | VOL-V 29.3 p3 | contractual_post_award | Commercial | Commercial lead |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE — STALE | none stated in the documents |  | VOL-V-RAMP-UP-END: None (unknown_anchor) | medium: verbatim clause; the parameters exempt from Ramp-Up deductions come from an image reading still pending review; PCOD is not a pack event | pending | proposed (not reviewed) | n/a | VOL-V:29.3 (VOL-V p3; text layer) | I-READING-T24
VOL-V-29.4-01 | VOL-V:29.4 | contract; post_award; payment; invoicing | Submit invoices within 10 Working Days of each month end (the Authority pays within 30 days of receipt) | Invoices shall be submitted within ten (10) Working Days of each month end and shall be paid within thirty (30) days of receipt. | Invoices shall be submitted within ten (10) Working Days of each month end and shall be paid within thirty (30) days of receipt. | Invoices shall be submitted within ten (10) Working Days of each month end | VOL-V 29.4 p3 | contractual_post_award | Commercial | Commercial lead |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE — STALE | none stated in the documents |  | VOL-V-INVOICE-DUE: None (unknown_anchor) | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:29.4 (VOL-V p3; text layer)
VOL-V-31.1-01 | VOL-V:31.1 | contract; post_award; availability; deductions | Treat the flow delivered to the Facility (failure is an Unavailability Event under 31.1(a)) | An Unavailability Event occurs where (a) the Facility is unable to treat the flow delivered to it, (b) the treated effluent fails any parameter in Volume II Table 2-4, or (c) the Facility fails to deliver treated effluent to the delivery point at the required residual head. | An Unavailability Event occurs where (a) the Facility is unable to treat the flow delivered to it, (b) the treated effluent fails any parameter in Volume II Table 2-4, or (c) the Facility fails to deliver treated effluent to the delivery point at the required residual head. | (a) the Facility is unable to treat the flow delivered to it | VOL-V 31.1 p3 | contractual_post_award | Operations | O&M lead |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | contractual remedy (post-award): "the Authority shall deduct from the Availability Payment the amounts calculated under Schedule 7" | VOL-V 31.2 p3 |  | medium: verbatim; the deduction amounts are in Schedule 7, not supplied; how 'the flow delivered' relates to the design flows is open | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:31.1 (VOL-V p3; text layer) | I-VOL-V-MISSING; I-FLOWS
VOL-V-31.1-02 | VOL-V:31.1 | contract; post_award; availability; deductions; effluent | Treated effluent to meet every parameter in VOL-II Table 2-4 (failure is an Unavailability Event under 31.1(b)) | An Unavailability Event occurs where (a) the Facility is unable to treat the flow delivered to it, (b) the treated effluent fails any parameter in Volume II Table 2-4, or (c) the Facility fails to deliver treated effluent to the delivery point at the required residual head. | An Unavailability Event occurs where (a) the Facility is unable to treat the flow delivered to it, (b) the treated effluent fails any parameter in Volume II Table 2-4, or (c) the Facility fails to deliver treated effluent to the delivery point at the required residual head. | (b) the treated effluent fails any parameter in Volume II Table 2-4 | VOL-V 31.1 p3 | contractual_post_award | Operations | O&M lead |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | contractual remedy (post-award): "the Authority shall deduct from the Availability Payment the amounts calculated under Schedule 7" | VOL-V 31.2 p3 |  | medium: verbatim; Table 2-4 is an image reading pending review, the Permit that prevails over it in VOL-II is not supplied, and Schedule 7 is not supplied | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:31.1 (VOL-V p3; text layer) | I-READING-T24; I-PERMIT; I-VOL-V-MISSING
VOL-V-31.1-03 | VOL-V:31.1 | contract; post_award; availability; deductions; transmission_main | Deliver treated effluent to the delivery point at the required residual head (failure is an Unavailability Event under 31.1(c)) | An Unavailability Event occurs where (a) the Facility is unable to treat the flow delivered to it, (b) the treated effluent fails any parameter in Volume II Table 2-4, or (c) the Facility fails to deliver treated effluent to the delivery point at the required residual head. | An Unavailability Event occurs where (a) the Facility is unable to treat the flow delivered to it, (b) the treated effluent fails any parameter in Volume II Table 2-4, or (c) the Facility fails to deliver treated effluent to the delivery point at the required residual head. | (c) the Facility fails to deliver treated effluent to the delivery point at the required residual head | VOL-V 31.1 p3 | contractual_post_award | Operations | O&M lead |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | contractual remedy (post-award): "the Authority shall deduct from the Availability Payment the amounts calculated under Schedule 7" | VOL-V 31.2 p3 |  | medium: verbatim; the delivery point (Drawing 03-C-114) and the deduction amounts (Schedule 7) are not supplied | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:31.1 (VOL-V p3; text layer) | I-VOL-III; I-VOL-V-MISSING
VOL-V-31.3-02 | VOL-V:31.3 | contract; post_award; availability; cure_period | Cure period of 24 hours for an Unavailability Event under VOL-V 31.1(a) | A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a) and of seventy-two (72) hours to an event under Clause 31.1(c). No cure period applies to an event under Clause 31.1(b). | A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a) and of seventy-two (72) hours to an event under Clause 31.1(c). No cure period applies to an event under Clause 31.1(b). | A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a) | VOL-V 31.3 p3 | contractual_post_award | Legal | Legal counsel |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:31.3 (VOL-V p3; text layer)
VOL-V-31.3-03 | VOL-V:31.3 | contract; post_award; availability; cure_period; effluent | No cure period for an Unavailability Event under VOL-V 31.1(b) (a Table 2-4 failure) | A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a) and of seventy-two (72) hours to an event under Clause 31.1(c). No cure period applies to an event under Clause 31.1(b). | A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a) and of seventy-two (72) hours to an event under Clause 31.1(c). No cure period applies to an event under Clause 31.1(b). | No cure period applies to an event under Clause 31.1(b). | VOL-V 31.3 p3 | contractual_post_award | Legal | Legal counsel |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:31.3 (VOL-V p3; text layer)
VOL-V-31.4-01 | VOL-V:31.4 | contract; post_award; availability; persistent_breach; termination | Persistent breach (3+ Unavailability Events in a rolling 90 days): remediation plan on request; a second occurrence allows termination | Persistent breach, being three (3) or more Unavailability Events in any rolling ninety (90) day period, entitles the Authority to require a remediation plan and, on a second occurrence, to terminate under Clause 39.3. | Persistent breach, being three (3) or more Unavailability Events in any rolling ninety (90) day period, entitles the Authority to require a remediation plan and, on a second occurrence, to terminate under Clause 39.3. | Persistent breach, being three (3) or more Unavailability Events in any rolling ninety (90) day period, entitles the Authority to require a remediation plan | VOL-V 31.4 p3 | contractual_post_award | Operations | O&M lead |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | contractual remedy (post-award): "on a second occurrence, to terminate under Clause 39.3" | VOL-V 31.4 p3 |  | medium: verbatim; the trigger for termination ('a second occurrence') is not defined | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:31.4 (VOL-V p3; text layer) | I-VOL-V-PERSISTENT-BREACH
VOL-V-34.3-01 | VOL-V:34.3 | contract; post_award; relief_events; notice | Notify a Relief Event within 5 Working Days of becoming aware of it, or no relief is granted | The Project Company shall notify a Relief Event within five (5) Working Days of becoming aware of it, failing which no relief shall be granted. | The Project Company shall notify a Relief Event within five (5) Working Days of becoming aware of it, failing which no relief shall be granted. | shall notify a Relief Event within five (5) Working Days of becoming aware of it | VOL-V 34.3 p3 | contractual_post_award | Legal | Legal counsel |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | contractual remedy (post-award): "failing which no relief shall be granted" | VOL-V 34.3 p3 | VOL-V-RELIEF-EVENT-NOTICE: None (unknown_anchor) | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:34.3 (VOL-V p3; text layer)
VOL-V-36.2-01 | VOL-V:36.2 | contract; post_award; change_in_law; threshold | General Change in Law: compensation only for the capital expenditure it requires, and only above the stated aggregate threshold | A General Change in Law entitles the Project Company to compensation only in respect of capital expenditure required by that change and only to the extent that such expenditure exceeds SAR 5,000,000 in aggregate over the term. | A General Change in Law entitles the Project Company to compensation only in respect of capital expenditure required by that change and only to the extent that such expenditure exceeds SAR 2,500,000 in aggregate over the term. | only to the extent that such expenditure exceeds SAR 2,500,000 in aggregate over the term | VOL-V 36.2 p4 as amended by ADD-02 8.1 p3 | contractual_post_award | Commercial | Commercial lead |  | ACTIVE | ACTIVE | AMENDED (ADD-02/8.1) | ACTIVE (as amended by ADD-02/8.1) | none stated in the documents |  |  | high: verbatim at each stage | n/a (text layer) | proposed (not reviewed) | ADD-02/8.1: proposed | VOL-V:36.2 (VOL-V p4; text layer); ADD-02/8.1 [proposed] <- ADD-02:8.1 (ADD-02 p3)
VOL-V-39.1-01 | VOL-V:39.1 | contract; post_award; termination; events_of_default | Avoid the Project Company Events of Default listed in Schedule 11 (not supplied); the Authority may terminate for them | The Authority may terminate for a Project Company Event of Default, being the events listed in Schedule 11. | The Authority may terminate for a Project Company Event of Default, being the events listed in Schedule 11. | being the events listed in Schedule 11 | VOL-V 39.1 p4 | contractual_post_award | Legal | Legal counsel |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | contractual remedy (post-award): "The Authority may terminate for a Project Company Event of Default" | VOL-V 39.1 p4 |  | low: the events of default themselves (Schedule 11) are not in the pack | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:39.1 (VOL-V p4; text layer) | I-VOL-V-MISSING
VOL-V-42.1-01 | VOL-V:42.1 | contract; post_award; handback | On expiry, transfer the Facility in the condition required by VOL-II 8.5, free of encumbrance | The Project Company shall transfer the Facility to the Authority on expiry in the condition required by Volume II Clause 8.5, free of encumbrance and with a remaining design life of not less than five (5) years for all major assets. | The Project Company shall transfer the Facility to the Authority on expiry in the condition required by Volume II Clause 8.5, free of encumbrance and with a remaining design life of not less than five (5) years for all major assets. | shall transfer the Facility to the Authority on expiry in the condition required by Volume II Clause 8.5, free of encumbrance | VOL-V 42.1 p4 | contractual_post_award | Operations | O&M lead |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim; the expiry date depends on the term start (I-CONCESSION) | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:42.1 (VOL-V p4; text layer) | I-CONCESSION
VOL-V-42.1-02 | VOL-V:42.1 | contract; post_award; handback; design_life | At handback, at least 5 years of remaining design life for all major assets | The Project Company shall transfer the Facility to the Authority on expiry in the condition required by Volume II Clause 8.5, free of encumbrance and with a remaining design life of not less than five (5) years for all major assets. | The Project Company shall transfer the Facility to the Authority on expiry in the condition required by Volume II Clause 8.5, free of encumbrance and with a remaining design life of not less than five (5) years for all major assets. | with a remaining design life of not less than five (5) years for all major assets | VOL-V 42.1 p4 | contractual_post_award | Operations | O&M lead |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | medium: verbatim; 'major assets' is not defined | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:42.1 (VOL-V p4; text layer)
VOL-V-42.2-01 | VOL-V:42.2 | contract; post_award; handback; reserves | Fund a handback reserve from the start of year 20 of the term, in the amount the Independent Engineer certifies | A handback reserve shall be funded from the start of year twenty (20) of the term in an amount certified by the Independent Engineer. | A handback reserve shall be funded from the start of year twenty (20) of the term in an amount certified by the Independent Engineer. | A handback reserve shall be funded from the start of year twenty (20) of the term in an amount certified by the Independent Engineer. | VOL-V 42.2 p4 | contractual_post_award | Finance | Financial modeller |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  | VOL-V-HANDBACK-RESERVE-START: None (unknown_anchor) | medium: verbatim; when year 20 starts depends on the unresolved term start | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:42.2 (VOL-V p4; text layer) | I-CONCESSION
VOL-V-44.2-01 | VOL-V:44.2 | contract; post_award; disputes | Refer disputes first to senior representatives, then an expert if technical, then arbitration seated in Riyadh in English | The parties shall first refer a dispute to senior representatives, then to an expert where the dispute is technical, and failing resolution to arbitration seated in Riyadh conducted in the English language before three arbitrators under the arbitration rules applicable in the Kingdom. | The parties shall first refer a dispute to senior representatives, then to an expert where the dispute is technical, and failing resolution to arbitration seated in Riyadh conducted in the English language before three arbitrators under the arbitration rules applicable in the Kingdom. | The parties shall first refer a dispute to senior representatives, then to an expert where the dispute is technical, and failing resolution to arbitration seated in Riyadh conducted in the English language before three arbitrators | VOL-V 44.2 p4 | contractual_post_award | Legal | Legal counsel |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:44.2 (VOL-V p4; text layer)
VOL-V-44.3-01 | VOL-V:44.3 | contract; post_award; disputes | Continue performing the Agreement during any dispute | Performance of this Agreement shall continue during any dispute. | Performance of this Agreement shall continue during any dispute. | Performance of this Agreement shall continue during any dispute. | VOL-V 44.3 p4 | contractual_post_award | Legal | Legal counsel |  | ACTIVE | ACTIVE | ACTIVE | ACTIVE | none stated in the documents |  |  | high: verbatim text-layer clause | n/a (text layer) | proposed (not reviewed) | n/a | VOL-V:44.3 (VOL-V p4; text layer)

## Dates
Row | Stage | Rule | Text | Anchor | Readings | Planning | Readings differ
VOL-I-6.1-01 | BASE | PDD | not later than 14:00 hours Riyadh time on <date> | PDD = 2026-11-12 | as_stated: 2026-11-12 (stated in VOL-I:6.1) | 2026-11-12 (as_stated, policy conservative) | FALSE
VOL-I-6.1-01 | ADD-01 | PDD | not later than 14:00 hours Riyadh time on <date> | PDD = 2026-11-26 | as_stated: 2026-11-26 (stated in VOL-I:6.1) | 2026-11-26 (as_stated, policy conservative) | FALSE
VOL-I-6.1-01 | ADD-02 | PDD | not later than 14:00 hours Riyadh time on <date> | PDD = 2026-11-26 | as_stated: 2026-11-26 (stated in VOL-I:6.1) | 2026-11-26 (as_stated, policy conservative) | FALSE
VOL-I-6.1-01 | ADD-03 | PDD | not later than 14:00 hours Riyadh time on <date> | PDD = 2026-12-10 | as_stated: 2026-12-10 (stated in VOL-I:6.1) | 2026-12-10 (as_stated, policy conservative) | FALSE
VOL-I-5.2-01 | BASE | CLARIFICATION-CUTOFF | no later than ten (10) Working Days before the Proposal Due Date | PDD = 2026-11-12 | stated_date_excluded: 2026-10-29 (VOL-I §2.4) | 2026-10-29 (stated_date_excluded, policy conservative) | FALSE
VOL-I-5.2-01 | ADD-01 | CLARIFICATION-CUTOFF | no later than ten (10) Working Days before the Proposal Due Date | PDD = 2026-11-26 | stated_date_excluded: 2026-11-12 (VOL-I §2.4) | 2026-11-12 (stated_date_excluded, policy conservative) | FALSE
VOL-I-5.2-01 | ADD-02 | CLARIFICATION-CUTOFF | no later than ten (10) Working Days before the Proposal Due Date | PDD = 2026-11-26 | stated_date_excluded: 2026-11-12 (VOL-I §2.4) | 2026-11-12 (stated_date_excluded, policy conservative) | FALSE
VOL-I-5.2-01 | ADD-03 | CLARIFICATION-CUTOFF | no later than ten (10) Working Days before the Proposal Due Date | PDD = 2026-12-10 | stated_date_excluded: 2026-11-19 (VOL-I §2.4) | 2026-11-19 (stated_date_excluded, policy conservative) | FALSE
VOL-I-6.3-01 | BASE | BID-BOND-VALIDITY | valid for one hundred and eighty (180) days from the Proposal Due Date | PDD = 2026-11-12 | day0: 2027-05-11 (not stated in the pack); day1: 2027-05-10 (not stated in the pack) | 2027-05-11 (day0, policy conservative) | TRUE
VOL-I-6.3-01 | ADD-01 | BID-BOND-VALIDITY | valid for one hundred and eighty (180) days from the Proposal Due Date | PDD = 2026-11-26 | day0: 2027-05-25 (not stated in the pack); day1: 2027-05-24 (not stated in the pack) | 2027-05-25 (day0, policy conservative) | TRUE
VOL-I-6.3-01 | ADD-02 | BID-BOND-VALIDITY | valid for one hundred and eighty (180) days from the Proposal Due Date | PDD = 2026-11-26 | day0: 2027-05-25 (not stated in the pack); day1: 2027-05-24 (not stated in the pack) | 2027-05-25 (day0, policy conservative) | TRUE
VOL-I-6.3-01 | ADD-03 | BID-BOND-VALIDITY | valid for one hundred and eighty (180) days from the Proposal Due Date | PDD = 2026-12-10 | day0: 2027-06-08 (not stated in the pack); day1: 2027-06-07 (not stated in the pack) | 2027-06-08 (day0, policy conservative) | TRUE
VOL-I-7.1-01 | BASE | PROPOSAL-VALIDITY | one hundred and fifty (150) days from the Proposal Due Date | PDD = 2026-11-12 | day0: 2027-04-11 (not stated in the pack); day1: 2027-04-10 (not stated in the pack) | 2027-04-11 (day0, policy conservative) | TRUE
VOL-I-7.1-01 | ADD-01 | PROPOSAL-VALIDITY | one hundred and fifty (150) days from the Proposal Due Date | PDD = 2026-11-26 | day0: 2027-04-25 (not stated in the pack); day1: 2027-04-24 (not stated in the pack) | 2027-04-25 (day0, policy conservative) | TRUE
VOL-I-7.1-01 | ADD-02 | PROPOSAL-VALIDITY | one hundred and fifty (150) days from the Proposal Due Date | PDD = 2026-11-26 | day0: 2027-04-25 (not stated in the pack); day1: 2027-04-24 (not stated in the pack) | 2027-04-25 (day0, policy conservative) | TRUE
VOL-I-7.1-01 | ADD-03 | PROPOSAL-VALIDITY | one hundred and fifty (150) days from the Proposal Due Date | PDD = 2026-12-10 | day0: 2027-05-09 (not stated in the pack); day1: 2027-05-08 (not stated in the pack) | 2027-05-09 (day0, policy conservative) | TRUE
VOL-I-8.3-01 | BASE | ISO-CURRENT-AT | current as at the Proposal Due Date | PDD = 2026-11-12 | as_stated: 2026-11-12 (stated in VOL-I:8.3) | 2026-11-12 (as_stated, policy conservative) | FALSE
VOL-I-8.3-01 | ADD-01 | ISO-CURRENT-AT | current as at the Proposal Due Date | PDD = 2026-11-26 | as_stated: 2026-11-26 (stated in VOL-I:8.3) | 2026-11-26 (as_stated, policy conservative) | FALSE
VOL-I-8.3-01 | ADD-02 | ISO-CURRENT-AT | current as at the Proposal Due Date | PDD = 2026-11-26 | as_stated: 2026-11-26 (stated in VOL-I:8.3) | 2026-11-26 (as_stated, policy conservative) | FALSE
VOL-I-8.3-01 | ADD-03 | ISO-CURRENT-AT | current as at the Proposal Due Date | PDD = 2026-12-10 | as_stated: 2026-12-10 (stated in VOL-I:8.3) | 2026-12-10 (as_stated, policy conservative) | FALSE
VOL-I-8.5-01 | BASE | REFERENCE-LOOKBACK | within the ten (10) years preceding the Proposal Due Date | PDD = 2026-11-12 | boundary_inclusive: 2016-11-12 (not stated in the pack); boundary_exclusive: 2016-11-13 (not stated in the pack) | 2016-11-13 (boundary_exclusive, policy conservative) | TRUE
VOL-I-8.5-01 | ADD-01 | REFERENCE-LOOKBACK | within the ten (10) years preceding the Proposal Due Date | PDD = 2026-11-26 | boundary_inclusive: 2016-11-26 (not stated in the pack); boundary_exclusive: 2016-11-27 (not stated in the pack) | 2016-11-27 (boundary_exclusive, policy conservative) | TRUE
VOL-I-8.5-01 | ADD-02 | REFERENCE-LOOKBACK | within the ten (10) years preceding the Proposal Due Date | PDD = 2026-11-26 | boundary_inclusive: 2016-11-26 (not stated in the pack); boundary_exclusive: 2016-11-27 (not stated in the pack) | 2016-11-27 (boundary_exclusive, policy conservative) | TRUE
VOL-I-8.5-01 | ADD-03 | REFERENCE-LOOKBACK | within the ten (10) years preceding the Proposal Due Date | PDD = 2026-12-10 | boundary_inclusive: 2016-12-10 (not stated in the pack); boundary_exclusive: 2016-12-11 (not stated in the pack) | 2016-12-11 (boundary_exclusive, policy conservative) | TRUE
VOL-I-5.4-01 | BASE | PRE-BID | Wednesday 30 September 2026 at 10:00 Riyadh time |  | as_stated: 2026-09-30 (stated in VOL-I:5.4) | 2026-09-30 (as_stated, policy conservative) | FALSE
VOL-I-5.4-01 | ADD-01 | PRE-BID | Wednesday 30 September 2026 at 10:00 Riyadh time |  | as_stated: 2026-09-30 (stated in VOL-I:5.4) | 2026-09-30 (as_stated, policy conservative) | FALSE
VOL-I-5.4-01 | ADD-02 | PRE-BID | Wednesday 30 September 2026 at 10:00 Riyadh time |  | as_stated: 2026-09-30 (stated in VOL-I:5.4) | 2026-09-30 (as_stated, policy conservative) | FALSE
VOL-I-5.4-01 | ADD-03 | PRE-BID | Wednesday 30 September 2026 at 10:00 Riyadh time |  | as_stated: 2026-09-30 (stated in VOL-I:5.4) | 2026-09-30 (as_stated, policy conservative) | FALSE
ADD-01-3.1-01 | BASE | ATTENDANCE-NOTICE | within five (5) Working Days of this Addendum | ADD-01-issue = 2026-10-08 | event_day_excluded: 2026-10-15 (not stated in the pack (VOL-I §2.4 covers backward counting only)); event_day_counted: 2026-10-14 (not stated in the pack (VOL-I §2.4 covers backward counting only)) | 2026-10-14 (event_day_counted, policy conservative) | TRUE
ADD-01-3.1-01 | ADD-01 | ATTENDANCE-NOTICE | within five (5) Working Days of this Addendum | ADD-01-issue = 2026-10-08 | event_day_excluded: 2026-10-15 (not stated in the pack (VOL-I §2.4 covers backward counting only)); event_day_counted: 2026-10-14 (not stated in the pack (VOL-I §2.4 covers backward counting only)) | 2026-10-14 (event_day_counted, policy conservative) | TRUE
ADD-01-3.1-01 | ADD-02 | ATTENDANCE-NOTICE | within five (5) Working Days of this Addendum | ADD-01-issue = 2026-10-08 | event_day_excluded: 2026-10-15 (not stated in the pack (VOL-I §2.4 covers backward counting only)); event_day_counted: 2026-10-14 (not stated in the pack (VOL-I §2.4 covers backward counting only)) | 2026-10-14 (event_day_counted, policy conservative) | TRUE
ADD-01-3.1-01 | ADD-03 | ATTENDANCE-NOTICE | within five (5) Working Days of this Addendum | ADD-01-issue = 2026-10-08 | event_day_excluded: 2026-10-15 (not stated in the pack (VOL-I §2.4 covers backward counting only)); event_day_counted: 2026-10-14 (not stated in the pack (VOL-I §2.4 covers backward counting only)) | 2026-10-14 (event_day_counted, policy conservative) | TRUE
VOL-IV-F4C-06 | BASE | F4C-SIXTH-LOOKBACK | within the preceding five (5) years | date the declaration is signed = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-IV-F4C-06 | ADD-01 | F4C-SIXTH-LOOKBACK | within the preceding five (5) years | date the declaration is signed = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-IV-F4C-06 | ADD-02 | F4C-SIXTH-LOOKBACK | within the preceding five (5) years | date the declaration is signed = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-IV-F4C-06 | ADD-03 | F4C-SIXTH-LOOKBACK | within the preceding five (5) years | date the declaration is signed = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-3.4-01 | BASE | OMISSION-CLAIM-CUTOFF | No claim arising from an alleged omission shall be entertained after the Proposal Due Date. | PDD = 2026-11-12 | as_stated: 2026-11-12 (stated in VOL-I:3.4) | 2026-11-12 (as_stated, policy conservative) | FALSE
VOL-I-3.4-01 | ADD-01 | OMISSION-CLAIM-CUTOFF | No claim arising from an alleged omission shall be entertained after the Proposal Due Date. | PDD = 2026-11-26 | as_stated: 2026-11-26 (stated in VOL-I:3.4) | 2026-11-26 (as_stated, policy conservative) | FALSE
VOL-I-3.4-01 | ADD-02 | OMISSION-CLAIM-CUTOFF | No claim arising from an alleged omission shall be entertained after the Proposal Due Date. | PDD = 2026-11-26 | as_stated: 2026-11-26 (stated in VOL-I:3.4) | 2026-11-26 (as_stated, policy conservative) | FALSE
VOL-I-3.4-01 | ADD-03 | OMISSION-CLAIM-CUTOFF | No claim arising from an alleged omission shall be entertained after the Proposal Due Date. | PDD = 2026-12-10 | as_stated: 2026-12-10 (stated in VOL-I:3.4) | 2026-12-10 (as_stated, policy conservative) | FALSE
VOL-I-4.2-01 | BASE | BLACKOUT-START | From the date of issue of this Volume |  | as_stated: 2026-09-14 (stated in VOL-I:4.2) | 2026-09-14 (as_stated, policy conservative) | FALSE
VOL-I-4.2-01 | BASE | BLACKOUT-END | until the issue of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-4.2-01 | ADD-01 | BLACKOUT-START | From the date of issue of this Volume |  | as_stated: 2026-09-14 (stated in VOL-I:4.2) | 2026-09-14 (as_stated, policy conservative) | FALSE
VOL-I-4.2-01 | ADD-01 | BLACKOUT-END | until the issue of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-4.2-01 | ADD-02 | BLACKOUT-START | From the date of issue of this Volume |  | as_stated: 2026-09-14 (stated in VOL-I:4.2) | 2026-09-14 (as_stated, policy conservative) | FALSE
VOL-I-4.2-01 | ADD-02 | BLACKOUT-END | until the issue of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-4.2-01 | ADD-03 | BLACKOUT-START | From the date of issue of this Volume |  | as_stated: 2026-09-14 (stated in VOL-I:4.2) | 2026-09-14 (as_stated, policy conservative) | FALSE
VOL-I-4.2-01 | ADD-03 | BLACKOUT-END | until the issue of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-4.3-01 | BASE | SPOC-CHANGE-NOTICE | notify the Authority of any change within two (2) Working Days | SPOC-CHANGE = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-4.3-01 | ADD-01 | SPOC-CHANGE-NOTICE | notify the Authority of any change within two (2) Working Days | SPOC-CHANGE = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-4.3-01 | ADD-02 | SPOC-CHANGE-NOTICE | notify the Authority of any change within two (2) Working Days | SPOC-CHANGE = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-4.3-01 | ADD-03 | SPOC-CHANGE-NOTICE | notify the Authority of any change within two (2) Working Days | SPOC-CHANGE = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-6.7-01 | BASE | MODIFY-CUTOFF | at any time before the Proposal Due Date | PDD = 2026-11-12 | as_stated: 2026-11-12 (stated in VOL-I:6.7) | 2026-11-12 (as_stated, policy conservative) | FALSE
VOL-I-6.7-01 | ADD-01 | MODIFY-CUTOFF | at any time before the Proposal Due Date | PDD = 2026-11-26 | as_stated: 2026-11-26 (stated in VOL-I:6.7) | 2026-11-26 (as_stated, policy conservative) | FALSE
VOL-I-6.7-01 | ADD-02 | MODIFY-CUTOFF | at any time before the Proposal Due Date | PDD = 2026-11-26 | as_stated: 2026-11-26 (stated in VOL-I:6.7) | 2026-11-26 (as_stated, policy conservative) | FALSE
VOL-I-6.7-01 | ADD-03 | MODIFY-CUTOFF | at any time before the Proposal Due Date | PDD = 2026-12-10 | as_stated: 2026-12-10 (stated in VOL-I:6.7) | 2026-12-10 (as_stated, policy conservative) | FALSE
VOL-I-8.9-01 | BASE | INVESTMENT-LICENCE-BY-FC | a signed undertaking to obtain such licence prior to Financial Close | FC = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-8.9-01 | ADD-01 | INVESTMENT-LICENCE-BY-FC | a signed undertaking to obtain such licence prior to Financial Close | FC = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-8.9-01 | ADD-02 | INVESTMENT-LICENCE-BY-FC | a signed undertaking to obtain such licence prior to Financial Close | FC = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-8.9-01 | ADD-03 | INVESTMENT-LICENCE-BY-FC | a signed undertaking to obtain such licence prior to Financial Close | FC = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-8.10-01 | BASE | DEBARMENT-LOOKBACK | within the preceding five (5) years |  | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-8.10-01 | ADD-01 | DEBARMENT-LOOKBACK | within the preceding five (5) years |  | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-8.10-01 | ADD-02 | DEBARMENT-LOOKBACK | within the preceding five (5) years |  | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-8.10-01 | ADD-03 | DEBARMENT-LOOKBACK | within the preceding five (5) years |  | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.1-01 | BASE | CONCESSION-END-PCOD | twenty-five (25) years commencing on the Project Commercial Operation Date | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.1-01 | ADD-01 | CONCESSION-END-PCOD | twenty-five (25) years commencing on the Project Commercial Operation Date | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.1-01 | ADD-02 | CONCESSION-END-PCOD | twenty-five (25) years commencing on the Project Commercial Operation Date | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.1-01 | ADD-03 | CONCESSION-END-PCOD | twenty-five (25) years commencing on the Project Commercial Operation Date | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.2-01 | BASE | PB-COMMERCIAL-CLOSE | Commercial Close within one hundred and twenty (120) days ... of the date of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.2-01 | ADD-01 | PB-COMMERCIAL-CLOSE | Commercial Close within one hundred and twenty (120) days ... of the date of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.2-01 | ADD-02 | PB-COMMERCIAL-CLOSE | Commercial Close within one hundred and twenty (120) days ... of the date of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.2-01 | ADD-03 | PB-COMMERCIAL-CLOSE | Commercial Close within one hundred and twenty (120) days ... of the date of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.2-02 | BASE | PB-FINANCIAL-CLOSE | Financial Close within two hundred and seventy (270) days, of the date of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.2-02 | ADD-01 | PB-FINANCIAL-CLOSE | Financial Close within two hundred and seventy (270) days, of the date of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.2-02 | ADD-02 | PB-FINANCIAL-CLOSE | Financial Close within two hundred and seventy (270) days, of the date of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.2-02 | ADD-03 | PB-FINANCIAL-CLOSE | Financial Close within two hundred and seventy (270) days, of the date of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-6.3-02 | BASE | VOL-II-SECURITY-ARCHITECTURE-DUE | prior to commissioning | Commissioning = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-6.3-02 | ADD-01 | VOL-II-SECURITY-ARCHITECTURE-DUE | prior to commissioning | Commissioning = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-6.3-02 | ADD-02 | VOL-II-SECURITY-ARCHITECTURE-DUE | prior to commissioning | Commissioning = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-6.3-02 | ADD-03 | VOL-II-SECURITY-ARCHITECTURE-DUE | prior to commissioning | Commissioning = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-7.4-01 | BASE | VOL-II-AS-BUILT-DUE | not later than sixty (60) days after PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-7.4-01 | ADD-01 | VOL-II-AS-BUILT-DUE | not later than sixty (60) days after PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-7.4-01 | ADD-02 | VOL-II-AS-BUILT-DUE | not later than sixty (60) days after PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-7.4-01 | ADD-03 | VOL-II-AS-BUILT-DUE | not later than sixty (60) days after PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.2-01 | BASE | VOL-II-CMMS-BY-PCOD | implemented before PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.2-01 | ADD-01 | VOL-II-CMMS-BY-PCOD | implemented before PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.2-01 | ADD-02 | VOL-II-CMMS-BY-PCOD | implemented before PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.2-01 | ADD-03 | VOL-II-CMMS-BY-PCOD | implemented before PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.5-01 | BASE | VOL-II-HANDBACK-SURVEY-WINDOW | in the final two (2) years of the concession | End of the concession period = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.5-01 | ADD-01 | VOL-II-HANDBACK-SURVEY-WINDOW | in the final two (2) years of the concession | End of the concession period = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.5-01 | ADD-02 | VOL-II-HANDBACK-SURVEY-WINDOW | in the final two (2) years of the concession | End of the concession period = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.5-01 | ADD-03 | VOL-II-HANDBACK-SURVEY-WINDOW | in the final two (2) years of the concession | End of the concession period = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.5-02 | BASE | VOL-II-HANDBACK-REMEDIALS-DUE | completed before transfer | Transfer of the Facility = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.5-02 | ADD-01 | VOL-II-HANDBACK-REMEDIALS-DUE | completed before transfer | Transfer of the Facility = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.5-02 | ADD-02 | VOL-II-HANDBACK-REMEDIALS-DUE | completed before transfer | Transfer of the Facility = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.5-02 | ADD-03 | VOL-II-HANDBACK-REMEDIALS-DUE | completed before transfer | Transfer of the Facility = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-9.2-01 | BASE | VOL-II-ENV-CLEARANCE-DUE | before commencement of construction | Commencement of construction = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-9.2-01 | ADD-01 | VOL-II-ENV-CLEARANCE-DUE | before commencement of construction | Commencement of construction = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-9.2-01 | ADD-02 | VOL-II-ENV-CLEARANCE-DUE | before commencement of construction | Commencement of construction = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-9.2-01 | ADD-03 | VOL-II-ENV-CLEARANCE-DUE | before commencement of construction | Commencement of construction = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-9.3-01 | BASE | VOL-II-GRIEVANCE-DUE | established before construction | Commencement of construction = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-9.3-01 | ADD-01 | VOL-II-GRIEVANCE-DUE | established before construction | Commencement of construction = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-9.3-01 | ADD-02 | VOL-II-GRIEVANCE-DUE | established before construction | Commencement of construction = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-9.3-01 | ADD-03 | VOL-II-GRIEVANCE-DUE | established before construction | Commencement of construction = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-IV-F4A-04 | BASE | PROPOSAL-VALIDITY-F4A | valid for one hundred and fifty (150) days from the Proposal Due Date | PDD = 2026-11-12 | day0: 2027-04-11 (not stated in the pack); day1: 2027-04-10 (not stated in the pack) | 2027-04-11 (day0, policy conservative) | TRUE
VOL-IV-F4A-04 | ADD-01 | PROPOSAL-VALIDITY-F4A | valid for one hundred and fifty (150) days from the Proposal Due Date | PDD = 2026-11-26 | day0: 2027-04-25 (not stated in the pack); day1: 2027-04-24 (not stated in the pack) | 2027-04-25 (day0, policy conservative) | TRUE
VOL-IV-F4A-04 | ADD-02 | PROPOSAL-VALIDITY-F4A | valid for one hundred and fifty (150) days from the Proposal Due Date | PDD = 2026-11-26 | day0: 2027-04-25 (not stated in the pack); day1: 2027-04-24 (not stated in the pack) | 2027-04-25 (day0, policy conservative) | TRUE
VOL-IV-F4A-04 | ADD-03 | PROPOSAL-VALIDITY-F4A | valid for one hundred and fifty (150) days from the Proposal Due Date | PDD = 2026-12-10 | day0: 2027-05-09 (not stated in the pack); day1: 2027-05-08 (not stated in the pack) | 2027-05-09 (day0, policy conservative) | TRUE
VOL-V-3.1-01 | BASE | VOL-V-TERM-END | twenty-five (25) years from the Effective Date | Effective Date = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-3.1-01 | ADD-01 | VOL-V-TERM-END | twenty-five (25) years from the Effective Date | Effective Date = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-3.1-01 | ADD-02 | VOL-V-TERM-END | twenty-five (25) years from the Effective Date | Effective Date = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-3.1-01 | ADD-03 | VOL-V-TERM-END | twenty-five (25) years from the Effective Date | Effective Date = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-12.1-01 | BASE | VOL-V-SCHEDULED-PCOD | within thirty-six (36) months of the Notice to Proceed | Notice to Proceed = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-12.1-01 | ADD-01 | VOL-V-SCHEDULED-PCOD | within thirty-six (36) months of the Notice to Proceed | Notice to Proceed = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-12.1-01 | ADD-02 | VOL-V-SCHEDULED-PCOD | within thirty-six (36) months of the Notice to Proceed | Notice to Proceed = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-12.1-01 | ADD-03 | VOL-V-SCHEDULED-PCOD | within thirty-six (36) months of the Notice to Proceed | Notice to Proceed = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-18.3-01 | BASE | VOL-V-PCOD-LONG-STOP | within three hundred and sixty-five (365) days after the Scheduled PCOD | Scheduled PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-18.3-01 | ADD-01 | VOL-V-PCOD-LONG-STOP | within three hundred and sixty-five (365) days after the Scheduled PCOD | Scheduled PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-18.3-01 | ADD-02 | VOL-V-PCOD-LONG-STOP | within three hundred and sixty-five (365) days after the Scheduled PCOD | Scheduled PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-18.3-01 | ADD-03 | VOL-V-PCOD-LONG-STOP | within three hundred and sixty-five (365) days after the Scheduled PCOD | Scheduled PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-29.3-01 | BASE | VOL-V-RAMP-UP-END | the first twelve (12) months after PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-29.3-01 | ADD-01 | VOL-V-RAMP-UP-END | the first twelve (12) months after PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-29.3-01 | ADD-02 | VOL-V-RAMP-UP-END | the first twelve (12) months after PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-29.3-01 | ADD-03 | VOL-V-RAMP-UP-END | the first twelve (12) months after PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-29.4-01 | BASE | VOL-V-INVOICE-DUE | within ten (10) Working Days of each month end | Each month end = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-29.4-01 | ADD-01 | VOL-V-INVOICE-DUE | within ten (10) Working Days of each month end | Each month end = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-29.4-01 | ADD-02 | VOL-V-INVOICE-DUE | within ten (10) Working Days of each month end | Each month end = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-29.4-01 | ADD-03 | VOL-V-INVOICE-DUE | within ten (10) Working Days of each month end | Each month end = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-34.3-01 | BASE | VOL-V-RELIEF-EVENT-NOTICE | within five (5) Working Days of becoming aware of it | Becoming aware of a Relief Event = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-34.3-01 | ADD-01 | VOL-V-RELIEF-EVENT-NOTICE | within five (5) Working Days of becoming aware of it | Becoming aware of a Relief Event = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-34.3-01 | ADD-02 | VOL-V-RELIEF-EVENT-NOTICE | within five (5) Working Days of becoming aware of it | Becoming aware of a Relief Event = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-34.3-01 | ADD-03 | VOL-V-RELIEF-EVENT-NOTICE | within five (5) Working Days of becoming aware of it | Becoming aware of a Relief Event = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-42.2-01 | BASE | VOL-V-HANDBACK-RESERVE-START | from the start of year twenty (20) of the term | Start of the term = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-42.2-01 | ADD-01 | VOL-V-HANDBACK-RESERVE-START | from the start of year twenty (20) of the term | Start of the term = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-42.2-01 | ADD-02 | VOL-V-HANDBACK-RESERVE-START | from the start of year twenty (20) of the term | Start of the term = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-42.2-01 | ADD-03 | VOL-V-HANDBACK-RESERVE-START | from the start of year twenty (20) of the term | Start of the term = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE

## Issues
Id | Text | Owner | Source | Rows
I-NO-CONSEQUENCE | Mandatory under the VOL-I 11.1(i) pass/fail check, but the clause states no consequence; whether failure puts the bid out is for a person | Bid manager | curated (proposed wording) | VOL-I-6.3-01; VOL-I-6.4-01; VOL-I-6.4-02; VOL-I-7.1-01; VOL-I-8.3-01; ADD-01-AppA-01; ADD-02-5.2-01; ADD-02-F4G-04; VOL-I-6.2-01; VOL-I-6.5-01; VOL-I-8.4-01; VOL-I-8.4-02; VOL-I-8.7-01; VOL-I-8.8-01; VOL-I-8.9-01; VOL-I-8.10-01; VOL-I-9.1-01; VOL-I-9.1h-01; VOL-I-9.7-01; VOL-I-10.1-01; VOL-I-10.2-01; VOL-I-10.3-01; VOL-I-10.3-02; VOL-I-10.4-01; VOL-I-10.5-02; VOL-I-10.6-01; VOL-I-App3-01; VOL-IV-F4A-03; VOL-IV-F4A-04; VOL-IV-F4A-05; VOL-IV-F4A-06; VOL-IV-F4A-07; VOL-IV-F4B-01; VOL-IV-F4C-01; VOL-IV-F4C-02; VOL-IV-F4C-03; VOL-IV-F4C-05; VOL-IV-F4D-01; VOL-IV-F4E-01; VOL-IV-F4F-01; VOL-IV-F4F-02
I-LCC-ISSUER | Local Content Certificate: issuing 'competent authority' not named and no lead time stated; the minutes (non-binding) record bidders' difficulty obtaining it in time | Commercial | curated (proposed wording) | VOL-I-8.6-01
I-BIDDER-FACTS | Bidder facts (members, signatories, attendance, references) are configurable assumptions, not facts; confirm them | Bid manager | curated (proposed wording) | VOL-I-5.4-01; VOL-I-9.4-01; VOL-I-1.4-01; VOL-I-8.1-01; VOL-I-8.2-01; VOL-I-8.4-01; VOL-I-8.4-02; VOL-I-8.8-01; VOL-I-8.9-01; VOL-I-8.10-01; VOL-I-9.1h-01; VOL-I-9.5-01; VOL-IV-F4A-06; VOL-IV-F4A-07; VOL-IV-F4B-01; VOL-IV-F4C-01; VOL-IV-F4C-02; VOL-IV-F4C-03
I-F4A-FIELDS | Reissued Form 4-A (ADD-01 App A) drops fields and the numbered confirmations of the original and states a purpose ('acknowledgement of Addenda at paragraph 1') it has no paragraph for; what to print and sign, and whether to seek clarification before the cut-off | Legal | curated (proposed wording) | VOL-I-9.3-01; VOL-IV-F4A-01; ADD-01-AppA-01; VOL-IV-FORMS-01; VOL-IV-F4A-02; VOL-IV-F4A-03; VOL-IV-F4A-04; VOL-IV-F4A-05; VOL-IV-F4A-06; VOL-IV-F4A-07
I-READING-F4C | Form 4-C (image, Arabic) reading pending the owner's review, including the declaration 5 clause reference (٢ or ٣) and diacritics | Owner (Arabic reviewer) | curated (proposed wording) | VOL-IV-F4C-04; VOL-IV-F4C-N1; VOL-IV-F4C-01; VOL-IV-F4C-02; VOL-IV-F4C-03; VOL-IV-F4C-05
I-READING-T24 | Table 2-4 (image) reading pending the owner's review, including the decimal point in 2.2 and the pH unit dash | Owner | curated (proposed wording) | VOL-II-T2-4-TN; ADD-02-5.2-01; VOL-II-2.4-01; VOL-II-2.5-01; VOL-II-T2-4-BOD5; VOL-II-T2-4-COD; VOL-II-T2-4-TSS; VOL-II-T2-4-TP; VOL-II-T2-4-Turbidity; VOL-II-T2-4-FaecalColiforms; VOL-II-T2-4-ResidualChlorine; VOL-II-T2-4-pH; VOL-II-T2-4-OilGrease; VOL-II-T2-4-NOTE1; VOL-II-3.1-01; VOL-II-4.3-02; VOL-II-7.2-01; VOL-V-29.3-01; VOL-V-31.1-02
I-F4G-LETTERING | Form 4-G is inserted after item (e) of VOL-I 9.1; the re-lettering of items (f)-(i) is not stated | Bid manager | curated (proposed wording) | ADD-02-7.2-01; VOL-I-9.1-01
I-F4G-NO | Form 4-G undertakings are answered Yes/No; the effect of 'No' is not stated, and undertakings 3-6 add post-award obligations not in VOL-II 6 | Technical | curated (proposed wording) | ADD-02-F4G-01; ADD-02-F4G-02; ADD-02-F4G-03
I-PERMIT | Table 2-4 is reproduced from an Environmental Permit that is not in the pack and prevails over the reproduction (VOL-II 2.4); compliance with the Permit cannot be established | Technical | curated (proposed wording) | VOL-II-T2-4-TN; ADD-02-5.2-01; VOL-II-2.4-01; VOL-II-T2-4-BOD5; VOL-II-T2-4-COD; VOL-II-T2-4-TSS; VOL-II-T2-4-TP; VOL-II-T2-4-Turbidity; VOL-II-T2-4-FaecalColiforms; VOL-II-T2-4-ResidualChlorine; VOL-II-T2-4-pH; VOL-II-T2-4-OilGrease; VOL-II-T2-4-NOTE1; VOL-II-3.1-01; VOL-II-7.2-01; VOL-V-31.1-02
I-CONCESSION | Concession term: VOL-I 12.1 (from PCOD) vs VOL-V 3.1 (from the Effective Date); ADD-02 Q7 declined to amend. A legal/commercial question | Legal | curated (proposed wording) | VOL-I-3.3-01; VOL-I-9.6-01; VOL-I-12.1-01; VOL-II-1.1-01; VOL-II-8.5-01; VOL-II-8.5-02; VOL-V-NOTE-01; VOL-V-3.1-01; VOL-V-3.2-01; VOL-V-42.1-01; VOL-V-42.2-01
I-FLOWS | Design flows: Table 2-6 peak hourly flow vs 3 x dry weather flow; ADD-02 Q11 did not answer. An engineering question | Technical | curated (proposed wording) | ADD-03-11.2-01; VOL-II-4.1-01; VOL-II-T2-6-1; VOL-II-T2-6-2; VOL-II-T2-6-4; VOL-II-4.2-01; VOL-II-5.2-01; VOL-V-31.1-01
I-VOL-III | Volume III referenced (VOL-I 3.1), not supplied; pack confirmed complete (2 Oct). Only Drawing 03-C-114 shows the effluent main's delivery point (VOL-II 5.1). No omission claim after the PDD (VOL-I 3.4) | Technical | curated (proposed wording) | ADD-01-Q4-01; VOL-I-3.4-01; VOL-I-5.5-01; VOL-II-5.1-01; VOL-II-5.2-02; VOL-V-31.1-03
I-BLIND-CAP | New VOL-I 10.5 (ADD-03 8.1) caps the Availability Payment at SAR 210m per annum for year 1, excluding VAT, with rejection; how the cap applies to the indexed profile in later years is not stated, and the renumbering of 10.5/10.6 must be followed in every reference | Commercial | curated (proposed wording) | ADD-03-8.1-01
I-BLIND-F4C-LANG | ADD-03 12.1 adds a sixth Form 4-C declaration in English only, while Form 4-C is completed in Arabic and the Arabic governs (VOL-I 9.4); which wording each member signs, and how the look-back is dated, should be clarified | Legal | curated (proposed wording) | VOL-IV-F4C-06
I-BLIND-Q16 | ADD-03 Q16 amends VOL-II 6.1 (control room manned 06:00-22:00, not permanently) in a clarification answer rather than a numbered provision; staffing and O&M costs change | Technical | curated (proposed wording)
I-BLIND-TSS | ADD-03 10.1 sets TSS at 15 mg/l assessed on any single sample, against the table's general 30-day rolling average; the reading of Table 2-4 (pending) shows the previous value | Technical | curated (proposed wording)
I-VOL-I-ENV-B | VOL-I 10.1: Envelope B holds 'only' Form 4-F and the Financial Model, yet 10.3 (model auditor's opinion) and 10.6 (financing assumptions schedule) need more documents; where they go is unstated | Bid manager | curated (proposed wording) | VOL-I-3.3-01; VOL-I-10.1-01; VOL-I-10.3-02; VOL-I-10.6-01; VOL-IV-F4F-01
I-VOL-I-ENV-A-PRICES | VOL-I 6.2 makes any price, rate or other commercial information in Envelope A non-responsive, but Form 4-B (Envelope A) asks for each reference's contract value in SAR | Bid manager | curated (proposed wording) | VOL-I-3.3-01; VOL-I-6.2-02; VOL-I-9.5-01; VOL-IV-F4B-01
I-VOL-I-COPIES | VOL-I 6.5 (1 marked original, 3 hard copies, 1 encrypted USB copy) does not say whether the copies are per envelope or per Proposal | Bid manager | curated (proposed wording) | VOL-I-6.5-01
I-VOL-I-FILE-NAMES | VOL-I Appendix 2 names every file '.pdf', but VOL-I 10.3 requires the Financial Model in Excel; the meaning of [YYYYMMDD] is not stated | Bid manager | curated (proposed wording) | VOL-I-6.5-02; VOL-I-10.3-01
I-VOL-I-BOND-LONGSTOP | Bid Bond valid 180 days from the PDD (VOL-I 6.3), but 12.2 lets the Authority call it if Financial Close is missed 270 days after the PBN; 'long-stop date' is undefined | Commercial lead | curated (proposed wording) | VOL-I-12.2-02
I-VOL-I-APPENDICES | VOL-I 9.2 excludes 'the appendices expressly permitted by Volume II' from the page limit; none was found in the Volume II extract | Technical lead | curated (proposed wording) | VOL-I-9.2-01
I-VOL-II-MISSING | Not in the pack: ESIA (VOL-II 9.1) and geotechnical report (ADD-01 Q4), both 'in the data room'; tie-in points (1.3); asset register format (7.4). ESIA compliance and ground risk unverifiable | Technical lead | curated (proposed wording) | VOL-II-1.3-01; VOL-II-5.4-01; VOL-II-7.4-01; VOL-II-9.1-01
I-VOL-II-T24-TENSIONS | Table 2-4 says 'all values are maxima' but chlorine and pH are ranges; chlorine 0.5-1.0 mg/l continuous vs UV-only allowed by VOL-II 3.3; 'at all times' (2.4) vs averaging bases | Process engineer | curated (proposed wording) | VOL-II-2.4-01; VOL-II-T2-4-ResidualChlorine; VOL-II-T2-4-pH; VOL-II-3.3-01
I-VOL-V-MISSING | VOL-V is an extract: omitted clauses, Schedules 7 (deductions), 9 (indexation), 11 (defaults), 12 (termination sums) and the Direct Agreement are not supplied, yet unlisted deviations are accepted | Legal counsel | curated (proposed wording) | VOL-V-NOTE-01; VOL-V-31.1-01; VOL-V-31.1-02; VOL-V-31.1-03; VOL-V-39.1-01
I-VOL-V-PERSISTENT-BREACH | VOL-V 31.4: 'on a second occurrence' is not defined (a second persistent breach, or a further event after the remediation plan); the termination right in 39.3 turns on it | Legal counsel | curated (proposed wording) | VOL-V-31.4-01
I-VOL-IV-SCALE | ADD-02 note (3) to Table 1-1: marks on the Authority's 'standard five-point scale' multiplied by 'the weight shown'; the scale is not in the pack and the table shows Marks, not weights | Bid manager | curated (proposed wording) | ADD-02-T1-1-N3-01
I-OP-ADD-01/Q4 | ADD-01/Q4: the geotechnical report and the wadi-crossing drawing (Volume III) are referenced but not supplied | Bid manager | amendment op
I-OP-ADD-01/AppA/para1 | ADD-01/AppA/para1: the reissued form may differ from the original in more than its stated purpose; compare | Bid manager | amendment op
I-OP-ADD-02/T1-1-rev/note(2) | ADD-02/T1-1-rev/note(2): the addendum restates the value without quoting the old words; the old words were located in the target by shape and need a person's check | Bid manager | amendment op
I-OP-ADD-02/T1-1-rev/note(3) | ADD-02/T1-1-rev/note(3): the 'standard five-point scale' is not defined in the pack and the table shows Marks, not weights | Bid manager | amendment op
I-OP-ADD-02/Q7 | ADD-02/Q7: which start date governs the concession term is not answered; a legal and commercial question for people | Bid manager | amendment op
I-OP-ADD-02/Q11 | ADD-02/Q11: the Table 2-6 peak hourly flow vs storm flow question is not answered | Bid manager | amendment op
I-OP-ADD-02/7.1 | ADD-02/7.1: re-lettering of the items after (e) is not stated | Bid manager | amendment op
I-OP-ADD-03/5.1 | ADD-03/5.1: the three hard copies are deleted: the A5 copy counts (config submission.hard_copies) must follow (replanned in this rehearsal) | Bid manager | amendment op
I-OP-ADD-03/10.1(b) | ADD-03/10.1(b): TSS is now assessed on any single sample, not the 30-day rolling average the table's qualifier states for all values: a stricter test (process design) | Bid manager | amendment op
I-OP-ADD-03/12.1 | ADD-03/12.1: Form 4-C is an Arabic form whose Arabic text governs (VOL-I 9.4); the sixth declaration is given only in English | Bid manager | amendment op
I-OP-ADD-03/Q16 | ADD-03/Q16: a substantive amendment made in a clarification answer | Bid manager | amendment op
I-AUTO-SUMMARY-ADD-01 | ADD-01's cover summary does not match its provisions (C28): [understated] 'responds to clarification requests 1 to 6', but ADD-01/Q4 adds an obligation (ADD-01:Q4): 'The geotechnical report in the data room is provided for information. Bidders shall satisfy themselves as to ground conditions.'; [omitted] ADD-01/3.1 adds an obligation (ADD-01:3.1); the summary does not mention it: 'The attendance record is held by the Authority. A Bidder that considers its attendance to have been incorrectly recorded shall notify the Authority through the Portal within five (5) Working Days of this Addendum.'; [omitted] ADD-01/AppA/para1 replaces VOL-IV:F4-A; the summary does not mention it: 'Form 4-A is reissued below to add the acknowledgement of Addenda at paragraph 1. Bidders shall use this version.'. The summary is never applied; a person decides whether to raise a clarification | Bid manager | C28 (automatic)
I-AUTO-SUMMARY-ADD-02 | ADD-02's cover summary does not match its provisions (C28): [consequence not mentioned] ADD-02:7.2 states 'Failure to submit Form 4-G shall render the Proposal non-responsive.'; the summary says only 'adds Form 4-G'; [understated] 'reinstates Volume I Clause 8.6', but ADD-02/9.1 reinstates it in an amended form: 'The Bidder shall submit a Local Content Certificate issued by the competent authority evidencing a local content ratio of not less than thirty-five per cent (35%) for the construction phase. Failure …' (as issued: 'The Bidder shall submit a Local Content Certificate issued by the competent authority evidencing a local content ratio of not less than thirty per cent (30%) f…'); [consequence not mentioned] ADD-02:9.1 states 'Failure to submit the certificate shall render the Proposal non-responsive.'; the summary says only 'reinstates Volume I Clause 8.6'; [omitted] ADD-02/T1-1-rev/note(2) amends VOL-I:11.2; the summary does not mention it: '(2) The combined score weighting stated in Volume I Clause 11.2 is amended to sixty-five per cent (65%) technical and thirty-five per cent (35%) commercial.'; [omitted] ADD-02/5.2 adds an obligation (VOL-II:S3); the summary does not mention it: 'Bidders shall reflect the amended limit in the process design submitted under Volume II Section 3.'; [omitted] ADD-02/9.2 ends the effect of ADD-01:4.2; the summary does not mention it: 'Section 4.2 of Addendum No. 1 ceases to have effect.'. The summary is never applied; a person decides whether to raise a clarification | Bid manager | C28 (automatic)
I-AUTO-SUMMARY-ADD-03 | ADD-03's cover summary does not match its provisions (C28): [consequence not mentioned] ADD-03:8.1 states 'A Proposal that quotes an Availability Payment exceeding this amount shall be rejected.'; the summary says only 'inserts a new Volume I Clause 10.5'; [understated] 'responds to clarification requests 15 to 20', but ADD-03/Q16 amends VOL-II:6.1: 'No. In Volume II Clause 6.1, ‘a permanently manned central control room’ is deleted and ‘a central control room manned between 06:00 and 22:00 daily’ is substituted. Volume II Clause 8.3 is unchanged.'; [understated] 'responds to clarification requests 15 to 20', but ADD-03/Q17 adds an obligation (VOL-I:8.5): 'No. Only a reference project for which the consortium member itself was responsible for design, construction or operation will be considered. A reference project of an affiliate will be disregarded.'; [omitted] ADD-03/2.3 amends ADD-01:AppA/proposal-due-date; the summary does not mention it: 'In the revised Form 4-A at Appendix A to Addendum No. 1, the entry against ‘Proposal Due Date’, which was not updated by that Addendum, is corrected to read ‘10 December 2026, 14:00 Riyadh time’.'; [omitted] ADD-03/3.2 amends VOL-I:5.2; the summary does not mention it: 'In Volume I Clause 5.2, ‘Requests received after that time will not be answered.’ is deleted and ‘Requests received after 14:00 Riyadh time on the last day for submission will not be answered.’ is substituted.'; [omitted] ADD-03/8.2 renumbers VOL-I:10.5, VOL-I:10.6; the summary does not mention it: 'Existing Volume I Clauses 10.5 and 10.6 are renumbered 10.6 and 10.7 respectively. A reference to Clause 10.5 or Clause 10.6 in Volumes I to V or in Addenda Nos. 1 and 2, including in the response to clarification request 14 in Addendum No…'; [omitted] ADD-03/9.2 ends the effect of ADD-02:Q13; the summary does not mention it: 'The response to clarification request 13 in Addendum No. 2 is superseded.'; [omitted] ADD-03/11.2 adds an obligation (ADD-03:11.2); the summary does not mention it: 'Bidders shall reflect the amended flow in the hydraulic design submitted under Volume II Section 4.'; [omitted] ADD-03/12.2 adds an obligation (VOL-I:9.4); the summary does not mention it: 'Each member of the Bidder shall give the sixth declaration in its Form 4-C. Volume I Clause 9.4 applies.'. The summary is never applied; a person decides whether to raise a clarification | Bid manager | C28 (automatic)
I-AUTO-STALE | 28 row(s) STALE at ADD-03: a dependency changed after the interpretation was made (dates recomputed; the reading needs a person). Rows: VOL-I-6.3-01, VOL-I-6.4-02, VOL-I-7.1-01, VOL-I-8.3-01, VOL-IV-F4A-01, VOL-I-9.4-01, ADD-02-7.2-01, VOL-I-3.4-01, VOL-I-5.5-01, VOL-I-6.5-02, VOL-I-6.7-01, VOL-I-8.7-01, VOL-I-9.1-01, VOL-I-9.1h-01, VOL-I-9.2-01, VOL-I-9.5-01, VOL-I-9.6-01, VOL-I-9.7-01, VOL-I-10.5-01, VOL-I-10.5-02, VOL-I-10.6-01, VOL-I-12.2-01, VOL-II-5.2-01, VOL-II-6.1-01, VOL-II-7.2-01, VOL-IV-F4A-02, VOL-V-29.3-01, VOL-V-29.4-01 | Bid manager | C11 (automatic) | VOL-I-6.3-01; VOL-I-6.4-02; VOL-I-7.1-01; VOL-I-8.3-01; VOL-IV-F4A-01; VOL-I-9.4-01; ADD-02-7.2-01; VOL-I-3.4-01; VOL-I-5.5-01; VOL-I-6.5-02; VOL-I-6.7-01; VOL-I-8.7-01; VOL-I-9.1-01; VOL-I-9.1h-01; VOL-I-9.2-01; VOL-I-9.5-01; VOL-I-9.6-01; VOL-I-9.7-01; VOL-I-10.5-01; VOL-I-10.5-02; VOL-I-10.6-01; VOL-I-12.2-01; VOL-II-5.2-01; VOL-II-6.1-01; VOL-II-7.2-01; VOL-IV-F4A-02; VOL-V-29.3-01; VOL-V-29.4-01
I-AUTO-COUNTING | Counting conventions not stated in the pack for ATTENDANCE-NOTICE, BID-BOND-VALIDITY, PROPOSAL-VALIDITY, PROPOSAL-VALIDITY-F4A, REFERENCE-LOOKBACK: every reading is shown (A1 Dates); planning uses the conservative reading (config/assumptions.yaml) | Bid manager | D4 (automatic)
I-AUTO-PENDING-READINGS | 20 row(s) rely on image readings (Table 2-4, Form 4-C) still pending the owner's review. Rows: VOL-I-9.4-01, VOL-II-2.5-01, VOL-II-T2-4-BOD5, VOL-II-T2-4-COD, VOL-II-T2-4-FaecalColiforms, VOL-II-T2-4-NOTE1, VOL-II-T2-4-OilGrease, VOL-II-T2-4-ResidualChlorine, VOL-II-T2-4-TN, VOL-II-T2-4-TP, VOL-II-T2-4-TSS, VOL-II-T2-4-Turbidity, VOL-II-T2-4-pH, VOL-IV-F4C-01, VOL-IV-F4C-02, VOL-IV-F4C-03, VOL-IV-F4C-04, VOL-IV-F4C-05, VOL-IV-F4C-N1, VOL-V-29.3-01 | Owner | readings (automatic) | VOL-I-9.4-01; VOL-II-2.5-01; VOL-II-T2-4-BOD5; VOL-II-T2-4-COD; VOL-II-T2-4-FaecalColiforms; VOL-II-T2-4-NOTE1; VOL-II-T2-4-OilGrease; VOL-II-T2-4-ResidualChlorine; VOL-II-T2-4-TN; VOL-II-T2-4-TP; VOL-II-T2-4-TSS; VOL-II-T2-4-Turbidity; VOL-II-T2-4-pH; VOL-IV-F4C-01; VOL-IV-F4C-02; VOL-IV-F4C-03; VOL-IV-F4C-04; VOL-IV-F4C-05; VOL-IV-F4C-N1; VOL-V-29.3-01
I-A5-attendance-notice | A5 attendance-notice: DEADLINE PASSED (ATTENDANCE-NOTICE = 2026-10-14 is before the status date 2026-11-05; record whether it was done) (ADD-01-3.1-01, VOL-I-5.4-01; duration 2 WD is an ASSUMPTION: clarification_drafting) | Bid management | A5 (automatic) | ADD-01-3.1-01; VOL-I-5.4-01
I-A5-lcc-ratio | A5 lcc-ratio: INFEASIBLE by 12 WD (latest start 2026-10-20 is before the status date 2026-11-05; not compressed) (VOL-I-8.6-01; duration 5 WD is an ASSUMPTION: lcc_ratio_calc) | Commercial | A5 (automatic) | VOL-I-8.6-01
I-A5-lcc-certificate | A5 lcc-certificate: INFEASIBLE by 7 WD (latest start 2026-10-27 is before the status date 2026-11-05; not compressed) (VOL-I-8.6-01; duration 30 WD is an ASSUMPTION: lcc_certificate) | Commercial | A5 (automatic) | VOL-I-8.6-01
I-A5-FEASIBILITY | A5 at the status date: attendance-notice DEADLINE PASSED; lcc-ratio INFEASIBLE by 12 WD; lcc-certificate INFEASIBLE by 7 WD. Lead times are PROVISIONAL assumptions (A5 drivers) | Bid manager | A5 (automatic) | ADD-01-3.1-01; VOL-I-5.4-01; VOL-I-8.6-01

## Stages
Stage | Addendum | Issued | Status | Ops | Invalid ops | Ops review | Provisions | Unresolved | Validated
BASE |  |  | BASE | 0 | 0 |  | 0 | 0 | TRUE
ADD-01 | ADD-01 | 2026-10-08 | APPLIED | 15 | 0 | proposed 15 | 36 | 0 | TRUE
ADD-02 | ADD-02 | 2026-10-22 | APPLIED | 22 | 0 | proposed 22 | 40 | 0 | TRUE
ADD-03 | ADD-03 | 2026-11-05 | APPLIED | 28 | 0 | proposed 28 | 29 | 0 | TRUE

## Assumptions
Key | Value | Basis | Owner
lead_times.poa_board_resolutions | 5 WD | PROVISIONAL ASSUMPTION: board resolutions of each member authorising its signatories, members in parallel; not stated in the pack | Legal
lead_times.poa_notarisation | 5 WD | PROVISIONAL ASSUMPTION: typical notarisation of a Power of Attorney, signatories in parallel; not stated in the pack | Legal
lead_times.form_4a_signature | 1 WD | PROVISIONAL ASSUMPTION: signature by the PoA holder; not stated | Legal
lead_times.spoc_confirmation | 1 WD | PROVISIONAL ASSUMPTION: confirm the single point of contact named in Form 4-A; not stated | Bid management
lead_times.form_4b_preparation | 3 WD | PROVISIONAL ASSUMPTION: complete one Form 4-B per reference project from the reference evidence; not stated | Technical
lead_times.completion_certificate | 15 WD | PROVISIONAL ASSUMPTION: obtain a client completion certificate for each reference plant from a third-party client (may already be held); not stated | Technical
lead_times.form_4c_arabic_prep | 2 WD | PROVISIONAL ASSUMPTION: prepare the Arabic form per member; not stated | Legal
lead_times.form_4c_member_sign | 3 WD | PROVISIONAL ASSUMPTION: signature and stamp at each member's office, members in parallel; not stated | Legal
lead_times.pcg_wording | 10 WD | PROVISIONAL ASSUMPTION: agree the Parent Company Guarantee wording (substantially Form 4-D) with the EPC Contractor's ultimate parent; not stated | Legal
lead_times.pcg_execution | 10 WD | PROVISIONAL ASSUMPTION: parent board approval and execution of the guarantee; not stated | Legal
lead_times.deviations_review | 10 WD | PROVISIONAL ASSUMPTION: review Volume V and list every deviation, qualification or reservation; not stated | Legal
lead_times.form_4e_finalise | 2 WD | PROVISIONAL ASSUMPTION: finalise and sign Form 4-E, cross-check that no qualification appears elsewhere (VOL-I 9.6); not stated | Legal
lead_times.form_4g_review | 5 WD | PROVISIONAL ASSUMPTION: review the six cybersecurity undertakings with the O&M and OT teams; not stated | Technical
lead_times.form_4g_signature | 1 WD | PROVISIONAL ASSUMPTION: signature for the Bidder; not stated | Technical
lead_times.technical_proposal | 20 WD | PROVISIONAL ASSUMPTION: remaining work on the narrative incl. process design to the amended TN limit and standby power; not stated | Technical
lead_times.investment_licence | 5 WD | PROVISIONAL ASSUMPTION: copy of a current licence or a signed undertaking per foreign member (the undertaking route); not stated | Legal
lead_times.bid_bond_bank_approval | 10 WD | PROVISIONAL ASSUMPTION: bank credit approval for a SAR 4.5m first-demand bond; not stated | Commercial
lead_times.bid_bond_issue | 3 WD | PROVISIONAL ASSUMPTION: issue of the bond after approval; not stated | Commercial
lead_times.lcc_ratio_calc | 5 WD | PROVISIONAL ASSUMPTION: compute the construction-phase local content ratio; not stated | Commercial
lead_times.lcc_certificate | 30 WD | PROVISIONAL ASSUMPTION: issuing authority not named and no lead time stated; the (non-binding) minutes record bidders' difficulty obtaining it 'within the programme'; set deliberately long until the owner confirms | Commercial
lead_times.iso_certificate_copy | 2 WD | PROVISIONAL ASSUMPTION: copy of an existing certificate from the EPC Contractor; not stated | Technical
lead_times.reference_evidence | 10 WD | PROVISIONAL ASSUMPTION: commercial-operation evidence for the reference plants, plants in parallel; not stated | Technical
lead_times.fin_statements_collection | 5 WD | PROVISIONAL ASSUMPTION: collect each member's most recent audited financial statements, members in parallel; not stated | Commercial
lead_times.fin_standing_calc | 3 WD | PROVISIONAL ASSUMPTION: combined net worth and turnover weighted by shareholding (VOL-I 8.4); not stated | Commercial
lead_times.om_experience_evidence | 10 WD | PROVISIONAL ASSUMPTION: operating-experience evidence from the O&M Operator; not stated | Technical
lead_times.fin_model_build | 15 WD | PROVISIONAL ASSUMPTION: remaining build of a Financial Model already in development (unlocked, formula-linked, no macros); not stated | Commercial
lead_times.fin_model_freeze | 1 WD | PROVISIONAL ASSUMPTION: freeze inputs and version for audit and Form 4-F; not stated | Commercial
lead_times.lender_terms | 10 WD | PROVISIONAL ASSUMPTION: indicative financing terms (tenor, margin, gearing) from lenders; not stated | Commercial
lead_times.fin_assumptions_schedule | 2 WD | PROVISIONAL ASSUMPTION: schedule of principal financing assumptions from the frozen model (VOL-I 10.6); not stated | Commercial
lead_times.model_auditor_appointment | 5 WD | PROVISIONAL ASSUMPTION: engage an independent model auditor (opinion addressed to the Authority); not stated | Commercial
lead_times.model_audit_review | 10 WD | PROVISIONAL ASSUMPTION: rolling review of the draft model by the auditor; not stated | Commercial
lead_times.model_audit_opinion | 5 WD | PROVISIONAL ASSUMPTION: final review of the frozen model and issue of the opinion; not stated | Commercial
lead_times.form_4f_preparation | 2 WD | PROVISIONAL ASSUMPTION: complete and sign Form 4-F from the frozen model; not stated | Commercial
lead_times.ground_due_diligence | 10 WD | PROVISIONAL ASSUMPTION: review of the data-room geotechnical report and any own investigation needed to price ground risk; not stated | Technical
lead_times.clarification_drafting | 2 WD | PROVISIONAL ASSUMPTION: draft and submit clarification requests through the Portal; not stated | Bid management
lead_times.envelope_assembly | 1 WD | PROVISIONAL ASSUMPTION: assemble the marked original of one envelope in the required order with numbered dividers; not stated | Bid management
lead_times.copies_and_usb | 1 WD | PROVISIONAL ASSUMPTION: three hard copies of each envelope and the encrypted searchable USB copy named per Appendix 2; not stated | Bid management
lead_times.seal_and_mark | 0 WD | PROVISIONAL ASSUMPTION: a few hours at the end of the day the copies are finished (0 = no separate Working Day); not stated | Bid management
lead_times.delivery | 1 WD | PROVISIONAL ASSUMPTION: courier to the Appendix 3 address before 14:00 on the PDD; not stated | Bid management
bidder.name | Unnamed consortium (the Bidder) | configurable assumption (owner's email of 1 Oct; confirmed by the hiring team's reply of 2 Oct) | Bid manager
bidder.members | 3 | PROVISIONAL ASSUMPTION: owner's email of 1 Oct (unnamed consortium, count configurable); VOL-I Appendix 1 lists one two-member consortium | Bid manager
bidder.signatories_per_member | 1 | PROVISIONAL ASSUMPTION: one authorised signatory per member (signs Form 4-C; the lead member's also signs Form 4-A) | Legal
bidder.reference_plants_offered | 2 | PROVISIONAL ASSUMPTION: the minimum of two reference plants in VOL-I 8.5 footnote 12 | Technical
bidder.epc_contractors | 1 | PROVISIONAL ASSUMPTION: one proposed EPC Contractor | Bid manager
bidder.om_operators | 1 | PROVISIONAL ASSUMPTION: one proposed O&M Operator | Bid manager
resources.bid_manager | capacity 2 | PROVISIONAL ASSUMPTION: bid manager plus one coordinator, one activity each at a time; not stated in the pack | Bid manager
resources.document_controller | capacity 2 | PROVISIONAL ASSUMPTION: two document controllers for assembly, copies, sealing and delivery; not stated | Bid manager
resources.legal_counsel | capacity 2 | PROVISIONAL ASSUMPTION: two lawyers on PoAs, forms and guarantees; an activity waiting on a notary or a member counts as one; not stated | Legal
resources.commercial_manager | capacity 2 | PROVISIONAL ASSUMPTION: two commercial staff; an activity waiting on a bank, an authority or an auditor counts as one; not stated | Commercial
resources.financial_modeller | capacity 1 | PROVISIONAL ASSUMPTION: one financial modeller (build, freeze, auditor queries); not stated | Commercial
resources.technical_lead | capacity 2 | PROVISIONAL ASSUMPTION: technical lead plus one engineer for certificates, references and Form 4-G; not stated | Technical
resources.proposal_writers | capacity 1 | PROVISIONAL ASSUMPTION: one writing team for the Technical Proposal narrative; not stated | Technical
submission.marked_originals | 1 | stated in VOL-I 6.5 | Bid manager
submission.hard_copies | 0 | stated in VOL-I 6.5 | Bid manager
submission.electronic_copy | one searchable electronic copy on encrypted USB media, files named per Appendix 2 | stated in VOL-I 6.5 | Bid manager
submission.source | VOL-I:6.5; VOL-I:App2/para1; VOL-I:6.2 | stated in VOL-I 6.5 | Bid manager
submission.usb_per_envelope | 1 | stated in VOL-I 6.5 | Bid manager
planning.status_date | latest_validated_addendum_issue_date | configurable planning choice | Bid manager
planning.counting_policy | conservative | configurable planning choice | Bid manager
planning.delivery_cutoff_time | 14:00 | configurable planning choice | Bid manager
calendar.holidays | none | the pack declares none (VOL-I 2.4 excludes declared public holidays) | Bid manager

## Date coverage
Unit | Phrase | Treatment | By | Sentence
VOL-I:cover/para3 | 14 September 2026 | disposition | informational: tender reference and date of issue (14 September 2026, the start of the VOL-I 4.2 blackout) | 14 September 2026
VOL-I:4.3 | two (2) Working Days | rule | VOL-I-4.3-01 SPOC-CHANGE-NOTICE | Each Bidder shall nominate a single point of contact and shall notify the Authority of any change within two (2) Working Days.
VOL-I:5.2 | fifteen (15) Working Days | rule | VOL-I-5.2-01 CLARIFICATION-CUTOFF | Requests for clarification shall be submitted no later than fifteen (15) Working Days before the Proposal Due Date.
VOL-I:5.4 | 30 September 2026 | rule | VOL-I-5.4-01 PRE-BID | A Pre-Bid Conference will be held on Wednesday 30 September 2026 at 10:00 Riyadh time at the Authority's offices.
VOL-I:6.1 | 00 hours | rule | VOL-I-6.1-01 PDD | Proposals shall be received by the Authority not later than 14:00 hours Riyadh time on Thursday 10 December 2026 at the address given in Appendix 3.
VOL-I:6.1 | 10 December 2026 | anchor | defines PDD | Proposals shall be received by the Authority not later than 14:00 hours Riyadh time on Thursday 10 December 2026 at the address given in Appendix 3.
VOL-I:6.3 | eighty (180) days | rule | VOL-I-6.3-01 BID-BOND-VALIDITY | Envelope A shall be accompanied by a Bid Bond which shall remain valid for one hundred and eighty (180) days from the Proposal Due Date and shall be extended on demand where the Authority extends the period of Proposal v
VOL-I:7.1 | fifty (150) days | rule | VOL-I-7.1-01 PROPOSAL-VALIDITY | Each Proposal shall remain open for acceptance for one hundred and fifty (150) days from the Proposal Due Date.
VOL-I:8.5#fn12 | ten (10) years | rule | VOL-I-8.5-01 REFERENCE-LOOKBACK | For the avoidance of doubt, a Bidder that does not evidence at least two (2) reference sewage treatment plants, each of nominal capacity not less than 60,000 m3/day and each having achieved commercial operation within th
VOL-I:8.8 | five (5) years | duration | VOL-I-8.8-01 quotes it as part of the requirement | The proposed O&M Operator shall evidence not less than five (5) years of continuous operation of at least one (1) wastewater treatment facility of nominal capacity not less than 50,000 m³/day.
VOL-I:8.10 | five (5) years | rule | VOL-I-8.10-01 DEBARMENT-LOOKBACK | No member of the Bidder shall be the subject of, or have been the subject of within the preceding five (5) years, any debarment by a public authority in the Kingdom.
VOL-I:12.1 | twenty-five (25) years | rule | VOL-I-12.1-01 CONCESSION-END-PCOD | The concession period shall be twenty-five (25) years commencing on the Project Commercial Operation Date, following which the Project shall transfer to the Authority in accordance with Volume V.
VOL-I:12.2 | twenty (120) days | rule | VOL-I-12.2-01 PB-COMMERCIAL-CLOSE | The Preferred Bidder shall achieve Commercial Close within one hundred and twenty (120) days, and Financial Close within three hundred (300) days, of the date of the Preferred Bidder Notification.
VOL-I:12.2 | hundred (300) days | duration | VOL-I-12.2-02 quotes it as part of the requirement | The Preferred Bidder shall achieve Commercial Close within one hundred and twenty (120) days, and Financial Close within three hundred (300) days, of the date of the Preferred Bidder Notification.
VOL-I:12.3 | ten (10) Working Days | disposition | authority: standstill of ten Working Days before the Authority executes the Project Agreement; no bidder action | A standstill period of ten (10) Working Days shall apply between the Preferred Bidder Notification and execution of the Project Agreement.
VOL-I:12.4 | twenty (20) Working Days | disposition | informational: an optional right of unsuccessful Bidders to request a debrief; not an obligation | Unsuccessful Bidders may request a debrief within twenty (20) Working Days of notification.
VOL-II:cover/para3 | 14 September 2026 | disposition | informational: tender reference and date of issue (14 September 2026, fixed) | 14 September 2026
VOL-II:2.2 | fifty (50) years | duration | VOL-II-2.2-01 quotes it as part of the requirement | The design life of all civil structures shall be not less than fifty (50) years.
VOL-II:2.2 | twenty (20) years | duration | VOL-II-2.2-02 quotes it as part of the requirement | The design life of mechanical and electrical equipment shall be not less than twenty (20) years or the manufacturer's rated life, whichever is the shorter, with lifecycle replacement provided for in the Project Company's
VOL-II:3.2 | seven (7) years | duration | VOL-II-3.2-02 quotes it as part of the requirement | Where a membrane process is proposed, the Project Company shall demonstrate membrane replacement provisions in the lifecycle plan and shall warrant a membrane life of not less than seven (7) years.
VOL-II:4.4 | ninety-six (96) hours | duration | VOL-II-4.4-01 quotes it as part of the requirement | Standby power shall be sized to carry the full inlet works, the disinfection stage and the effluent pumping station for not less than ninety-six (96) hours.
VOL-II:5.5 | 475 years | duration | VOL-II-5.5-01 quotes it as part of the requirement | All permanent civil structures shall be designed for a seismic event with a return period of 475 years and for a flood with a return period of 100 years.
VOL-II:5.5 | 100 years | duration | VOL-II-5.5-02 quotes it as part of the requirement | All permanent civil structures shall be designed for a seismic event with a return period of 475 years and for a flood with a return period of 100 years.
VOL-II:6.4 | seven (7) years | duration | VOL-II-6.4-01 quotes it as part of the requirement | All process data shall be retained for not less than seven (7) years and shall be made available to the Authority on demand in a non-proprietary format.
VOL-II:7.2 | thirty (30) days | duration | VOL-II-7.2-01 quotes it as part of the requirement | PCOD shall not be certified until the Facility has completed a continuous reliability run of thirty (30) days at not less than 90% of nominal capacity, during which every parameter in Table 2-4 has been met.
VOL-II:7.4 | sixty (60) days | rule | VOL-II-7.4-01 VOL-II-AS-BUILT-DUE | The Project Company shall provide as-built documentation, operation and maintenance manuals, and an asset register in the Authority's standard format not later than sixty (60) days after PCOD.
VOL-II:8.1 | two (2) years | duration | VOL-II-8.1-01 quotes it as part of the requirement | The Project Company shall hold a spare parts inventory sufficient for two (2) years of normal operation for all items with a lead time exceeding twelve (12) weeks.
VOL-II:8.1 | twelve (12) weeks | duration | VOL-II-8.1-01 quotes it as part of the requirement | The Project Company shall hold a spare parts inventory sufficient for two (2) years of normal operation for all items with a lead time exceeding twelve (12) weeks.
VOL-II:8.5 | two (2) years | rule | VOL-II-8.5-01 VOL-II-HANDBACK-SURVEY-WINDOW | A handback condition survey shall be carried out in the final two (2) years of the concession, and any remedial works identified shall be completed before transfer.
VOL-IV:cover/para3 | 14 September 2026 | disposition | informational: tender reference and issue date (14 September 2026, a fixed date); no bidder obligation | 14 September 2026
VOL-V:cover/para3 | 14 September 2026 | disposition | informational: tender reference and date of issue (14 September 2026, fixed) | 14 September 2026
VOL-V:3.1 | twenty-five (25) years | rule | VOL-V-3.1-01 VOL-V-TERM-END | This Agreement shall come into force on the Effective Date and shall continue for a period of twenty-five (25) years from the Effective Date, unless terminated earlier in accordance with its terms.
VOL-V:12.1 | thirty-six (36) months | rule | VOL-V-12.1-01 VOL-V-SCHEDULED-PCOD | The Project Company shall achieve PCOD within thirty-six (36) months of the Notice to Proceed (the Scheduled PCOD).
VOL-V:18.3 | sixty-five (365) days | rule | VOL-V-18.3-01 VOL-V-PCOD-LONG-STOP | If PCOD has not been achieved within three hundred and sixty-five (365) days after the Scheduled PCOD, the Authority may terminate under Clause 39.2.
VOL-V:29.3 | twelve (12) months | rule | VOL-V-29.3-01 VOL-V-RAMP-UP-END | During the first twelve (12) months after PCOD (the Ramp-Up Period) the Availability Payment shall be paid at ninety per cent (90%) of the full rate, and no availability deduction shall apply to a parameter listed in Tab
VOL-V:29.4 | ten (10) Working Days | rule | VOL-V-29.4-01 VOL-V-INVOICE-DUE | Invoices shall be submitted within ten (10) Working Days of each month end and shall be paid within thirty (30) days of receipt.
VOL-V:29.4 | thirty (30) days | rule | VOL-V-29.4-01 VOL-V-INVOICE-DUE | Invoices shall be submitted within ten (10) Working Days of each month end and shall be paid within thirty (30) days of receipt.
VOL-V:31.3 | twenty-four (24) hours | duration | VOL-V-31.3-02 quotes it as part of the requirement | A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a) and of seventy-two (72) hours to an event under Clause 31.1(c).
VOL-V:31.3 | seventy-two (72) hours | duration | VOL-V-31.3-01 quotes it as part of the requirement | A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a) and of seventy-two (72) hours to an event under Clause 31.1(c).
VOL-V:31.4 | ninety (90) day | duration | VOL-V-31.4-01 quotes it as part of the requirement | Persistent breach, being three (3) or more Unavailability Events in any rolling ninety (90) day period, entitles the Authority to require a remediation plan and, on a second occurrence, to terminate under Clause 39.3.
VOL-V:34.3 | five (5) Working Days | rule | VOL-V-34.3-01 VOL-V-RELIEF-EVENT-NOTICE | The Project Company shall notify a Relief Event within five (5) Working Days of becoming aware of it, failing which no relief shall be granted.
VOL-V:39.4 | sixty (60) days | disposition | informational: the Project Company's right to terminate for an Authority Event of Default (unpaid undisputed sum over SAR 20,000,000 for 60 days after notice); | The Project Company may terminate for an Authority Event of Default, being a failure to pay an undisputed sum exceeding SAR 20,000,000 that continues for sixty (60) days after notice.
VOL-V:42.1 | five (5) years | duration | VOL-V-42.1-02 quotes it as part of the requirement | The Project Company shall transfer the Facility to the Authority on expiry in the condition required by Volume II Clause 8.5, free of encumbrance and with a remaining design life of not less than five (5) years for all m
ADD-01:3.1 | five (5) Working Days | rule | ADD-01-3.1-01 ATTENDANCE-NOTICE | A Bidder that considers its attendance to have been incorrectly recorded shall notify the Authority through the Portal within five (5) Working Days of this Addendum.
ADD-01:AppA/proposal-due-date | 10 December 2026 | anchor | a form field printing the PDD as in force | 10 December 2026, 14:00 Riyadh time
ADD-02:F4-G/T1/4 | twenty-four (24) hours | post_award | ADD-02-F4G-01: undertaking 4: notify security incidents within 24 hours of detection, after award; an event-driven period, not a bid-stage date | Security incidents affecting the Facility will be notified to the Authority within twenty-four (24) hours of detection.
ADD-03:12.1 | five (5) years | rule | VOL-IV-F4C-06 F4C-SIXTH-LOOKBACK | that neither the member nor any of its directors has, within the preceding five (5) years, been convicted in the Kingdom of an offence involving fraud, bribery or corruption.’
VOL-IV:F4-C/image/decl5+ADD-03 | five (5) years | rule | VOL-IV-F4C-06 F4C-SIXTH-LOOKBACK | that neither the member nor any of its directors has, within the preceding five (5) years, been convicted in the Kingdom of an offence involving fraud, bribery or corruption.