## A1 register
CANDIDATE — INTERVIEW DEMO — A1 Obligations and compliance register — WORKING DRAFT
CANDIDATE: proposed by the AI workflow; not reviewed; nothing accepted. INTERVIEW DEMO: approvals assumed for demonstration; not an actual human review or tender release. WORKING DRAFT, full register: 210 rows (review status: accepted 205, changed 5; amendment ops: accepted 51). Rows and ops count as accepted only with a named person's decision bound to their current content. Image readings pending the owner's review: none; approved by the owner: VOL-II-p3-r1 (transcription), VOL-IV-p6-r1 (transcription and displayed translations); their interpretations stay proposed. Validated state: ADD-02; working state ADD-03 is PARTIAL. Pass/fail or scored: contractual_post_award = an obligation under the Project Agreement after award; not assessed at bid stage; informational = context only; nothing to do; pass_fail = a gate checked as met or not met at bid stage (a stated rejection, disqualification, non-responsiveness or exclusion, or a document the VOL-I 11.1 checks require); procedural = a step of the tender process with no stated effect on whether the Proposal stays in; scored = marked under the evaluation criteria (Table 1-1 or the financial evaluation); a shortfall loses marks. 'Change at <stage>' says what that addendum did to the row besides its status (the reading re-made, with its note; dates moved; the ops and annotations, with provision and page); a row whose unit an op reissued or amended elsewhere with the row's own words unchanged reads 'ACTIVE (reissued by <op>, unchanged)'. In 'Text as issued', a segment marked '[<document> <clause> p<n>; issued by ADD-0x]' is that addendum's own text, not text of the volumes as issued. The three state columns: 'Value at the validated stage' says what the row's own quoted words, cells and consequence did across the stages (unchanged, changed, amended with the quoted words unchanged, new, not in force; a deletion and a later reinstatement are both named; at a PARTIAL working state, a row an unresolved provision of ADD-03 names reads 'value in question (unresolved: <provision and reason>)', never 'unchanged'), with each op that re-reads the row named with its kind and review ('proposed, not accepted'), never counted as a confirmation; 'Interpretation' lists the open issues on the reading (HUMAN DECISION PENDING where a person decides; an applied rule awaiting a person's confirmation; other open issues); 'Approval' says what a person has recorded for the row, its image transcription and every op on its units (an image transcription approval covers the transcription and its displayed translation only, never the interpretation). Evidence codes are defined in the Evidence sheet. Relationship status: confirmed = stated in the documents (the entry quotes the cross-reference), not confirmed by a person; proposed = inferred by a curator or a model, a person decides; possible = a weaker inference.
Requirement ID | Candidate status (this AI workflow run: proposed / unresolved / decided) | Clause group | Scope tags | Requirement (summary) | Text as issued (original document; never assembled) | Effective text at the validated state (ASSEMBLED by applying the addenda; not a printed text) | Quoted words relied on | Latest reference for the quoted words (document clause page; amending provision) | Every unit the row cites (reference at the validated state; amending ops) | Pass/fail or scored | Discipline | Owner (role) | Evidence needed | Status after BASE | Status after ADD-01 | Status after ADD-02 | Status after ADD-03 (WORKING, not validated) | Change at ADD-01 (reading re-made with its note, dates moved, the ops; not a status) | Change at ADD-02 (reading re-made with its note, dates moved, the ops; not a status) | Change at ADD-03 (reading re-made with its note, dates moved, the ops; not a status) | Source after BASE (latest reference for the quoted words) | Source after ADD-01 (latest reference for the quoted words) | Source after ADD-02 (latest reference for the quoted words) | Source after ADD-03 (latest reference for the quoted words) | Stated consequence (quoted) | Consequence source | Dates (planning reading; all readings in Dates sheet) | Confidence | Interpretation note (the reading at the validated state) | Value at the validated stage (the value only: unchanged/changed/new; not a confirmation) | Interpretation (open judgments on the reading; HUMAN DECISION PENDING where a person decides) | Approval (what a person has recorded; an image transcription approval is not an approval of the interpretation) | Image reading status | Interpretation review | Amendment ops review | Evidence chain (original -> ops) | Issues | Relationships (curated links, their status; reached at the validated stage; documents not supplied)
VOL-I-6.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-15) | VOL-I:6.1 | bid_submission; deadline | Deliver the Proposal to the Authority by the Proposal Due Date and time, at the Appendix 3 address | Proposals shall be received by the Authority not later than 14:00 hours Riyadh time on Thursday 12 November 2026 at the address given in Appendix 3. | Proposals shall be received by the Authority not later than 14:00 hours Riyadh time on Thursday 26 November 2026 at the address given in Appendix 3. | Thursday 26 November 2026 | ADD-01 2.1 p1 (amending VOL-I 6.1) | VOL-I 6.1 p3 <- ADD-01/2.1 | pass_fail | Bid management | Bid manager | EV-DELIVERY | ACTIVE | AMENDED (ADD-01/2.1) | ACTIVE (as amended by ADD-01/2.1) | AMENDED (ADD-03/2.1) | status ACTIVE -> AMENDED (ADD-01/2.1). reading re-made at ADD-01: ADD-01 §2.1 amends the date; the time is unchanged. dates moved: PDD 2026-11-12 -> 2026-11-26. by ADD-01/2.1 [ADD-01; proposed] <- ADD-01:2.1 (ADD-01 p1) | status AMENDED (ADD-01/2.1) -> ACTIVE (as amended by ADD-01/2.1) | status ACTIVE (as amended by ADD-01/2.1) -> AMENDED (ADD-03/2.1). reading re-made at ADD-03: ADD-03 2.1 (op ADD-03/2.1) amends the date to 'Thursday 10 December 2026'. The time it restates ('14:00 Riyadh time') matches the unchanged '14:00 hours Riyadh time' in the target. The consequence in VOL-I 6.6 refers to 'the time stated in Clause 6.1', so it follows the amended date. Date rule PDD is carried unchanged. Dependent rows re-read in this set: VOL-I-3.4-01, VOL-I-5.2-01, VOL-I-6.3-01. Other rules anchored on the PDD move under ADD-03 2.2, for example the VOL-I 7.1 Proposal validity, whose length ADD-03 5.2 states is unchanged. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed]. dates moved: PDD 2026-11-26 -> 2026-12-10. by ADD-03/2.1 [ADD-03; proposed] <- ADD-03:2.1 (ADD-03 p1) | VOL-I 6.1 p3 | ADD-01 2.1 p1 (amending VOL-I 6.1) | ADD-01 2.1 p1 (amending VOL-I 6.1) | VOL-I 6.1 p3 as amended by ADD-03 2.1 p1 | rejection: "will be rejected unopened and returned to the Bidder" | VOL-I 6.6 p3 | PDD: 2026-11-26 (as_stated) | high: verbatim text-layer clause; the consequence is stated in VOL-I 6.6 | ADD-01 §2.1 amends the date; the time is unchanged. | changed at ADD-01 by ADD-01/2.1 (the quoted value); value as read: 'Thursday 26 November 2026' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/2.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-01/2.1: accepted | VOL-I:6.1 (VOL-I p3; text layer); ADD-01/2.1 [ADD-01; proposed] <- ADD-01:2.1 (ADD-01 p1); ADD-03/2.1 [ADD-03; proposed] <- ADD-03:2.1 (ADD-03 p1)
VOL-I-5.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-15) | VOL-I:5.2 | clarification; deadline | Submit any clarification requests no later than ten Working Days before the Proposal Due Date | Requests for clarification shall be submitted no later than ten (10) Working Days before the Proposal Due Date. Requests received after that time will not be answered. | Requests for clarification shall be submitted no later than ten (10) Working Days before the Proposal Due Date. Requests received after that time will not be answered. | no later than ten (10) Working Days before the Proposal Due Date | VOL-I 5.2 p3 | VOL-I 5.2 p3 | procedural | Bid management | Bid manager | EV-CLARIFICATIONS | ACTIVE | ACTIVE | ACTIVE | ACTIVE | reading re-made at ADD-01: ADD-01 §2.2 names this period as moving with the Proposal Due Date. dates moved: CLARIFICATION-CUTOFF 2026-10-29 -> 2026-11-12. by ADD-01/2.2 [ADD-01; proposed; annotates VOL-I:5.2 (interprets)] <- ADD-01:2.2 (ADD-01 p1); ADD-01/2.1 [ADD-01; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-01:2.1 (ADD-01 p1) |  | reading re-made at ADD-03: Re-made at ADD-03 because op ADD-03/2.1 changed the anchor (PDD, VOL-I 6.1). The words of VOL-I 5.2 are unchanged. ADD-03 2.2 prints 'Every period calculated by reference to the Proposal Due Date is adjusted accordingly.', so the period moves with the amended PDD ('Thursday 10 December 2026'). Date rule CLARIFICATION-CUTOFF is carried unchanged (relative, 10 Working Days before PDD). calculate (VOL-I 2.4) gives a single reading, Thursday 26 November 2026; that date is not typed into the rule. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed]. dates moved: CLARIFICATION-CUTOFF 2026-11-12 -> 2026-11-26. by ADD-03/2.1 [ADD-03; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-03:2.1 (ADD-03 p1) | VOL-I 5.2 p3 | VOL-I 5.2 p3 | VOL-I 5.2 p3 | VOL-I 5.2 p3 | lesser consequence: "Requests received after that time will not be answered." | VOL-I 5.2 p3 | CLARIFICATION-CUTOFF: 2026-11-12 (stated_date_excluded) | high: backward Working Day counting is defined in VOL-I 2.4 | ADD-01 §2.2 names this period as moving with the Proposal Due Date. | value in question (unresolved: ADD-03:2.2 UNRESOLVED POSSIBLE TARGET: ambiguous: 'Every period calculated by reference to the Proposal Due Date is adjusted accordingly.' names no clause, unlike ADD-01:2.2 which listed Volume I Cl…); re-read by ADD-01/2.2 (interprets; accepted by a person; not counted as a confirmation); value as read at ADD-02, in question at ADD-03: 'no later than ten (10) Working Days before the Proposal Due Date' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/2.2: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:5.2 (VOL-I p3; text layer); ADD-01/2.2 [ADD-01; proposed; annotates VOL-I:5.2 (interprets)] <- ADD-01:2.2 (ADD-01 p1); ADD-01/2.1 [ADD-01; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-01:2.1 (ADD-01 p1); ADD-03/2.1 [ADD-03; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-03:2.1 (ADD-03 p1)
VOL-I-6.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-15) | VOL-I:6.3 | envelope_A; bid_security; validity | Bid Bond valid for 210 days from the Proposal Due Date (extendable on demand) | Envelope A shall be accompanied by a Bid Bond which shall remain valid for one hundred and eighty (180) days from the Proposal Due Date and shall be extended on demand where the Authority extends the period of Proposal validity. | Envelope A shall be accompanied by a Bid Bond which shall remain valid for one hundred and eighty (180) days from the Proposal Due Date and shall be extended on demand where the Authority extends the period of Proposal validity. | valid for one hundred and eighty (180) days from the Proposal Due Date | VOL-I 6.3 p3 | VOL-I 6.3 p3 | pass_fail | Commercial | Commercial lead | EV-BID-BOND | ACTIVE | ACTIVE | ACTIVE | AMENDED (ADD-03/5.2(a)) | reading re-made at ADD-01: ADD-01 §2.2 names this period as moving with the Proposal Due Date. dates moved: BID-BOND-VALIDITY 2027-05-11 -> 2027-05-25. by ADD-01/2.2 [ADD-01; proposed; annotates VOL-I:6.3 (interprets)] <- ADD-01:2.2 (ADD-01 p1); ADD-01/2.1 [ADD-01; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-01:2.1 (ADD-01 p1) |  | status ACTIVE -> AMENDED (ADD-03/5.2(a)). reading re-made at ADD-03: ADD-03 5.2 (op ADD-03/5.2(a)) substitutes 'two hundred and ten (210) days' for 'one hundred and eighty (180) days'. The anchor (PDD) also moved under ADD-03 2.1 and 2.2. The duty to extend on demand where the Authority extends Proposal validity is unchanged. ADD-03 5.2 states that the VOL-I 7.1 Proposal validity is unchanged. The calculate tool gives two end-date readings that differ (day 0 or day 1); that point stays open as before and neither reading is chosen. The row's date rule BID-BOND-VALIDITY still has offset 180 and the old text (see the escalation in this set). VOL-I 6.3 states no consequence (I-NO-CONSEQUENCE, kept as recorded; its interview_demo acceptance is not a resolution). The Bid Bond amount moved separately under ADD-03 5.1 (VOL-I 6.4). Evidence item EV-BID-BOND is still named 'SAR 4,500,000', which is outside this task. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed]. dates moved: BID-BOND-VALIDITY 2027-05-25 -> 2027-07-08. by ADD-03/5.2(a) [ADD-03; proposed] <- ADD-03:5.2 (ADD-03 p1); ADD-03/2.1 [ADD-03; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-03:2.1 (ADD-03 p1) | VOL-I 6.3 p3 | VOL-I 6.3 p3 | VOL-I 6.3 p3 | VOL-I 6.3 p3 as amended by ADD-03 5.2 p1 | none stated in the documents |  | BID-BOND-VALIDITY: 2027-05-25 (day0) | medium: no consequence is stated; whether day 0 or day 1 is the PDD is not stated (two readings) | ADD-01 §2.2 names this period as moving with the Proposal Due Date. | value in question (unresolved: ADD-03:2.2 UNRESOLVED POSSIBLE TARGET: ambiguous: 'Every period calculated by reference to the Proposal Due Date is adjusted accordingly.' names no clause, unlike ADD-01:2.2 which listed Volume I Cl…); re-read by ADD-01/2.2 (interprets; accepted by a person; not counted as a confirmation); value as read at ADD-02, in question at ADD-03: 'valid for one hundred and eighty (180) days from the Proposal Due Date' | decided (recorded): I-NO-CONSEQUENCE | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/2.2: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:6.3 (VOL-I p3; text layer); ADD-01/2.2 [ADD-01; proposed; annotates VOL-I:6.3 (interprets)] <- ADD-01:2.2 (ADD-01 p1); ADD-01/2.1 [ADD-01; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-01:2.1 (ADD-01 p1); ADD-03/5.2(a) [ADD-03; proposed] <- ADD-03:5.2 (ADD-03 p1); ADD-03/2.1 [ADD-03; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-03:2.1 (ADD-03 p1) | I-NO-CONSEQUENCE
VOL-I-6.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-15) | VOL-I:6.4 | envelope_A; bid_security | Bid Bond of SAR 5,600,000, unconditional and payable on first written demand | The Bid Bond shall be in the amount of SAR 4,500,000 (four million five hundred thousand Saudi Riyals), shall be unconditional and payable on first written demand, and shall be issued by a bank licensed to operate in the Kingdom holding a long-term credit rating of not lower than A- from a recognised international rating agency. | The Bid Bond shall be in the amount of SAR 4,500,000 (four million five hundred thousand Saudi Riyals), shall be unconditional and payable on first written demand, and shall be issued by a bank licensed to operate in the Kingdom holding a long-term credit rating of not lower than A- from a recognised international rating agency. | in the amount of SAR 4,500,000 | VOL-I 6.4 p3 | VOL-I 6.4 p3 | pass_fail | Commercial | Commercial lead | EV-BID-BOND | ACTIVE | ACTIVE | ACTIVE | AMENDED (ADD-03/5.1) | reading re-made at ADD-01: ADD-01 Q3 answers about the issuer, not the amount; reviewed for this row, no change. by ADD-01/Q3 [ADD-01; proposed; annotates VOL-I:6.4 (interprets)] <- ADD-01:Q3 (ADD-01 p2) | reading re-made at ADD-02: ADD-02 Q8 confirms the amount is fixed, not a percentage of the bid price. by ADD-02/Q8 [ADD-02; proposed; annotates VOL-I:6.4 (confirms)] <- ADD-02:Q8 (ADD-02 p2) | status ACTIVE -> AMENDED (ADD-03/5.1). reading re-made at ADD-03: ADD-03 5.1 deletes 'SAR 4,500,000 (four million five hundred thousand Saudi Riyals)' in VOL-I 6.4 and substitutes 'SAR 5,600,000 (five million six hundred thousand Saudi Riyals)' (op ADD-03/5.1, proposed). The figure is read from the printed words, not computed. ADD-02 Q8 says 'The amount is fixed and stated in Volume I Clause 6.4'; 6.4 now prints the new amount. The form words ('unconditional and payable on first written demand') are unchanged. VOL-I 6.4 still states no consequence of its own (I-NO-CONSEQUENCE). The evidence item EV-BID-BOND still names the old amount: see issue I-ADD03-BOND-AMOUNT-FOLLOW-ON. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed]. by ADD-03/5.1 [ADD-03; proposed] <- ADD-03:5.1 (ADD-03 p1) | VOL-I 6.4 p3 | VOL-I 6.4 p3 | VOL-I 6.4 p3 | VOL-I 6.4 p3 as amended by ADD-03 5.1 p1 | none stated in the documents |  |  | high: verbatim; confirmed by ADD-02 Q8 (no consequence stated) | ADD-02 Q8 confirms the amount is fixed, not a percentage of the bid price. | unchanged since BASE; re-read by ADD-01/Q3 (interprets; accepted by a person; not counted as a confirmation), ADD-02/Q8 (confirms; accepted by a person; not counted as a confirmation); value as read: 'in the amount of SAR 4,500,000' | decided (recorded): I-NO-CONSEQUENCE | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/Q3: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/Q8: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:6.4 (VOL-I p3; text layer); ADD-01/Q3 [ADD-01; proposed; annotates VOL-I:6.4 (interprets)] <- ADD-01:Q3 (ADD-01 p2); ADD-02/Q8 [ADD-02; proposed; annotates VOL-I:6.4 (confirms)] <- ADD-02:Q8 (ADD-02 p2); ADD-03/5.1 [ADD-03; proposed] <- ADD-03:5.1 (ADD-03 p1) | I-NO-CONSEQUENCE
VOL-I-6.4-02 | DECIDED: accepted by Interview demo assumption (2026-10-15) | VOL-I:6.4 | envelope_A; bid_security | Bid Bond issued by a bank licensed in the Kingdom with a long-term rating not lower than A- | The Bid Bond shall be in the amount of SAR 4,500,000 (four million five hundred thousand Saudi Riyals), shall be unconditional and payable on first written demand, and shall be issued by a bank licensed to operate in the Kingdom holding a long-term credit rating of not lower than A- from a recognised international rating agency. | The Bid Bond shall be in the amount of SAR 4,500,000 (four million five hundred thousand Saudi Riyals), shall be unconditional and payable on first written demand, and shall be issued by a bank licensed to operate in the Kingdom holding a long-term credit rating of not lower than A- from a recognised international rating agency. | issued by a bank licensed to operate in the Kingdom holding a long-term credit rating of not lower than A- | VOL-I 6.4 p3 | VOL-I 6.4 p3 | pass_fail | Commercial | Commercial lead | EV-BID-BOND | ACTIVE | ACTIVE | ACTIVE | AMENDED (ADD-03/5.1) | reading re-made at ADD-01: ADD-01 Q3: a foreign bank's branch only where licensed in the Kingdom and the issuer meets the rating. by ADD-01/Q3 [ADD-01; proposed; annotates VOL-I:6.4 (interprets)] <- ADD-01:Q3 (ADD-01 p2) | reading re-made at ADD-02: ADD-02 Q8 concerns the amount; reviewed for this row, no change. by ADD-02/Q8 [ADD-02; proposed; annotates VOL-I:6.4 (confirms)] <- ADD-02:Q8 (ADD-02 p2) | status ACTIVE -> AMENDED (ADD-03/5.1). reading re-made at ADD-03: ADD-03 5.1 replaces only the amount words of VOL-I 6.4 ('SAR 4,500,000 (four million five hundred thousand Saudi Riyals)'). After the op, the issuer and rating words are printed unchanged. ADD-01 Q3 still stands: a foreign bank's branch may issue only where it is licensed in the Kingdom and the issuer meets the rating. The row is re-read at ADD-03 because the unit changed; the requirement is the same. VOL-I 6.4 states no consequence of its own (I-NO-CONSEQUENCE). [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed]. by ADD-03/5.1 [ADD-03; proposed] <- ADD-03:5.1 (ADD-03 p1) | VOL-I 6.4 p3 | VOL-I 6.4 p3 | VOL-I 6.4 p3 | VOL-I 6.4 p3 as amended by ADD-03 5.1 p1 | none stated in the documents |  |  | high: verbatim; clarified by ADD-01 Q3 (no consequence stated) | ADD-02 Q8 concerns the amount; reviewed for this row, no change. | unchanged since BASE; re-read by ADD-01/Q3 (interprets; accepted by a person; not counted as a confirmation), ADD-02/Q8 (confirms; accepted by a person; not counted as a confirmation); value as read: 'issued by a bank licensed to operate in the Kingdom holding a long-term credit rating of not lower than A-' | decided (recorded): I-NO-CONSEQUENCE | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/Q3: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/Q8: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:6.4 (VOL-I p3; text layer); ADD-01/Q3 [ADD-01; proposed; annotates VOL-I:6.4 (interprets)] <- ADD-01:Q3 (ADD-01 p2); ADD-02/Q8 [ADD-02; proposed; annotates VOL-I:6.4 (confirms)] <- ADD-02:Q8 (ADD-02 p2); ADD-03/5.1 [ADD-03; proposed] <- ADD-03:5.1 (ADD-03 p1) | I-NO-CONSEQUENCE
VOL-I-7.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-15) | VOL-I:7.1 | validity | Proposal open for acceptance for 150 days from the Proposal Due Date | Each Proposal shall remain open for acceptance for one hundred and fifty (150) days from the Proposal Due Date. | Each Proposal shall remain open for acceptance for one hundred and fifty (150) days from the Proposal Due Date. | one hundred and fifty (150) days from the Proposal Due Date | VOL-I 7.1 p4 | VOL-I 7.1 p4 | pass_fail | Commercial | Commercial lead | EV-FORM-4A | ACTIVE | ACTIVE | ACTIVE | ACTIVE | reading re-made at ADD-01: ADD-01 §2.2 names this period as moving with the Proposal Due Date. dates moved: PROPOSAL-VALIDITY 2027-04-11 -> 2027-04-25. by ADD-01/2.2 [ADD-01; proposed; annotates VOL-I:7.1 (interprets)] <- ADD-01:2.2 (ADD-01 p1); ADD-01/2.1 [ADD-01; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-01:2.1 (ADD-01 p1); EV-FORM-4A: evidence field not on the reissued form (VOL-IV-F4A-04) (I-F4A-FIELDS) |  | reading re-made at ADD-03: ADD-03 5.2 states 'The Proposal validity period in Clause 7.1 is unchanged.' (op ADD-03/5.2(b), confirms; proposed). The 150-day period is unchanged. It counts from the Proposal Due Date, which ADD-03/2.1 moves to 'Thursday 10 December 2026', so the end of validity moves with it through the unchanged date rule PROPOSAL-VALIDITY. The program computes that date; the pack still does not say whether counting starts at day 0 or day 1. The same provision changes the Bid Bond validity in VOL-I 6.3 to two hundred and ten (210) days from the Proposal Due Date. That belongs to a separate row and does not change this period. VOL-I 7.1 states no consequence of its own (I-NO-CONSEQUENCE). [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed]. dates moved: PROPOSAL-VALIDITY 2027-04-25 -> 2027-05-09. by ADD-03/5.2(b) [ADD-03; proposed; annotates VOL-I:7.1 (confirms)] <- ADD-03:5.2 (ADD-03 p1); ADD-03/2.1 [ADD-03; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-03:2.1 (ADD-03 p1) | VOL-I 7.1 p4 | VOL-I 7.1 p4 | VOL-I 7.1 p4 | VOL-I 7.1 p4 | none stated in the documents |  | PROPOSAL-VALIDITY: 2027-04-25 (day0) | medium: no consequence stated; day 0 / day 1 not stated | ADD-01 §2.2 names this period as moving with the Proposal Due Date. | value in question (unresolved: ADD-03:2.2 UNRESOLVED POSSIBLE TARGET: ambiguous: 'Every period calculated by reference to the Proposal Due Date is adjusted accordingly.' names no clause, unlike ADD-01:2.2 which listed Volume I Cl…); re-read by ADD-01/2.2 (interprets; accepted by a person; not counted as a confirmation); value as read at ADD-02, in question at ADD-03: 'one hundred and fifty (150) days from the Proposal Due Date' | decided (recorded): I-NO-CONSEQUENCE, I-F4A-FIELDS | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/2.2: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:7.1 (VOL-I p4; text layer); ADD-01/2.2 [ADD-01; proposed; annotates VOL-I:7.1 (interprets)] <- ADD-01:2.2 (ADD-01 p1); ADD-01/2.1 [ADD-01; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-01:2.1 (ADD-01 p1); ADD-03/5.2(b) [ADD-03; proposed; annotates VOL-I:7.1 (confirms)] <- ADD-03:5.2 (ADD-03 p1); ADD-03/2.1 [ADD-03; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-03:2.1 (ADD-03 p1) | I-NO-CONSEQUENCE; I-F4A-FIELDS (evidence field not on the reissued form (VOL-IV-F4A-04))
VOL-I-8.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-15) | VOL-I:8.3 | qualification; envelope_A | EPC Contractor ISO 9001:2015 certificate from an accredited certification body, current as at the Proposal Due Date (as amended), copy with Envelope A; checked pass/fail under VOL-I 11.1(i) | The proposed EPC Contractor shall hold a valid ISO 9001:2015 quality management certificate, current as at the Proposal Due Date, issued by an accredited certification body. A copy of the certificate shall be submitted with Envelope A. | The proposed EPC Contractor shall hold a valid ISO 9001:2015 quality management certificate, current as at the Proposal Due Date, issued by an accredited certification body. A copy of the certificate shall be submitted with Envelope A. | current as at the Proposal Due Date | VOL-I 8.3 p4 | VOL-I 8.3 p4 | pass_fail | Technical | Technical lead | EV-ISO | ACTIVE | ACTIVE | ACTIVE | ACTIVE | reading re-made at ADD-01: As directed by the owner on 3 Oct 2026 (worklog/2026-10-03_session-08_prompt.md §3): the EPC Contractor's ISO 9001:2015 certificate must be valid (current) at the latest amended Proposal Due Date, 26 November 2026, 14:00 Riyadh time (VOL-I 2.6 defines the Proposal Due Date as the date and time in 6.1 as amended; ADD-01 2.1 moved the date and kept the time; ADD-02 does not change it). It must also be issued by an accredited certification body, and a copy must be submitted with Envelope A (VOL-I 8.3). VOL-I 8.3 states no consequence of its own; the requirement is checked at the responsiveness and mandatory compliance stage on a pass or fail basis, and only Proposals that pass that stage go on to technical evaluation (VOL-I 11.1(i)-(ii)). The pack gives no ISO-specific rejection label and says nothing on whether a failure can be cured; neither is implied. [Applied from proposal P-S08-VOL-I-8.3-01 by Claude Code (assistant), on Ahmad's written instruction of 3 Oct 2026 (session 08 §3) on 2026-10-03.]. dates moved: ISO-CURRENT-AT 2026-11-12 -> 2026-11-26. by ADD-01/2.1 [ADD-01; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-01:2.1 (ADD-01 p1) |  | reading re-made at ADD-03: VOL-I 8.3 is printed unchanged at ADD-03. The certificate must be current at the Proposal Due Date, which ADD-03 2.1 (op ADD-03/2.1, proposed) moves to 'Thursday 10 December 2026'. The owner's session-08 direction on this row is carried with the same substance: the certificate must be current at the latest amended Proposal Due Date and issued by an accredited certification body, a copy goes with Envelope A, and it is checked under 11.1(i). No ISO-specific rejection label is implied, and nothing is implied about whether a failure can be cured. That direction named the earlier date, 26 November 2026; a person decides whether it carries over (issue I-ADD03-PDD-OWNER-DIRECTIONS). Whether the bidder's certificate is current at the amended date is a bidder fact the pack does not hold. The date rule ISO-CURRENT-AT is unchanged. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed]. dates moved: ISO-CURRENT-AT 2026-11-26 -> 2026-12-10. by ADD-03/2.1 [ADD-03; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-03:2.1 (ADD-03 p1) | VOL-I 8.3 p4 | VOL-I 8.3 p4 | VOL-I 8.3 p4 | VOL-I 8.3 p4 | none stated in the documents |  | ISO-CURRENT-AT: 2026-11-26 (as_stated) | medium: no consequence stated; this period is not named in ADD-01 §2.2 (whose list is non-exhaustive) | As directed by the owner on 3 Oct 2026 (worklog/2026-10-03_session-08_prompt.md §3): the EPC Contractor's ISO 9001:2015 certificate must be valid (current) at the latest amended Proposal Due Date, 26 November 2026, 14:00 Riyadh time (VOL-I 2.6 defines the Proposal Due Date as the date and time in 6.1 as amended; ADD-01 2.1 moved the date and kept the time; ADD-02 does not change it). It must also be issued by an accredited certification body, and a copy must be submitted with Envelope A (VOL-I 8.3). VOL-I 8.3 states no consequence of its own; the requirement is checked at the responsiveness and mandatory compliance stage on a pass or fail basis, and only Proposals that pass that stage go on to technical evaluation (VOL-I 11.1(i)-(ii)). The pack gives no ISO-specific rejection label and says nothing on whether a failure can be cured; neither is implied. [Applied from proposal P-S08-VOL-I-8.3-01 by Claude Code (assistant), on Ahmad's written instruction of 3 Oct 2026 (session 08 §3) on 2026-10-03.] | own words unchanged at ADD-01, but what it depends on changed (parameters; see A2); value as read: 'current as at the Proposal Due Date' | decided (recorded): I-NO-CONSEQUENCE | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:8.3 (VOL-I p4; text layer); ADD-01/2.1 [ADD-01; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-01:2.1 (ADD-01 p1); ADD-03/2.1 [ADD-03; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-03:2.1 (ADD-03 p1) | I-NO-CONSEQUENCE
VOL-I-8.5-01 | DECIDED: accepted by Interview demo assumption (2026-10-15) | VOL-I:8.5 | qualification; references | Evidence at least two (2) reference sewage treatment plants of at least 100,000 m3/day, each having achieved commercial operation within the ten (10) years preceding the Proposal Due Date | [VOL-I 8.5#fn12 p4] For the avoidance of doubt, a Bidder that does not evidence at least two (2) reference sewage treatment plants, each of nominal capacity not less than 80,000 m³/day and each having achieved commercial operation within the ten (10) years preceding the Proposal Due Date, shall be rejected without further evaluation. [VOL-I 8.5 p4] The Bidder shall demonstrate technical capability in the design, construction and operation of wastewater treatment facilities. The Authority will assess technical capability on the basis of the reference projects submitted under Form 4-B.¹² | [VOL-I 8.5#fn12 p4] For the avoidance of doubt, a Bidder that does not evidence at least two (2) reference sewage treatment plants, each of nominal capacity not less than 80,000 m³/day and each having achieved commercial operation within the ten (10) years preceding the Proposal Due Date, shall be rejected without further evaluation. [VOL-I 8.5 p4] The Bidder shall demonstrate technical capability in the design, construction and operation of wastewater treatment facilities. The Authority will assess technical capability on the basis of the reference projects submitted under Form 4-B.¹² | at least two (2) reference sewage treatment plants, each of nominal capacity not less than 80,000 m³/day and each having achieved commercial operation within the ten (10) years preceding the Proposal Due Date | VOL-I 8.5#fn12 p4 | VOL-I 8.5#fn12 p4; VOL-I 8.5 p4 | pass_fail | Technical | Technical lead | EV-REFERENCES | ACTIVE | ACTIVE | ACTIVE | AMENDED (ADD-03/4.2(a)) | reading re-made at ADD-01: ADD-01 §2.2 names footnote 12; ADD-01 Q5: a plant under construction does not count. dates moved: REFERENCE-LOOKBACK 2016-11-13 -> 2016-11-27. by ADD-01/2.2 [ADD-01; proposed; annotates VOL-I:8.5#fn12 (interprets)] <- ADD-01:2.2 (ADD-01 p1); ADD-01/Q5 [ADD-01; proposed; annotates VOL-I:8.5#fn12 (interprets)] <- ADD-01:Q5 (ADD-01 p2); ADD-01/2.1 [ADD-01; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-01:2.1 (ADD-01 p1) |  | status ACTIVE -> AMENDED (ADD-03/4.2(a)). reading re-made at ADD-03: ADD-03 4.2 (op ADD-03/4.2(a), proposed) deletes '80,000 m³/day' in footnote 12 and substitutes '100,000 m³/day'. It also states 'The requirement for two (2) reference plants and the ten (10) year look-back are unchanged.' (op ADD-03/4.2(b), confirms). The figure is read from the printed words. The rejection rule remains in footnote 12, not in the body of 8.5. ADD-03 does not change ADD-01 Q5 (a plant under construction does not count). The look-back counts back from the Proposal Due Date, which ADD-03/2.1 moves to 'Thursday 10 December 2026'. The date rule REFERENCE-LOOKBACK is unchanged, and its boundary still has two readings. Follow-on: issue I-ADD03-REFERENCE-THRESHOLD. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed]. dates moved: REFERENCE-LOOKBACK 2016-11-27 -> 2016-12-11. by ADD-03/4.2(a) [ADD-03; proposed] <- ADD-03:4.2 (ADD-03 p1); ADD-03/4.2(b) [ADD-03; proposed; annotates VOL-I:8.5#fn12 (confirms)] <- ADD-03:4.2 (ADD-03 p1); ADD-03/2.1 [ADD-03; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-03:2.1 (ADD-03 p1) | VOL-I 8.5#fn12 p4 | VOL-I 8.5#fn12 p4 | VOL-I 8.5#fn12 p4 | VOL-I 8.5#fn12 p4 as amended by ADD-03 4.2 p1 | rejection: "shall be rejected without further evaluation" | VOL-I 8.5#fn12 p4 | REFERENCE-LOOKBACK: 2016-11-27 (boundary_exclusive) | high: verbatim footnote; boundary of the look-back not stated (two readings) | ADD-01 §2.2 names footnote 12; ADD-01 Q5: a plant under construction does not count. | value in question (unresolved: ADD-03:2.2 UNRESOLVED POSSIBLE TARGET: ambiguous: 'Every period calculated by reference to the Proposal Due Date is adjusted accordingly.' names no clause, unlike ADD-01:2.2 which listed Volume I Cl…); re-read by ADD-01/2.2 (interprets; accepted by a person; not counted as a confirmation), ADD-01/Q5 (interprets; accepted by a person; not counted as a confirmation); value as read at ADD-02, in question at ADD-03: 'at least two (2) reference sewage treatment plants, each of nominal capacity not less than 80,000 m³/day and each havin…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/2.2: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/Q5: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:8.5#fn12 (VOL-I p4; text layer); VOL-I:8.5 (VOL-I p4; text layer); ADD-01/2.2 [ADD-01; proposed; annotates VOL-I:8.5#fn12 (interprets)] <- ADD-01:2.2 (ADD-01 p1); ADD-01/Q5 [ADD-01; proposed; annotates VOL-I:8.5#fn12 (interprets)] <- ADD-01:Q5 (ADD-01 p2); ADD-01/2.1 [ADD-01; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-01:2.1 (ADD-01 p1); ADD-03/4.2(a) [ADD-03; proposed] <- ADD-03:4.2 (ADD-03 p1); ADD-03/4.2(b) [ADD-03; proposed; annotates VOL-I:8.5#fn12 (confirms)] <- ADD-03:4.2 (ADD-03 p1); ADD-03/2.1 [ADD-03; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-03:2.1 (ADD-03 p1)
VOL-I-8.6-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:8.6 | qualification; envelope_A | Local Content Certificate from the competent authority showing the minimum construction-phase local content ratio | [VOL-I 8.6 p4] The Bidder shall submit a Local Content Certificate issued by the competent authority evidencing a local content ratio of not less than thirty per cent (30%) for the construction phase. [ADD-01 4.2 p1; issued by ADD-01] Consequentially, any reference to a Local Content Certificate elsewhere in the RFP Documents shall be disregarded. | [VOL-I 8.6 p4] The Bidder shall submit a Local Content Certificate issued by the competent authority evidencing a local content ratio of not less than thirty-five per cent (35%) for the construction phase. Failure to submit the certificate shall render the Proposal non-responsive. [ADD-01 4.2 p1] (REVOKED) | not less than thirty-five per cent (35%) for the construction phase | ADD-02 9.1 p3 (reinstating VOL-I 8.6) | VOL-I 8.6 p4 <- ADD-01/4.1, ADD-02/9.1; ADD-01 4.2 p1 <- ADD-02/9.2 | pass_fail | Commercial | Commercial lead | EV-LCC | ACTIVE | DELETED (ADD-01/4.1) | REINSTATED-AMENDED (ADD-02/9.1) | ACTIVE (as amended by ADD-01/4.1, ADD-02/9.1) | status ACTIVE -> DELETED (ADD-01/4.1). by ADD-01/4.1 [ADD-01; proposed] <- ADD-01:4.1 (ADD-01 p1) | status DELETED (ADD-01/4.1) -> REINSTATED-AMENDED (ADD-02/9.1). reading re-made at ADD-02: Reinstated in amended form by ADD-02 §9.1; ADD-01 §4.2's disregard rule revoked by ADD-02 §9.2. by ADD-02/9.1 [ADD-02; proposed] <- ADD-02:9.1 (ADD-02 p3); ADD-02/9.2 [ADD-02; proposed] <- ADD-02:9.2 (ADD-02 p3) | status REINSTATED-AMENDED (ADD-02/9.1) -> ACTIVE (as amended by ADD-01/4.1, ADD-02/9.1) | VOL-I 8.6 p4 | VOL-I 8.6 p4 as amended by ADD-01 4.1 p1 | ADD-02 9.1 p3 (reinstating VOL-I 8.6) | ADD-02 9.1 p3 (reinstating VOL-I 8.6) | non-responsive: "Failure to submit the certificate shall render the Proposal non-responsive." | ADD-02 9.1 p3 (reinstating VOL-I 8.6) |  | high: verbatim at every stage; the issuing authority is not named and the lead time is unknown | Reinstated in amended form by ADD-02 §9.1; ADD-01 §4.2's disregard rule revoked by ADD-02 §9.2. | changed at ADD-02 by ADD-02/9.1 (reinstated in amended form; the quoted value, consequence differ from BASE; deleted at ADD-01 by ADD-01/4.1); re-read by ADD-01/4.2 (interprets; revoked by ADD-02/9.2; no longer in force); value as read: 'not less than thirty-five per cent (35%) for the construction phase' | decided (recorded): I-LCC-ISSUER | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/4.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/9.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/4.2: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-01/4.1: accepted; ADD-02/9.1: accepted | VOL-I:8.6 (VOL-I p4; text layer); ADD-01:4.2 (ADD-01 p1; text layer; issued by ADD-01); ADD-01/4.1 [ADD-01; proposed] <- ADD-01:4.1 (ADD-01 p1); ADD-02/9.1 [ADD-02; proposed] <- ADD-02:9.1 (ADD-02 p3); ADD-02/9.2 [ADD-02; proposed] <- ADD-02:9.2 (ADD-02 p3) | I-LCC-ISSUER
VOL-I-5.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:5.4 | pre_bid; fixed_date | Be represented at the Pre-Bid Conference on 30 September 2026 | A Pre-Bid Conference will be held on Wednesday 30 September 2026 at 10:00 Riyadh time at the Authority's offices. Attendance by at least one authorised representative of each Bidder is mandatory. A Bidder that is not represented at the Pre-Bid Conference shall be disqualified. | A Pre-Bid Conference will be held on Wednesday 30 September 2026 at 10:00 Riyadh time at the Authority's offices. Attendance by at least one authorised representative of each Bidder is mandatory. A Bidder that is not represented at the Pre-Bid Conference shall be disqualified. | Attendance by at least one authorised representative of each Bidder is mandatory. | VOL-I 5.4 p3 | VOL-I 5.4 p3 | pass_fail | Bid management | Bid manager | EV-ATTENDANCE | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 5.4 p3 | VOL-I 5.4 p3 | VOL-I 5.4 p3 | VOL-I 5.4 p3 | disqualification: "A Bidder that is not represented at the Pre-Bid Conference shall be disqualified." | VOL-I 5.4 p3 | PRE-BID: 2026-09-30 (as_stated) | high: verbatim; a fixed past date (does not move with the PDD); attendance is a bidder fact |  | unchanged since BASE; value as read: 'Attendance by at least one authorised representative of each Bidder is mandatory.' | decided (recorded): I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:5.4 (VOL-I p3; text layer) | I-BIDDER-FACTS
ADD-01-3.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | ADD-01:3.1 | pre_bid; deadline | If the attendance record is wrong, notify the Authority within five Working Days of Addendum No. 1 | [ADD-01 3.1 p1; issued by ADD-01] The attendance record is held by the Authority. A Bidder that considers its attendance to have been incorrectly recorded shall notify the Authority through the Portal within five (5) Working Days of this Addendum. | The attendance record is held by the Authority. A Bidder that considers its attendance to have been incorrectly recorded shall notify the Authority through the Portal within five (5) Working Days of this Addendum. | shall notify the Authority through the Portal within five (5) Working Days of this Addendum | ADD-01 3.1 p1 | ADD-01 3.1 p1 | procedural | Bid management | Bid manager | EV-ATTENDANCE | NOT ISSUED | NEW | ACTIVE | ACTIVE | status NOT ISSUED -> NEW. reading re-made at ADD-01. by ADD-01/3.1 [ADD-01; proposed; annotates ADD-01:3.1 (adds_obligation)] <- ADD-01:3.1 (ADD-01 p1) | status NEW -> ACTIVE |  |  | ADD-01 3.1 p1 | ADD-01 3.1 p1 | ADD-01 3.1 p1 | none stated in the documents |  | ATTENDANCE-NOTICE: 2026-10-14 (event_day_counted) | medium: forward Working Day counting is not defined (two readings) |  | new at ADD-01; re-read by ADD-01/3.1 (adds_obligation; accepted by a person; not counted as a confirmation); value as read: 'shall notify the Authority through the Portal within five (5) Working Days of this Addendum' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/3.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | ADD-01:3.1 (ADD-01 p1; text layer; issued by ADD-01); ADD-01/3.1 [ADD-01; proposed; annotates ADD-01:3.1 (adds_obligation)] <- ADD-01:3.1 (ADD-01 p1)
VOL-I-9.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:9.3 | envelope_A; forms | Form 4-A (as reissued by ADD-01 App A) signed by a person holding a notarised Power of Attorney from the lead member; an unsigned or improperly executed Form 4-A renders the Proposal non-responsive | Form 4-A shall be signed by a person holding a notarised Power of Attorney from the lead member of the Bidder. An unsigned or improperly executed Form 4-A shall render the Proposal non-responsive. | Form 4-A shall be signed by a person holding a notarised Power of Attorney from the lead member of the Bidder. An unsigned or improperly executed Form 4-A shall render the Proposal non-responsive. | Form 4-A shall be signed by a person holding a notarised Power of Attorney from the lead member of the Bidder. | VOL-I 9.3 p5 | VOL-I 9.3 p5 | pass_fail | Legal | Legal counsel | EV-FORM-4A; EV-POA | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 9.3 p5 | VOL-I 9.3 p5 | VOL-I 9.3 p5 | VOL-I 9.3 p5 | non-responsive: "An unsigned or improperly executed Form 4-A shall render the Proposal non-responsive." | VOL-I 9.3 p5 |  | high: verbatim |  | unchanged since BASE; value as read: 'Form 4-A shall be signed by a person holding a notarised Power of Attorney from the lead member of the Bidder.' | decided (recorded): I-F4A-FIELDS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:9.3 (VOL-I p5; text layer) | I-F4A-FIELDS
VOL-IV-F4A-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-A | forms; printed_date | Use the Form 4-A as issued (reissued by ADD-01 App A: 'Bidders shall use this version'); its printed Proposal Due Date | Proposal Due Date: 12 November 2026, 14:00 Riyadh time | Proposal Due Date: 12 November 2026, 14:00 Riyadh time | Proposal Due Date: 12 November 2026, 14:00 Riyadh time | ADD-01 AppA/proposal-due-date p3 (replacing VOL-IV F4-A/proposal-due-date p3, ADD-01/AppA/para1) | ADD-01 AppA/proposal-due-date p3 (issued as VOL-IV:F4-A/proposal-due-date) <- ADD-01/AppA/para1 | procedural | Legal | Legal counsel | EV-FORM-4A | ACTIVE | ACTIVE (reissued by ADD-01/AppA/para1, unchanged) | ACTIVE (reissued by ADD-01/AppA/para1, unchanged) | ACTIVE (reissued by ADD-01/AppA/para1, unchanged) | status ACTIVE -> ACTIVE (reissued by ADD-01/AppA/para1, unchanged). reading re-made at ADD-01: The reissued form still prints 12 November 2026; the PDD is 26 November 2026. Not corrected: a decision for a person. by ADD-01/AppA/para1 [ADD-01; proposed] <- ADD-01:AppA/para1 (ADD-01 p3) |  |  | VOL-IV F4-A/proposal-due-date p3 | ADD-01 AppA/proposal-due-date p3 (replacing VOL-IV F4-A/proposal-due-date p3, ADD-01/AppA/para1) | ADD-01 AppA/proposal-due-date p3 (replacing VOL-IV F4-A/proposal-due-date p3, ADD-01/AppA/para1) | ADD-01 AppA/proposal-due-date p3 (replacing VOL-IV F4-A/proposal-due-date p3, ADD-01/AppA/para1) | none stated in the documents |  |  | high: verbatim printed field; the conflict with the amended PDD is shown, not resolved | The reissued form still prints 12 November 2026; the PDD is 26 November 2026. Not corrected: a decision for a person. | unchanged since BASE (unit reissued at ADD-01 by ADD-01/AppA/para1; the row's words unchanged); value as read: 'Proposal Due Date: 12 November 2026, 14:00 Riyadh time' | decided (recorded): I-F4A-FIELDS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/AppA/para1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-01/AppA/para1: accepted | VOL-IV:F4-A/proposal-due-date (VOL-IV p3; text layer); ADD-01/AppA/para1 [ADD-01; proposed] <- ADD-01:AppA/para1 (ADD-01 p3) | I-F4A-FIELDS
VOL-I-9.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:9.4 | envelope_A; forms; arabic | Form 4-C completed in Arabic, signed and stamped by an authorised signatory of each member | [VOL-I 9.4 p5] Form 4-C shall be completed in the Arabic language, signed and stamped by an authorised signatory of each member of the Bidder. A translation may be attached for convenience but the Arabic text shall govern. Failure to submit a complete and properly executed Form 4-C for each member shall render the Proposal non-responsive. [VOL-IV F4-C/image p6] Form 4-C (image, Arabic with English labels): Conflict of Interest and Debarment Declaration | [VOL-I 9.4 p5] Form 4-C shall be completed in the Arabic language, signed and stamped by an authorised signatory of each member of the Bidder. A translation may be attached for convenience but the Arabic text shall govern. Failure to submit a complete and properly executed Form 4-C for each member shall render the Proposal non-responsive. [VOL-IV F4-C/image p6] Form 4-C (image, Arabic with English labels): Conflict of Interest and Debarment Declaration | Form 4-C shall be completed in the Arabic language, signed and stamped by an authorised signatory of each member of the Bidder. | VOL-I 9.4 p5 | VOL-I 9.4 p5; VOL-IV F4-C/image p6 | pass_fail | Legal | Legal counsel | EV-FORM-4C | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q9 confirms Arabic; an English translation may be attached for convenience only. by ADD-02/Q9 [ADD-02; proposed; annotates VOL-IV:F4-C/image (confirms)] <- ADD-02:Q9 (ADD-02 p2) |  | VOL-I 9.4 p5 | VOL-I 9.4 p5 | VOL-I 9.4 p5 | VOL-I 9.4 p5 | non-responsive: "Failure to submit a complete and properly executed Form 4-C for each member shall render the Proposal non-responsive." | VOL-I 9.4 p5 |  | high: text-layer clause; the form itself is an image (transcription and displayed translations confirmed by the owner, 3 Oct 2026) | ADD-02 Q9 confirms Arabic; an English translation may be attached for convenience only. | unchanged since BASE; re-read by ADD-02/Q9 (confirms; accepted by a person; not counted as a confirmation); value as read: 'Form 4-C shall be completed in the Arabic language, signed and stamped by an authorised signatory of each member of the…' | decided (recorded): I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/Q9: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:9.4 (VOL-I p5; text layer); VOL-IV:F4-C/image (VOL-IV p6; image reading); ADD-02/Q9 [ADD-02; proposed; annotates VOL-IV:F4-C/image (confirms)] <- ADD-02:Q9 (ADD-02 p2) | I-BIDDER-FACTS | <- REL-MEMBER-FORM-4C [confirmed member_scope] from VOL-I:8.1, words:member of the Bidder, words:consortium member, words:member of the consortium
VOL-IV-F4C-04 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-C | forms; arabic; declaration | Form 4-C declaration 4 (Arabic only): all information in the Proposal is true and complete | رابعاً: أن جميع المعلومات المقدمة في هذا العرض صحيحة وكاملة، وندرك أن أي بيان غير صحيح يؤدي إلى استبعاد العرض. | رابعاً: أن جميع المعلومات المقدمة في هذا العرض صحيحة وكاملة، وندرك أن أي بيان غير صحيح يؤدي إلى استبعاد العرض. | أن جميع المعلومات المقدمة في هذا العرض صحيحة وكاملة | VOL-IV F4-C/image/decl4 p6 | VOL-IV F4-C/image/decl4 p6 | pass_fail | Legal | Legal counsel | EV-FORM-4C | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q9 (Form 4-C in Arabic) reviewed: no change to this declaration. by ADD-02/Q9 [ADD-02; proposed; annotates VOL-IV:F4-C/image (confirms)] <- ADD-02:Q9 (ADD-02 p2) |  | VOL-IV F4-C/image/decl4 p6 | VOL-IV F4-C/image/decl4 p6 | VOL-IV F4-C/image/decl4 p6 | VOL-IV F4-C/image/decl4 p6 | exclusion: "يؤدي إلى استبعاد العرض" (translation confirmed by the owner 2026-10-03 (VOL-IV-p6-r1); category mapping open (I-F4C-EXCLUSION): 'leads to the exclusion of the proposal') | VOL-IV F4-C/image/decl4 p6 |  | medium: from an image reading (transcription and displayed translations confirmed by the owner, 3 Oct 2026); Arabic-only consequence whose category is unresolved | ADD-02 Q9 (Form 4-C in Arabic) reviewed: no change to this declaration. | unchanged since BASE; re-read by ADD-02/Q9 (confirms; accepted by a person; not counted as a confirmation); value as read: 'أن جميع المعلومات المقدمة في هذا العرض صحيحة وكاملة' | decided (recorded): I-READING-F4C, I-F4C-EXCLUSION | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/Q9: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:F4-C/image/decl4 (VOL-IV p6; image reading); ADD-02/Q9 [ADD-02; proposed; annotates VOL-IV:F4-C/image (confirms)] <- ADD-02:Q9 (ADD-02 p2) | I-READING-F4C; I-F4C-EXCLUSION
VOL-IV-F4C-N1 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-C | forms; arabic | Form 4-C note (Arabic): submit the form in Arabic for each consortium member | ملاحظة: يجب تقديم هذا النموذج باللغة العربية عن كل عضو من أعضاء الائتلاف. عدم تقديمه كاملاً يجعل العرض غير مستجيب. | ملاحظة: يجب تقديم هذا النموذج باللغة العربية عن كل عضو من أعضاء الائتلاف. عدم تقديمه كاملاً يجعل العرض غير مستجيب. | يجب تقديم هذا النموذج باللغة العربية عن كل عضو من أعضاء الائتلاف | VOL-IV F4-C/image/note p6 | VOL-IV F4-C/image/note p6 | pass_fail | Legal | Legal counsel | EV-FORM-4C | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q9 confirms the Arabic requirement. by ADD-02/Q9 [ADD-02; proposed; annotates VOL-IV:F4-C/image (confirms)] <- ADD-02:Q9 (ADD-02 p2) |  | VOL-IV F4-C/image/note p6 | VOL-IV F4-C/image/note p6 | VOL-IV F4-C/image/note p6 | VOL-IV F4-C/image/note p6 | non-responsive: "عدم تقديمه كاملاً يجعل العرض غير مستجيب" (translation confirmed by the owner 2026-10-03 (VOL-IV-p6-r1): 'failure to submit it complete renders the proposal non-responsive') | VOL-IV F4-C/image/note p6 |  | medium: from an image reading (transcription and displayed translations confirmed by the owner, 3 Oct 2026) | ADD-02 Q9 confirms the Arabic requirement. | unchanged since BASE; re-read by ADD-02/Q9 (confirms; accepted by a person; not counted as a confirmation); value as read: 'يجب تقديم هذا النموذج باللغة العربية عن كل عضو من أعضاء الائتلاف' | decided (recorded): I-READING-F4C, I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/Q9: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:F4-C/image/note (VOL-IV p6; image reading); ADD-02/Q9 [ADD-02; proposed; annotates VOL-IV:F4-C/image (confirms)] <- ADD-02:Q9 (ADD-02 p2) | I-READING-F4C; I-BIDDER-FACTS (via REL-MEMBER-FORM-4C (confirmed)) | <- REL-MEMBER-FORM-4C [confirmed member_scope] from VOL-I:8.1, words:member of the Bidder, words:consortium member, words:member of the consortium
ADD-02-7.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-15) | ADD-02:7 | envelope_A; forms; new_in_addendum | Complete and submit the new Form 4-G (cybersecurity undertaking) with Envelope A | [ADD-02 7.2 p3; issued by ADD-02] Form 4-G shall be completed and submitted with Envelope A. Failure to submit Form 4-G shall render the Proposal non-responsive. [ADD-02 p3 (inserted after VOL-I 9.1(e), p4)] FORM 4-G — CYBERSECURITY COMPLIANCE UNDERTAKING | [ADD-02 7.2 p3] Form 4-G shall be completed and submitted with Envelope A. Failure to submit Form 4-G shall render the Proposal non-responsive. [ADD-02 p3 (inserted after VOL-I 9.1(e), p4)] FORM 4-G — CYBERSECURITY COMPLIANCE UNDERTAKING | Form 4-G shall be completed and submitted with Envelope A. | ADD-02 7.2 p3 | ADD-02 7.2 p3; ADD-02 p3 (inserted after VOL-I 9.1(e), p4) <- ADD-02/7.1 | pass_fail | Technical | Technical lead | EV-FORM-4G | NOT ISSUED | NOT ISSUED | NEW | REVOKED (ADD-03/3.1(a)) |  | status NOT ISSUED -> NEW. reading re-made at ADD-02: ADD-02 7.1 adds Form 4-G 'to Volume IV and to the list at Volume I Clause 9.1'; it prints no entry for the Index of Forms (VOL-IV p2, which lists Forms 4-A to 4-F), so no index row is inserted, and where the form sits in Volume IV is not stated. by ADD-02/7.1 [ADD-02; proposed] <- ADD-02:7.1 (ADD-02 p3) | status NEW -> REVOKED (ADD-03/3.1(a)). by ADD-03/3.1(a) [ADD-03; proposed] <- ADD-03:3.1 (ADD-03 p1) |  |  | ADD-02 7.2 p3 | ADD-03 3.1 p1 (changing ADD-02 7.2) | non-responsive: "Failure to submit Form 4-G shall render the Proposal non-responsive." | ADD-02 7.2 p3 |  | high: verbatim; the re-lettering of the Envelope A list after item (e) is not stated | ADD-02 7.1 adds Form 4-G 'to Volume IV and to the list at Volume I Clause 9.1'; it prints no entry for the Index of Forms (VOL-IV p2, which lists Forms 4-A to 4-F), so no index row is inserted, and where the form sits in Volume IV is not stated. | new at ADD-02; value as read: 'Form 4-G shall be completed and submitted with Envelope A.' | decided (recorded): I-F4G-LETTERING | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | ADD-02:7.2 (ADD-02 p3; text layer; issued by ADD-02); VOL-I:9.1(e)+ADD-02 (ADD-02 p3; addendum op; issued by ADD-02; inserted after VOL-I 9.1(e), p4); ADD-02/7.1 [ADD-02; proposed] <- ADD-02:7.1 (ADD-02 p3); ADD-03/3.1(a) [ADD-03; proposed] <- ADD-03:3.1 (ADD-03 p1) | I-F4G-LETTERING
ADD-02-F4G-01 | UNRESOLVED: STALE at ADD-03 (its reading was not re-made: ADD-02:7.2 changed since ADD-02 (by ADD-03/3.1(a))) | ADD-02:F4-G | forms; post_award; new_in_addendum; cybersecurity | Form 4-G undertaking 3: appoint a named accountable security officer for the concession period (confirmed Yes or No) | [ADD-02 F4-G/T1/3 p3; issued by ADD-02] Item: 3 ¦ Undertaking: A named accountable security officer will be appointed for the concession period. ¦ Confirmed: Yes / No | Item: 3 ¦ Undertaking: A named accountable security officer will be appointed for the concession period. ¦ Confirmed: Yes / No | A named accountable security officer will be appointed for the concession period. | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/3) | ADD-02 F4-G/T1/3 p3 <- ADD-02/7.1 | contractual_post_award | Technical | Technical lead | EV-FORM-4G | NOT ISSUED | NOT ISSUED | NEW | ACTIVE (as amended by ADD-02/7.1) — STALE |  | status NOT ISSUED -> NEW. reading re-made at ADD-02: Form 4-G undertaking 3. A separate post-award obligation added by ADD-02 (Form 4-G, ADD-02 7.1-7.2); not in VOL-II 6. Confirmed Yes or No on the form at bid stage; the effect of answering 'No' is not stated (I-F4G-NO). by ADD-02/7.1 [ADD-02; proposed] <- ADD-02:7.1 (ADD-02 p3); ADD-02/7.2 [ADD-02; proposed; annotates ADD-02:F4-G/T1 (adds_obligation)] <- ADD-02:7.2 (ADD-02 p3) | status NEW -> ACTIVE (as amended by ADD-02/7.1) |  |  | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/3) | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/3) | none stated in the documents |  |  | medium: verbatim; the effect of answering 'No' is not stated | Form 4-G undertaking 3. A separate post-award obligation added by ADD-02 (Form 4-G, ADD-02 7.1-7.2); not in VOL-II 6. Confirmed Yes or No on the form at bid stage; the effect of answering 'No' is not stated (I-F4G-NO). | new at ADD-02; re-read by ADD-02/7.2 (adds_obligation; accepted by a person; not counted as a confirmation); value as read: 'A named accountable security officer will be appointed for the concession period.' | decided (recorded): I-F4G-NO | row: accepted by Interview demo assumption (2026-10-11) but CHANGED since: review again; ADD-02/7.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/7.2: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | accepted by Interview demo assumption (2026-10-11) but CHANGED since: review again | ADD-02/7.1: accepted | ADD-02:F4-G/T1/3 (ADD-02 p3; text layer; issued by ADD-02); ADD-02/7.1 [ADD-02; proposed] <- ADD-02:7.1 (ADD-02 p3); ADD-02/7.2 [ADD-02; proposed; annotates ADD-02:F4-G/T1 (adds_obligation)] <- ADD-02:7.2 (ADD-02 p3) | I-F4G-NO
ADD-02-F4G-05 | UNRESOLVED: STALE at ADD-03 (its reading was not re-made: ADD-02:7.2 changed since ADD-02 (by ADD-03/3.1(a))) | ADD-02:F4-G | forms; post_award; new_in_addendum; cybersecurity | Form 4-G undertaking 4: notify security incidents affecting the Facility to the Authority within 24 hours of detection (confirmed Yes or No) | [ADD-02 F4-G/T1/4 p3; issued by ADD-02] Item: 4 ¦ Undertaking: Security incidents affecting the Facility will be notified to the Authority within twenty-four (24) hours of detection. ¦ Confirmed: Yes / No | Item: 4 ¦ Undertaking: Security incidents affecting the Facility will be notified to the Authority within twenty-four (24) hours of detection. ¦ Confirmed: Yes / No | Security incidents affecting the Facility will be notified to the Authority within twenty-four (24) hours of detection. | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/4) | ADD-02 F4-G/T1/4 p3 <- ADD-02/7.1 | contractual_post_award | Technical | Technical lead | EV-FORM-4G | NOT ISSUED | NOT ISSUED | NEW | ACTIVE (as amended by ADD-02/7.1) — STALE |  | status NOT ISSUED -> NEW. reading re-made at ADD-02: Form 4-G undertaking 4. A separate post-award obligation added by ADD-02 (Form 4-G, ADD-02 7.1-7.2); not in VOL-II 6. Confirmed Yes or No on the form at bid stage; the effect of answering 'No' is not stated (I-F4G-NO). by ADD-02/7.1 [ADD-02; proposed] <- ADD-02:7.1 (ADD-02 p3); ADD-02/7.2 [ADD-02; proposed; annotates ADD-02:F4-G/T1 (adds_obligation)] <- ADD-02:7.2 (ADD-02 p3) | status NEW -> ACTIVE (as amended by ADD-02/7.1) |  |  | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/4) | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/4) | none stated in the documents |  |  | medium: verbatim; the effect of answering 'No' is not stated | Form 4-G undertaking 4. A separate post-award obligation added by ADD-02 (Form 4-G, ADD-02 7.1-7.2); not in VOL-II 6. Confirmed Yes or No on the form at bid stage; the effect of answering 'No' is not stated (I-F4G-NO). | new at ADD-02; re-read by ADD-02/7.2 (adds_obligation; accepted by a person; not counted as a confirmation); value as read: 'Security incidents affecting the Facility will be notified to the Authority within twenty-four (24) hours of detection.' | decided (recorded): I-F4G-NO | row: accepted by Interview demo assumption (2026-10-11) but CHANGED since: review again; ADD-02/7.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/7.2: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | accepted by Interview demo assumption (2026-10-11) but CHANGED since: review again | ADD-02/7.1: accepted | ADD-02:F4-G/T1/4 (ADD-02 p3; text layer; issued by ADD-02); ADD-02/7.1 [ADD-02; proposed] <- ADD-02:7.1 (ADD-02 p3); ADD-02/7.2 [ADD-02; proposed; annotates ADD-02:F4-G/T1 (adds_obligation)] <- ADD-02:7.2 (ADD-02 p3) | I-F4G-NO
ADD-02-F4G-06 | DECIDED: accepted by Interview demo assumption (2026-10-15) | ADD-02:F4-G | forms; post_award; new_in_addendum; cybersecurity | Form 4-G undertaking 5: an independent penetration test of the OT environment every year, with the report provided to the Authority (confirmed Yes or No) | [ADD-02 F4-G/T1/5 p3; issued by ADD-02] Item: 5 ¦ Undertaking: An independent penetration test of the operational technology environment will be carried out annually and the report provided to the Authority. ¦ Confirmed: Yes / No | Item: 5 ¦ Undertaking: An independent penetration test of the operational technology environment will be carried out annually and the report provided to the Authority. ¦ Confirmed: Yes / No | An independent penetration test of the operational technology environment will be carried out annually and the report provided to the Authority. | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/5) | ADD-02 F4-G/T1/5 p3 <- ADD-02/7.1 | contractual_post_award | Technical | Technical lead | EV-FORM-4G | NOT ISSUED | NOT ISSUED | NEW | ACTIVE (as amended by ADD-02/7.1) |  | status NOT ISSUED -> NEW. reading re-made at ADD-02: Form 4-G undertaking 5. A separate post-award obligation added by ADD-02 (Form 4-G, ADD-02 7.1-7.2); not in VOL-II 6. Confirmed Yes or No on the form at bid stage; the effect of answering 'No' is not stated (I-F4G-NO). by ADD-02/7.1 [ADD-02; proposed] <- ADD-02:7.1 (ADD-02 p3); ADD-02/7.2 [ADD-02; proposed; annotates ADD-02:F4-G/T1 (adds_obligation)] <- ADD-02:7.2 (ADD-02 p3) | status NEW -> ACTIVE (as amended by ADD-02/7.1). reading re-made at ADD-03: Re-made at ADD-03 because op ADD-03/3.1(a) revoked ADD-02:7.2. The undertaking unit ADD-02:F4-G/T1/5 is still 'active' in the effective text after the proposed ops, so the quote is unchanged. ADD-03 3.1, however, prints 'Form 4-G (Cybersecurity Compliance Undertaking), added by Addendum No. 2 Section 7, is withdrawn. Bidders shall disregard it and shall not submit it.' No promoted op withdraws the Form 4-G units themselves. Until a person decides that point (I-ADD03-F4G-UNITS), this row stays in force only because those units remain active; that is not a finding that the undertaking survives the withdrawal. ADD-02:7.2 (submission with Envelope A; non-responsive on failure) no longer has effect, so nothing in force at ADD-03 asks for this undertaking to be confirmed at bid stage. I-F4G-NO (the effect of a 'No' answer) is kept as recorded; its interview_demo acceptance is not a resolution. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] |  |  | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/5) | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/5) | none stated in the documents |  |  | medium: verbatim; the effect of answering 'No' is not stated | Form 4-G undertaking 5. A separate post-award obligation added by ADD-02 (Form 4-G, ADD-02 7.1-7.2); not in VOL-II 6. Confirmed Yes or No on the form at bid stage; the effect of answering 'No' is not stated (I-F4G-NO). | new at ADD-02; re-read by ADD-02/7.2 (adds_obligation; accepted by a person; not counted as a confirmation); value as read: 'An independent penetration test of the operational technology environment will be carried out annually and the report p…' | decided (recorded): I-F4G-NO | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/7.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/7.2: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-02/7.1: accepted | ADD-02:F4-G/T1/5 (ADD-02 p3; text layer; issued by ADD-02); ADD-02/7.1 [ADD-02; proposed] <- ADD-02:7.1 (ADD-02 p3); ADD-02/7.2 [ADD-02; proposed; annotates ADD-02:F4-G/T1 (adds_obligation)] <- ADD-02:7.2 (ADD-02 p3) | I-F4G-NO
ADD-02-F4G-07 | DECIDED: accepted by Interview demo assumption (2026-10-15) | ADD-02:F4-G | forms; post_award; new_in_addendum; cybersecurity | Form 4-G undertaking 6: remote access to the control system requires multi-factor authentication and is logged (confirmed Yes or No) | [ADD-02 F4-G/T1/6 p3; issued by ADD-02] Item: 6 ¦ Undertaking: Remote access to the control system will require multi-factor authentication and will be logged. ¦ Confirmed: Yes / No | Item: 6 ¦ Undertaking: Remote access to the control system will require multi-factor authentication and will be logged. ¦ Confirmed: Yes / No | Remote access to the control system will require multi-factor authentication and will be logged. | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/6) | ADD-02 F4-G/T1/6 p3 <- ADD-02/7.1 | contractual_post_award | Technical | Technical lead | EV-FORM-4G | NOT ISSUED | NOT ISSUED | NEW | ACTIVE (as amended by ADD-02/7.1) |  | status NOT ISSUED -> NEW. reading re-made at ADD-02: Form 4-G undertaking 6. A separate post-award obligation added by ADD-02 (Form 4-G, ADD-02 7.1-7.2); not in VOL-II 6. Confirmed Yes or No on the form at bid stage; the effect of answering 'No' is not stated (I-F4G-NO). by ADD-02/7.1 [ADD-02; proposed] <- ADD-02:7.1 (ADD-02 p3); ADD-02/7.2 [ADD-02; proposed; annotates ADD-02:F4-G/T1 (adds_obligation)] <- ADD-02:7.2 (ADD-02 p3) | status NEW -> ACTIVE (as amended by ADD-02/7.1). reading re-made at ADD-03: Re-made at ADD-03 because op ADD-03/3.1(a) revoked ADD-02:7.2. The undertaking unit ADD-02:F4-G/T1/6 is still 'active' in the effective text after the proposed ops, so the quote is unchanged. ADD-03 3.1, however, withdraws Form 4-G ('Bidders shall disregard it and shall not submit it.'), and no promoted op withdraws the Form 4-G units. Until a person decides that point (I-ADD03-F4G-UNITS), this row stays in force only because those units remain active; that is not a finding that the undertaking survives the withdrawal. ADD-02:7.2 no longer has effect, so nothing in force at ADD-03 asks for this undertaking to be confirmed at bid stage. I-F4G-NO is kept as recorded; its interview_demo acceptance is not a resolution. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] |  |  | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/6) | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/6) | none stated in the documents |  |  | medium: verbatim; the effect of answering 'No' is not stated | Form 4-G undertaking 6. A separate post-award obligation added by ADD-02 (Form 4-G, ADD-02 7.1-7.2); not in VOL-II 6. Confirmed Yes or No on the form at bid stage; the effect of answering 'No' is not stated (I-F4G-NO). | new at ADD-02; re-read by ADD-02/7.2 (adds_obligation; accepted by a person; not counted as a confirmation); value as read: 'Remote access to the control system will require multi-factor authentication and will be logged.' | decided (recorded): I-F4G-NO | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/7.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/7.2: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-02/7.1: accepted | ADD-02:F4-G/T1/6 (ADD-02 p3; text layer; issued by ADD-02); ADD-02/7.1 [ADD-02; proposed] <- ADD-02:7.1 (ADD-02 p3); ADD-02/7.2 [ADD-02; proposed; annotates ADD-02:F4-G/T1 (adds_obligation)] <- ADD-02:7.2 (ADD-02 p3) | I-F4G-NO
VOL-II-4.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:4.4 | technical_design; repeated_wording | Standby power sized to carry the inlet works, disinfection and effluent pumping for the stated duration | Standby provision for all rotating equipment shall be N+1. Standby power shall be sized to carry the full inlet works, the disinfection stage and the effluent pumping station for not less than seventy-two (72) hours. | Standby provision for all rotating equipment shall be N+1. Standby power shall be sized to carry the full inlet works, the disinfection stage and the effluent pumping station for not less than ninety-six (96) hours. | ninety-six (96) hours | ADD-02 4.1 p1 (amending VOL-II 4.4) | VOL-II 4.4 p4 <- ADD-02/4.1 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | AMENDED (ADD-02/4.1) | ACTIVE (as amended by ADD-02/4.1) |  | status ACTIVE -> AMENDED (ADD-02/4.1). reading re-made at ADD-02: ADD-02 §4.1. The same words 'seventy-two (72) hours' in VOL-V 31.3 are not targeted. by ADD-02/4.1 [ADD-02; proposed] <- ADD-02:4.1 (ADD-02 p1) | status AMENDED (ADD-02/4.1) -> ACTIVE (as amended by ADD-02/4.1) | VOL-II 4.4 p4 | VOL-II 4.4 p4 | ADD-02 4.1 p1 (amending VOL-II 4.4) | ADD-02 4.1 p1 (amending VOL-II 4.4) | none stated in the documents |  |  | high: verbatim; how non-compliance in the technical proposal is treated is not stated | ADD-02 §4.1. The same words 'seventy-two (72) hours' in VOL-V 31.3 are not targeted. | changed at ADD-02 by ADD-02/4.1 (the quoted value); value as read: 'ninety-six (96) hours' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/4.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-02/4.1: accepted | VOL-II:4.4 (VOL-II p4; text layer); ADD-02/4.1 [ADD-02; proposed] <- ADD-02:4.1 (ADD-02 p1)
VOL-V-31.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:31.3 | contract; post_award; repeated_wording | Cure period of 72 hours for an Unavailability Event under VOL-V 31.1(c) (unchanged by the addenda) | A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a) and of seventy-two (72) hours to an event under Clause 31.1(c). No cure period applies to an event under Clause 31.1(b). | A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a) and of seventy-two (72) hours to an event under Clause 31.1(c). No cure period applies to an event under Clause 31.1(b). | of seventy-two (72) hours to an event under Clause 31.1(c) | VOL-V 31.3 p3 | VOL-V 31.3 p3 | contractual_post_award | Legal | Legal counsel | Unresolved: the record that would show a VOL-V 31.1(c) event was cured within the 72-hour cure period cannot be specified from the extract, which states the length of the period but not when it starts or what a cure changes, and the deductions are calculated under Schedule 7 (VOL-V 31.2), which is not supplied. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 31.3 p3 | VOL-V 31.3 p3 | VOL-V 31.3 p3 | VOL-V 31.3 p3 | none stated in the documents |  |  | high: verbatim; must not change when VOL-II 4.4's identical words do |  | unchanged since BASE; value as read: 'of seventy-two (72) hours to an event under Clause 31.1(c)' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:31.3 (VOL-V p3; text layer)
VOL-I-11.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:11.2 | evaluation; weighting; repeated_wording | Combined score weighting, technical / commercial | Proposals reaching stage (iii) will be ranked on a combined score calculated on a weighting of sixty per cent (60%) technical and forty per cent (40%) commercial. | Proposals reaching stage (iii) will be ranked on a combined score calculated on a weighting of sixty-five per cent (65%) technical and thirty-five per cent (35%) commercial. | sixty-five per cent (65%) technical and thirty-five per cent (35%) commercial | ADD-02 T1-1-rev/note(2) p1 (amending VOL-I 11.2) | VOL-I 11.2 p5 <- ADD-02/T1-1-rev/note(2) | scored | Bid management | Bid manager | none: an evaluation rule the Authority applies; what it weighs are the Technical Proposal and the commercial proposal, required by their own rows | ACTIVE | ACTIVE | AMENDED (ADD-02/T1-1-rev/note(2)) | ACTIVE (as amended by ADD-02/T1-1-rev/note(2)) |  | status ACTIVE -> AMENDED (ADD-02/T1-1-rev/note(2)). reading re-made at ADD-02: ADD-02 note (2) to Table 1-1 (small print). The old words were located by shape, not quoted by the addendum. The minutes' 'seventy / thirty' is non-binding. by ADD-02/T1-1-rev/note(2) [ADD-02; proposed] <- ADD-02:T1-1-rev/note(2) (ADD-02 p1) | status AMENDED (ADD-02/T1-1-rev/note(2)) -> ACTIVE (as amended by ADD-02/T1-1-rev/note(2)) | VOL-I 11.2 p5 | VOL-I 11.2 p5 | ADD-02 T1-1-rev/note(2) p1 (amending VOL-I 11.2) | ADD-02 T1-1-rev/note(2) p1 (amending VOL-I 11.2) | none stated in the documents |  |  | medium: the amendment is in a small-print table note and does not quote the words it replaces | ADD-02 note (2) to Table 1-1 (small print). The old words were located by shape, not quoted by the addendum. The minutes' 'seventy / thirty' is non-binding. | changed at ADD-02 by ADD-02/T1-1-rev/note(2) (the quoted value); value as read: 'sixty-five per cent (65%) technical and thirty-five per cent (35%) commercial' | decided (recorded): I-ADD03-11-6-BAND-COND | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/T1-1-rev/note(2): ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-02/T1-1-rev/note(2): accepted | VOL-I:11.2 (VOL-I p5; text layer); ADD-02/T1-1-rev/note(2) [ADD-02; proposed] <- ADD-02:T1-1-rev/note(2) (ADD-02 p1) | I-ADD03-11-6-BAND-COND (via REL-AI-010 (possible)) | <- REL-AI-010 [possible depends_on] from ADD-03:6.1
VOL-V-29.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:29.2 | contract; payment; repeated_wording | Availability Payment indexation: 60% indexed to CPI, 40% fixed (unchanged by the addenda) | The Availability Payment shall be indexed annually in accordance with Schedule 9, with sixty per cent (60%) of the payment indexed to the published consumer price index and forty per cent (40%) remaining fixed. | The Availability Payment shall be indexed annually in accordance with Schedule 9, with sixty per cent (60%) of the payment indexed to the published consumer price index and forty per cent (40%) remaining fixed. | sixty per cent (60%) of the payment indexed to the published consumer price index and forty per cent (40%) remaining fixed | VOL-V 29.2 p3 | VOL-V 29.2 p3 | contractual_post_award | Commercial | Commercial lead | Not applicable: indexation of the Availability Payment (60% indexed to the published consumer price index, 40% fixed) is a payment term applied in accordance with Schedule 9, not an act the Project Company performs and evidences. | ACTIVE | ACTIVE | ACTIVE | ACTIVE | reading re-made at ADD-01: ADD-01 Q6 (offtake volume not guaranteed; the payment mechanism at Clause 29 is availability based) reviewed for this row: the indexation split is unchanged. by ADD-01/Q6 [ADD-01; proposed; annotates VOL-V:29.2 (interprets)] <- ADD-01:Q6 (ADD-01 p2) |  |  | VOL-V 29.2 p3 | VOL-V 29.2 p3 | VOL-V 29.2 p3 | VOL-V 29.2 p3 | none stated in the documents |  |  | high: verbatim; must not change when VOL-I 11.2's similar words do | ADD-01 Q6 (offtake volume not guaranteed; the payment mechanism at Clause 29 is availability based) reviewed for this row: the indexation split is unchanged. | unchanged since BASE; re-read by ADD-01/Q6 (interprets; accepted by a person; not counted as a confirmation); value as read: 'sixty per cent (60%) of the payment indexed to the published consumer price index and forty per cent (40%) remaining fi…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/Q6: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:29.2 (VOL-V p3; text layer); ADD-01/Q6 [ADD-01; proposed; annotates VOL-V:29.2 (interprets)] <- ADD-01:Q6 (ADD-01 p2)
VOL-I-11.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:11.3 | evaluation; threshold | Technical score of at least 70 out of 100 to proceed to commercial evaluation | A Proposal scoring less than seventy (70) marks out of one hundred (100) at the technical evaluation shall not proceed to commercial evaluation and its Envelope B shall be returned unopened. | A Proposal scoring less than seventy (70) marks out of one hundred (100) at the technical evaluation shall not proceed to commercial evaluation and its Envelope B shall be returned unopened. | scoring less than seventy (70) marks out of one hundred (100) | VOL-I 11.3 p5 | VOL-I 11.3 p5 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 note (1) confirms the threshold is unchanged. by ADD-02/T1-1-rev/note(1) [ADD-02; proposed; annotates VOL-I:11.3 (confirms)] <- ADD-02:T1-1-rev/note(1) (ADD-02 p1) |  | VOL-I 11.3 p5 | VOL-I 11.3 p5 | VOL-I 11.3 p5 | VOL-I 11.3 p5 | Envelope B returned unopened: "its Envelope B shall be returned unopened" | VOL-I 11.3 p5 |  | high: verbatim; confirmed unchanged by ADD-02 note (1) | ADD-02 note (1) confirms the threshold is unchanged. | unchanged since BASE; re-read by ADD-02/T1-1-rev/note(1) (confirms; accepted by a person; not counted as a confirmation); value as read: 'scoring less than seventy (70) marks out of one hundred (100)' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/T1-1-rev/note(1): ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:11.3 (VOL-I p5; text layer); ADD-02/T1-1-rev/note(1) [ADD-02; proposed; annotates VOL-I:11.3 (confirms)] <- ADD-02:T1-1-rev/note(1) (ADD-02 p1)
VOL-I-T1-1-B | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:T1-1 | evaluation; weighting | Marks available for criterion B (construction methodology, programme and interfaces) | Ref: B ¦ Criterion: Construction methodology, programme and interface management ¦ Marks: 20 | Ref: B ¦ Criterion: Construction methodology, programme and interface management ¦ Marks: 15 | Marks: 15 | ADD-02 T1-1-rev/B p1 (replacing VOL-I T1-1/B p6, ADD-02/3.1) | ADD-02 T1-1-rev/B p1 (issued as VOL-I:T1-1/B) <- ADD-02/3.1 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | AMENDED (ADD-02/3.1) | ACTIVE (as amended by ADD-02/3.1) |  | status ACTIVE -> AMENDED (ADD-02/3.1). reading re-made at ADD-02: Table 1-1 reissued by ADD-02 §3.1; B reduced by 5, D increased by 5, total 100 (checked). Note (3) adds a scoring method (a 'standard five-point scale' multiplied by 'the weight shown'); the scale is not defined (issue). by ADD-02/3.1 [ADD-02; proposed] <- ADD-02:3.1 (ADD-02 p1); ADD-02/T1-1-rev/note(3) [ADD-02; proposed; annotates ADD-02:T1-1-rev (interprets)] <- ADD-02:T1-1-rev/note(3) (ADD-02 p1) | status AMENDED (ADD-02/3.1) -> ACTIVE (as amended by ADD-02/3.1) | VOL-I T1-1/B p6 | VOL-I T1-1/B p6 | ADD-02 T1-1-rev/B p1 (replacing VOL-I T1-1/B p6, ADD-02/3.1) | ADD-02 T1-1-rev/B p1 (replacing VOL-I T1-1/B p6, ADD-02/3.1) | none stated in the documents |  |  | high: verbatim table rows | Table 1-1 reissued by ADD-02 §3.1; B reduced by 5, D increased by 5, total 100 (checked). Note (3) adds a scoring method (a 'standard five-point scale' multiplied by 'the weight shown'); the scale is not defined (issue). | changed at ADD-02 by ADD-02/3.1 (the quoted value, cells); value as read: 'Marks: 15' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/3.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-02/3.1: accepted | VOL-I:T1-1/B (VOL-I p6; text layer); ADD-02/3.1 [ADD-02; proposed] <- ADD-02:3.1 (ADD-02 p1); ADD-02/T1-1-rev/note(3) [ADD-02; proposed; annotates ADD-02:T1-1-rev (interprets)] <- ADD-02:T1-1-rev/note(3) (ADD-02 p1)
VOL-I-T1-1-D | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:T1-1 | evaluation; weighting | Marks available for criterion D (environmental and social management) | Ref: D ¦ Criterion: Environmental and social management ¦ Marks: 15 | Ref: D ¦ Criterion: Environmental and social management ¦ Marks: 20 | Marks: 20 | ADD-02 T1-1-rev/D p1 (replacing VOL-I T1-1/D p6, ADD-02/3.1) | ADD-02 T1-1-rev/D p1 (issued as VOL-I:T1-1/D) <- ADD-02/3.1 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | AMENDED (ADD-02/3.1) | ACTIVE (as amended by ADD-02/3.1) |  | status ACTIVE -> AMENDED (ADD-02/3.1). reading re-made at ADD-02: Table 1-1 reissued by ADD-02 §3.1. Note (3) adds a scoring method (a 'standard five-point scale' multiplied by 'the weight shown'); the scale is not defined (issue). by ADD-02/3.1 [ADD-02; proposed] <- ADD-02:3.1 (ADD-02 p1); ADD-02/T1-1-rev/note(3) [ADD-02; proposed; annotates ADD-02:T1-1-rev (interprets)] <- ADD-02:T1-1-rev/note(3) (ADD-02 p1) | status AMENDED (ADD-02/3.1) -> ACTIVE (as amended by ADD-02/3.1) | VOL-I T1-1/D p6 | VOL-I T1-1/D p6 | ADD-02 T1-1-rev/D p1 (replacing VOL-I T1-1/D p6, ADD-02/3.1) | ADD-02 T1-1-rev/D p1 (replacing VOL-I T1-1/D p6, ADD-02/3.1) | none stated in the documents |  |  | high: verbatim table rows | Table 1-1 reissued by ADD-02 §3.1. Note (3) adds a scoring method (a 'standard five-point scale' multiplied by 'the weight shown'); the scale is not defined (issue). | changed at ADD-02 by ADD-02/3.1 (the quoted value, cells); value as read: 'Marks: 20' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/3.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-02/3.1: accepted | VOL-I:T1-1/D (VOL-I p6; text layer); ADD-02/3.1 [ADD-02; proposed] <- ADD-02:3.1 (ADD-02 p1); ADD-02/T1-1-rev/note(3) [ADD-02; proposed; annotates ADD-02:T1-1-rev (interprets)] <- ADD-02:T1-1-rev/note(3) (ADD-02 p1)
VOL-II-T2-4-TN | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:T2-4 | technical_design; effluent; image | Treated effluent Total Nitrogen (TN): value shown in Table 2-4, unit and basis of assessment | Parameter: Total Nitrogen (TN) ¦ Unit: mg/l ¦ Limit: 5 ¦ Basis of assessment: 30-day rolling average | Parameter: Total Nitrogen (TN) ¦ Unit: mg/l ¦ Limit: 3 ¦ Basis of assessment: 30-day rolling average | Limit: 3 | VOL-II T2-4/TN p3 as amended by ADD-02 5.1 p1 | VOL-II T2-4/TN p3 <- ADD-02/5.1 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | AMENDED (ADD-02/5.1) | ACTIVE (as amended by ADD-02/5.1) |  | status ACTIVE -> AMENDED (ADD-02/5.1). reading re-made at ADD-02: ADD-02 §5.1 amends 'from the value shown' (which exists only in the image) to 3 mg/l, same basis. The Environmental Permit, which prevails over the reproduction (VOL-II p3, reproduction preamble), is not in the pack; no Permit compliance is claimed, including for the amended TN limit. by ADD-02/5.1 [ADD-02; proposed] <- ADD-02:5.1 (ADD-02 p1) | status AMENDED (ADD-02/5.1) -> ACTIVE (as amended by ADD-02/5.1) | VOL-II T2-4/TN p3 | VOL-II T2-4/TN p3 | VOL-II T2-4/TN p3 as amended by ADD-02 5.1 p1 | VOL-II T2-4/TN p3 as amended by ADD-02 5.1 p1 | none stated in the documents |  |  | medium: base value 5 mg/l and basis come from the image reading (transcription confirmed by the owner, 3 Oct 2026); the separate amended value 3 mg/l comes from ADD-02 5.1 (op proposed); the Permit is not supplied | ADD-02 §5.1 amends 'from the value shown' (which exists only in the image) to 3 mg/l, same basis. The Environmental Permit, which prevails over the reproduction (VOL-II p3, reproduction preamble), is not in the pack; no Permit compliance is claimed, including for the amended TN limit. Printed table title: 'Table 2-4 Minimum Effluent Quality Parameters at the Point of Discharge'. | changed at ADD-02 by ADD-02/5.1 (the quoted value, cells); value as read: 'Limit: 3' | decided (recorded): I-PERMIT, I-READING-T24, I-VOL-II-COMPLIANCE-POINT | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/5.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-02/5.1: accepted | VOL-II:T2-4/TN (VOL-II p3; image reading); ADD-02/5.1 [ADD-02; proposed] <- ADD-02:5.1 (ADD-02 p1) | I-PERMIT; I-READING-T24; I-VOL-II-COMPLIANCE-POINT | NOT SUPPLIED: the Environmental Permit issued for the site (REL-MISSING-ENVIRONMENTAL-PERMIT, link confirmed): cannot be established: that the reproduced Table 2-4 limits, as amended by the addenda, are the limits that govern (the Permit prevails over the reproduction), and the limit of any parameter not listed (Note 1); Permit compliance is not claimed
ADD-03-cover-para3-01 | DECIDED: accepted by Interview demo assumption (2026-10-15) | ADD-03:cover | envelope_A; forms; addenda_acknowledgement; new_in_addendum | Acknowledge receipt of Addendum No. 3 in Form 4-A (reissued form field 'Addenda acknowledged (numbers)') | [ADD-03 cover/para3 p1; issued by ADD-03] This Addendum amends the Proposal Due Date and Bid Bond, withdraws Form 4-G, increases the nominal capacity with a consequential change to the reference project threshold, amends Table 2-4, adds a new Clause 11.6, and responds to clarification requests 15 to 18. This Addendum forms part of the RFP Documents and takes precedence in accordance with Volume I Clause 3.2. Bidders shall acknowledge receipt in Form 4-A. All other terms of the RFP Documents remain unchanged. [ADD-01 AppA/addenda-acknowledged-numbers p3; issued by ADD-01] Addenda acknowledged (numbers): [ADD-01 AppA/para1 p3; issued by ADD-01] Form 4-A is reissued below to add the acknowledgement of Addenda at paragraph 1. Bidders shall use this version. | [ADD-03 cover/para3 p1] This Addendum amends the Proposal Due Date and Bid Bond, withdraws Form 4-G, increases the nominal capacity with a consequential change to the reference project threshold, amends Table 2-4, adds a new Clause 11.6, and responds to clarification requests 15 to 18. This Addendum forms part of the RFP Documents and takes precedence in accordance with Volume I Clause 3.2. Bidders shall acknowledge receipt in Form 4-A. All other terms of the RFP Documents remain unchanged. [ADD-01 AppA/addenda-acknowledged-numbers p3] Addenda acknowledged (numbers): [ADD-01 AppA/para1 p3] Form 4-A is reissued below to add the acknowledgement of Addenda at paragraph 1. Bidders shall use this version. | Bidders shall acknowledge receipt in Form 4-A. | ADD-03 cover/para3 p1 | ADD-03 cover/para3 p1; ADD-01 AppA/addenda-acknowledged-numbers p3 <- ADD-01/AppA/para1; ADD-01 AppA/para1 p3 | pass_fail | Bid management | Bid manager | EV-FORM-4A | NOT IN FORCE (introduced at ADD-03 by ADD-03/cover/para3) | NOT IN FORCE (introduced at ADD-03 by ADD-03/cover/para3) | NOT IN FORCE (introduced at ADD-03 by ADD-03/cover/para3) | NEW (introduced by ADD-03/cover/para3) |  |  | status NOT IN FORCE (introduced at ADD-03 by ADD-03/cover/para3) -> NEW (introduced by ADD-03/cover/para3). reading re-made at ADD-03: ADD-03's cover repeats the acknowledgement obligation of the ADD-01 and ADD-02 covers (row ADD-01-AppA-01) and does not reissue Form 4-A. The ADD-01 App A version ('Bidders shall use this version.') remains the form, with its 'Addenda acknowledged (numbers)' field. VOL-IV:F4-A/item1 is superseded and is not used. The reissued form's printed 'Proposal Due Date: 12 November 2026, 14:00 Riyadh time' predates ADD-03 2.1 as well as ADD-01. What to print and sign is the open question in I-F4A-FIELDS. No consequence specific to the acknowledgement is stated (I-NO-CONSEQUENCE). The rest of the cover paragraph summarises the operative provisions and does not amend. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed]. by ADD-03/cover/para3 [ADD-03; proposed; annotates ADD-03:cover/para3 (adds_obligation)] <- ADD-03:cover/para3 (ADD-03 p1) |  |  |  | ADD-03 cover/para3 p1 | none stated in the documents |  |  | medium: verbatim cover sentence; the reissued form's layout does not match its stated purpose ('paragraph 1'), and no consequence is stated | ADD-03's cover repeats the acknowledgement obligation of the ADD-01 and ADD-02 covers (row ADD-01-AppA-01) and does not reissue Form 4-A. The ADD-01 App A version ('Bidders shall use this version.') remains the form, with its 'Addenda acknowledged (numbers)' field. VOL-IV:F4-A/item1 is superseded and is not used. The reissued form's printed 'Proposal Due Date: 12 November 2026, 14:00 Riyadh time' predates ADD-03 2.1 as well as ADD-01. What to print and sign is the open question in I-F4A-FIELDS. No consequence specific to the acknowledgement is stated (I-NO-CONSEQUENCE). The rest of the cover paragraph summarises the operative provisions and does not amend. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | not in force at ADD-02 (NOT IN FORCE (introduced at ADD-03 by ADD-03/cover/para3)) | decided (recorded): I-F4A-FIELDS, I-NO-CONSEQUENCE | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | ADD-03:cover/para3 (ADD-03 p1; text layer; issued by ADD-03); ADD-01:AppA/addenda-acknowledged-numbers (ADD-01 p3; text layer; issued by ADD-01); ADD-01:AppA/para1 (ADD-01 p3; text layer; issued by ADD-01); ADD-01/AppA/para1 [ADD-01; proposed] <- ADD-01:AppA/para1 (ADD-01 p3); ADD-03/cover/para3 [ADD-03; proposed; annotates ADD-03:cover/para3 (adds_obligation)] <- ADD-03:cover/para3 (ADD-03 p1) | I-F4A-FIELDS; I-NO-CONSEQUENCE | -> REL-AI-002 [proposed depends_on] to ADD-01-AppA-01
ADD-03-6.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-15) | VOL-I:11.5+ADD-03 | evaluation; preferred_bidder; new_in_addendum | VOL-I 11.6 (new, ADD-03 6.1): where two or more Proposals are within 2% of one another after the combined evaluation, the Authority may apply further criteria it considers appropriate to determine the Preferred Bidder, and its determination shall be final | [ADD-03 p1,2 (inserted after VOL-I 11.5, p5)] Where, on completion of the combined evaluation, two or more Proposals are within two per cent (2%) of one another, the Authority may apply such further criteria as it considers appropriate to determine the Preferred Bidder, and its determination shall be final. [ADD-03 6.1 p1,2; issued by ADD-03] A new Clause 11.6 is added to Volume I: ‘11.6 Where, on completion of the combined evaluation, two or more Proposals are within two per cent (2%) of one another, the Authority may apply such further criteria as it considers appropriate to determine the Preferred Bidder, and its determination shall be final.’ | [ADD-03 p1,2 (inserted after VOL-I 11.5, p5)] Where, on completion of the combined evaluation, two or more Proposals are within two per cent (2%) of one another, the Authority may apply such further criteria as it considers appropriate to determine the Preferred Bidder, and its determination shall be final. [ADD-03 6.1 p1,2] A new Clause 11.6 is added to Volume I: ‘11.6 Where, on completion of the combined evaluation, two or more Proposals are within two per cent (2%) of one another, the Authority may apply such further criteria as it considers appropriate to determine the Preferred Bidder, and its determination shall be final.’ | Where, on completion of the combined evaluation, two or more Proposals are within two per cent (2%) of one another, the Authority may apply such further criteria as it considers appropriate to determine the Preferred Bidder, and its determination shall be final. | ADD-03 6.1 p1,2 (amending ADD-03 (inserted after VOL-I 11.5)) | ADD-03 p1,2 (inserted after VOL-I 11.5, p5) <- ADD-03/6.1; ADD-03 6.1 p1,2 | informational | Bid management | Bid manager | none: An Authority evaluation discretion; the clause asks the Bidder to submit nothing. | NOT IN FORCE (introduced at ADD-03 by ADD-03/6.1) | NOT IN FORCE (introduced at ADD-03 by ADD-03/6.1) | NOT IN FORCE (introduced at ADD-03 by ADD-03/6.1) | NEW (introduced by ADD-03/6.1) |  |  | status NOT IN FORCE (introduced at ADD-03 by ADD-03/6.1) -> NEW (introduced by ADD-03/6.1). reading re-made at ADD-03: An Authority discretion in evaluation, not a submission obligation. The measure of the 2% is not stated: combined-score points, a relative percentage or another measure (ambiguous; I-ADD03-TIE-BAND, draft CQ-ADD03-TIE-BAND). The further criteria are not stated. What 'its determination shall be final' means is a legal question for a person. The determination precedes the Preferred Bidder Notification (VOL-I 12.1, 12.2, 12.3; the blackout in VOL-I 4.2 runs until that notification). [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed]. by ADD-03/6.1 [ADD-03; proposed] <- ADD-03:6.1 (ADD-03 p1,2) |  |  |  | ADD-03 6.1 p1,2 (amending ADD-03 (inserted after VOL-I 11.5)) | none stated in the documents |  |  | medium: verbatim inserted clause; the basis of the 2% band and the further criteria are not stated | An Authority discretion in evaluation, not a submission obligation. The measure of the 2% is not stated: combined-score points, a relative percentage or another measure (ambiguous; I-ADD03-TIE-BAND, draft CQ-ADD03-TIE-BAND). The further criteria are not stated. What 'its determination shall be final' means is a legal question for a person. The determination precedes the Preferred Bidder Notification (VOL-I 12.1, 12.2, 12.3; the blackout in VOL-I 4.2 runs until that notification). [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | not in force at ADD-02 (NOT IN FORCE (introduced at ADD-03 by ADD-03/6.1)) | decided (recorded): I-ADD03-TIE-BAND | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:11.5+ADD-03 (ADD-03 p1,2; addendum op; issued by ADD-03; inserted after VOL-I 11.5, p5); ADD-03:6.1 (ADD-03 p1,2; text layer; issued by ADD-03); ADD-03/6.1 [ADD-03; proposed] <- ADD-03:6.1 (ADD-03 p1,2) | I-ADD03-TIE-BAND
ADD-03-Q17-01 | DECIDED: accepted by Interview demo assumption (2026-10-15) | ADD-03:Q17 | envelope_B; price; new_in_addendum | Price the Project as amended by Addendum No. 3 (Authority response to bidder question 17 on adjusting the Availability Payment for the increased capacity) | [ADD-03 Q17 p2; issued by ADD-03] No: 17 ¦ Bidder question: Will the Availability Payment be adjusted for the increased capacity? ¦ Authority response: Bidders shall price the Project as amended by this Addendum. | No: 17 ¦ Bidder question: Will the Availability Payment be adjusted for the increased capacity? ¦ Authority response: Bidders shall price the Project as amended by this Addendum. | Bidders shall price the Project as amended by this Addendum. | ADD-03 Q17 p2 | ADD-03 Q17 p2 | procedural | Commercial | Commercial lead | EV-FORM-4F; EV-FIN-MODEL | NOT IN FORCE (introduced at ADD-03 by ADD-03/Q17) | NOT IN FORCE (introduced at ADD-03 by ADD-03/Q17) | NOT IN FORCE (introduced at ADD-03 by ADD-03/Q17) | NEW (introduced by ADD-03/Q17) |  |  | status NOT IN FORCE (introduced at ADD-03 by ADD-03/Q17) -> NEW (introduced by ADD-03/Q17). reading re-made at ADD-03: Authority response to bidder question 17 ('Will the Availability Payment be adjusted for the increased capacity?'). No consequence is printed in ADD-03:Q17. The price is quoted as a single Availability Payment (VOL-I 10.2, row VOL-I-10.2-01) on Form 4-F, confirmed unconditional and derived from the Financial Model (rows VOL-IV-F4F-01, VOL-IV-F4F-02). Whether the response says the Availability Payment will or will not be adjusted for capacity is ambiguous (I-ADD03-Q17-AP-CAPACITY); not decided here. The analysis phase's reference id R-ADD03-Q17 is not used: new row ids follow <ADDENDUM>-<provision>-NN. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed]. by ADD-03/Q17 [ADD-03; proposed; annotates ADD-03:Q17 (adds_obligation)] <- ADD-03:Q17 (ADD-03 p2) |  |  |  | ADD-03 Q17 p2 | none stated in the documents |  |  | medium: verbatim; what the response means for the Availability Payment question is ambiguous and pending a Commercial decision; no consequence printed | Authority response to bidder question 17 ('Will the Availability Payment be adjusted for the increased capacity?'). No consequence is printed in ADD-03:Q17. The price is quoted as a single Availability Payment (VOL-I 10.2, row VOL-I-10.2-01) on Form 4-F, confirmed unconditional and derived from the Financial Model (rows VOL-IV-F4F-01, VOL-IV-F4F-02). Whether the response says the Availability Payment will or will not be adjusted for capacity is ambiguous (I-ADD03-Q17-AP-CAPACITY); not decided here. The analysis phase's reference id R-ADD03-Q17 is not used: new row ids follow <ADDENDUM>-<provision>-NN. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | not in force at ADD-02 (NOT IN FORCE (introduced at ADD-03 by ADD-03/Q17)) | decided (recorded): I-ADD03-Q17-AP-CAPACITY | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | ADD-03:Q17 (ADD-03 p2; text layer; issued by ADD-03); ADD-03/Q17 [ADD-03; proposed; annotates ADD-03:Q17 (adds_obligation)] <- ADD-03:Q17 (ADD-03 p2) | I-ADD03-Q17-AP-CAPACITY | -> REL-AI-004 [proposed depends_on] to VOL-I-10.2-01, VOL-IV-F4F-01, VOL-IV-F4F-02
ADD-03-3.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-15) | ADD-03:3.1 | envelope_A; forms; new_in_addendum | Disregard Form 4-G (Cybersecurity Compliance Undertaking, withdrawn by ADD-03 3.1) and do not submit it | [ADD-03 3.1 p1; issued by ADD-03] Form 4-G (Cybersecurity Compliance Undertaking), added by Addendum No. 2 Section 7, is withdrawn. Bidders shall disregard it and shall not submit it. Section 7.2 of Addendum No. 2 ceases to have effect. | Form 4-G (Cybersecurity Compliance Undertaking), added by Addendum No. 2 Section 7, is withdrawn. Bidders shall disregard it and shall not submit it. Section 7.2 of Addendum No. 2 ceases to have effect. | Bidders shall disregard it and shall not submit it. | ADD-03 3.1 p1 | ADD-03 3.1 p1 | procedural | Bid management | Bid manager | none: a prohibition: nothing is produced; Form 4-G is not prepared, signed or placed in Envelope A | NOT IN FORCE (introduced at ADD-03 by ADD-03:3.1) | NOT IN FORCE (introduced at ADD-03 by ADD-03:3.1) | NOT IN FORCE (introduced at ADD-03 by ADD-03:3.1) | NEW (introduced by ADD-03:3.1) |  |  | status NOT IN FORCE (introduced at ADD-03 by ADD-03:3.1) -> NEW (introduced by ADD-03:3.1). reading re-made at ADD-03: 'it' is Form 4-G (Cybersecurity Compliance Undertaking), which the same provision states 'is withdrawn'. No consequence is printed for submitting it. The VOL-I 9.1 list entry and the Form 4-G units added by ADD-02 remain active after the promoted ops (I-ADD03-F4G-UNITS-ACTIVE). [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] |  |  |  | ADD-03 3.1 p1 | none stated in the documents |  |  | high: verbatim prohibition; no consequence printed | 'it' is Form 4-G (Cybersecurity Compliance Undertaking), which the same provision states 'is withdrawn'. No consequence is printed for submitting it. The VOL-I 9.1 list entry and the Form 4-G units added by ADD-02 remain active after the promoted ops (I-ADD03-F4G-UNITS-ACTIVE). [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | not in force at ADD-02 (NOT IN FORCE (introduced at ADD-03 by ADD-03:3.1)) | decided (recorded): I-ADD03-F4G-UNITS-ACTIVE | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | ADD-03:3.1 (ADD-03 p1; text layer; issued by ADD-03) | I-ADD03-F4G-UNITS-ACTIVE
ADD-03-3.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-15) | ADD-03:3.2 | envelope_A; technical_proposal; cybersecurity; new_in_addendum | Address the substantive requirements of Volume II Section 6 (SCADA, control and cyber security) in the Technical Proposal narrative | [ADD-03 3.2 p1; issued by ADD-03] The substantive requirements of Volume II Section 6 are unchanged and shall be addressed in the Technical Proposal narrative. | The substantive requirements of Volume II Section 6 are unchanged and shall be addressed in the Technical Proposal narrative. | The substantive requirements of Volume II Section 6 are unchanged and shall be addressed in the Technical Proposal narrative. | ADD-03 3.2 p1 | ADD-03 3.2 p1 | procedural | Technical | Technical lead | EV-TECH-PROPOSAL | NOT IN FORCE (introduced at ADD-03 by ADD-03:3.2) | NOT IN FORCE (introduced at ADD-03 by ADD-03:3.2) | NOT IN FORCE (introduced at ADD-03 by ADD-03:3.2) | NEW (introduced by ADD-03:3.2) |  |  | status NOT IN FORCE (introduced at ADD-03 by ADD-03:3.2) -> NEW (introduced by ADD-03:3.2). reading re-made at ADD-03: Volume II Section 6 is headed 'SECTION 6 — SCADA, CONTROL AND CYBER SECURITY' (VOL-II:H:S6, p4; Clauses 6.1 to 6.3). No consequence is printed in ADD-03:3.2. The narrative is subject to the VOL-I 9.2 page limit (row VOL-I-9.2-01; pages over the limit are removed before evaluation); how the Section 6 content is scored is not stated here. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] |  |  |  | ADD-03 3.2 p1 | none stated in the documents |  |  | high: verbatim; no consequence printed | Volume II Section 6 is headed 'SECTION 6 — SCADA, CONTROL AND CYBER SECURITY' (VOL-II:H:S6, p4; Clauses 6.1 to 6.3). No consequence is printed in ADD-03:3.2. The narrative is subject to the VOL-I 9.2 page limit (row VOL-I-9.2-01; pages over the limit are removed before evaluation); how the Section 6 content is scored is not stated here. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | not in force at ADD-02 (NOT IN FORCE (introduced at ADD-03 by ADD-03:3.2)) | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | ADD-03:3.2 (ADD-03 p1; text layer; issued by ADD-03) |  | <- REL-AI-005 [proposed limit_applies] from VOL-I-9.2-01; REACHED at ADD-02 (proposed relationship): from VOL-I-9.2-01 via REL-AI-005
ADD-01-AppA-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | ADD-01:AppA | envelope_A; forms; addenda_acknowledgement; reissued_form; new_in_addendum | Acknowledge receipt of each Addendum in Form 4-A (reissued form field 'Addenda acknowledged (numbers)') | [ADD-01 cover/para3 p1; issued by ADD-01] This Addendum amends the Proposal Due Date, deletes one qualification requirement, amends Volume II Clause 5.3, publishes the minutes of the Pre-Bid Conference, and responds to clarification requests 1 to 6. This Addendum forms part of the RFP Documents and takes precedence in accordance with Volume I Clause 3.2. Bidders shall acknowledge receipt in Form 4-A. All other terms of the RFP Documents remain unchanged. [ADD-01 AppA/addenda-acknowledged-numbers p3; issued by ADD-01] Addenda acknowledged (numbers): [ADD-01 AppA/para1 p3; issued by ADD-01] Form 4-A is reissued below to add the acknowledgement of Addenda at paragraph 1. Bidders shall use this version. [ADD-02 cover/para3 p1; issued by ADD-02] This Addendum amends the page limit, reissues the technical evaluation table, amends Volume II Clauses 4.4 and Table 2-4, adds Form 4-G, amends Volume V Clause 36.2, reinstates Volume I Clause 8.6, and responds to clarification requests 7 to 14. This Addendum forms part of the RFP Documents and takes precedence in accordance with Volume I Clause 3.2. Bidders shall acknowledge receipt in Form 4-A. All other terms of the RFP Documents remain unchanged. | [ADD-01 cover/para3 p1] This Addendum amends the Proposal Due Date, deletes one qualification requirement, amends Volume II Clause 5.3, publishes the minutes of the Pre-Bid Conference, and responds to clarification requests 1 to 6. This Addendum forms part of the RFP Documents and takes precedence in accordance with Volume I Clause 3.2. Bidders shall acknowledge receipt in Form 4-A. All other terms of the RFP Documents remain unchanged. [ADD-01 AppA/addenda-acknowledged-numbers p3] Addenda acknowledged (numbers): [ADD-01 AppA/para1 p3] Form 4-A is reissued below to add the acknowledgement of Addenda at paragraph 1. Bidders shall use this version. [ADD-02 cover/para3 p1] This Addendum amends the page limit, reissues the technical evaluation table, amends Volume II Clauses 4.4 and Table 2-4, adds Form 4-G, amends Volume V Clause 36.2, reinstates Volume I Clause 8.6, and responds to clarification requests 7 to 14. This Addendum forms part of the RFP Documents and takes precedence in accordance with Volume I Clause 3.2. Bidders shall acknowledge receipt in Form 4-A. All other terms of the RFP Documents remain unchanged. | Bidders shall acknowledge receipt in Form 4-A. | ADD-01 cover/para3 p1 | ADD-01 cover/para3 p1; ADD-01 AppA/addenda-acknowledged-numbers p3 <- ADD-01/AppA/para1; ADD-01 AppA/para1 p3; ADD-02 cover/para3 p1 | pass_fail | Bid management | Bid manager | EV-FORM-4A | NOT ISSUED | NEW | ACTIVE | ACTIVE | status NOT ISSUED -> NEW. reading re-made at ADD-01: App A reissues Form 4-A 'to add the acknowledgement of Addenda at paragraph 1', but the reissued form has no paragraph 1; it has an 'Addenda acknowledged (numbers)' field. No consequence stated; whether a missing acknowledgement makes Form 4-A 'improperly executed' (VOL-I 9.3) is for a person. by ADD-01/AppA/para1 [ADD-01; proposed] <- ADD-01:AppA/para1 (ADD-01 p3); ADD-01/cover/para3 [ADD-01; proposed; annotates ADD-01:cover/para3 (adds_obligation)] <- ADD-01:cover/para3 (ADD-01 p1) | status NEW -> ACTIVE. reading re-made at ADD-02: ADD-02's cover repeats 'Bidders shall acknowledge receipt in Form 4-A.' and does not reissue the form; the ADD-01 App A version remains the one to use. by ADD-02/cover/para3 [ADD-02; proposed; annotates ADD-02:cover/para3 (adds_obligation)] <- ADD-02:cover/para3 (ADD-02 p1) |  |  | ADD-01 cover/para3 p1 | ADD-01 cover/para3 p1 | ADD-01 cover/para3 p1 | none stated in the documents |  |  | medium: verbatim; the reissued form's stated purpose ('paragraph 1') does not match its layout | ADD-02's cover repeats 'Bidders shall acknowledge receipt in Form 4-A.' and does not reissue the form; the ADD-01 App A version remains the one to use. | new at ADD-01; re-read by ADD-01/cover/para3 (adds_obligation; accepted by a person; not counted as a confirmation), ADD-02/cover/para3 (adds_obligation; accepted by a person; not counted as a confirmation); value as read: 'Bidders shall acknowledge receipt in Form 4-A.' | decided (recorded): I-F4A-FIELDS, I-NO-CONSEQUENCE | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/cover/para3: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/cover/para3: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | ADD-01:cover/para3 (ADD-01 p1; text layer; issued by ADD-01); ADD-01:AppA/addenda-acknowledged-numbers (ADD-01 p3; text layer; issued by ADD-01); ADD-01:AppA/para1 (ADD-01 p3; text layer; issued by ADD-01); ADD-02:cover/para3 (ADD-02 p1; text layer; issued by ADD-02); ADD-01/AppA/para1 [ADD-01; proposed] <- ADD-01:AppA/para1 (ADD-01 p3); ADD-01/cover/para3 [ADD-01; proposed; annotates ADD-01:cover/para3 (adds_obligation)] <- ADD-01:cover/para3 (ADD-01 p1); ADD-02/cover/para3 [ADD-02; proposed; annotates ADD-02:cover/para3 (adds_obligation)] <- ADD-02:cover/para3 (ADD-02 p1) | I-F4A-FIELDS; I-NO-CONSEQUENCE | <- REL-AI-002 [proposed depends_on] from ADD-03-cover-para3-01
ADD-01-Q4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | ADD-01:Q4 | site_conditions; risk; data_gap; new_in_addendum | ADD-01 Q4 confirms VOL-I 5.5 (satisfy yourselves as to ground conditions, asked for the wadi crossing) and adds a no-reliance statement: the data-room geotechnical report is provided for information | [ADD-01 Q4 p2; issued by ADD-01] No: 4 ¦ Bidder question: Can the Authority confirm the ground conditions at the wadi crossing? ¦ Authority response: The geotechnical report in the data room is provided for information. Bidders shall satisfy themselves as to ground conditions. | No: 4 ¦ Bidder question: Can the Authority confirm the ground conditions at the wadi crossing? ¦ Authority response: The geotechnical report in the data room is provided for information. Bidders shall satisfy themselves as to ground conditions. | Bidders shall satisfy themselves as to ground conditions. | ADD-01 Q4 p2 | ADD-01 Q4 p2 | procedural | Technical | Technical lead | EV-GROUND-DD | NOT ISSUED | NEW | ACTIVE | ACTIVE | status NOT ISSUED -> NEW. reading re-made at ADD-01: Confirms VOL-I 5.5 (row VOL-I-5.5-01; p3: 'does not relieve a Bidder of its obligation to satisfy itself as to site conditions') for the ground conditions asked about; adds a no-reliance statement on the geotechnical report ('provided for information'). The question concerned the wadi crossing (VOL-II 5.4: trenchless). The geotechnical report 'in the data room' is not in the pack, and Volume III (Drawings) is referenced but not supplied (I-VOL-III), so ground conditions cannot be assessed from the pack. No consequence stated. by ADD-01/Q4 [ADD-01; proposed; annotates ADD-01:Q4 (interprets)] <- ADD-01:Q4 (ADD-01 p2) | status NEW -> ACTIVE |  |  | ADD-01 Q4 p2 | ADD-01 Q4 p2 | ADD-01 Q4 p2 | none stated in the documents |  |  | medium: verbatim answer; the report it refers to and the drawings are not in the pack | Confirms VOL-I 5.5 (row VOL-I-5.5-01; p3: 'does not relieve a Bidder of its obligation to satisfy itself as to site conditions') for the ground conditions asked about; adds a no-reliance statement on the geotechnical report ('provided for information'). The question concerned the wadi crossing (VOL-II 5.4: trenchless). The geotechnical report 'in the data room' is not in the pack, and Volume III (Drawings) is referenced but not supplied (I-VOL-III), so ground conditions cannot be assessed from the pack. No consequence stated. | new at ADD-01; re-read by ADD-01/Q4 (interprets; accepted by a person; not counted as a confirmation); value as read: 'Bidders shall satisfy themselves as to ground conditions.' | decided (recorded): I-VOL-III | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/Q4: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | ADD-01:Q4 (ADD-01 p2; text layer; issued by ADD-01); ADD-01/Q4 [ADD-01; proposed; annotates ADD-01:Q4 (interprets)] <- ADD-01:Q4 (ADD-01 p2) | I-VOL-III
ADD-02-5.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | ADD-02:5.2 | technical_design; effluent; new_in_addendum | Reflect the amended Total Nitrogen limit (3 mg/l, ADD-02 5.1) in the process design submitted under Volume II Section 3 | [ADD-02 5.2 p1; issued by ADD-02] Bidders shall reflect the amended limit in the process design submitted under Volume II Section 3. [ADD-02 5.1 p1; issued by ADD-02] In Volume II Table 2-4, the limit for Total Nitrogen (TN) is amended from the value shown to 3 mg/l, assessed on the same basis. All other parameters in Table 2-4 are unchanged. | [ADD-02 5.2 p1] Bidders shall reflect the amended limit in the process design submitted under Volume II Section 3. [ADD-02 5.1 p1] In Volume II Table 2-4, the limit for Total Nitrogen (TN) is amended from the value shown to 3 mg/l, assessed on the same basis. All other parameters in Table 2-4 are unchanged. | Bidders shall reflect the amended limit in the process design submitted under Volume II Section 3. | ADD-02 5.2 p1 | ADD-02 5.2 p1; ADD-02 5.1 p1 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | NOT ISSUED | NOT ISSUED | NEW | ACTIVE |  | status NOT ISSUED -> NEW. reading re-made at ADD-02: The amended limit is '3 mg/l, assessed on the same basis' (ADD-02 5.1; row VOL-II-T2-4-TN). The old value and the basis exist only in the Table 2-4 image (transcription confirmed by the owner, 3 Oct 2026); the Environmental Permit prevails over the reproduction and is not supplied (I-PERMIT). No consequence stated | status NEW -> ACTIVE |  |  | ADD-02 5.2 p1 | ADD-02 5.2 p1 | none stated in the documents |  |  | medium: verbatim; the basis of assessment rests on the image reading (transcription confirmed by the owner, 3 Oct 2026) and the Permit is not supplied. An obligation with no consequence stated (I-NO-CONSEQUENCE): the pack states no rejection or non-responsiveness for a design that does not reflect the limit, and does not say whether the VOL-I 11.1(i) mandatory compliance check covers it; the process design it governs is marked under Table 1-1 criterion A 'Process design, treatment performance and compliance with Volume II' (25 marks, reissued by ADD-02 3.1; row VOL-I-T1-1-A), so it is classed scored, as VOL-II-3.1-01 is | The amended limit is '3 mg/l, assessed on the same basis' (ADD-02 5.1; row VOL-II-T2-4-TN). The old value and the basis exist only in the Table 2-4 image (transcription confirmed by the owner, 3 Oct 2026); the Environmental Permit prevails over the reproduction and is not supplied (I-PERMIT). No consequence stated. | new at ADD-02; value as read: 'Bidders shall reflect the amended limit in the process design submitted under Volume II Section 3.' | decided (recorded): I-PERMIT, I-READING-T24 | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | ADD-02:5.2 (ADD-02 p1; text layer; issued by ADD-02); ADD-02:5.1 (ADD-02 p1; text layer; issued by ADD-02) | I-PERMIT; I-READING-T24
ADD-02-T1-1-N3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | ADD-02:T1-1-rev | evaluation; scoring; new_in_addendum | Technical marks awarded on the Authority's 'standard five-point scale' and multiplied by the weight shown (reissued Table 1-1) | [ADD-02 T1-1-rev/note(3) p1; issued by ADD-02] (3) Marks are awarded on the Authority's standard five-point scale and multiplied by the weight shown. [ADD-02 T1-1-rev p1; issued by ADD-02] Table 1-1 (revised) — Technical evaluation criteria — Ref ¦ Criterion ¦ Marks | [ADD-02 T1-1-rev/note(3) p1] (3) Marks are awarded on the Authority's standard five-point scale and multiplied by the weight shown. [ADD-02 T1-1-rev p1] Table 1-1 (revised) — Technical evaluation criteria — Ref ¦ Criterion ¦ Marks | Marks are awarded on the Authority's standard five-point scale and multiplied by the weight shown. | ADD-02 T1-1-rev/note(3) p1 | ADD-02 T1-1-rev/note(3) p1; ADD-02 T1-1-rev p1 <- ADD-02/3.1 | scored | Bid management | Bid manager | EV-TECH-PROPOSAL | NOT ISSUED | NOT ISSUED | NEW | ACTIVE |  | status NOT ISSUED -> NEW. reading re-made at ADD-02: A new scoring method in a small-print note. The scale is not defined in the pack and the reissued table shows 'Marks', not weights; how it combines with the 70-mark threshold (VOL-I 11.3) is not stated. by ADD-02/3.1 [ADD-02; proposed] <- ADD-02:3.1 (ADD-02 p1); ADD-02/T1-1-rev/note(3) [ADD-02; proposed; annotates ADD-02:T1-1-rev (interprets)] <- ADD-02:T1-1-rev/note(3) (ADD-02 p1) | status NEW -> ACTIVE |  |  | ADD-02 T1-1-rev/note(3) p1 | ADD-02 T1-1-rev/note(3) p1 | none stated in the documents |  |  | medium: verbatim; the method it states cannot be applied from the pack | A new scoring method in a small-print note. The scale is not defined in the pack and the reissued table shows 'Marks', not weights; how it combines with the 70-mark threshold (VOL-I 11.3) is not stated. | new at ADD-02; re-read by ADD-02/T1-1-rev/note(3) (interprets; accepted by a person; not counted as a confirmation); value as read: 'Marks are awarded on the Authority's standard five-point scale and multiplied by the weight shown.' | decided (recorded): I-VOL-IV-SCALE | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/T1-1-rev/note(3): ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | ADD-02:T1-1-rev/note(3) (ADD-02 p1; text layer; issued by ADD-02); ADD-02:T1-1-rev (ADD-02 p1; text layer; issued by ADD-02); ADD-02/3.1 [ADD-02; proposed] <- ADD-02:3.1 (ADD-02 p1); ADD-02/T1-1-rev/note(3) [ADD-02; proposed; annotates ADD-02:T1-1-rev (interprets)] <- ADD-02:T1-1-rev/note(3) (ADD-02 p1) | I-VOL-IV-SCALE
ADD-02-F4G-02 | UNRESOLVED: STALE at ADD-03 (its reading was not re-made: ADD-02:7.2 changed since ADD-02 (by ADD-03/3.1(a))) | ADD-02:F4-G | forms; post_award; cybersecurity; new_in_addendum | Form 4-G undertaking 1: segregate the OT environment from any business network per VOL-II 6.2 (confirmed Yes or No) | [ADD-02 F4-G/T1/1 p3; issued by ADD-02] Item: 1 ¦ Undertaking: The operational technology environment will be segregated from any business network in accordance with Volume II Clause 6.2. ¦ Confirmed: Yes / No | Item: 1 ¦ Undertaking: The operational technology environment will be segregated from any business network in accordance with Volume II Clause 6.2. ¦ Confirmed: Yes / No | The operational technology environment will be segregated from any business network in accordance with Volume II Clause 6.2. | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/1) | ADD-02 F4-G/T1/1 p3 <- ADD-02/7.1 | contractual_post_award | Technical | Technical lead | EV-FORM-4G | NOT ISSUED | NOT ISSUED | NEW | ACTIVE (as amended by ADD-02/7.1) — STALE |  | status NOT ISSUED -> NEW. reading re-made at ADD-02: Restates VOL-II 6.2 as an undertaking. The effect of answering 'No' is not stated. by ADD-02/7.1 [ADD-02; proposed] <- ADD-02:7.1 (ADD-02 p3); ADD-02/7.2 [ADD-02; proposed; annotates ADD-02:F4-G/T1 (adds_obligation)] <- ADD-02:7.2 (ADD-02 p3) | status NEW -> ACTIVE (as amended by ADD-02/7.1) |  |  | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/1) | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/1) | none stated in the documents |  |  | medium: verbatim; the effect of answering 'No' is not stated | Restates VOL-II 6.2 as an undertaking. The effect of answering 'No' is not stated. | new at ADD-02; re-read by ADD-02/7.2 (adds_obligation; accepted by a person; not counted as a confirmation); value as read: 'The operational technology environment will be segregated from any business network in accordance with Volume II Clause…' | decided (recorded): I-F4G-NO | row: accepted by Interview demo assumption (2026-10-11) but CHANGED since: review again; ADD-02/7.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/7.2: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | accepted by Interview demo assumption (2026-10-11) but CHANGED since: review again | ADD-02/7.1: accepted | ADD-02:F4-G/T1/1 (ADD-02 p3; text layer; issued by ADD-02); ADD-02/7.1 [ADD-02; proposed] <- ADD-02:7.1 (ADD-02 p3); ADD-02/7.2 [ADD-02; proposed; annotates ADD-02:F4-G/T1 (adds_obligation)] <- ADD-02:7.2 (ADD-02 p3) | I-F4G-NO
ADD-02-F4G-03 | UNRESOLVED: STALE at ADD-03 (its reading was not re-made: ADD-02:7.2 changed since ADD-02 (by ADD-03/3.1(a))) | ADD-02:F4-G | forms; post_award; cybersecurity; new_in_addendum | Form 4-G undertaking 2: implement an information security management system covering the OT environment before commissioning | [ADD-02 F4-G/T1/2 p3; issued by ADD-02] Item: 2 ¦ Undertaking: An information security management system covering the operational technology environment will be implemented before commissioning. ¦ Confirmed: Yes / No | Item: 2 ¦ Undertaking: An information security management system covering the operational technology environment will be implemented before commissioning. ¦ Confirmed: Yes / No | An information security management system covering the operational technology environment will be implemented before commissioning. | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/2) | ADD-02 F4-G/T1/2 p3 <- ADD-02/7.1 | contractual_post_award | Technical | Technical lead | EV-FORM-4G | NOT ISSUED | NOT ISSUED | NEW | ACTIVE (as amended by ADD-02/7.1) — STALE |  | status NOT ISSUED -> NEW. reading re-made at ADD-02: Compare VOL-II 6.3 (implement and maintain the system; security architecture for review prior to commissioning). The effect of answering 'No' is not stated. by ADD-02/7.1 [ADD-02; proposed] <- ADD-02:7.1 (ADD-02 p3); ADD-02/7.2 [ADD-02; proposed; annotates ADD-02:F4-G/T1 (adds_obligation)] <- ADD-02:7.2 (ADD-02 p3) | status NEW -> ACTIVE (as amended by ADD-02/7.1) |  |  | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/2) | ADD-02 7.1 p3 (amending ADD-02 F4-G/T1/2) | none stated in the documents |  |  | medium: verbatim; the effect of answering 'No' is not stated | Compare VOL-II 6.3 (implement and maintain the system; security architecture for review prior to commissioning). The effect of answering 'No' is not stated. | new at ADD-02; re-read by ADD-02/7.2 (adds_obligation; accepted by a person; not counted as a confirmation); value as read: 'An information security management system covering the operational technology environment will be implemented before co…' | decided (recorded): I-F4G-NO | row: accepted by Interview demo assumption (2026-10-11) but CHANGED since: review again; ADD-02/7.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/7.2: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | accepted by Interview demo assumption (2026-10-11) but CHANGED since: review again | ADD-02/7.1: accepted | ADD-02:F4-G/T1/2 (ADD-02 p3; text layer; issued by ADD-02); ADD-02/7.1 [ADD-02; proposed] <- ADD-02:7.1 (ADD-02 p3); ADD-02/7.2 [ADD-02; proposed; annotates ADD-02:F4-G/T1 (adds_obligation)] <- ADD-02:7.2 (ADD-02 p3) | I-F4G-NO
ADD-02-F4G-04 | UNRESOLVED: STALE at ADD-03 (its reading was not re-made: ADD-02:7.2 changed since ADD-02 (by ADD-03/3.1(a))) | ADD-02:F4-G | envelope_A; forms; new_in_addendum | Sign Form 4-G for and on behalf of the Bidder, with name and date | [ADD-02 F4-G/para1 p3; issued by ADD-02] Signed for and on behalf of the Bidder: _______________________ Name: _______________________ Date: ____________ | Signed for and on behalf of the Bidder: _______________________ Name: _______________________ Date: ____________ | Signed for and on behalf of the Bidder | ADD-02 7.1 p3 (amending ADD-02 F4-G/para1) | ADD-02 F4-G/para1 p3 <- ADD-02/7.1 | pass_fail | Technical | Bid manager | EV-FORM-4G | NOT ISSUED | NOT ISSUED | NEW | ACTIVE (as amended by ADD-02/7.1) — STALE |  | status NOT ISSUED -> NEW. reading re-made at ADD-02: ADD-02 7.2 states non-responsiveness for failure to submit Form 4-G (row ADD-02-7.2-01); no consequence is stated for signing, and who may sign is not stated. by ADD-02/7.1 [ADD-02; proposed] <- ADD-02:7.1 (ADD-02 p3); ADD-02/7.2 [ADD-02; proposed; annotates ADD-02:F4-G/para1 (adds_obligation)] <- ADD-02:7.2 (ADD-02 p3) | status NEW -> ACTIVE (as amended by ADD-02/7.1) |  |  | ADD-02 7.1 p3 (amending ADD-02 F4-G/para1) | ADD-02 7.1 p3 (amending ADD-02 F4-G/para1) | none stated in the documents |  |  | high: verbatim signature line | ADD-02 7.2 states non-responsiveness for failure to submit Form 4-G (row ADD-02-7.2-01); no consequence is stated for signing, and who may sign is not stated. | new at ADD-02; re-read by ADD-02/7.2 (adds_obligation; accepted by a person; not counted as a confirmation); value as read: 'Signed for and on behalf of the Bidder' | decided (recorded): I-NO-CONSEQUENCE | row: accepted by Interview demo assumption (2026-10-11) but CHANGED since: review again; ADD-02/7.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/7.2: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | accepted by Interview demo assumption (2026-10-11) but CHANGED since: review again | ADD-02/7.1: accepted | ADD-02:F4-G/para1 (ADD-02 p3; text layer; issued by ADD-02); ADD-02/7.1 [ADD-02; proposed] <- ADD-02:7.1 (ADD-02 p3); ADD-02/7.2 [ADD-02; proposed; annotates ADD-02:F4-G/para1 (adds_obligation)] <- ADD-02:7.2 (ADD-02 p3) | I-NO-CONSEQUENCE
VOL-I-1.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:1.4 | eligibility; qualification | Only a Bidder prequalified under RFQ NUPA/ISTP/2025/031 and named in Appendix 1 may submit a Proposal | Only Bidders prequalified under Request for Qualification NUPA/ISTP/2025/031 and named in Appendix 1 to this Volume are eligible to submit a Proposal. A Proposal received from any other person shall be rejected without evaluation. | Only Bidders prequalified under Request for Qualification NUPA/ISTP/2025/031 and named in Appendix 1 to this Volume are eligible to submit a Proposal. A Proposal received from any other person shall be rejected without evaluation. | Only Bidders prequalified under Request for Qualification NUPA/ISTP/2025/031 and named in Appendix 1 to this Volume are eligible to submit a Proposal. | VOL-I 1.4 p2 | VOL-I 1.4 p2 | pass_fail | Bid management | Bid manager | none: an eligibility status (prequalified and named in Appendix 1), not a document; the Bidder submits in its prequalified name | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 1.4 p2 | VOL-I 1.4 p2 | VOL-I 1.4 p2 | VOL-I 1.4 p2 | rejection: "A Proposal received from any other person shall be rejected without evaluation." | VOL-I 1.4 p2 |  | high: verbatim; the Bidder's identity is an assumption, not a fact from the pack | Appendix 1 names five prequalified Bidders; which one is ours is a bidder fact. | unchanged since BASE; value as read: 'Only Bidders prequalified under Request for Qualification NUPA/ISTP/2025/031 and named in Appendix 1 to this Volume are…' | decided (recorded): I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:1.4 (VOL-I p2; text layer) | I-BIDDER-FACTS
VOL-I-3.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:3.3 | clarification; conflicts | Raise any conflict, ambiguity or discrepancy found in the RFP Documents as a clarification request under Section 5 | A Bidder that identifies a conflict, ambiguity or discrepancy shall raise it as a request for clarification under Section 5. A Bidder that resolves such a conflict unilaterally does so at its own risk, and the Authority shall not be bound by the Bidder's interpretation. | A Bidder that identifies a conflict, ambiguity or discrepancy shall raise it as a request for clarification under Section 5. A Bidder that resolves such a conflict unilaterally does so at its own risk, and the Authority shall not be bound by the Bidder's interpretation. | A Bidder that identifies a conflict, ambiguity or discrepancy shall raise it as a request for clarification under Section 5. | VOL-I 3.3 p2 | VOL-I 3.3 p2 | procedural | Bid management | Bid manager | EV-CLARIFICATIONS | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 3.3 p2 | VOL-I 3.3 p2 | VOL-I 3.3 p2 | VOL-I 3.3 p2 | lesser consequence: "A Bidder that resolves such a conflict unilaterally does so at its own risk, and the Authority shall not be bound by the Bidder's interpretation." | VOL-I 3.3 p2 |  | high: verbatim; the consequence ('at its own risk') is stated in the same clause | Conflicts found in the pack (Envelope B contents, Form 4-B contract value, concession term) fall under this clause; requests are subject to the VOL-I 5.2 cut-off. | unchanged since BASE; value as read: 'A Bidder that identifies a conflict, ambiguity or discrepancy shall raise it as a request for clarification under Secti…' | decided (recorded): I-VOL-I-ENV-B, I-VOL-I-ENV-A-PRICES, I-CONCESSION | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:3.3 (VOL-I p2; text layer) | I-VOL-I-ENV-B; I-VOL-I-ENV-A-PRICES; I-CONCESSION
VOL-I-3.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-15) | VOL-I:3.4 | clarification; completeness; deadline | Check the completeness of the RFP Documents downloaded from the Portal; omission claims are not entertained after the Proposal Due Date and time as amended (a cut-off separate from the VOL-I 5.2 clarification deadline) | Bidders shall satisfy themselves as to the completeness of the RFP Documents downloaded from the Portal. No claim arising from an alleged omission shall be entertained after the Proposal Due Date. | Bidders shall satisfy themselves as to the completeness of the RFP Documents downloaded from the Portal. No claim arising from an alleged omission shall be entertained after the Proposal Due Date. | Bidders shall satisfy themselves as to the completeness of the RFP Documents downloaded from the Portal. | VOL-I 3.4 p3 | VOL-I 3.4 p3 | procedural | Bid management | Bid manager | EV-CLARIFICATIONS | ACTIVE | ACTIVE | ACTIVE | ACTIVE | reading re-made at ADD-01: As directed by the owner on 3 Oct 2026 (worklog/2026-10-03_session-08_prompt.md §3): the cut-off for omission claims follows the amended Proposal Due Date and time; no claim arising from an alleged omission is entertained after 26 November 2026, 14:00 Riyadh time (VOL-I 3.4 with 2.6; ADD-01 2.1). It is a separate cut-off from the earlier clarification-request deadline of VOL-I 5.2 (ten Working Days before the Proposal Due Date, adjusted under ADD-01 2.2; row VOL-I-5.2-01): VOL-I 3.4 does not refer to 5.2 and the two are not merged. Whether to raise a known gap as a clarification request is a separate decision (the clarification register). [Applied from proposal P-S08-VOL-I-3.4-01 by Claude Code (assistant), on Ahmad's written instruction of 3 Oct 2026 (session 08 §3) on 2026-10-03.]. dates moved: OMISSION-CLAIM-CUTOFF 2026-11-12 -> 2026-11-26. by ADD-01/2.1 [ADD-01; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-01:2.1 (ADD-01 p1) |  | reading re-made at ADD-03: Re-made at ADD-03 because op ADD-03/2.1 changed VOL-I 6.1 (the PDD). The words of VOL-I 3.4 are unchanged. The owner's recorded direction of 3 Oct 2026 (session 08 §3) is carried forward unchanged: the omission-claim cut-off follows the amended Proposal Due Date and time, and it is a separate cut-off from the VOL-I 5.2 clarification deadline. Only the PDD it depends on has moved; it now reads 'Thursday 10 December 2026' at 14:00 hours Riyadh time. On the tool's computation, the VOL-I 5.2 clarification cut-off now falls on the date that was the omission-claim cut-off under ADD-01 (the ADD-01 PDD). The two cut-offs are still not merged. Volume III is still not supplied (I-VOL-III, kept as recorded; its interview_demo acceptance is not a resolution). [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed]. dates moved: OMISSION-CLAIM-CUTOFF 2026-11-26 -> 2026-12-10. by ADD-03/2.1 [ADD-03; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-03:2.1 (ADD-03 p1) | VOL-I 3.4 p3 | VOL-I 3.4 p3 | VOL-I 3.4 p3 | VOL-I 3.4 p3 | lesser consequence: "No claim arising from an alleged omission shall be entertained after the Proposal Due Date." | VOL-I 3.4 p3 | OMISSION-CLAIM-CUTOFF: 2026-11-26 (as_stated) | medium: verbatim; the cut-off moves with the PDD but this clause is not named in ADD-01 §2.2 (non-exhaustive list) | As directed by the owner on 3 Oct 2026 (worklog/2026-10-03_session-08_prompt.md §3): the cut-off for omission claims follows the amended Proposal Due Date and time; no claim arising from an alleged omission is entertained after 26 November 2026, 14:00 Riyadh time (VOL-I 3.4 with 2.6; ADD-01 2.1). It is a separate cut-off from the earlier clarification-request deadline of VOL-I 5.2 (ten Working Days before the Proposal Due Date, adjusted under ADD-01 2.2; row VOL-I-5.2-01): VOL-I 3.4 does not refer to 5.2 and the two are not merged. Whether to raise a known gap as a clarification request is a separate decision (the clarification register). [Applied from proposal P-S08-VOL-I-3.4-01 by Claude Code (assistant), on Ahmad's written instruction of 3 Oct 2026 (session 08 §3) on 2026-10-03.] | own words unchanged at ADD-01, but what it depends on changed (parameters; see A2); value as read: 'Bidders shall satisfy themselves as to the completeness of the RFP Documents downloaded from the Portal.' | decided (recorded): I-VOL-III | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:3.4 (VOL-I p3; text layer); ADD-01/2.1 [ADD-01; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-01:2.1 (ADD-01 p1); ADD-03/2.1 [ADD-03; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-03:2.1 (ADD-03 p1) | I-VOL-III
VOL-I-4.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:4.1 | communications; conduct | Make all communications with the Authority through the Portal, in English unless Volume I expressly requires Arabic | All communications between a Bidder and the Authority shall be made exclusively through the Portal and shall be in the English language, save where this Volume expressly requires Arabic. | All communications between a Bidder and the Authority shall be made exclusively through the Portal and shall be in the English language, save where this Volume expressly requires Arabic. | All communications between a Bidder and the Authority shall be made exclusively through the Portal and shall be in the English language, save where this Volume expressly requires Arabic. | VOL-I 4.1 p3 | VOL-I 4.1 p3 | procedural | Bid management | Bid manager | none: a rule on how every communication is made; no deliverable of its own | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 4.1 p3 | VOL-I 4.1 p3 | VOL-I 4.1 p3 | VOL-I 4.1 p3 | none stated in the documents |  |  | high: verbatim; no consequence stated (a procedural rule) |  | unchanged since BASE; value as read: 'All communications between a Bidder and the Authority shall be made exclusively through the Portal and shall be in the …' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:4.1 (VOL-I p3; text layer)
VOL-I-4.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:4.2 | communications; conduct; blackout | Blackout: no contact with the Authority's board, staff, consultants or advisors about the Project other than through the Portal, until the PBN | From the date of issue of this Volume until the issue of the Preferred Bidder Notification, no Bidder, and no person acting for a Bidder, shall contact any board member, officer, employee, consultant or advisor of the Authority in relation to the Project other than through the Portal. Breach of this Clause shall result in the disqualification of the Bidder. | From the date of issue of this Volume until the issue of the Preferred Bidder Notification, no Bidder, and no person acting for a Bidder, shall contact any board member, officer, employee, consultant or advisor of the Authority in relation to the Project other than through the Portal. Breach of this Clause shall result in the disqualification of the Bidder. | no Bidder, and no person acting for a Bidder, shall contact any board member, officer, employee, consultant or advisor of the Authority in relation to the Project other than through the Portal | VOL-I 4.2 p3 | VOL-I 4.2 p3 | pass_fail | Bid management | Bid manager | none: a conduct rule binding the Bidder and anyone acting for it; nothing to submit | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 4.2 p3 | VOL-I 4.2 p3 | VOL-I 4.2 p3 | VOL-I 4.2 p3 | disqualification: "Breach of this Clause shall result in the disqualification of the Bidder." | VOL-I 4.2 p3 | BLACKOUT-START: 2026-09-14 (as_stated); BLACKOUT-END: None (unknown_anchor) | high: verbatim; the window's end date depends on an event not yet known | The issue date (14 September 2026) is printed on the Volume I cover. The window ends at the Preferred Bidder Notification, an event not in the pack. | unchanged since BASE; value as read: 'no Bidder, and no person acting for a Bidder, shall contact any board member, officer, employee, consultant or advisor …' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:4.2 (VOL-I p3; text layer)
VOL-I-4.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:4.3 | communications | Nominate a single point of contact and notify the Authority of any change within two Working Days | Each Bidder shall nominate a single point of contact and shall notify the Authority of any change within two (2) Working Days. | Each Bidder shall nominate a single point of contact and shall notify the Authority of any change within two (2) Working Days. | Each Bidder shall nominate a single point of contact and shall notify the Authority of any change within two (2) Working Days. | VOL-I 4.3 p3 | VOL-I 4.3 p3 | procedural | Bid management | Bid manager | EV-SPOC | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 4.3 p3 | VOL-I 4.3 p3 | VOL-I 4.3 p3 | VOL-I 4.3 p3 | none stated in the documents |  | SPOC-CHANGE-NOTICE: None (unknown_anchor) | high: verbatim; the period runs from a change (an event), and forward Working Day counting is not defined |  | unchanged since BASE; value as read: 'Each Bidder shall nominate a single point of contact and shall notify the Authority of any change within two (2) Workin…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:4.3 (VOL-I p3; text layer)
VOL-I-5.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:5.1 | clarification | Submit clarification requests through the Portal, each citing the Volume, Clause and page it relates to | A Bidder may submit requests for clarification of the RFP Documents through the Portal. Each request shall cite the Volume, Clause and page to which it relates. | A Bidder may submit requests for clarification of the RFP Documents through the Portal. Each request shall cite the Volume, Clause and page to which it relates. | Each request shall cite the Volume, Clause and page to which it relates. | VOL-I 5.1 p3 | VOL-I 5.1 p3 | procedural | Bid management | Bid manager | EV-CLARIFICATIONS | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 5.1 p3 | VOL-I 5.1 p3 | VOL-I 5.1 p3 | VOL-I 5.1 p3 | none stated in the documents |  |  | high: verbatim; no consequence stated (a procedural rule) |  | unchanged since BASE; value as read: 'Each request shall cite the Volume, Clause and page to which it relates.' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:5.1 (VOL-I p3; text layer)
VOL-I-5.5-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:5.5 | site; risk | The Bidder must satisfy itself as to site conditions; attending the site visit is optional and does not relieve it of this | A site visit will be offered on the day following the Pre-Bid Conference. Attendance at the site visit is optional and does not relieve a Bidder of its obligation to satisfy itself as to site conditions. | A site visit will be offered on the day following the Pre-Bid Conference. Attendance at the site visit is optional and does not relieve a Bidder of its obligation to satisfy itself as to site conditions. | Attendance at the site visit is optional and does not relieve a Bidder of its obligation to satisfy itself as to site conditions. | VOL-I 5.5 p3 | VOL-I 5.5 p3 | procedural | Technical | Technical lead | none: a risk the Bidder carries; the site visit (the day after the Pre-Bid Conference) was optional | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 5.5 p3 | VOL-I 5.5 p3 | VOL-I 5.5 p3 | VOL-I 5.5 p3 | none stated in the documents |  |  | medium: the clause refers to the obligation rather than stating it; no consequence stated | ADD-01 Q4 (ground conditions at the wadi crossing) states the same for ground conditions; the geotechnical report is in the data room, not the pack. | unchanged since BASE; value as read: 'Attendance at the site visit is optional and does not relieve a Bidder of its obligation to satisfy itself as to site c…' | decided (recorded): I-VOL-III | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:5.5 (VOL-I p3; text layer) | I-VOL-III
VOL-I-6.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:6.2 | bid_submission; envelopes | Submit the Proposal in two separately sealed, clearly marked envelopes: A (Technical Proposal) and B (Commercial Proposal) | Each Proposal shall be submitted in two separately sealed and clearly marked envelopes: Envelope A (Technical Proposal) and Envelope B (Commercial Proposal). The appearance of any price, rate, or other commercial information within Envelope A shall render the Proposal non-responsive. | Each Proposal shall be submitted in two separately sealed and clearly marked envelopes: Envelope A (Technical Proposal) and Envelope B (Commercial Proposal). The appearance of any price, rate, or other commercial information within Envelope A shall render the Proposal non-responsive. | Each Proposal shall be submitted in two separately sealed and clearly marked envelopes: Envelope A (Technical Proposal) and Envelope B (Commercial Proposal). | VOL-I 6.2 p3 | VOL-I 6.2 p3 | pass_fail | Bid management | Bid manager | EV-DELIVERY | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 6.2 p3 | VOL-I 6.2 p3 | VOL-I 6.2 p3 | VOL-I 6.2 p3 | none stated in the documents |  |  | high: verbatim; no consequence stated for the envelopes themselves | The marking wording is not stated here; Appendix 3 gives a marking (row VOL-I-App3-01). | unchanged since BASE; value as read: 'Each Proposal shall be submitted in two separately sealed and clearly marked envelopes: Envelope A (Technical Proposal)…' | decided (recorded): I-NO-CONSEQUENCE | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:6.2 (VOL-I p3; text layer) | I-NO-CONSEQUENCE
VOL-I-6.2-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:6.2 | envelope_A; commercial_separation | No price, rate or other commercial information anywhere in Envelope A | Each Proposal shall be submitted in two separately sealed and clearly marked envelopes: Envelope A (Technical Proposal) and Envelope B (Commercial Proposal). The appearance of any price, rate, or other commercial information within Envelope A shall render the Proposal non-responsive. | Each Proposal shall be submitted in two separately sealed and clearly marked envelopes: Envelope A (Technical Proposal) and Envelope B (Commercial Proposal). The appearance of any price, rate, or other commercial information within Envelope A shall render the Proposal non-responsive. | The appearance of any price, rate, or other commercial information within Envelope A | VOL-I 6.2 p3 | VOL-I 6.2 p3 | pass_fail | Commercial | Commercial lead | none: a check on the content of every Envelope A document, not a deliverable of its own | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 6.2 p3 | VOL-I 6.2 p3 | VOL-I 6.2 p3 | VOL-I 6.2 p3 | non-responsive: "The appearance of any price, rate, or other commercial information within Envelope A shall render the Proposal non-responsive." | VOL-I 6.2 p3 |  | medium: verbatim consequence; the scope of 'other commercial information' is not defined and Form 4-B conflicts | 'Other commercial information' is not defined. Form 4-B (Envelope A) asks for a contract value in SAR: see I-VOL-I-ENV-A-PRICES. | unchanged since BASE; value as read: 'The appearance of any price, rate, or other commercial information within Envelope A' | decided (recorded): I-VOL-I-ENV-A-PRICES, I-FORM-4E-COMMERCIAL-QUALIFICATION | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:6.2 (VOL-I p3; text layer) | I-VOL-I-ENV-A-PRICES; I-FORM-4E-COMMERCIAL-QUALIFICATION (the issue names the row (curated, PROPOSED))
VOL-I-6.5-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:6.5 | bid_submission; copies | Submit one marked original, three hard copies and one searchable electronic copy on encrypted USB media | Each Proposal shall be submitted as one (1) marked original, three (3) hard copies, and one (1) searchable electronic copy on encrypted USB media. Electronic files shall be named strictly in accordance with the convention at Appendix 2. A Proposal whose electronic copy materially differs from the marked original shall be evaluated on the basis of the marked original. | Each Proposal shall be submitted as one (1) marked original, three (3) hard copies, and one (1) searchable electronic copy on encrypted USB media. Electronic files shall be named strictly in accordance with the convention at Appendix 2. A Proposal whose electronic copy materially differs from the marked original shall be evaluated on the basis of the marked original. | Each Proposal shall be submitted as one (1) marked original, three (3) hard copies, and one (1) searchable electronic copy on encrypted USB media. | VOL-I 6.5 p3 | VOL-I 6.5 p3 | pass_fail | Bid management | Bid manager | EV-COPIES | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 6.5 p3 | VOL-I 6.5 p3 | VOL-I 6.5 p3 | VOL-I 6.5 p3 | none stated in the documents |  |  | medium: verbatim; whether the copies are per envelope or per Proposal is not stated; no consequence stated | Where the electronic copy materially differs, the marked original is evaluated (same clause); that is a rule of precedence, not a bid-out consequence. | unchanged since BASE; value as read: 'Each Proposal shall be submitted as one (1) marked original, three (3) hard copies, and one (1) searchable electronic c…' | decided (recorded): I-NO-CONSEQUENCE, I-VOL-I-COPIES | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:6.5 (VOL-I p3; text layer) | I-NO-CONSEQUENCE; I-VOL-I-COPIES
VOL-I-6.5-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:6.5 | bid_submission; electronic_copy; file_naming | Name electronic files per the Appendix 2 convention (pattern, folder depth up to 3 levels, names up to 120 characters) | [VOL-I 6.5 p3] Each Proposal shall be submitted as one (1) marked original, three (3) hard copies, and one (1) searchable electronic copy on encrypted USB media. Electronic files shall be named strictly in accordance with the convention at Appendix 2. A Proposal whose electronic copy materially differs from the marked original shall be evaluated on the basis of the marked original. [VOL-I App2/para1 p7] Files shall be named: ISTP2026-014_[BIDDER]_[ENV]_[VOL]_[NN]_[YYYYMMDD].pdf where [ENV] is A or B, [VOL] is the volume or form reference, and [NN] is a two-digit sequence. Folder depth shall not exceed three levels. File names shall not exceed 120 characters. Non-conforming file names will be corrected by the Authority at the Bidder's risk. | [VOL-I 6.5 p3] Each Proposal shall be submitted as one (1) marked original, three (3) hard copies, and one (1) searchable electronic copy on encrypted USB media. Electronic files shall be named strictly in accordance with the convention at Appendix 2. A Proposal whose electronic copy materially differs from the marked original shall be evaluated on the basis of the marked original. [VOL-I App2/para1 p7] Files shall be named: ISTP2026-014_[BIDDER]_[ENV]_[VOL]_[NN]_[YYYYMMDD].pdf where [ENV] is A or B, [VOL] is the volume or form reference, and [NN] is a two-digit sequence. Folder depth shall not exceed three levels. File names shall not exceed 120 characters. Non-conforming file names will be corrected by the Authority at the Bidder's risk. | Electronic files shall be named strictly in accordance with the convention at Appendix 2. | VOL-I 6.5 p3 | VOL-I 6.5 p3; VOL-I App2/para1 p7 | procedural | Bid management | Bid manager | EV-COPIES | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 6.5 p3 | VOL-I 6.5 p3 | VOL-I 6.5 p3 | VOL-I 6.5 p3 | lesser consequence: "Non-conforming file names will be corrected by the Authority at the Bidder's risk." | VOL-I App2/para1 p7 |  | medium: verbatim; the '.pdf' pattern cannot fit the Excel Financial Model and [YYYYMMDD] is not explained |  | unchanged since BASE; value as read: 'Electronic files shall be named strictly in accordance with the convention at Appendix 2.' | decided (recorded): I-VOL-I-FILE-NAMES | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:6.5 (VOL-I p3; text layer); VOL-I:App2/para1 (VOL-I p7; text layer) | I-VOL-I-FILE-NAMES
VOL-I-6.7-01 | DECIDED: accepted by Interview demo assumption (2026-10-15) | VOL-I:6.7 | bid_submission; deadline | A withdrawal or modification of the Proposal may be made by written notice through the Portal at any time before the Proposal Due Date; no modification will be accepted thereafter | A Bidder may withdraw or modify its Proposal at any time before the Proposal Due Date by written notice through the Portal. No modification will be accepted thereafter. | A Bidder may withdraw or modify its Proposal at any time before the Proposal Due Date by written notice through the Portal. No modification will be accepted thereafter. | A Bidder may withdraw or modify its Proposal at any time before the Proposal Due Date by written notice through the Portal. | VOL-I 6.7 p3 | VOL-I 6.7 p3 | procedural | Bid management | Bid manager | none: an option: arises only if the Bidder withdraws or modifies its Proposal | ACTIVE | ACTIVE | ACTIVE | ACTIVE | reading re-made at ADD-01: As directed by the owner on 3 Oct 2026 (worklog/2026-10-03_session-08_prompt.md §3): a Bidder may withdraw or modify its Proposal by written notice through the Portal at any time before the amended Proposal Due Date, 26 November 2026, 14:00 Riyadh time (VOL-I 6.7 with 2.6; ADD-01 2.1). The clause's express prohibition after that time concerns modifications only ('No modification will be accepted thereafter'); it is not extended to withdrawals, and nothing further is read into it. [Applied from proposal P-S08-VOL-I-6.7-01 by Claude Code (assistant), on Ahmad's written instruction of 3 Oct 2026 (session 08 §3) on 2026-10-03.]. dates moved: MODIFY-CUTOFF 2026-11-12 -> 2026-11-26. by ADD-01/2.1 [ADD-01; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-01:2.1 (ADD-01 p1) |  | reading re-made at ADD-03: VOL-I 6.7 is printed unchanged at ADD-03. Its cut-off is the Proposal Due Date, which ADD-03 2.1 (op ADD-03/2.1, proposed) moves in VOL-I 6.1 to 'Thursday 10 December 2026'. The time is unchanged: '14:00 hours Riyadh time'. The owner's session-08 direction on this row is carried with the same substance: the express prohibition after the cut-off concerns modifications only and is not extended to withdrawals. That direction named the earlier date, 26 November 2026; a person decides whether it carries over to the date as amended by ADD-03 (issue I-ADD03-PDD-OWNER-DIRECTIONS). The date rule MODIFY-CUTOFF (anchor PDD) is unchanged, and the program computes it from the amended anchor; no date is typed here. no_deliverable is unchanged (an option). [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed]. dates moved: MODIFY-CUTOFF 2026-11-26 -> 2026-12-10. by ADD-03/2.1 [ADD-03; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-03:2.1 (ADD-03 p1) | VOL-I 6.7 p3 | VOL-I 6.7 p3 | VOL-I 6.7 p3 | VOL-I 6.7 p3 | lesser consequence: "No modification will be accepted thereafter." | VOL-I 6.7 p3 | MODIFY-CUTOFF: 2026-11-26 (as_stated) | high: verbatim; the cut-off moves with the PDD although ADD-01 §2.2 does not name this clause | As directed by the owner on 3 Oct 2026 (worklog/2026-10-03_session-08_prompt.md §3): a Bidder may withdraw or modify its Proposal by written notice through the Portal at any time before the amended Proposal Due Date, 26 November 2026, 14:00 Riyadh time (VOL-I 6.7 with 2.6; ADD-01 2.1). The clause's express prohibition after that time concerns modifications only ('No modification will be accepted thereafter'); it is not extended to withdrawals, and nothing further is read into it. [Applied from proposal P-S08-VOL-I-6.7-01 by Claude Code (assistant), on Ahmad's written instruction of 3 Oct 2026 (session 08 §3) on 2026-10-03.] | own words unchanged at ADD-01, but what it depends on changed (parameters; see A2); value as read: 'A Bidder may withdraw or modify its Proposal at any time before the Proposal Due Date by written notice through the Por…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:6.7 (VOL-I p3; text layer); ADD-01/2.1 [ADD-01; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-01:2.1 (ADD-01 p1); ADD-03/2.1 [ADD-03; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-03:2.1 (ADD-03 p1)
VOL-I-7.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:7.2 | validity; bid_security | If the Bidder agrees to an Authority request to extend validity, procure a corresponding extension of its Bid Bond | The Authority may, before expiry of the validity period, request Bidders to extend validity. A Bidder may refuse without forfeiting its Bid Bond; a Bidder that agrees shall procure a corresponding extension of its Bid Bond. | The Authority may, before expiry of the validity period, request Bidders to extend validity. A Bidder may refuse without forfeiting its Bid Bond; a Bidder that agrees shall procure a corresponding extension of its Bid Bond. | a Bidder that agrees shall procure a corresponding extension of its Bid Bond | VOL-I 7.2 p4 | VOL-I 7.2 p4 | procedural | Commercial | Commercial lead | none: conditional: arises only if the Authority requests an extension and the Bidder agrees (refusal is allowed) | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 7.2 p4 | VOL-I 7.2 p4 | VOL-I 7.2 p4 | VOL-I 7.2 p4 | none stated in the documents |  |  | high: verbatim; no consequence stated for failing to procure the extension | A Bidder may refuse without forfeiting its Bid Bond (same clause): the absence of a consequence, not a consequence. | unchanged since BASE; value as read: 'a Bidder that agrees shall procure a corresponding extension of its Bid Bond' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:7.2 (VOL-I p4; text layer)
VOL-I-8.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:8.1 | qualification; consortium | Bid as the prequalified entity or consortium; no change to composition, shareholding or lead member without the Authority's prior written consent | A Bidder shall be either a single entity or a consortium, in each case prequalified under the RFQ. No change to the composition, shareholding or lead member of a prequalified consortium shall be effective without the prior written consent of the Authority. An unapproved change shall result in rejection of the Proposal. | A Bidder shall be either a single entity or a consortium, in each case prequalified under the RFQ. No change to the composition, shareholding or lead member of a prequalified consortium shall be effective without the prior written consent of the Authority. An unapproved change shall result in rejection of the Proposal. | No change to the composition, shareholding or lead member of a prequalified consortium shall be effective without the prior written consent of the Authority. | VOL-I 8.1 p4 | VOL-I 8.1 p4 | pass_fail | Legal | Legal counsel | none: a status (the consortium as prequalified); the Authority's written consent is needed only before any change | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 8.1 p4 | VOL-I 8.1 p4 | VOL-I 8.1 p4 | VOL-I 8.1 p4 | rejection: "An unapproved change shall result in rejection of the Proposal." | VOL-I 8.1 p4 |  | high: verbatim; the consortium's composition is a bidder fact |  | unchanged since BASE; value as read: 'No change to the composition, shareholding or lead member of a prequalified consortium shall be effective without the p…' | decided (recorded): I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:8.1 (VOL-I p4; text layer) | I-BIDDER-FACTS
VOL-I-8.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:8.2 | qualification; conduct; multiple_participation | No firm or affiliate of a member may participate in more than one Proposal | No firm, and no affiliate of a firm, shall participate in more than one Proposal. Participation in more than one Proposal shall cause every Proposal in which that firm or affiliate participates to be rejected. | No firm, and no affiliate of a firm, shall participate in more than one Proposal. Participation in more than one Proposal shall cause every Proposal in which that firm or affiliate participates to be rejected. | No firm, and no affiliate of a firm, shall participate in more than one Proposal. | VOL-I 8.2 p4 | VOL-I 8.2 p4 | pass_fail | Legal | Legal counsel | EV-FORM-4C | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 8.2 p4 | VOL-I 8.2 p4 | VOL-I 8.2 p4 | VOL-I 8.2 p4 | rejection: "Participation in more than one Proposal shall cause every Proposal in which that firm or affiliate participates to be rejected." | VOL-I 8.2 p4 |  | high: verbatim; 'affiliate' is not defined | Form 4-C declaration 2 (Arabic, image reading; transcription confirmed by the owner, 3 Oct 2026) declares this; 'affiliate' is not defined in the pack. | unchanged since BASE; value as read: 'No firm, and no affiliate of a firm, shall participate in more than one Proposal.' | decided (recorded): I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:8.2 (VOL-I p4; text layer) | I-BIDDER-FACTS | <- REL-MEMBER-MULTIPLE-PARTICIPATION [confirmed member_scope] from VOL-I:8.1, words:member of the Bidder, words:consortium member, words:member of the consortium
VOL-I-8.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:8.4 | qualification; financial; envelope_A | Combined tangible net worth (weighted by shareholding) of at least SAR 800,000,000 per the most recent audited statements | The Bidder shall demonstrate, on a combined basis across consortium members weighted by shareholding, (a) a consolidated tangible net worth of not less than SAR 800,000,000 as at the most recent audited financial statements, and (b) an average annual turnover over the last three (3) audited financial years of not less than SAR 1,200,000,000. | The Bidder shall demonstrate, on a combined basis across consortium members weighted by shareholding, (a) a consolidated tangible net worth of not less than SAR 800,000,000 as at the most recent audited financial statements, and (b) an average annual turnover over the last three (3) audited financial years of not less than SAR 1,200,000,000. | (a) a consolidated tangible net worth of not less than SAR 800,000,000 as at the most recent audited financial statements | VOL-I 8.4 p4 | VOL-I 8.4 p4 | pass_fail | Finance | Financial modeller | EV-FIN-STANDING | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 8.4 p4 | VOL-I 8.4 p4 | VOL-I 8.4 p4 | VOL-I 8.4 p4 | none stated in the documents |  |  | medium: verbatim; how the shareholding weighting is applied and which statements count as most recent are not stated |  | unchanged since BASE; value as read: '(a) a consolidated tangible net worth of not less than SAR 800,000,000 as at the most recent audited financial statemen…' | decided (recorded): I-NO-CONSEQUENCE, I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:8.4 (VOL-I p4; text layer) | I-NO-CONSEQUENCE; I-BIDDER-FACTS | <- REL-MEMBER-FIN-STANDING [confirmed member_scope] from VOL-I:8.1, words:member of the Bidder, words:consortium member, words:member of the consortium
VOL-I-8.4-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:8.4 | qualification; financial; envelope_A | Combined average annual turnover (weighted by shareholding) over the last three audited years of at least SAR 1,200,000,000 | The Bidder shall demonstrate, on a combined basis across consortium members weighted by shareholding, (a) a consolidated tangible net worth of not less than SAR 800,000,000 as at the most recent audited financial statements, and (b) an average annual turnover over the last three (3) audited financial years of not less than SAR 1,200,000,000. | The Bidder shall demonstrate, on a combined basis across consortium members weighted by shareholding, (a) a consolidated tangible net worth of not less than SAR 800,000,000 as at the most recent audited financial statements, and (b) an average annual turnover over the last three (3) audited financial years of not less than SAR 1,200,000,000. | (b) an average annual turnover over the last three (3) audited financial years of not less than SAR 1,200,000,000 | VOL-I 8.4 p4 | VOL-I 8.4 p4 | pass_fail | Finance | Financial modeller | EV-FIN-STANDING | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 8.4 p4 | VOL-I 8.4 p4 | VOL-I 8.4 p4 | VOL-I 8.4 p4 | none stated in the documents |  |  | medium: verbatim; how the shareholding weighting is applied is not stated |  | unchanged since BASE; value as read: '(b) an average annual turnover over the last three (3) audited financial years of not less than SAR 1,200,000,000' | decided (recorded): I-NO-CONSEQUENCE, I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:8.4 (VOL-I p4; text layer) | I-NO-CONSEQUENCE; I-BIDDER-FACTS | <- REL-MEMBER-FIN-STANDING [confirmed member_scope] from VOL-I:8.1, words:member of the Bidder, words:consortium member, words:member of the consortium
VOL-I-8.7-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:8.7 | qualification; guarantee; envelope_A | Executed Parent Company Guarantee from the EPC Contractor's ultimate parent, substantially in Form 4-D, unconditional for the construction period | [VOL-I 8.7 p4] The Bidder shall submit an executed Parent Company Guarantee from the ultimate parent company of the proposed EPC Contractor, substantially in the form set out in Form 4-D, unconditional as to the EPC Contractor's obligations during the construction period. [VOL-I 9.1(d) p4] (d) Form 4-D — Parent Company Guarantee (executed); | [VOL-I 8.7 p4] The Bidder shall submit an executed Parent Company Guarantee from the ultimate parent company of the proposed EPC Contractor, substantially in the form set out in Form 4-D, unconditional as to the EPC Contractor's obligations during the construction period. [VOL-I 9.1(d) p4] (d) Form 4-D — Parent Company Guarantee (executed); | The Bidder shall submit an executed Parent Company Guarantee from the ultimate parent company of the proposed EPC Contractor, substantially in the form set out in Form 4-D | VOL-I 8.7 p4 | VOL-I 8.7 p4; VOL-I 9.1(d) p4 | pass_fail | Legal | Legal counsel | EV-FORM-4D | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q10: required from the ultimate parent of the EPC Contractor only, not from the O&M Operator; no change to this row. by ADD-02/Q10 [ADD-02; proposed; annotates VOL-I:8.7 (confirms)] <- ADD-02:Q10 (ADD-02 p2) |  | VOL-I 8.7 p4 | VOL-I 8.7 p4 | VOL-I 8.7 p4 | VOL-I 8.7 p4 | none stated in the documents |  |  | high: verbatim; confirmed by ADD-02 Q10 (no consequence stated) | ADD-02 Q10: required from the ultimate parent of the EPC Contractor only, not from the O&M Operator; no change to this row. | unchanged since BASE; re-read by ADD-02/Q10 (confirms; accepted by a person; not counted as a confirmation); value as read: 'The Bidder shall submit an executed Parent Company Guarantee from the ultimate parent company of the proposed EPC Contr…' | decided (recorded): I-NO-CONSEQUENCE | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/Q10: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:8.7 (VOL-I p4; text layer); VOL-I:9.1(d) (VOL-I p4; text layer); ADD-02/Q10 [ADD-02; proposed; annotates VOL-I:8.7 (confirms)] <- ADD-02:Q10 (ADD-02 p2) | I-NO-CONSEQUENCE
VOL-I-8.8-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:8.8 | qualification; operations; envelope_A | O&M Operator: at least five years' continuous operation of a wastewater treatment facility of at least 50,000 m3/day | The proposed O&M Operator shall evidence not less than five (5) years of continuous operation of at least one (1) wastewater treatment facility of nominal capacity not less than 50,000 m³/day. | The proposed O&M Operator shall evidence not less than five (5) years of continuous operation of at least one (1) wastewater treatment facility of nominal capacity not less than 50,000 m³/day. | shall evidence not less than five (5) years of continuous operation of at least one (1) wastewater treatment facility of nominal capacity not less than 50,000 | VOL-I 8.8 p4 | VOL-I 8.8 p4 | pass_fail | Operations | O&M lead | EV-OM-EXPERIENCE | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 8.8 p4 | VOL-I 8.8 p4 | VOL-I 8.8 p4 | VOL-I 8.8 p4 | none stated in the documents |  |  | high: verbatim; no consequence stated; the period's end date is not stated |  | unchanged since BASE; value as read: 'shall evidence not less than five (5) years of continuous operation of at least one (1) wastewater treatment facility o…' | decided (recorded): I-NO-CONSEQUENCE, I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:8.8 (VOL-I p4; text layer) | I-NO-CONSEQUENCE; I-BIDDER-FACTS
VOL-I-8.9-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:8.9 | qualification; licensing; envelope_A | For each foreign member: a current investment licence, or a signed undertaking to obtain one before Financial Close | The Bidder shall submit either evidence of a current investment licence for each foreign consortium member, or a signed undertaking to obtain such licence prior to Financial Close. | The Bidder shall submit either evidence of a current investment licence for each foreign consortium member, or a signed undertaking to obtain such licence prior to Financial Close. | The Bidder shall submit either evidence of a current investment licence for each foreign consortium member, or a signed undertaking to obtain such licence prior to Financial Close. | VOL-I 8.9 p4 | VOL-I 8.9 p4 | pass_fail | Legal | Legal counsel | EV-INVESTMENT-LICENCE | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 8.9 p4 | VOL-I 8.9 p4 | VOL-I 8.9 p4 | VOL-I 8.9 p4 | none stated in the documents |  | INVESTMENT-LICENCE-BY-FC: None (unknown_anchor) | high: verbatim; which members are foreign is a bidder fact; no consequence stated |  | unchanged since BASE; value as read: 'The Bidder shall submit either evidence of a current investment licence for each foreign consortium member, or a signed…' | decided (recorded): I-NO-CONSEQUENCE, I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:8.9 (VOL-I p4; text layer) | I-NO-CONSEQUENCE; I-BIDDER-FACTS | <- REL-MEMBER-INVESTMENT-LICENCE [confirmed member_scope] from VOL-I:8.1, words:member of the Bidder, words:consortium member, words:member of the consortium
VOL-I-8.10-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:8.10 | qualification; debarment; envelope_A | No member debarred by a public authority in the Kingdom now or in the preceding five years; declared in Form 4-C | No member of the Bidder shall be the subject of, or have been the subject of within the preceding five (5) years, any debarment by a public authority in the Kingdom. A declaration to this effect shall be given in Form 4-C. | No member of the Bidder shall be the subject of, or have been the subject of within the preceding five (5) years, any debarment by a public authority in the Kingdom. A declaration to this effect shall be given in Form 4-C. | No member of the Bidder shall be the subject of, or have been the subject of within the preceding five (5) years, any debarment by a public authority in the Kingdom. | VOL-I 8.10 p4 | VOL-I 8.10 p4 | pass_fail | Legal | Legal counsel | EV-FORM-4C | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 8.10 p4 | VOL-I 8.10 p4 | VOL-I 8.10 p4 | VOL-I 8.10 p4 | none stated in the documents |  | DEBARMENT-LOOKBACK: None (unknown_anchor) | medium: verbatim; the look-back's reference date is not stated; no consequence stated in this clause | The same clause requires the declaration in Form 4-C. The date the five years run back from is not stated (external rule, not computed). | unchanged since BASE; value as read: 'No member of the Bidder shall be the subject of, or have been the subject of within the preceding five (5) years, any d…' | decided (recorded): I-NO-CONSEQUENCE, I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:8.10 (VOL-I p4; text layer) | I-NO-CONSEQUENCE; I-BIDDER-FACTS | <- REL-MEMBER-DEBARMENT [confirmed member_scope] from VOL-I:8.1, words:member of the Bidder, words:consortium member, words:member of the consortium
VOL-I-9.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:9.1 | envelope_A; order | Envelope A contains items (a) to (i) in the stated order, separated by numbered dividers | [VOL-I 9.1 p4] Envelope A shall contain, in the following order and separated by numbered dividers: [VOL-I 9.1(a) p4] (a) Form 4-A — Proposal Submission Letter; [VOL-I 9.1(b) p4] (b) Form 4-B — Reference Projects Schedule (one per reference project); [VOL-I 9.1(c) p4] (c) Form 4-C — Conflict of Interest and Debarment Declaration; [VOL-I 9.1(d) p4] (d) Form 4-D — Parent Company Guarantee (executed); [VOL-I 9.1(e) p4] (e) Form 4-E — Schedule of Deviations; [ADD-02 p3 (inserted after VOL-I 9.1(e), p4); issued by ADD-02] FORM 4-G — CYBERSECURITY COMPLIANCE UNDERTAKING [VOL-I 9.1(f) p4] (f) the Technical Proposal narrative; [VOL-I 9.1(g) p4] (g) the Bid Bond; [VOL-I 9.1(h) p4] (h) notarised Powers of Attorney for each signatory; [VOL-I 9.1(i) p4] (i) the certificates and evidence required under Section 8. | [VOL-I 9.1 p4] Envelope A shall contain, in the following order and separated by numbered dividers: [VOL-I 9.1(a) p4] (a) Form 4-A — Proposal Submission Letter; [VOL-I 9.1(b) p4] (b) Form 4-B — Reference Projects Schedule (one per reference project); [VOL-I 9.1(c) p4] (c) Form 4-C — Conflict of Interest and Debarment Declaration; [VOL-I 9.1(d) p4] (d) Form 4-D — Parent Company Guarantee (executed); [VOL-I 9.1(e) p4] (e) Form 4-E — Schedule of Deviations; [ADD-02 p3 (inserted after VOL-I 9.1(e), p4)] FORM 4-G — CYBERSECURITY COMPLIANCE UNDERTAKING [VOL-I 9.1(f) p4] (f) the Technical Proposal narrative; [VOL-I 9.1(g) p4] (g) the Bid Bond; [VOL-I 9.1(h) p4] (h) notarised Powers of Attorney for each signatory; [VOL-I 9.1(i) p4] (i) the certificates and evidence required under Section 8. | Envelope A shall contain, in the following order and separated by numbered dividers | VOL-I 9.1 p4 | VOL-I 9.1 p4; VOL-I 9.1(a) p4; VOL-I 9.1(b) p4; VOL-I 9.1(c) p4; VOL-I 9.1(d) p4; VOL-I 9.1(e) p4; ADD-02 p3 (inserted after VOL-I 9.1(e), p4) <- ADD-02/7.1; VOL-I 9.1(f) p4; VOL-I 9.1(g) p4; VOL-I 9.1(h) p4; VOL-I 9.1(i) p4 | pass_fail | Bid management | Bid manager | EV-DELIVERY | ACTIVE | ACTIVE | AMENDED (ADD-02/7.1) | ACTIVE (as amended by ADD-02/7.1) |  | status ACTIVE -> AMENDED (ADD-02/7.1). reading re-made at ADD-02: ADD-02 §7.1 inserts Form 4-G after item (e) (row ADD-02-7.2-01); the re-lettering of the later items is not stated. Item (i), 'the certificates and evidence required under Section 8', again includes the Local Content Certificate: ADD-01 4.1 deleted VOL-I 8.6 (the certificate left this list at ADD-01) and ADD-02 9.1 reinstates it at 35% (row VOL-I-8.6-01). by ADD-02/7.1 [ADD-02; proposed] <- ADD-02:7.1 (ADD-02 p3) | status AMENDED (ADD-02/7.1) -> ACTIVE (as amended by ADD-02/7.1) | VOL-I 9.1 p4 | VOL-I 9.1 p4 | VOL-I 9.1 p4 | VOL-I 9.1 p4 | none stated in the documents |  |  | medium: verbatim; no consequence stated; the lettering after ADD-02's insertion is not stated | ADD-02 §7.1 inserts Form 4-G after item (e) (row ADD-02-7.2-01); the re-lettering of the later items is not stated. Item (i), 'the certificates and evidence required under Section 8', again includes the Local Content Certificate: ADD-01 4.1 deleted VOL-I 8.6 (the certificate left this list at ADD-01) and ADD-02 9.1 reinstates it at 35% (row VOL-I-8.6-01). | amended at ADD-02 by ADD-02/7.1 (an item inserted; the quoted words unchanged); value as read: 'Envelope A shall contain, in the following order and separated by numbered dividers' | decided (recorded): I-NO-CONSEQUENCE, I-F4G-LETTERING | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/7.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-02/7.1: accepted | VOL-I:9.1 (VOL-I p4; text layer); VOL-I:9.1(a) (VOL-I p4; text layer); VOL-I:9.1(b) (VOL-I p4; text layer); VOL-I:9.1(c) (VOL-I p4; text layer); VOL-I:9.1(d) (VOL-I p4; text layer); VOL-I:9.1(e) (VOL-I p4; text layer); VOL-I:9.1(f) (VOL-I p4; text layer); VOL-I:9.1(g) (VOL-I p4; text layer); VOL-I:9.1(h) (VOL-I p4; text layer); VOL-I:9.1(i) (VOL-I p4; text layer); VOL-I:9.1(e)+ADD-02 (ADD-02 p3; addendum op; issued by ADD-02; inserted after VOL-I 9.1(e), p4); ADD-02/7.1 [ADD-02; proposed] <- ADD-02:7.1 (ADD-02 p3) | I-NO-CONSEQUENCE; I-F4G-LETTERING
VOL-I-9.1h-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:9.1 | envelope_A; authority_to_sign | Include a notarised Power of Attorney for each signatory in Envelope A | (h) notarised Powers of Attorney for each signatory; | (h) notarised Powers of Attorney for each signatory; | notarised Powers of Attorney for each signatory | VOL-I 9.1(h) p4 | VOL-I 9.1(h) p4 | pass_fail | Legal | Legal counsel | EV-POA | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 9.1(h) p4 | VOL-I 9.1(h) p4 | VOL-I 9.1(h) p4 | VOL-I 9.1(h) p4 | none stated in the documents |  |  | medium: verbatim list item; 'each signatory' is not defined; no consequence stated | Wider than VOL-I 9.3 (the Form 4-A signatory): covers every signatory, e.g. the Form 4-C signatory of each member. Which documents' signatories are meant is not listed. | unchanged since BASE; value as read: 'notarised Powers of Attorney for each signatory' | decided (recorded): I-NO-CONSEQUENCE, I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:9.1(h) (VOL-I p4; text layer) | I-NO-CONSEQUENCE; I-BIDDER-FACTS
VOL-I-9.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:9.2 | envelope_A; technical_proposal; page_limit | Technical Proposal narrative within the A4 page limit (Form Sheets and Volume II-permitted appendices excluded) | The Technical Proposal narrative shall not exceed one hundred and twenty (120) pages of A4, excluding the Form Sheets and the appendices expressly permitted by Volume II. Pages in excess of the limit will be removed before evaluation and will not be scored. | The Technical Proposal narrative shall not exceed one hundred and fifty (150) pages of A4, excluding the Form Sheets and the appendices expressly permitted by Volume II. Pages in excess of the limit will be removed before evaluation and will not be scored. | one hundred and fifty (150) pages | ADD-02 2.1 p1 (amending VOL-I 9.2) | VOL-I 9.2 p5 <- ADD-02/2.1 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | AMENDED (ADD-02/2.1) | ACTIVE (as amended by ADD-02/2.1) | reading re-made at ADD-01: ADD-01 Q2: the limit applies to the narrative only; Form Sheets and the appendices permitted by Volume II are excluded. by ADD-01/Q2 [ADD-01; proposed; annotates VOL-I:9.2 (interprets)] <- ADD-01:Q2 (ADD-01 p1) | status ACTIVE -> AMENDED (ADD-02/2.1). reading re-made at ADD-02: ADD-02 §2.1 raises the limit from 120 to 150 pages; the clause as amended still prints 'excluding the Form Sheets and the appendices expressly permitted by Volume II'. ADD-01 Q2 answered about the '120-page limit': whether that answer still holds after ADD-02 2.1 is listed for review in A2 (a decision for a person; none recorded). by ADD-02/2.1 [ADD-02; proposed] <- ADD-02:2.1 (ADD-02 p1) | status AMENDED (ADD-02/2.1) -> ACTIVE (as amended by ADD-02/2.1) | VOL-I 9.2 p5 | VOL-I 9.2 p5 | ADD-02 2.1 p1 (amending VOL-I 9.2) | ADD-02 2.1 p1 (amending VOL-I 9.2) | lesser consequence: "Pages in excess of the limit will be removed before evaluation and will not be scored." | VOL-I 9.2 p5 as amended by ADD-02 2.1 p1 |  | high: verbatim at every stage; the 'appendices expressly permitted by Volume II' were not found in the extract | ADD-02 §2.1 raises the limit from 120 to 150 pages; the clause as amended still prints 'excluding the Form Sheets and the appendices expressly permitted by Volume II'. ADD-01 Q2 answered about the '120-page limit': whether that answer still holds after ADD-02 2.1 is listed for review in A2 (a decision for a person; none recorded). | changed at ADD-02 by ADD-02/2.1 (the quoted value); re-read by ADD-01/Q2 (interprets; accepted by a person; not counted as a confirmation); value as read: 'one hundred and fifty (150) pages' | decided (recorded): I-VOL-I-APPENDICES, I-VOL-I-PAGE-LIMIT-Q2 | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/2.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/Q2: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-02/2.1: accepted | VOL-I:9.2 (VOL-I p5; text layer); ADD-01/Q2 [ADD-01; proposed; annotates VOL-I:9.2 (interprets)] <- ADD-01:Q2 (ADD-01 p1); ADD-02/2.1 [ADD-02; proposed] <- ADD-02:2.1 (ADD-02 p1) | I-VOL-I-APPENDICES; I-VOL-I-PAGE-LIMIT-Q2 | -> REL-AI-005 [proposed limit_applies] to ADD-03-3.2-01
VOL-I-9.5-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:9.5 | envelope_A; references; forms | A separate Form 4-B for each reference project relied on under 8.5, each with a client completion certificate | [VOL-I 9.5 p5] A separate Form 4-B shall be submitted for each reference project relied upon under Clause 8.5, accompanied by a client completion certificate. A reference project not evidenced by a completion certificate will be disregarded. [VOL-I 9.1(b) p4] (b) Form 4-B — Reference Projects Schedule (one per reference project); | [VOL-I 9.5 p5] A separate Form 4-B shall be submitted for each reference project relied upon under Clause 8.5, accompanied by a client completion certificate. A reference project not evidenced by a completion certificate will be disregarded. [VOL-I 9.1(b) p4] (b) Form 4-B — Reference Projects Schedule (one per reference project); | A separate Form 4-B shall be submitted for each reference project relied upon under Clause 8.5, accompanied by a client completion certificate. | VOL-I 9.5 p5 | VOL-I 9.5 p5; VOL-I 9.1(b) p4 | pass_fail | Technical | Technical lead | EV-FORM-4B; EV-COMPLETION-CERT | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 9.5 p5 | VOL-I 9.5 p5 | VOL-I 9.5 p5 | VOL-I 9.5 p5 | lesser consequence: "A reference project not evidenced by a completion certificate will be disregarded." | VOL-I 9.5 p5 |  | high: verbatim; Form 4-B also asks for a contract value in SAR (Envelope A), see I-VOL-I-ENV-A-PRICES | A disregarded reference may leave fewer than the two plants footnote 12 requires (row VOL-I-8.5-01, rejection); that link is for a person to confirm. | unchanged since BASE; value as read: 'A separate Form 4-B shall be submitted for each reference project relied upon under Clause 8.5, accompanied by a client…' | decided (recorded): I-VOL-I-ENV-A-PRICES, I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:9.5 (VOL-I p5; text layer); VOL-I:9.1(b) (VOL-I p4; text layer) | I-VOL-I-ENV-A-PRICES; I-BIDDER-FACTS
VOL-I-9.6-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:9.6 | envelope_A; deviations; forms | Form 4-E lists every deviation, qualification or reservation to Volume V; never 'no deviations' with a qualification elsewhere | [VOL-I 9.6 p5] Form 4-E shall list every deviation, qualification or reservation to Volume V. A Proposal that states ‘no deviations’ in Form 4-E while containing a qualification elsewhere in the Proposal shall be treated as non-responsive. [VOL-I 9.1(e) p4] (e) Form 4-E — Schedule of Deviations; | [VOL-I 9.6 p5] Form 4-E shall list every deviation, qualification or reservation to Volume V. A Proposal that states ‘no deviations’ in Form 4-E while containing a qualification elsewhere in the Proposal shall be treated as non-responsive. [VOL-I 9.1(e) p4] (e) Form 4-E — Schedule of Deviations; | Form 4-E shall list every deviation, qualification or reservation to Volume V. | VOL-I 9.6 p5 | VOL-I 9.6 p5; VOL-I 9.1(e) p4 | pass_fail | Legal | Legal counsel | EV-FORM-4E | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 9.6 p5 | VOL-I 9.6 p5 | VOL-I 9.6 p5 | VOL-I 9.6 p5 | non-responsive: "A Proposal that states ‘no deviations’ in Form 4-E while containing a qualification elsewhere in the Proposal shall be treated as non-responsive." | VOL-I 9.6 p5 |  | high: verbatim | Whether to list the concession-term point (VOL-I 12.1 vs VOL-V 3.1) as a deviation is for a person (I-CONCESSION). | unchanged since BASE; value as read: 'Form 4-E shall list every deviation, qualification or reservation to Volume V.' | decided (recorded): I-CONCESSION, I-FORM-4E-COMMERCIAL-QUALIFICATION, I-FORM-4E-CROSS-CHECK | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:9.6 (VOL-I p5; text layer); VOL-I:9.1(e) (VOL-I p4; text layer) | I-CONCESSION; I-FORM-4E-COMMERCIAL-QUALIFICATION (the issue names the row (curated, PROPOSED)); I-FORM-4E-CROSS-CHECK (the issue names the row (curated, PROPOSED))
VOL-I-9.7-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:9.7 | envelope_A; technical_proposal | Technical Proposal narrative (Envelope A item (f)) addressing at least the six listed topics | [VOL-I 9.7 p5] The Technical Proposal shall address, as a minimum, the process design, the construction methodology and programme, the operations and maintenance philosophy, the health and safety plan, the environmental and social management approach, and the organisation and key personnel. [VOL-I 9.1(f) p4] (f) the Technical Proposal narrative; | [VOL-I 9.7 p5] The Technical Proposal shall address, as a minimum, the process design, the construction methodology and programme, the operations and maintenance philosophy, the health and safety plan, the environmental and social management approach, and the organisation and key personnel. [VOL-I 9.1(f) p4] (f) the Technical Proposal narrative; | The Technical Proposal shall address, as a minimum, the process design, the construction methodology and programme, the operations and maintenance philosophy, the health and safety plan, the environmental and social management approach, and the organisation and key personnel. | VOL-I 9.7 p5 | VOL-I 9.7 p5; VOL-I 9.1(f) p4 | pass_fail | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 9.7 p5 | VOL-I 9.7 p5 | VOL-I 9.7 p5 | VOL-I 9.7 p5 | none stated in the documents |  |  | high: verbatim; no consequence stated for a missing topic | The topics correspond to the Table 1-1 criteria, where they are scored. | unchanged since BASE; value as read: 'The Technical Proposal shall address, as a minimum, the process design, the construction methodology and programme, the…' | decided (recorded): I-NO-CONSEQUENCE | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:9.7 (VOL-I p5; text layer); VOL-I:9.1(f) (VOL-I p4; text layer) | I-NO-CONSEQUENCE
VOL-I-10.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:10.1 | envelope_B; commercial | Envelope B contains only Form 4-F and the Financial Model; no other document | Envelope B shall contain only (a) Form 4-F (Financial Proposal Schedule) and (b) the Financial Model. No other document shall be placed in Envelope B. | Envelope B shall contain only (a) Form 4-F (Financial Proposal Schedule) and (b) the Financial Model. No other document shall be placed in Envelope B. | Envelope B shall contain only (a) Form 4-F (Financial Proposal Schedule) and (b) the Financial Model. No other document shall be placed in Envelope B. | VOL-I 10.1 p5 | VOL-I 10.1 p5 | pass_fail | Commercial | Commercial lead | EV-FORM-4F; EV-FIN-MODEL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 10.1 p5 | VOL-I 10.1 p5 | VOL-I 10.1 p5 | VOL-I 10.1 p5 | none stated in the documents |  |  | medium: verbatim; conflicts with VOL-I 10.3 and 10.6; no consequence stated | VOL-I 10.3 (model auditor's opinion) and 10.6 (financing assumptions schedule) require further documents; not resolved here. | unchanged since BASE; value as read: 'Envelope B shall contain only (a) Form 4-F (Financial Proposal Schedule) and (b) the Financial Model. No other document…' | decided (recorded): I-NO-CONSEQUENCE, I-VOL-I-ENV-B | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:10.1 (VOL-I p5; text layer) | I-NO-CONSEQUENCE; I-VOL-I-ENV-B
VOL-I-10.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:10.2 | envelope_B; price | Quote a single Availability Payment in SAR per annum, calculated per the Volume V Clause 29 payment mechanism | The Bidder shall quote a single Availability Payment expressed in Saudi Riyals per annum, calculated in accordance with the payment mechanism at Volume V Clause 29. | The Bidder shall quote a single Availability Payment expressed in Saudi Riyals per annum, calculated in accordance with the payment mechanism at Volume V Clause 29. | The Bidder shall quote a single Availability Payment expressed in Saudi Riyals per annum, calculated in accordance with the payment mechanism at Volume V Clause 29. | VOL-I 10.2 p5 | VOL-I 10.2 p5 | pass_fail | Commercial | Commercial lead | EV-FORM-4F | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 10.2 p5 | VOL-I 10.2 p5 | VOL-I 10.2 p5 | VOL-I 10.2 p5 | none stated in the documents |  |  | high: verbatim; no consequence stated (VOL-I 10.5 covers conditional or alternative prices) |  | unchanged since BASE; value as read: 'The Bidder shall quote a single Availability Payment expressed in Saudi Riyals per annum, calculated in accordance with…' | decided (recorded): I-NO-CONSEQUENCE, I-ADD03-Q17-AP-CAPACITY, I-ADD03-Q17-PRICING-COND | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:10.2 (VOL-I p5; text layer) | I-NO-CONSEQUENCE; I-ADD03-Q17-AP-CAPACITY (via REL-AI-004 (proposed)); I-ADD03-Q17-PRICING-COND (via REL-AI-011 (possible)) | <- REL-PAY-QUOTED-PRICE [confirmed feeds_calculation] from calc:availability-payment; <- REL-AI-004 [proposed depends_on] from ADD-03-Q17-01; <- REL-AI-011 [possible depends_on] from ADD-03:Q17
VOL-I-10.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:10.3 | envelope_B; financial_model | Financial Model in unlocked, fully formula-linked Excel, with no macros and no hard-coded values in calculation cells | The Financial Model shall be submitted in unlocked, fully formula-linked Microsoft Excel format, without macros and without hard-coded values in calculation cells, and shall be accompanied by an opinion from an independent model auditor addressed to the Authority. | The Financial Model shall be submitted in unlocked, fully formula-linked Microsoft Excel format, without macros and without hard-coded values in calculation cells, and shall be accompanied by an opinion from an independent model auditor addressed to the Authority. | The Financial Model shall be submitted in unlocked, fully formula-linked Microsoft Excel format, without macros and without hard-coded values in calculation cells | VOL-I 10.3 p5 | VOL-I 10.3 p5 | pass_fail | Finance | Financial modeller | EV-FIN-MODEL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 10.3 p5 | VOL-I 10.3 p5 | VOL-I 10.3 p5 | VOL-I 10.3 p5 | none stated in the documents |  |  | high: verbatim; no consequence stated; Appendix 2 names files '.pdf' |  | unchanged since BASE; value as read: 'The Financial Model shall be submitted in unlocked, fully formula-linked Microsoft Excel format, without macros and wit…' | decided (recorded): I-NO-CONSEQUENCE, I-VOL-I-FILE-NAMES | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:10.3 (VOL-I p5; text layer) | I-NO-CONSEQUENCE; I-VOL-I-FILE-NAMES | <- REL-PAY-FINANCIAL-MODEL [proposed depends_on] from calc:availability-payment; -> REL-MODEL-FORM-4F [confirmed feeds_calculation] to VOL-IV-F4F-02; <- REL-CHANGE-IN-LAW-FINANCIAL-MODEL [possible depends_on] from VOL-V:36.2; REACHED at ADD-02 (possible impact): from VOL-V:36.2 via REL-CHANGE-IN-LAW-FINANCIAL-MODEL
VOL-I-10.3-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:10.3 | envelope_B; financial_model; model_audit | Financial Model accompanied by an independent model auditor's opinion addressed to the Authority | The Financial Model shall be submitted in unlocked, fully formula-linked Microsoft Excel format, without macros and without hard-coded values in calculation cells, and shall be accompanied by an opinion from an independent model auditor addressed to the Authority. | The Financial Model shall be submitted in unlocked, fully formula-linked Microsoft Excel format, without macros and without hard-coded values in calculation cells, and shall be accompanied by an opinion from an independent model auditor addressed to the Authority. | shall be accompanied by an opinion from an independent model auditor addressed to the Authority | VOL-I 10.3 p5 | VOL-I 10.3 p5 | pass_fail | Finance | Financial modeller | EV-MODEL-AUDIT | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 10.3 p5 | VOL-I 10.3 p5 | VOL-I 10.3 p5 | VOL-I 10.3 p5 | none stated in the documents |  |  | medium: verbatim; conflicts with VOL-I 10.1; no consequence stated | VOL-I 10.1 allows only Form 4-F and the Financial Model in Envelope B; where the opinion goes is not stated. | unchanged since BASE; value as read: 'shall be accompanied by an opinion from an independent model auditor addressed to the Authority' | decided (recorded): I-NO-CONSEQUENCE, I-VOL-I-ENV-B | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:10.3 (VOL-I p5; text layer) | I-NO-CONSEQUENCE; I-VOL-I-ENV-B
VOL-I-10.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:10.4 | envelope_B; price | All prices exclusive of VAT and stated in Saudi Riyals | All prices shall be exclusive of value added tax and shall be stated in Saudi Riyals. | All prices shall be exclusive of value added tax and shall be stated in Saudi Riyals. | All prices shall be exclusive of value added tax and shall be stated in Saudi Riyals. | VOL-I 10.4 p5 | VOL-I 10.4 p5 | pass_fail | Commercial | Commercial lead | EV-FORM-4F | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 10.4 p5 | VOL-I 10.4 p5 | VOL-I 10.4 p5 | VOL-I 10.4 p5 | none stated in the documents |  |  | high: verbatim; no consequence stated |  | unchanged since BASE; value as read: 'All prices shall be exclusive of value added tax and shall be stated in Saudi Riyals.' | decided (recorded): I-NO-CONSEQUENCE | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:10.4 (VOL-I p5; text layer) | I-NO-CONSEQUENCE
VOL-I-10.5-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:10.5 | envelope_B; price | No conditional price, alternative price, or price subject to adjustment other than as provided in Volume V | Any conditional price, price subject to adjustment other than as provided in Volume V, or alternative price shall render the Proposal non-responsive. An alternative technical solution may be submitted only as a supplement to a fully compliant base Proposal and will be considered at the Authority's sole discretion. | Any conditional price, price subject to adjustment other than as provided in Volume V, or alternative price shall render the Proposal non-responsive. An alternative technical solution may be submitted only as a supplement to a fully compliant base Proposal and will be considered at the Authority's sole discretion. | Any conditional price, price subject to adjustment other than as provided in Volume V, or alternative price | VOL-I 10.5 p5 | VOL-I 10.5 p5 | pass_fail | Commercial | Commercial lead | EV-FORM-4F | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q14 concerns alternative technical solutions (row VOL-I-10.5-02); reviewed for this row, no change. by ADD-02/Q14 [ADD-02; proposed; annotates VOL-I:10.5 (confirms)] <- ADD-02:Q14 (ADD-02 p2) |  | VOL-I 10.5 p5 | VOL-I 10.5 p5 | VOL-I 10.5 p5 | VOL-I 10.5 p5 | non-responsive: "Any conditional price, price subject to adjustment other than as provided in Volume V, or alternative price shall render the Proposal non-responsive." | VOL-I 10.5 p5 |  | high: verbatim | ADD-02 Q14 concerns alternative technical solutions (row VOL-I-10.5-02); reviewed for this row, no change. | unchanged since BASE; re-read by ADD-02/Q14 (confirms; accepted by a person; not counted as a confirmation); value as read: 'Any conditional price, price subject to adjustment other than as provided in Volume V, or alternative price' | decided (recorded): I-FORM-4E-COMMERCIAL-QUALIFICATION | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/Q14: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:10.5 (VOL-I p5; text layer); ADD-02/Q14 [ADD-02; proposed; annotates VOL-I:10.5 (confirms)] <- ADD-02:Q14 (ADD-02 p2) | I-FORM-4E-COMMERCIAL-QUALIFICATION (the issue names the row (curated, PROPOSED))
VOL-I-10.5-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:10.5 | alternative_solution | An alternative technical solution only as a supplement to a fully compliant base Proposal (considered at the Authority's discretion) | Any conditional price, price subject to adjustment other than as provided in Volume V, or alternative price shall render the Proposal non-responsive. An alternative technical solution may be submitted only as a supplement to a fully compliant base Proposal and will be considered at the Authority's sole discretion. | Any conditional price, price subject to adjustment other than as provided in Volume V, or alternative price shall render the Proposal non-responsive. An alternative technical solution may be submitted only as a supplement to a fully compliant base Proposal and will be considered at the Authority's sole discretion. | An alternative technical solution may be submitted only as a supplement to a fully compliant base Proposal and will be considered at the Authority's sole discretion. | VOL-I 10.5 p5 | VOL-I 10.5 p5 | pass_fail | Technical | Technical lead | none: applies only if the Bidder offers an alternative technical solution; nothing to submit otherwise | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q14: an alternative technical solution may not be submitted alone; VOL-I 10.5 applies. by ADD-02/Q14 [ADD-02; proposed; annotates VOL-I:10.5 (confirms)] <- ADD-02:Q14 (ADD-02 p2) |  | VOL-I 10.5 p5 | VOL-I 10.5 p5 | VOL-I 10.5 p5 | VOL-I 10.5 p5 | none stated in the documents |  |  | medium: verbatim; what happens to an alternative submitted without a compliant base is not stated | ADD-02 Q14: an alternative technical solution may not be submitted alone; VOL-I 10.5 applies. | unchanged since BASE; re-read by ADD-02/Q14 (confirms; accepted by a person; not counted as a confirmation); value as read: 'An alternative technical solution may be submitted only as a supplement to a fully compliant base Proposal and will be …' | decided (recorded): I-NO-CONSEQUENCE | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/Q14: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:10.5 (VOL-I p5; text layer); ADD-02/Q14 [ADD-02; proposed; annotates VOL-I:10.5 (confirms)] <- ADD-02:Q14 (ADD-02 p2) | I-NO-CONSEQUENCE
VOL-I-10.6-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:10.6 | envelope_B; financing | With Form 4-F, a schedule of the principal financing assumptions (debt tenor, margin, gearing) | The Bidder shall submit with Form 4-F a schedule of the principal financing assumptions underlying the Availability Payment, including the assumed debt tenor, margin and gearing. | The Bidder shall submit with Form 4-F a schedule of the principal financing assumptions underlying the Availability Payment, including the assumed debt tenor, margin and gearing. | The Bidder shall submit with Form 4-F a schedule of the principal financing assumptions underlying the Availability Payment, including the assumed debt tenor, margin and gearing. | VOL-I 10.6 p5 | VOL-I 10.6 p5 | pass_fail | Finance | Financial modeller | EV-FIN-ASSUMPTIONS | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 10.6 p5 | VOL-I 10.6 p5 | VOL-I 10.6 p5 | VOL-I 10.6 p5 | none stated in the documents |  |  | medium: verbatim; conflicts with VOL-I 10.1; no consequence stated | VOL-I 10.1 allows only Form 4-F and the Financial Model in Envelope B; whether this schedule is part of Form 4-F is not stated. | unchanged since BASE; value as read: 'The Bidder shall submit with Form 4-F a schedule of the principal financing assumptions underlying the Availability Pay…' | decided (recorded): I-NO-CONSEQUENCE, I-VOL-I-ENV-B | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:10.6 (VOL-I p5; text layer) | I-NO-CONSEQUENCE; I-VOL-I-ENV-B | <- REL-PAY-FINANCING-ASSUMPTIONS [possible depends_on] from calc:availability-payment
VOL-I-11.5-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:11.5 | clarification; post_submission; price | A response to an Authority clarification request must not change the Availability Payment quoted | The Authority may seek written clarification of any Proposal. A response to a clarification shall not change the Availability Payment quoted; any response that does so shall render the Proposal non-responsive. | The Authority may seek written clarification of any Proposal. A response to a clarification shall not change the Availability Payment quoted; any response that does so shall render the Proposal non-responsive. | A response to a clarification shall not change the Availability Payment quoted | VOL-I 11.5 p5 | VOL-I 11.5 p5 | pass_fail | Commercial | Commercial lead | none: arises only after submission, if the Authority seeks a written clarification | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 11.5 p5 | VOL-I 11.5 p5 | VOL-I 11.5 p5 | VOL-I 11.5 p5 | non-responsive: "any response that does so shall render the Proposal non-responsive" | VOL-I 11.5 p5 |  | high: verbatim |  | unchanged since BASE; value as read: 'A response to a clarification shall not change the Availability Payment quoted' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:11.5 (VOL-I p5; text layer)
VOL-I-T1-1-A | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:T1-1 | evaluation; weighting | Marks available for criterion A (process design, treatment performance and compliance with Volume II) | Ref: A ¦ Criterion: Process design, treatment performance and compliance with Volume II ¦ Marks: 25 | Ref: A ¦ Criterion: Process design, treatment performance and compliance with Volume II ¦ Marks: 25 | Marks: 25 | ADD-02 T1-1-rev/A p1 (replacing VOL-I T1-1/A p6, ADD-02/3.1) | ADD-02 T1-1-rev/A p1 (issued as VOL-I:T1-1/A) <- ADD-02/3.1 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE (reissued by ADD-02/3.1, unchanged) | ACTIVE (reissued by ADD-02/3.1, unchanged) |  | status ACTIVE -> ACTIVE (reissued by ADD-02/3.1, unchanged). reading re-made at ADD-02: Table 1-1 reissued by ADD-02 §3.1; A unchanged. Note (3)'s 'standard five-point scale' and 'weight shown' are not defined in the pack. by ADD-02/3.1 [ADD-02; proposed] <- ADD-02:3.1 (ADD-02 p1); ADD-02/T1-1-rev/note(3) [ADD-02; proposed; annotates ADD-02:T1-1-rev (interprets)] <- ADD-02:T1-1-rev/note(3) (ADD-02 p1) |  | VOL-I T1-1/A p6 | VOL-I T1-1/A p6 | ADD-02 T1-1-rev/A p1 (replacing VOL-I T1-1/A p6, ADD-02/3.1) | ADD-02 T1-1-rev/A p1 (replacing VOL-I T1-1/A p6, ADD-02/3.1) | none stated in the documents |  |  | high: verbatim table rows | Table 1-1 reissued by ADD-02 §3.1; A unchanged. Note (3)'s 'standard five-point scale' and 'weight shown' are not defined in the pack. | unchanged since BASE (unit reissued at ADD-02 by ADD-02/3.1; the row's words unchanged); value as read: 'Marks: 25' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/3.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-02/3.1: accepted | VOL-I:T1-1/A (VOL-I p6; text layer); ADD-02/3.1 [ADD-02; proposed] <- ADD-02:3.1 (ADD-02 p1); ADD-02/T1-1-rev/note(3) [ADD-02; proposed; annotates ADD-02:T1-1-rev (interprets)] <- ADD-02:T1-1-rev/note(3) (ADD-02 p1)
VOL-I-T1-1-C | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:T1-1 | evaluation; weighting | Marks available for criterion C (operations and maintenance philosophy and lifecycle strategy) | Ref: C ¦ Criterion: Operations and maintenance philosophy and lifecycle strategy ¦ Marks: 20 | Ref: C ¦ Criterion: Operations and maintenance philosophy and lifecycle strategy ¦ Marks: 20 | Marks: 20 | ADD-02 T1-1-rev/C p1 (replacing VOL-I T1-1/C p6, ADD-02/3.1) | ADD-02 T1-1-rev/C p1 (issued as VOL-I:T1-1/C) <- ADD-02/3.1 | scored | Operations | O&M lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE (reissued by ADD-02/3.1, unchanged) | ACTIVE (reissued by ADD-02/3.1, unchanged) |  | status ACTIVE -> ACTIVE (reissued by ADD-02/3.1, unchanged). reading re-made at ADD-02: Table 1-1 reissued by ADD-02 §3.1; C unchanged. by ADD-02/3.1 [ADD-02; proposed] <- ADD-02:3.1 (ADD-02 p1); ADD-02/T1-1-rev/note(3) [ADD-02; proposed; annotates ADD-02:T1-1-rev (interprets)] <- ADD-02:T1-1-rev/note(3) (ADD-02 p1) |  | VOL-I T1-1/C p6 | VOL-I T1-1/C p6 | ADD-02 T1-1-rev/C p1 (replacing VOL-I T1-1/C p6, ADD-02/3.1) | ADD-02 T1-1-rev/C p1 (replacing VOL-I T1-1/C p6, ADD-02/3.1) | none stated in the documents |  |  | high: verbatim table rows | Table 1-1 reissued by ADD-02 §3.1; C unchanged. | unchanged since BASE (unit reissued at ADD-02 by ADD-02/3.1; the row's words unchanged); value as read: 'Marks: 20' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/3.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-02/3.1: accepted | VOL-I:T1-1/C (VOL-I p6; text layer); ADD-02/3.1 [ADD-02; proposed] <- ADD-02:3.1 (ADD-02 p1); ADD-02/T1-1-rev/note(3) [ADD-02; proposed; annotates ADD-02:T1-1-rev (interprets)] <- ADD-02:T1-1-rev/note(3) (ADD-02 p1)
VOL-I-T1-1-E | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:T1-1 | evaluation; weighting | Marks available for criterion E (organisation, key personnel and consortium governance) | Ref: E ¦ Criterion: Organisation, key personnel and consortium governance ¦ Marks: 10 | Ref: E ¦ Criterion: Organisation, key personnel and consortium governance ¦ Marks: 10 | Marks: 10 | ADD-02 T1-1-rev/E p1 (replacing VOL-I T1-1/E p6, ADD-02/3.1) | ADD-02 T1-1-rev/E p1 (issued as VOL-I:T1-1/E) <- ADD-02/3.1 | scored | Bid management | Bid manager | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE (reissued by ADD-02/3.1, unchanged) | ACTIVE (reissued by ADD-02/3.1, unchanged) |  | status ACTIVE -> ACTIVE (reissued by ADD-02/3.1, unchanged). reading re-made at ADD-02: Table 1-1 reissued by ADD-02 §3.1; E unchanged. by ADD-02/3.1 [ADD-02; proposed] <- ADD-02:3.1 (ADD-02 p1); ADD-02/T1-1-rev/note(3) [ADD-02; proposed; annotates ADD-02:T1-1-rev (interprets)] <- ADD-02:T1-1-rev/note(3) (ADD-02 p1) |  | VOL-I T1-1/E p6 | VOL-I T1-1/E p6 | ADD-02 T1-1-rev/E p1 (replacing VOL-I T1-1/E p6, ADD-02/3.1) | ADD-02 T1-1-rev/E p1 (replacing VOL-I T1-1/E p6, ADD-02/3.1) | none stated in the documents |  |  | high: verbatim table rows | Table 1-1 reissued by ADD-02 §3.1; E unchanged. | unchanged since BASE (unit reissued at ADD-02 by ADD-02/3.1; the row's words unchanged); value as read: 'Marks: 10' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/3.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-02/3.1: accepted | VOL-I:T1-1/E (VOL-I p6; text layer); ADD-02/3.1 [ADD-02; proposed] <- ADD-02:3.1 (ADD-02 p1); ADD-02/T1-1-rev/note(3) [ADD-02; proposed; annotates ADD-02:T1-1-rev (interprets)] <- ADD-02:T1-1-rev/note(3) (ADD-02 p1)
VOL-I-T1-1-F | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:T1-1 | evaluation; weighting | Marks available for criterion F (health, safety and security of supply) | Ref: F ¦ Criterion: Health, safety and security of supply ¦ Marks: 10 | Ref: F ¦ Criterion: Health, safety and security of supply ¦ Marks: 10 | Marks: 10 | ADD-02 T1-1-rev/F p1 (replacing VOL-I T1-1/F p6, ADD-02/3.1) | ADD-02 T1-1-rev/F p1 (issued as VOL-I:T1-1/F) <- ADD-02/3.1 | scored | HSE | HSE lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE (reissued by ADD-02/3.1, unchanged) | ACTIVE (reissued by ADD-02/3.1, unchanged) |  | status ACTIVE -> ACTIVE (reissued by ADD-02/3.1, unchanged). reading re-made at ADD-02: Table 1-1 reissued by ADD-02 §3.1; F unchanged. by ADD-02/3.1 [ADD-02; proposed] <- ADD-02:3.1 (ADD-02 p1); ADD-02/T1-1-rev/note(3) [ADD-02; proposed; annotates ADD-02:T1-1-rev (interprets)] <- ADD-02:T1-1-rev/note(3) (ADD-02 p1) |  | VOL-I T1-1/F p6 | VOL-I T1-1/F p6 | ADD-02 T1-1-rev/F p1 (replacing VOL-I T1-1/F p6, ADD-02/3.1) | ADD-02 T1-1-rev/F p1 (replacing VOL-I T1-1/F p6, ADD-02/3.1) | none stated in the documents |  |  | high: verbatim table rows | Table 1-1 reissued by ADD-02 §3.1; F unchanged. | unchanged since BASE (unit reissued at ADD-02 by ADD-02/3.1; the row's words unchanged); value as read: 'Marks: 10' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/3.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-02/3.1: accepted | VOL-I:T1-1/F (VOL-I p6; text layer); ADD-02/3.1 [ADD-02; proposed] <- ADD-02:3.1 (ADD-02 p1); ADD-02/T1-1-rev/note(3) [ADD-02; proposed; annotates ADD-02:T1-1-rev (interprets)] <- ADD-02:T1-1-rev/note(3) (ADD-02 p1)
VOL-I-12.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:12.1 | concession; post_award | Concession period of 25 years from the Project Commercial Operation Date, then transfer of the Project to the Authority per Volume V | The Authority will notify the successful Bidder as Preferred Bidder. The concession period shall be twenty-five (25) years commencing on the Project Commercial Operation Date, following which the Project shall transfer to the Authority in accordance with Volume V. | The Authority will notify the successful Bidder as Preferred Bidder. The concession period shall be twenty-five (25) years commencing on the Project Commercial Operation Date, following which the Project shall transfer to the Authority in accordance with Volume V. | The concession period shall be twenty-five (25) years commencing on the Project Commercial Operation Date, following which the Project shall transfer to the Authority in accordance with Volume V. | VOL-I 12.1 p6 | VOL-I 12.1 p6 | contractual_post_award | Legal | Legal counsel | Post-award (proposed requirement): to be obtained at PCOD, the Independent Engineer's certification that fixes PCOD (VOL-V 1.5), from which VOL-I 12.1 runs the 25-year concession period, and to be produced at the end of that period, the record of transfer of the Project to the Authority under Volume V (rows VOL-V-3.2-01 and VOL-V-42.1-01). | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q7 (p2) was asked 'Which applies?' and answers: 'The Authority notes the question. The order of precedence at Volume I Clause 3.2 applies. The Authority does not consider further amendment necessary at this stage.' It does not say which clause applies, and it amends neither. Two readings: this clause, 'twenty-five (25) years commencing on the Project Commercial Operation Date'; VOL-V 3.1 (p2), 'twenty-five (25) years from the Effective Date' (row VOL-V-3.1-01). VOL-I 3.2 (p2) orders the RFP Documents '(a) the Addenda, a later Addendum prevailing over an earlier one;' '(b) Volume I (Instructions to Bidders);' '(c) Volume V (Draft Project Agreement);' 'the first named prevailing'; VOL-I 3.3 (p2): 'A Bidder that resolves such a conflict unilaterally does so at its own risk'. Which clause governs the term, what to record in Form 4-E and which term start the Financial Model assumes are a decision for a person (Legal; I-CONCESSION, CQ-CONCESSION-TERM); no decision recorded. by ADD-02/Q7 [ADD-02; proposed; annotates VOL-I:12.1 (interprets)] <- ADD-02:Q7 (ADD-02 p2) |  | VOL-I 12.1 p6 | VOL-I 12.1 p6 | VOL-I 12.1 p6 | VOL-I 12.1 p6 | none stated in the documents |  | CONCESSION-END-PCOD: None (unknown_anchor) | medium: verbatim; conflicts with VOL-V 3.1 (from the Effective Date); ADD-02 Q7 refers to the order of precedence at VOL-I 3.2 without saying which clause applies; which clause governs is a decision for a person (Legal, I-CONCESSION); no decision recorded | ADD-02 Q7 (p2) was asked 'Which applies?' and answers: 'The Authority notes the question. The order of precedence at Volume I Clause 3.2 applies. The Authority does not consider further amendment necessary at this stage.' It does not say which clause applies, and it amends neither. Two readings: this clause, 'twenty-five (25) years commencing on the Project Commercial Operation Date'; VOL-V 3.1 (p2), 'twenty-five (25) years from the Effective Date' (row VOL-V-3.1-01). VOL-I 3.2 (p2) orders the RFP Documents '(a) the Addenda, a later Addendum prevailing over an earlier one;' '(b) Volume I (Instructions to Bidders);' '(c) Volume V (Draft Project Agreement);' 'the first named prevailing'; VOL-I 3.3 (p2): 'A Bidder that resolves such a conflict unilaterally does so at its own risk'. Which clause governs the term, what to record in Form 4-E and which term start the Financial Model assumes are a decision for a person (Legal; I-CONCESSION, CQ-CONCESSION-TERM); no decision recorded. | unchanged since BASE; re-read by ADD-02/Q7 (interprets; accepted by a person; not counted as a confirmation); value as read: 'The concession period shall be twenty-five (25) years commencing on the Project Commercial Operation Date, following wh…' | decided (recorded): I-CONCESSION | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/Q7: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:12.1 (VOL-I p6; text layer); ADD-02/Q7 [ADD-02; proposed; annotates VOL-I:12.1 (interprets)] <- ADD-02:Q7 (ADD-02 p2) | I-CONCESSION | <- REL-AI-003 [proposed depends_on] from VOL-I:11.5+ADD-03
VOL-I-12.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:12.2 | award; commercial_close; post_award | Preferred Bidder to achieve Commercial Close within 120 days of the Preferred Bidder Notification | The Preferred Bidder shall achieve Commercial Close within one hundred and twenty (120) days, and Financial Close within two hundred and seventy (270) days, of the date of the Preferred Bidder Notification. Failure to achieve Financial Close by the long-stop date entitles the Authority to call the Bid Bond and to proceed with the next ranked Bidder. | The Preferred Bidder shall achieve Commercial Close within one hundred and twenty (120) days, and Financial Close within two hundred and seventy (270) days, of the date of the Preferred Bidder Notification. Failure to achieve Financial Close by the long-stop date entitles the Authority to call the Bid Bond and to proceed with the next ranked Bidder. | The Preferred Bidder shall achieve Commercial Close within one hundred and twenty (120) days | VOL-I 12.2 p6 | VOL-I 12.2 p6 | contractual_post_award | Commercial | Commercial lead | Unresolved: the record that would show Commercial Close within 120 days of the Preferred Bidder Notification cannot be specified, because the pack does not define Commercial Close or say what it comprises (VOL-I Section 2 and the VOL-V extract give no definition). | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q13: the periods in VOL-I 12.2 are unchanged. by ADD-02/Q13 [ADD-02; proposed; annotates VOL-I:12.2 (confirms)] <- ADD-02:Q13 (ADD-02 p2) |  | VOL-I 12.2 p6 | VOL-I 12.2 p6 | VOL-I 12.2 p6 | VOL-I 12.2 p6 | none stated in the documents |  | PB-COMMERCIAL-CLOSE: None (unknown_anchor) | high: verbatim; anchored to the PBN, an event not in the pack; no consequence stated for Commercial Close | ADD-02 Q13: the periods in VOL-I 12.2 are unchanged. | unchanged since BASE; re-read by ADD-02/Q13 (confirms; accepted by a person; not counted as a confirmation); value as read: 'The Preferred Bidder shall achieve Commercial Close within one hundred and twenty (120) days' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/Q13: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:12.2 (VOL-I p6; text layer); ADD-02/Q13 [ADD-02; proposed; annotates VOL-I:12.2 (confirms)] <- ADD-02:Q13 (ADD-02 p2)
VOL-I-12.2-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:12.2 | award; financial_close; bid_security; post_award | Preferred Bidder to achieve Financial Close within 270 days of the Preferred Bidder Notification | The Preferred Bidder shall achieve Commercial Close within one hundred and twenty (120) days, and Financial Close within two hundred and seventy (270) days, of the date of the Preferred Bidder Notification. Failure to achieve Financial Close by the long-stop date entitles the Authority to call the Bid Bond and to proceed with the next ranked Bidder. | The Preferred Bidder shall achieve Commercial Close within one hundred and twenty (120) days, and Financial Close within two hundred and seventy (270) days, of the date of the Preferred Bidder Notification. Failure to achieve Financial Close by the long-stop date entitles the Authority to call the Bid Bond and to proceed with the next ranked Bidder. | Financial Close within two hundred and seventy (270) days, of the date of the Preferred Bidder Notification | VOL-I 12.2 p6 | VOL-I 12.2 p6 | contractual_post_award | Finance | Financial modeller | Unresolved: the record that would show Financial Close within 270 days of the Preferred Bidder Notification cannot be specified, because the pack defines neither Financial Close nor 'the long-stop date' by which failure entitles the Authority to call the Bid Bond. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q13 (p2), asked whether the Authority will extend the Financial Close long-stop date, answers: 'The periods in Volume I Clause 12.2 are unchanged.'. by ADD-02/Q13 [ADD-02; proposed; annotates VOL-I:12.2 (confirms)] <- ADD-02:Q13 (ADD-02 p2) |  | VOL-I 12.2 p6 | VOL-I 12.2 p6 | VOL-I 12.2 p6 | VOL-I 12.2 p6 | contractual remedy (post-award): "Failure to achieve Financial Close by the long-stop date entitles the Authority to call the Bid Bond and to proceed with the next ranked Bidder." | VOL-I 12.2 p6 | PB-FINANCIAL-CLOSE: None (unknown_anchor) | medium: verbatim; 'long-stop date' undefined and the Bid Bond's 180-day validity may not reach it | ADD-02 Q13 (p2), asked whether the Authority will extend the Financial Close long-stop date, answers: 'The periods in Volume I Clause 12.2 are unchanged.' | unchanged since BASE; re-read by ADD-02/Q13 (confirms; accepted by a person; not counted as a confirmation); value as read: 'Financial Close within two hundred and seventy (270) days, of the date of the Preferred Bidder Notification' | decided (recorded): I-VOL-I-BOND-LONGSTOP | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/Q13: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:12.2 (VOL-I p6; text layer); ADD-02/Q13 [ADD-02; proposed; annotates VOL-I:12.2 (confirms)] <- ADD-02:Q13 (ADD-02 p2) | I-VOL-I-BOND-LONGSTOP
VOL-I-13.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:13.2 | confidentiality; conduct | Keep the RFP Documents confidential; disclose only to members, advisors and financiers on a need-to-know basis under equivalent terms | The RFP Documents are confidential and shall not be disclosed other than to a Bidder's members, advisors and financiers on a need-to-know basis and subject to equivalent confidentiality obligations. | The RFP Documents are confidential and shall not be disclosed other than to a Bidder's members, advisors and financiers on a need-to-know basis and subject to equivalent confidentiality obligations. | The RFP Documents are confidential and shall not be disclosed other than to a Bidder's members, advisors and financiers on a need-to-know basis and subject to equivalent confidentiality obligations. | VOL-I 13.2 p6 | VOL-I 13.2 p6 | procedural | Legal | Legal counsel | none: a conduct rule on handling the RFP Documents; nothing to submit | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I 13.2 p6 | VOL-I 13.2 p6 | VOL-I 13.2 p6 | VOL-I 13.2 p6 | none stated in the documents |  |  | high: verbatim; no consequence stated |  | unchanged since BASE; value as read: 'The RFP Documents are confidential and shall not be disclosed other than to a Bidder's members, advisors and financiers…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:13.2 (VOL-I p6; text layer)
VOL-I-App3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-I:App3 | bid_submission; address; marking | Deliver to Tender Box 4, Administrative Building C, Sakaka; marking 'NUPA/ISTP/2026/014 — NOT TO BE OPENED BEFORE 14:00 ON THE PROPOSAL DUE DATE' | Tender Box 4, Ground Floor, Northern Utilities Procurement Authority, Administrative Building C, Sakaka. Marked: ‘NUPA/ISTP/2026/014 — NOT TO BE OPENED BEFORE 14:00 ON THE PROPOSAL DUE DATE’. | Tender Box 4, Ground Floor, Northern Utilities Procurement Authority, Administrative Building C, Sakaka. Marked: ‘NUPA/ISTP/2026/014 — NOT TO BE OPENED BEFORE 14:00 ON THE PROPOSAL DUE DATE’. | Tender Box 4, Ground Floor, Northern Utilities Procurement Authority, Administrative Building C, Sakaka. | VOL-I App3/para1 p7 | VOL-I App3/para1 p7 | pass_fail | Bid management | Bid manager | EV-DELIVERY | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-I App3/para1 p7 | VOL-I App3/para1 p7 | VOL-I App3/para1 p7 | VOL-I App3/para1 p7 | none stated in the documents |  |  | medium: verbatim; whether 'Marked:' is the envelope marking required by VOL-I 6.2 is not stated | The address of VOL-I 6.1 (row VOL-I-6.1-01 carries the deadline and the late-receipt rejection). | unchanged since BASE; value as read: 'Tender Box 4, Ground Floor, Northern Utilities Procurement Authority, Administrative Building C, Sakaka.' | decided (recorded): I-NO-CONSEQUENCE | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-I:App3/para1 (VOL-I p7; text layer) | I-NO-CONSEQUENCE
VOL-II-1.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:1.1 | scope_of_works; concession | Design, finance, construct, commission, own, operate and maintain the Facility; transfer it at concession end in the Volume V condition | The Project Company shall design, finance, construct, commission, own, operate and maintain the Wadi Sirhan Independent Sewage Treatment Plant and shall transfer the Facility to the Authority at the end of the concession period in the condition required by Volume V. | The Project Company shall design, finance, construct, commission, own, operate and maintain the Wadi Sirhan Independent Sewage Treatment Plant and shall transfer the Facility to the Authority at the end of the concession period in the condition required by Volume V. | The Project Company shall design, finance, construct, commission, own, operate and maintain the Wadi Sirhan Independent Sewage Treatment Plant | VOL-II 1.1 p2 | VOL-II 1.1 p2 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 1.1 p2 | VOL-II 1.1 p2 | VOL-II 1.1 p2 | VOL-II 1.1 p2 | none stated in the documents |  |  | high: verbatim text-layer clause; when the concession period ends depends on the term start (I-CONCESSION) | Transfer 'at the end of the concession period in the condition required by Volume V' (VOL-V 3.2 and 42.1). Binds the Project Company after award. | unchanged since BASE; value as read: 'The Project Company shall design, finance, construct, commission, own, operate and maintain the Wadi Sirhan Independent…' | decided (recorded): I-CONCESSION | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:1.1 (VOL-II p2; text layer) | I-CONCESSION
VOL-II-1.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:1.2 | scope_of_works | The Works include every listed element: inlet works to tertiary treatment, disinfection, sludge, odour control, effluent main and reservoir | The Works comprise: the inlet works and screening; primary, secondary and tertiary treatment; disinfection; sludge thickening, digestion and dewatering; odour control; the treated effluent transmission main; the treated effluent storage reservoir; and all associated electrical, control and civil works. | The Works comprise: the inlet works and screening; primary, secondary and tertiary treatment; disinfection; sludge thickening, digestion and dewatering; odour control; the treated effluent transmission main; the treated effluent storage reservoir; and all associated electrical, control and civil works. | The Works comprise: the inlet works and screening; primary, secondary and tertiary treatment; disinfection; sludge thickening, digestion and dewatering; odour control; the treated effluent transmission main; the treated effluent storage reservoir; and all associated electrical, control and civil works. | VOL-II 1.2 p2 | VOL-II 1.2 p2 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 1.2 p2 | VOL-II 1.2 p2 | VOL-II 1.2 p2 | VOL-II 1.2 p2 | none stated in the documents |  |  | high: verbatim text-layer clause | A scope list. The treated effluent storage reservoir is not specified anywhere else in the Volume II extract. | unchanged since BASE; value as read: 'The Works comprise: the inlet works and screening; primary, secondary and tertiary treatment; disinfection; sludge thic…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:1.2 (VOL-II p2; text layer)
VOL-II-1.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:1.3 | scope_of_works; interfaces | Manage all interfaces with the existing collection network at the two designated tie-in points, incl. temporary works to keep flows | The Project Company shall be responsible for all interfaces with the existing collection network at the two designated tie-in points, including any temporary works required to maintain flows during construction. | The Project Company shall be responsible for all interfaces with the existing collection network at the two designated tie-in points, including any temporary works required to maintain flows during construction. | shall be responsible for all interfaces with the existing collection network at the two designated tie-in points, including any temporary works required to maintain flows during construction | VOL-II 1.3 p2 | VOL-II 1.3 p2 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 1.3 p2 | VOL-II 1.3 p2 | VOL-II 1.3 p2 | VOL-II 1.3 p2 | none stated in the documents |  |  | medium: verbatim; the two designated tie-in points are not identified anywhere in the pack |  | unchanged since BASE; value as read: 'shall be responsible for all interfaces with the existing collection network at the two designated tie-in points, inclu…' | decided (recorded): I-VOL-II-MISSING | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:1.3 (VOL-II p2; text layer) | I-VOL-II-MISSING
VOL-II-1.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:1.4 | scope_of_works; utilities | Procure all utilities other than the grid connection point at the site boundary (which the Authority provides) | The Authority will provide the site free of encumbrance, together with a grid connection point at the site boundary. All other utilities shall be procured by the Project Company. | The Authority will provide the site free of encumbrance, together with a grid connection point at the site boundary. All other utilities shall be procured by the Project Company. | All other utilities shall be procured by the Project Company. | VOL-II 1.4 p2 | VOL-II 1.4 p2 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 1.4 p2 | VOL-II 1.4 p2 | VOL-II 1.4 p2 | VOL-II 1.4 p2 | none stated in the documents |  |  | high: verbatim text-layer clause | First sentence (an Authority duty): the Authority provides the site free of encumbrance and a grid connection point at the site boundary. | unchanged since BASE; value as read: 'All other utilities shall be procured by the Project Company.' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:1.4 (VOL-II p2; text layer)
VOL-II-2.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-15) | VOL-II:2.1 | design_basis; capacity | Design for a nominal capacity of 150,000 m3/day average daily flow at the inlet works, at the Table 2-2 design-year influent | [VOL-II 2.1 p2] The Facility shall be designed for a nominal treatment capacity of 120,000 m³/day average daily flow, measured at the inlet works, at the design year influent characteristics stated in Table 2-2. [VOL-II T2-2/bod5 p2] Parameter: BOD5 ¦ Unit: mg/l ¦ Average: 320 ¦ Peak (design): 480 [VOL-II T2-2/cod p2] Parameter: COD ¦ Unit: mg/l ¦ Average: 640 ¦ Peak (design): 950 [VOL-II T2-2/total-suspended-solids p2] Parameter: Total Suspended Solids ¦ Unit: mg/l ¦ Average: 350 ¦ Peak (design): 520 [VOL-II T2-2/total-nitrogen p2] Parameter: Total Nitrogen ¦ Unit: mg/l ¦ Average: 55 ¦ Peak (design): 80 [VOL-II T2-2/total-phosphorus p2] Parameter: Total Phosphorus ¦ Unit: mg/l ¦ Average: 9 ¦ Peak (design): 14 [VOL-II T2-2/temperature p2] Parameter: Temperature ¦ Unit: °C ¦ Average: 24 ¦ Peak (design): 34 (max) / 14 (min) | [VOL-II 2.1 p2] The Facility shall be designed for a nominal treatment capacity of 120,000 m³/day average daily flow, measured at the inlet works, at the design year influent characteristics stated in Table 2-2. [VOL-II T2-2/bod5 p2] Parameter: BOD5 ¦ Unit: mg/l ¦ Average: 320 ¦ Peak (design): 480 [VOL-II T2-2/cod p2] Parameter: COD ¦ Unit: mg/l ¦ Average: 640 ¦ Peak (design): 950 [VOL-II T2-2/total-suspended-solids p2] Parameter: Total Suspended Solids ¦ Unit: mg/l ¦ Average: 350 ¦ Peak (design): 520 [VOL-II T2-2/total-nitrogen p2] Parameter: Total Nitrogen ¦ Unit: mg/l ¦ Average: 55 ¦ Peak (design): 80 [VOL-II T2-2/total-phosphorus p2] Parameter: Total Phosphorus ¦ Unit: mg/l ¦ Average: 9 ¦ Peak (design): 14 [VOL-II T2-2/temperature p2] Parameter: Temperature ¦ Unit: °C ¦ Average: 24 ¦ Peak (design): 34 (max) / 14 (min) | designed for a nominal treatment capacity of 120,000 m³/day average daily flow, measured at the inlet works | VOL-II 2.1 p2 | VOL-II 2.1 p2; VOL-II T2-2/bod5 p2; VOL-II T2-2/cod p2; VOL-II T2-2/total-suspended-solids p2; VOL-II T2-2/total-nitrogen p2; VOL-II T2-2/total-phosphorus p2; VOL-II T2-2/temperature p2 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | AMENDED (ADD-03/4.1(a)) |  |  | status ACTIVE -> AMENDED (ADD-03/4.1(a)). reading re-made at ADD-03: Re-read at ADD-03: ADD-03 4.1 (op ADD-03/4.1(a), PROPOSED) substitutes 150,000 m³/day for 120,000 m³/day in VOL-II 2.1. The Table 2-2 design influent rows are not amended, and ADD-03 4.1 states 'The peak hourly flow in Table 2-6 row 2-6.2 is unchanged.' Follow-on items, listed and not decided here: (1) VOL-II 7.2 runs the reliability run 'at not less than 90% of nominal capacity' (row VOL-II-7.2-01), so its threshold now rests on 150,000 m³/day; no figure is computed here. (2) ADD-03 Q15 states that the 36-month period in VOL-V 12.1 is unchanged despite the capacity increase (row VOL-V-12.1-01). (3) The reference-plant threshold in VOL-I 8.5 footnote 12 is amended separately by ADD-03/4.2(a) (row VOL-I-8.5-01). (4) The Table 2-6 row 2-6.1 substitution named in ADD-03 4.1 is outside this row. The Technical Proposal and the pricing need to reflect the larger capacity. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed]. by ADD-03/4.1(a) [ADD-03; proposed] <- ADD-03:4.1 (ADD-03 p1); ADD-03/Q15 [ADD-03; proposed; cited by the reading made at ADD-03 (confirms)] <- ADD-03:Q15 (ADD-03 p2) | VOL-II 2.1 p2 | VOL-II 2.1 p2 | VOL-II 2.1 p2 | VOL-II 2.1 p2 as amended by ADD-03 4.1 p1 | none stated in the documents |  |  | high: verbatim text-layer clause and table | The Table 2-2 design influent rows (design data, not obligations) are listed as units, so a change to them changes this row. | unchanged since BASE; value as read: 'designed for a nominal treatment capacity of 120,000 m³/day average daily flow, measured at the inlet works' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:2.1 (VOL-II p2; text layer); VOL-II:T2-2/bod5 (VOL-II p2; text layer); VOL-II:T2-2/cod (VOL-II p2; text layer); VOL-II:T2-2/total-suspended-solids (VOL-II p2; text layer); VOL-II:T2-2/total-nitrogen (VOL-II p2; text layer); VOL-II:T2-2/total-phosphorus (VOL-II p2; text layer); VOL-II:T2-2/temperature (VOL-II p2; text layer); ADD-03/4.1(a) [ADD-03; proposed] <- ADD-03:4.1 (ADD-03 p1); ADD-03/Q15 [ADD-03; proposed; cited by the reading made at ADD-03 (confirms)] <- ADD-03:Q15 (ADD-03 p2)
VOL-II-2.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:2.2 | design_basis; design_life | Design life of all civil structures of at least 50 years | The design life of all civil structures shall be not less than fifty (50) years. The design life of mechanical and electrical equipment shall be not less than twenty (20) years or the manufacturer's rated life, whichever is the shorter, with lifecycle replacement provided for in the Project Company's lifecycle plan. | The design life of all civil structures shall be not less than fifty (50) years. The design life of mechanical and electrical equipment shall be not less than twenty (20) years or the manufacturer's rated life, whichever is the shorter, with lifecycle replacement provided for in the Project Company's lifecycle plan. | The design life of all civil structures shall be not less than fifty (50) years. | VOL-II 2.2 p2 | VOL-II 2.2 p2 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 2.2 p2 | VOL-II 2.2 p2 | VOL-II 2.2 p2 | VOL-II 2.2 p2 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'The design life of all civil structures shall be not less than fifty (50) years.' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:2.2 (VOL-II p2; text layer)
VOL-II-2.2-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:2.2 | design_basis; design_life; lifecycle | M&E design life of at least 20 years or the manufacturer's rated life, whichever is shorter; lifecycle replacement in the lifecycle plan | The design life of all civil structures shall be not less than fifty (50) years. The design life of mechanical and electrical equipment shall be not less than twenty (20) years or the manufacturer's rated life, whichever is the shorter, with lifecycle replacement provided for in the Project Company's lifecycle plan. | The design life of all civil structures shall be not less than fifty (50) years. The design life of mechanical and electrical equipment shall be not less than twenty (20) years or the manufacturer's rated life, whichever is the shorter, with lifecycle replacement provided for in the Project Company's lifecycle plan. | The design life of mechanical and electrical equipment shall be not less than twenty (20) years or the manufacturer's rated life, whichever is the shorter, with lifecycle replacement provided for in the Project Company's lifecycle plan. | VOL-II 2.2 p2 | VOL-II 2.2 p2 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 2.2 p2 | VOL-II 2.2 p2 | VOL-II 2.2 p2 | VOL-II 2.2 p2 | none stated in the documents |  |  | high: verbatim text-layer clause | 'whichever is the shorter' is recorded as written. | unchanged since BASE; value as read: 'The design life of mechanical and electrical equipment shall be not less than twenty (20) years or the manufacturer's r…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:2.2 (VOL-II p2; text layer)
VOL-II-2.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:2.3 | design_basis; future_expansion | Space for a future 50% expansion of nominal capacity without demolishing permanent structures (space provision only) | The Facility shall be designed to accommodate a future expansion of 50% of nominal capacity without demolition of permanent structures. Space provision only is required; no expansion works form part of the Works. | The Facility shall be designed to accommodate a future expansion of 50% of nominal capacity without demolition of permanent structures. Space provision only is required; no expansion works form part of the Works. | designed to accommodate a future expansion of 50% of nominal capacity without demolition of permanent structures | VOL-II 2.3 p2 | VOL-II 2.3 p2 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 2.3 p2 | VOL-II 2.3 p2 | VOL-II 2.3 p2 | VOL-II 2.3 p2 | none stated in the documents |  |  | high: verbatim text-layer clause | Space provision only is required; no expansion works form part of the Works. | unchanged since BASE; value as read: 'designed to accommodate a future expansion of 50% of nominal capacity without demolition of permanent structures' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:2.3 (VOL-II p2; text layer) |  | -> REL-AI-008 [proposed depends_on] to VOL-II:2.1
VOL-II-2.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:2.4 | technical_design; effluent; permit | Treated effluent to comply at all times with the Table 2-4 parameters (reproduced from the Environmental Permit, which prevails) | [VOL-II 2.4 p2] The treated effluent shall at all times comply with the parameters set out in Table 2-4. Table 2-4 is reproduced overleaf from the Environmental Permit issued for the site and is incorporated into this Volume by reference. [VOL-II T2-4-heading/para1 p3] The following page is reproduced as issued by the permitting authority. In the event of any discrepancy between this reproduction and the Environmental Permit, the Environmental Permit shall prevail. | [VOL-II 2.4 p2] The treated effluent shall at all times comply with the parameters set out in Table 2-4. Table 2-4 is reproduced overleaf from the Environmental Permit issued for the site and is incorporated into this Volume by reference. [VOL-II T2-4-heading/para1 p3] The following page is reproduced as issued by the permitting authority. In the event of any discrepancy between this reproduction and the Environmental Permit, the Environmental Permit shall prevail. | The treated effluent shall at all times comply with the parameters set out in Table 2-4. | VOL-II 2.4 p2 | VOL-II 2.4 p2; VOL-II T2-4-heading/para1 p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 2.4 p2 | VOL-II 2.4 p2 | VOL-II 2.4 p2 | VOL-II 2.4 p2 | none stated in the documents |  |  | medium: verbatim text-layer clause; the table it incorporates is an image reading (transcription confirmed by the owner, 3 Oct 2026) and the Permit that prevails is not supplied | The per-parameter limits are rows VOL-II-T2-4-*. VOL-II p3 reproduction preamble: in any discrepancy the Environmental Permit (not in the pack) prevails over the reproduction (the owner confirmed this location on 3 Oct 2026; the Permit's contents and compliance with it are not confirmed or claimed). How 'at all times' combines with the table's assessment bases is for a person. After award a Table 2-4 failure is an Unavailability Event (VOL-V 31.1(b), row VOL-V-31.1-02). | own words unchanged at ADD-02, but what it depends on changed (dependency; see A2); value as read: 'The treated effluent shall at all times comply with the parameters set out in Table 2-4.' | decided (recorded): I-PERMIT, I-READING-T24, I-VOL-II-T24-TENSIONS, I-VOL-II-AT-ALL-TIMES, I-VOL-II-COMPLIANCE-POINT | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:2.4 (VOL-II p2; text layer); VOL-II:T2-4-heading/para1 (VOL-II p3; text layer) | I-PERMIT; I-READING-T24; I-VOL-II-T24-TENSIONS; I-VOL-II-AT-ALL-TIMES; I-VOL-II-COMPLIANCE-POINT (via REL-T24-COMPLIANCE-MONITORING-STREAMS (confirmed)) | <- REL-T24-COMPLIANCE-MONITORING-STREAMS [confirmed limit_applies] from VOL-II:T2-4; NOT SUPPLIED: the Environmental Permit issued for the site (REL-MISSING-ENVIRONMENTAL-PERMIT, link confirmed): cannot be established: that the reproduced Table 2-4 limits, as amended by the addenda, are the limits that govern (the Permit prevails over the reproduction), and the limit of any parameter not listed (Note 1); Permit compliance is not claimed; REACHED at ADD-02 (confirmed dependency): from VOL-II:T2-4 via REL-T24-COMPLIANCE-MONITORING-STREAMS
VOL-II-2.5-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:2.5 | technical_design; monitoring; image | Continuous online monitoring of the Table 2-4 parameters assessed on a continuous basis, with real-time signals to the Authority | [VOL-II 2.5 p2] The Project Company shall install continuous online monitoring for those parameters identified in Table 2-4 as assessed on a continuous basis, with signals available to the Authority in real time. [VOL-II T2-4/ResidualChlorine p3] Parameter: Residual Chlorine ¦ Unit: mg/l ¦ Limit: 0.5 - 1.0 ¦ Basis of assessment: Continuous at outlet [VOL-II T2-4/pH p3] Parameter: pH ¦ Unit: - ¦ Limit: 6.0 - 9.0 ¦ Basis of assessment: Continuous at outlet | [VOL-II 2.5 p2] The Project Company shall install continuous online monitoring for those parameters identified in Table 2-4 as assessed on a continuous basis, with signals available to the Authority in real time. [VOL-II T2-4/ResidualChlorine p3] Parameter: Residual Chlorine ¦ Unit: mg/l ¦ Limit: 0.5 - 1.0 ¦ Basis of assessment: Continuous at outlet [VOL-II T2-4/pH p3] Parameter: pH ¦ Unit: - ¦ Limit: 6.0 - 9.0 ¦ Basis of assessment: Continuous at outlet | shall install continuous online monitoring for those parameters identified in Table 2-4 as assessed on a continuous basis, with signals available to the Authority in real time | VOL-II 2.5 p2 | VOL-II 2.5 p2; VOL-II T2-4/ResidualChlorine p3; VOL-II T2-4/pH p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED), so the parameters assessed 'Continuous at outlet' stay Residual Chlorine and pH. How the qualifier 'all values are maxima' applies to their ranges stays open (I-VOL-II-T24-TENSIONS; Process engineer); no decision recorded. by ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/ResidualChlorine (confirms)] <- ADD-02:5.1 (ADD-02 p1) |  | VOL-II 2.5 p2 | VOL-II 2.5 p2 | VOL-II 2.5 p2 | VOL-II 2.5 p2 | none stated in the documents |  |  | medium: verbatim clause, but the parameters it selects come from an image reading (transcription confirmed by the owner, 3 Oct 2026) | Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED), so the parameters assessed 'Continuous at outlet' stay Residual Chlorine and pH. How the qualifier 'all values are maxima' applies to their ranges stays open (I-VOL-II-T24-TENSIONS; Process engineer); no decision recorded. Printed table title: 'Table 2-4 Minimum Effluent Quality Parameters at the Point of Discharge'. | unchanged since BASE; re-read by ADD-02/5.1/unchanged (confirms; accepted by a person; not counted as a confirmation); value as read: 'shall install continuous online monitoring for those parameters identified in Table 2-4 as assessed on a continuous bas…' | decided (recorded): I-READING-T24, I-VOL-II-T24-TENSIONS, I-VOL-II-AT-ALL-TIMES, I-VOL-II-COMPLIANCE-POINT, I-PERMIT | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/5.1/unchanged: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:2.5 (VOL-II p2; text layer); VOL-II:T2-4/ResidualChlorine (VOL-II p3; image reading); VOL-II:T2-4/pH (VOL-II p3; image reading); ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/ResidualChlorine (confirms)] <- ADD-02:5.1 (ADD-02 p1) | I-READING-T24; I-VOL-II-T24-TENSIONS (via REL-T24-CONTINUOUS-MONITORING (confirmed)); I-VOL-II-AT-ALL-TIMES (via REL-T24-CONTINUOUS-MONITORING (confirmed)); I-VOL-II-COMPLIANCE-POINT (via REL-T24-CONTINUOUS-MONITORING (confirmed)); I-PERMIT (via REL-MISSING-ENVIRONMENTAL-PERMIT > REL-T24-CONTINUOUS-MONITORING (confirmed)) | <- REL-T24-CONTINUOUS-MONITORING [confirmed limit_applies] from VOL-II:T2-4
VOL-II-T2-4-BOD5 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:T2-4 | technical_design; effluent; image | Treated effluent Biochemical Oxygen Demand (BOD5): value shown in Table 2-4, unit and basis of assessment | Parameter: Biochemical Oxygen Demand (BOD5) ¦ Unit: mg/l ¦ Limit: 10 ¦ Basis of assessment: 30-day rolling average | Parameter: Biochemical Oxygen Demand (BOD5) ¦ Unit: mg/l ¦ Limit: 10 ¦ Basis of assessment: 30-day rolling average | Limit: 10 | VOL-II T2-4/BOD5 p3 | VOL-II T2-4/BOD5 p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED): the value, unit and basis read at BASE are unchanged. The Environmental Permit, which prevails over the reproduction, is not supplied (I-PERMIT). by ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/BOD5 (confirms)] <- ADD-02:5.1 (ADD-02 p1) |  | VOL-II T2-4/BOD5 p3 | VOL-II T2-4/BOD5 p3 | VOL-II T2-4/BOD5 p3 | VOL-II T2-4/BOD5 p3 | none stated in the documents |  |  | medium: value and basis come from an image reading (transcription confirmed by the owner, 3 Oct 2026); the Environmental Permit, which prevails, is not supplied | Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED): the value, unit and basis read at BASE are unchanged. The Environmental Permit, which prevails over the reproduction, is not supplied (I-PERMIT). Printed table title: 'Table 2-4 Minimum Effluent Quality Parameters at the Point of Discharge'. | unchanged since BASE; re-read by ADD-02/5.1/unchanged (confirms; accepted by a person; not counted as a confirmation); value as read: 'Limit: 10' | decided (recorded): I-PERMIT, I-READING-T24, I-VOL-II-COMPLIANCE-POINT | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/5.1/unchanged: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:T2-4/BOD5 (VOL-II p3; image reading); ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/BOD5 (confirms)] <- ADD-02:5.1 (ADD-02 p1) | I-PERMIT; I-READING-T24; I-VOL-II-COMPLIANCE-POINT | NOT SUPPLIED: the Environmental Permit issued for the site (REL-MISSING-ENVIRONMENTAL-PERMIT, link confirmed): cannot be established: that the reproduced Table 2-4 limits, as amended by the addenda, are the limits that govern (the Permit prevails over the reproduction), and the limit of any parameter not listed (Note 1); Permit compliance is not claimed
VOL-II-T2-4-COD | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:T2-4 | technical_design; effluent; image | Treated effluent Chemical Oxygen Demand (COD): value shown in Table 2-4, unit and basis of assessment | Parameter: Chemical Oxygen Demand (COD) ¦ Unit: mg/l ¦ Limit: 50 ¦ Basis of assessment: 30-day rolling average | Parameter: Chemical Oxygen Demand (COD) ¦ Unit: mg/l ¦ Limit: 50 ¦ Basis of assessment: 30-day rolling average | Limit: 50 | VOL-II T2-4/COD p3 | VOL-II T2-4/COD p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED): the value, unit and basis read at BASE are unchanged. The Environmental Permit, which prevails over the reproduction, is not supplied (I-PERMIT). by ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/COD (confirms)] <- ADD-02:5.1 (ADD-02 p1) |  | VOL-II T2-4/COD p3 | VOL-II T2-4/COD p3 | VOL-II T2-4/COD p3 | VOL-II T2-4/COD p3 | none stated in the documents |  |  | medium: value and basis come from an image reading (transcription confirmed by the owner, 3 Oct 2026); the Environmental Permit, which prevails, is not supplied | Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED): the value, unit and basis read at BASE are unchanged. The Environmental Permit, which prevails over the reproduction, is not supplied (I-PERMIT). Printed table title: 'Table 2-4 Minimum Effluent Quality Parameters at the Point of Discharge'. | unchanged since BASE; re-read by ADD-02/5.1/unchanged (confirms; accepted by a person; not counted as a confirmation); value as read: 'Limit: 50' | decided (recorded): I-PERMIT, I-READING-T24, I-VOL-II-COMPLIANCE-POINT | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/5.1/unchanged: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:T2-4/COD (VOL-II p3; image reading); ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/COD (confirms)] <- ADD-02:5.1 (ADD-02 p1) | I-PERMIT; I-READING-T24; I-VOL-II-COMPLIANCE-POINT | NOT SUPPLIED: the Environmental Permit issued for the site (REL-MISSING-ENVIRONMENTAL-PERMIT, link confirmed): cannot be established: that the reproduced Table 2-4 limits, as amended by the addenda, are the limits that govern (the Permit prevails over the reproduction), and the limit of any parameter not listed (Note 1); Permit compliance is not claimed
VOL-II-T2-4-TSS | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:T2-4 | technical_design; effluent; image | Treated effluent Total Suspended Solids (TSS): value shown in Table 2-4, unit and basis of assessment | Parameter: Total Suspended Solids (TSS) ¦ Unit: mg/l ¦ Limit: 10 ¦ Basis of assessment: 30-day rolling average | Parameter: Total Suspended Solids (TSS) ¦ Unit: mg/l ¦ Limit: 10 ¦ Basis of assessment: 30-day rolling average | Limit: 10 | VOL-II T2-4/TSS p3 | VOL-II T2-4/TSS p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED): the value, unit and basis read at BASE are unchanged. The Environmental Permit, which prevails over the reproduction, is not supplied (I-PERMIT). by ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/TSS (confirms)] <- ADD-02:5.1 (ADD-02 p1) |  | VOL-II T2-4/TSS p3 | VOL-II T2-4/TSS p3 | VOL-II T2-4/TSS p3 | VOL-II T2-4/TSS p3 | none stated in the documents |  |  | medium: value and basis come from an image reading (transcription confirmed by the owner, 3 Oct 2026); the Environmental Permit, which prevails, is not supplied | Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED): the value, unit and basis read at BASE are unchanged. The Environmental Permit, which prevails over the reproduction, is not supplied (I-PERMIT). Printed table title: 'Table 2-4 Minimum Effluent Quality Parameters at the Point of Discharge'. | unchanged since BASE; re-read by ADD-02/5.1/unchanged (confirms; accepted by a person; not counted as a confirmation); value as read: 'Limit: 10' | decided (recorded): I-PERMIT, I-READING-T24, I-VOL-II-COMPLIANCE-POINT | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/5.1/unchanged: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:T2-4/TSS (VOL-II p3; image reading); ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/TSS (confirms)] <- ADD-02:5.1 (ADD-02 p1) | I-PERMIT; I-READING-T24; I-VOL-II-COMPLIANCE-POINT | NOT SUPPLIED: the Environmental Permit issued for the site (REL-MISSING-ENVIRONMENTAL-PERMIT, link confirmed): cannot be established: that the reproduced Table 2-4 limits, as amended by the addenda, are the limits that govern (the Permit prevails over the reproduction), and the limit of any parameter not listed (Note 1); Permit compliance is not claimed
VOL-II-T2-4-TP | DECIDED: accepted by Interview demo assumption (2026-10-15) | VOL-II:T2-4 | technical_design; effluent; image | Treated effluent Total Phosphorus (TP): value shown in Table 2-4, unit and basis of assessment | Parameter: Total Phosphorus (TP) ¦ Unit: mg/l ¦ Limit: 1 ¦ Basis of assessment: 30-day rolling average | Parameter: Total Phosphorus (TP) ¦ Unit: mg/l ¦ Limit: 1 ¦ Basis of assessment: 30-day rolling average | Limit: 1 | VOL-II T2-4/TP p3 | VOL-II T2-4/TP p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | AMENDED (ADD-03/7.1) |  | reading re-made at ADD-02: Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED): the value, unit and basis read at BASE are unchanged. The Environmental Permit, which prevails over the reproduction, is not supplied (I-PERMIT). by ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/TP (confirms)] <- ADD-02:5.1 (ADD-02 p1) | status ACTIVE -> AMENDED (ADD-03/7.1). reading re-made at ADD-03: Re-read at ADD-03. ADD-03 7.1 (op ADD-03/7.1, PROPOSED) amends the TP limit 'from the value shown to 0.5 mg/l, assessed on the same basis'. The Unit cell (mg/l) and the Basis of assessment cell (30-day rolling average) are unchanged. The original value of 1 mg/l stays the image reading (crop row r05, cells r05c2 '1' and r05c3 '30-day rolling average'; transcription confirmed by the owner, 3 Oct 2026); 0.5 is ADD-03's separate amended value. The Environmental Permit, which prevails over the reproduction, is not supplied, so no Permit compliance is claimed for the amended TP limit (I-PERMIT). Follow-on items, listed and not decided here: rows VOL-II-3.1-01 (process capability), VOL-II-7.2-01 (reliability run, 'every parameter in Table 2-4'), VOL-II-2.4-01 and VOL-V-31.1-02 (whose post-award evidence text names only the TN amendment as 'the limits as amended') rest on this cell. VOL-V-29.3-01 is re-read separately. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed]. by ADD-03/7.1 [ADD-03; proposed] <- ADD-03:7.1 (ADD-03 p2) | VOL-II T2-4/TP p3 | VOL-II T2-4/TP p3 | VOL-II T2-4/TP p3 | VOL-II T2-4/TP p3 as amended by ADD-03 7.1 p2 | none stated in the documents |  |  | medium: value and basis come from an image reading (transcription confirmed by the owner, 3 Oct 2026); the Environmental Permit, which prevails, is not supplied | Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED): the value, unit and basis read at BASE are unchanged. The Environmental Permit, which prevails over the reproduction, is not supplied (I-PERMIT). Printed table title: 'Table 2-4 Minimum Effluent Quality Parameters at the Point of Discharge'. | unchanged since BASE; re-read by ADD-02/5.1/unchanged (confirms; accepted by a person; not counted as a confirmation); value as read: 'Limit: 1' | decided (recorded): I-PERMIT, I-READING-T24, I-VOL-II-COMPLIANCE-POINT | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/5.1/unchanged: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:T2-4/TP (VOL-II p3; image reading); ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/TP (confirms)] <- ADD-02:5.1 (ADD-02 p1); ADD-03/7.1 [ADD-03; proposed] <- ADD-03:7.1 (ADD-03 p2) | I-PERMIT; I-READING-T24; I-VOL-II-COMPLIANCE-POINT | NOT SUPPLIED: the Environmental Permit issued for the site (REL-MISSING-ENVIRONMENTAL-PERMIT, link confirmed): cannot be established: that the reproduced Table 2-4 limits, as amended by the addenda, are the limits that govern (the Permit prevails over the reproduction), and the limit of any parameter not listed (Note 1); Permit compliance is not claimed
VOL-II-T2-4-Turbidity | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:T2-4 | technical_design; effluent; image | Treated effluent turbidity: value shown in Table 2-4, unit and basis of assessment | Parameter: Turbidity ¦ Unit: NTU ¦ Limit: 2 ¦ Basis of assessment: Maximum instantaneous | Parameter: Turbidity ¦ Unit: NTU ¦ Limit: 2 ¦ Basis of assessment: Maximum instantaneous | Limit: 2 | VOL-II T2-4/Turbidity p3 | VOL-II T2-4/Turbidity p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED): the value, unit and basis read at BASE are unchanged. The Environmental Permit, which prevails over the reproduction, is not supplied (I-PERMIT). by ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/Turbidity (confirms)] <- ADD-02:5.1 (ADD-02 p1) |  | VOL-II T2-4/Turbidity p3 | VOL-II T2-4/Turbidity p3 | VOL-II T2-4/Turbidity p3 | VOL-II T2-4/Turbidity p3 | none stated in the documents |  |  | medium: value and basis come from an image reading (transcription confirmed by the owner, 3 Oct 2026); the Environmental Permit, which prevails, is not supplied | Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED): the value, unit and basis read at BASE are unchanged. The Environmental Permit, which prevails over the reproduction, is not supplied (I-PERMIT). Printed table title: 'Table 2-4 Minimum Effluent Quality Parameters at the Point of Discharge'. | unchanged since BASE; re-read by ADD-02/5.1/unchanged (confirms; accepted by a person; not counted as a confirmation); value as read: 'Limit: 2' | decided (recorded): I-PERMIT, I-READING-T24, I-VOL-II-COMPLIANCE-POINT | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/5.1/unchanged: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:T2-4/Turbidity (VOL-II p3; image reading); ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/Turbidity (confirms)] <- ADD-02:5.1 (ADD-02 p1) | I-PERMIT; I-READING-T24; I-VOL-II-COMPLIANCE-POINT | NOT SUPPLIED: the Environmental Permit issued for the site (REL-MISSING-ENVIRONMENTAL-PERMIT, link confirmed): cannot be established: that the reproduced Table 2-4 limits, as amended by the addenda, are the limits that govern (the Permit prevails over the reproduction), and the limit of any parameter not listed (Note 1); Permit compliance is not claimed
VOL-II-T2-4-FaecalColiforms | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:T2-4 | technical_design; effluent; image | Treated effluent faecal coliforms: value shown in Table 2-4, unit and basis of assessment | Parameter: Faecal Coliforms ¦ Unit: MPN/100 ml ¦ Limit: 2.2 ¦ Basis of assessment: Maximum, any single sample | Parameter: Faecal Coliforms ¦ Unit: MPN/100 ml ¦ Limit: 2.2 ¦ Basis of assessment: Maximum, any single sample | Limit: 2.2 | VOL-II T2-4/FaecalColiforms p3 | VOL-II T2-4/FaecalColiforms p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED): the value, unit and basis read at BASE are unchanged. The Environmental Permit, which prevails over the reproduction, is not supplied (I-PERMIT). by ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/FaecalColiforms (confirms)] <- ADD-02:5.1 (ADD-02 p1) |  | VOL-II T2-4/FaecalColiforms p3 | VOL-II T2-4/FaecalColiforms p3 | VOL-II T2-4/FaecalColiforms p3 | VOL-II T2-4/FaecalColiforms p3 | none stated in the documents |  |  | medium: value and basis come from an image reading (transcription confirmed by the owner, 3 Oct 2026); the Environmental Permit, which prevails, is not supplied | Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED): the value, unit and basis read at BASE are unchanged. The Environmental Permit, which prevails over the reproduction, is not supplied (I-PERMIT). Printed table title: 'Table 2-4 Minimum Effluent Quality Parameters at the Point of Discharge'. | unchanged since BASE; re-read by ADD-02/5.1/unchanged (confirms; accepted by a person; not counted as a confirmation); value as read: 'Limit: 2.2' | decided (recorded): I-PERMIT, I-READING-T24, I-VOL-II-COMPLIANCE-POINT | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/5.1/unchanged: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:T2-4/FaecalColiforms (VOL-II p3; image reading); ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/FaecalColiforms (confirms)] <- ADD-02:5.1 (ADD-02 p1) | I-PERMIT; I-READING-T24; I-VOL-II-COMPLIANCE-POINT | NOT SUPPLIED: the Environmental Permit issued for the site (REL-MISSING-ENVIRONMENTAL-PERMIT, link confirmed): cannot be established: that the reproduced Table 2-4 limits, as amended by the addenda, are the limits that govern (the Permit prevails over the reproduction), and the limit of any parameter not listed (Note 1); Permit compliance is not claimed
VOL-II-T2-4-ResidualChlorine | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:T2-4 | technical_design; effluent; image; disinfection | Treated effluent residual chlorine: range shown in Table 2-4, unit and basis of assessment | Parameter: Residual Chlorine ¦ Unit: mg/l ¦ Limit: 0.5 - 1.0 ¦ Basis of assessment: Continuous at outlet | Parameter: Residual Chlorine ¦ Unit: mg/l ¦ Limit: 0.5 - 1.0 ¦ Basis of assessment: Continuous at outlet | Limit: 0.5 - 1.0 | VOL-II T2-4/ResidualChlorine p3 | VOL-II T2-4/ResidualChlorine p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED): the value, unit and basis read at BASE are unchanged. How the qualifier 'all values are maxima' applies to this range stays open (I-VOL-II-T24-TENSIONS, CQ-T24-RANGES; Process engineer); no decision recorded. by ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/ResidualChlorine (confirms)] <- ADD-02:5.1 (ADD-02 p1) |  | VOL-II T2-4/ResidualChlorine p3 | VOL-II T2-4/ResidualChlorine p3 | VOL-II T2-4/ResidualChlorine p3 | VOL-II T2-4/ResidualChlorine p3 | none stated in the documents |  |  | medium: from an image reading (transcription confirmed by the owner, 3 Oct 2026); the Permit is not supplied; tension with VOL-II 3.3 recorded as an issue | Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED): the value, unit and basis read at BASE are unchanged. How the qualifier 'all values are maxima' applies to this range stays open (I-VOL-II-T24-TENSIONS, CQ-T24-RANGES; Process engineer); no decision recorded. Printed table title: 'Table 2-4 Minimum Effluent Quality Parameters at the Point of Discharge'. | unchanged since BASE; re-read by ADD-02/5.1/unchanged (confirms; accepted by a person; not counted as a confirmation); value as read: 'Limit: 0.5 - 1.0' | decided (recorded): I-PERMIT, I-READING-T24, I-VOL-II-T24-TENSIONS, I-VOL-II-COMPLIANCE-POINT | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/5.1/unchanged: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:T2-4/ResidualChlorine (VOL-II p3; image reading); ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/ResidualChlorine (confirms)] <- ADD-02:5.1 (ADD-02 p1) | I-PERMIT; I-READING-T24; I-VOL-II-T24-TENSIONS; I-VOL-II-COMPLIANCE-POINT | NOT SUPPLIED: the Environmental Permit issued for the site (REL-MISSING-ENVIRONMENTAL-PERMIT, link confirmed): cannot be established: that the reproduced Table 2-4 limits, as amended by the addenda, are the limits that govern (the Permit prevails over the reproduction), and the limit of any parameter not listed (Note 1); Permit compliance is not claimed
VOL-II-T2-4-pH | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:T2-4 | technical_design; effluent; image | Treated effluent pH: range shown in Table 2-4 and basis of assessment | Parameter: pH ¦ Unit: - ¦ Limit: 6.0 - 9.0 ¦ Basis of assessment: Continuous at outlet | Parameter: pH ¦ Unit: - ¦ Limit: 6.0 - 9.0 ¦ Basis of assessment: Continuous at outlet | Limit: 6.0 - 9.0 | VOL-II T2-4/pH p3 | VOL-II T2-4/pH p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED): the value, unit and basis read at BASE are unchanged. How the qualifier 'all values are maxima' applies to this range stays open (I-VOL-II-T24-TENSIONS, CQ-T24-RANGES; Process engineer); no decision recorded. by ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/pH (confirms)] <- ADD-02:5.1 (ADD-02 p1) |  | VOL-II T2-4/pH p3 | VOL-II T2-4/pH p3 | VOL-II T2-4/pH p3 | VOL-II T2-4/pH p3 | none stated in the documents |  |  | medium: from an image reading (transcription confirmed by the owner, 3 Oct 2026); the Environmental Permit, which prevails, is not supplied | Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED): the value, unit and basis read at BASE are unchanged. How the qualifier 'all values are maxima' applies to this range stays open (I-VOL-II-T24-TENSIONS, CQ-T24-RANGES; Process engineer); no decision recorded. Printed table title: 'Table 2-4 Minimum Effluent Quality Parameters at the Point of Discharge'. | unchanged since BASE; re-read by ADD-02/5.1/unchanged (confirms; accepted by a person; not counted as a confirmation); value as read: 'Limit: 6.0 - 9.0' | decided (recorded): I-PERMIT, I-READING-T24, I-VOL-II-T24-TENSIONS, I-VOL-II-COMPLIANCE-POINT | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/5.1/unchanged: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:T2-4/pH (VOL-II p3; image reading); ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/pH (confirms)] <- ADD-02:5.1 (ADD-02 p1) | I-PERMIT; I-READING-T24; I-VOL-II-T24-TENSIONS; I-VOL-II-COMPLIANCE-POINT | NOT SUPPLIED: the Environmental Permit issued for the site (REL-MISSING-ENVIRONMENTAL-PERMIT, link confirmed): cannot be established: that the reproduced Table 2-4 limits, as amended by the addenda, are the limits that govern (the Permit prevails over the reproduction), and the limit of any parameter not listed (Note 1); Permit compliance is not claimed
VOL-II-T2-4-OilGrease | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:T2-4 | technical_design; effluent; image | Treated effluent oil and grease: value shown in Table 2-4, unit and basis of assessment | Parameter: Oil and Grease ¦ Unit: mg/l ¦ Limit: 1 ¦ Basis of assessment: Maximum, any single sample | Parameter: Oil and Grease ¦ Unit: mg/l ¦ Limit: 1 ¦ Basis of assessment: Maximum, any single sample | Limit: 1 | VOL-II T2-4/OilGrease p3 | VOL-II T2-4/OilGrease p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED): the value, unit and basis read at BASE are unchanged. The Environmental Permit, which prevails over the reproduction, is not supplied (I-PERMIT). by ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/OilGrease (confirms)] <- ADD-02:5.1 (ADD-02 p1) |  | VOL-II T2-4/OilGrease p3 | VOL-II T2-4/OilGrease p3 | VOL-II T2-4/OilGrease p3 | VOL-II T2-4/OilGrease p3 | none stated in the documents |  |  | medium: value and basis come from an image reading (transcription confirmed by the owner, 3 Oct 2026); the Environmental Permit, which prevails, is not supplied | Re-read at ADD-02: 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED): the value, unit and basis read at BASE are unchanged. The Environmental Permit, which prevails over the reproduction, is not supplied (I-PERMIT). Printed table title: 'Table 2-4 Minimum Effluent Quality Parameters at the Point of Discharge'. | unchanged since BASE; re-read by ADD-02/5.1/unchanged (confirms; accepted by a person; not counted as a confirmation); value as read: 'Limit: 1' | decided (recorded): I-PERMIT, I-READING-T24, I-VOL-II-COMPLIANCE-POINT | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/5.1/unchanged: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:T2-4/OilGrease (VOL-II p3; image reading); ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/OilGrease (confirms)] <- ADD-02:5.1 (ADD-02 p1) | I-PERMIT; I-READING-T24; I-VOL-II-COMPLIANCE-POINT | NOT SUPPLIED: the Environmental Permit issued for the site (REL-MISSING-ENVIRONMENTAL-PERMIT, link confirmed): cannot be established: that the reproduced Table 2-4 limits, as amended by the addenda, are the limits that govern (the Permit prevails over the reproduction), and the limit of any parameter not listed (Note 1); Permit compliance is not claimed
VOL-II-T2-4-NOTE1 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:T2-4 | technical_design; effluent; image; permit | Parameters not listed in Table 2-4: the limits stated in the Environmental Permit apply (the Permit is not in the pack) | Note 1: Where a parameter is not listed above, the limit stated in the Environmental Permit shall apply. | Note 1: Where a parameter is not listed above, the limit stated in the Environmental Permit shall apply. | Where a parameter is not listed above, the limit stated in the Environmental Permit shall apply. | VOL-II T2-4/note1 p3 | VOL-II T2-4/note1 p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II T2-4/note1 p3 | VOL-II T2-4/note1 p3 | VOL-II T2-4/note1 p3 | VOL-II T2-4/note1 p3 | none stated in the documents |  |  | low: image reading (transcription confirmed by the owner, 3 Oct 2026); the Permit and its limits are not supplied, so these limits cannot be identified from the pack | Read from the image (transcription confirmed by the owner, 3 Oct 2026). | unchanged since BASE; value as read: 'Where a parameter is not listed above, the limit stated in the Environmental Permit shall apply.' | decided (recorded): I-PERMIT, I-READING-T24 | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:T2-4/note1 (VOL-II p3; image reading) | I-PERMIT; I-READING-T24 | NOT SUPPLIED: the Environmental Permit issued for the site (REL-MISSING-ENVIRONMENTAL-PERMIT, link confirmed): cannot be established: that the reproduced Table 2-4 limits, as amended by the addenda, are the limits that govern (the Permit prevails over the reproduction), and the limit of any parameter not listed (Note 1); Permit compliance is not claimed
VOL-II-3.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:3.1 | technical_design; process | Treatment process able to achieve the Table 2-4 effluent quality under all Table 2-2 design influent conditions | [VOL-II 3.1 p3] The treatment process shall be capable of achieving the effluent quality in Table 2-4 under all design influent conditions in Table 2-2. The Authority does not mandate a particular process train. [VOL-II H:S3 p3] SECTION 3 — PROCESS REQUIREMENTS [VOL-II T2-2/bod5 p2] Parameter: BOD5 ¦ Unit: mg/l ¦ Average: 320 ¦ Peak (design): 480 [VOL-II T2-2/cod p2] Parameter: COD ¦ Unit: mg/l ¦ Average: 640 ¦ Peak (design): 950 [VOL-II T2-2/total-suspended-solids p2] Parameter: Total Suspended Solids ¦ Unit: mg/l ¦ Average: 350 ¦ Peak (design): 520 [VOL-II T2-2/total-nitrogen p2] Parameter: Total Nitrogen ¦ Unit: mg/l ¦ Average: 55 ¦ Peak (design): 80 [VOL-II T2-2/total-phosphorus p2] Parameter: Total Phosphorus ¦ Unit: mg/l ¦ Average: 9 ¦ Peak (design): 14 [VOL-II T2-2/temperature p2] Parameter: Temperature ¦ Unit: °C ¦ Average: 24 ¦ Peak (design): 34 (max) / 14 (min) | [VOL-II 3.1 p3] The treatment process shall be capable of achieving the effluent quality in Table 2-4 under all design influent conditions in Table 2-2. The Authority does not mandate a particular process train. [VOL-II H:S3 p3] SECTION 3 — PROCESS REQUIREMENTS [VOL-II T2-2/bod5 p2] Parameter: BOD5 ¦ Unit: mg/l ¦ Average: 320 ¦ Peak (design): 480 [VOL-II T2-2/cod p2] Parameter: COD ¦ Unit: mg/l ¦ Average: 640 ¦ Peak (design): 950 [VOL-II T2-2/total-suspended-solids p2] Parameter: Total Suspended Solids ¦ Unit: mg/l ¦ Average: 350 ¦ Peak (design): 520 [VOL-II T2-2/total-nitrogen p2] Parameter: Total Nitrogen ¦ Unit: mg/l ¦ Average: 55 ¦ Peak (design): 80 [VOL-II T2-2/total-phosphorus p2] Parameter: Total Phosphorus ¦ Unit: mg/l ¦ Average: 9 ¦ Peak (design): 14 [VOL-II T2-2/temperature p2] Parameter: Temperature ¦ Unit: °C ¦ Average: 24 ¦ Peak (design): 34 (max) / 14 (min) | The treatment process shall be capable of achieving the effluent quality in Table 2-4 under all design influent conditions in Table 2-2. | VOL-II 3.1 p3 | VOL-II 3.1 p3; VOL-II H:S3 p3; VOL-II T2-2/bod5 p2; VOL-II T2-2/cod p2; VOL-II T2-2/total-suspended-solids p2; VOL-II T2-2/total-nitrogen p2; VOL-II T2-2/total-phosphorus p2; VOL-II T2-2/temperature p2 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE | reading re-made at ADD-01: ADD-01 Q1: no process train is mandated (a membrane bioreactor is not required); any process capable of meeting Table 2-4 under the Table 2-2 influent conditions is acceptable. by ADD-01/Q1 [ADD-01; proposed; annotates VOL-II:3.1 (interprets)] <- ADD-01:Q1 (ADD-01 p1) | reading re-made at ADD-02: ADD-02 5.2: Bidders shall reflect the amended TN limit (ADD-02 5.1: 3 mg/l, row VOL-II-T2-4-TN) in the process design submitted under Volume II Section 3. by ADD-02/5.2 [ADD-02; proposed; annotates VOL-II:H:S3 (adds_obligation)] <- ADD-02:5.2 (ADD-02 p1) |  | VOL-II 3.1 p3 | VOL-II 3.1 p3 | VOL-II 3.1 p3 | VOL-II 3.1 p3 | none stated in the documents |  |  | medium: verbatim; the effluent quality it refers to is an image reading (transcription confirmed by the owner, 3 Oct 2026) and the Permit that prevails is not supplied | ADD-02 5.2: Bidders shall reflect the amended TN limit (ADD-02 5.1: 3 mg/l, row VOL-II-T2-4-TN) in the process design submitted under Volume II Section 3. | own words unchanged at ADD-02, but what it depends on changed (dependency; see A2); re-read by ADD-01/Q1 (interprets; accepted by a person; not counted as a confirmation), ADD-02/5.2 (adds_obligation; accepted by a person; not counted as a confirmation); value as read: 'The treatment process shall be capable of achieving the effluent quality in Table 2-4 under all design influent conditi…' | decided (recorded): I-READING-T24, I-PERMIT, I-VOL-II-T24-TENSIONS, I-VOL-II-AT-ALL-TIMES, I-VOL-II-COMPLIANCE-POINT | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/Q1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/5.2: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:3.1 (VOL-II p3; text layer); VOL-II:H:S3 (VOL-II p3; text layer); VOL-II:T2-2/bod5 (VOL-II p2; text layer); VOL-II:T2-2/cod (VOL-II p2; text layer); VOL-II:T2-2/total-suspended-solids (VOL-II p2; text layer); VOL-II:T2-2/total-nitrogen (VOL-II p2; text layer); VOL-II:T2-2/total-phosphorus (VOL-II p2; text layer); VOL-II:T2-2/temperature (VOL-II p2; text layer); ADD-01/Q1 [ADD-01; proposed; annotates VOL-II:3.1 (interprets)] <- ADD-01:Q1 (ADD-01 p1); ADD-02/5.2 [ADD-02; proposed; annotates VOL-II:H:S3 (adds_obligation)] <- ADD-02:5.2 (ADD-02 p1) | I-READING-T24; I-PERMIT; I-VOL-II-T24-TENSIONS (via REL-T24-PROCESS-DESIGN (confirmed)); I-VOL-II-AT-ALL-TIMES (via REL-T24-PROCESS-DESIGN (confirmed)); I-VOL-II-COMPLIANCE-POINT (via REL-T24-PROCESS-DESIGN (confirmed)) | <- REL-T24-PROCESS-DESIGN [confirmed limit_applies] from VOL-II:T2-4; REACHED at ADD-02 (confirmed dependency): from VOL-II:T2-4 via REL-T24-PROCESS-DESIGN
VOL-II-3.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:3.2 | technical_design; process; membrane; lifecycle | If a membrane process is proposed: show membrane replacement provisions in the lifecycle plan | Where a membrane process is proposed, the Project Company shall demonstrate membrane replacement provisions in the lifecycle plan and shall warrant a membrane life of not less than seven (7) years. | Where a membrane process is proposed, the Project Company shall demonstrate membrane replacement provisions in the lifecycle plan and shall warrant a membrane life of not less than seven (7) years. | Where a membrane process is proposed, the Project Company shall demonstrate membrane replacement provisions in the lifecycle plan | VOL-II 3.2 p3 | VOL-II 3.2 p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 3.2 p3 | VOL-II 3.2 p3 | VOL-II 3.2 p3 | VOL-II 3.2 p3 | none stated in the documents |  |  | high: verbatim text-layer clause | Applies only where a membrane process is proposed. | unchanged since BASE; value as read: 'Where a membrane process is proposed, the Project Company shall demonstrate membrane replacement provisions in the life…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:3.2 (VOL-II p3; text layer)
VOL-II-3.2-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:3.2 | technical_design; process; membrane; warranty | If a membrane process is proposed: warrant a membrane life of at least 7 years | Where a membrane process is proposed, the Project Company shall demonstrate membrane replacement provisions in the lifecycle plan and shall warrant a membrane life of not less than seven (7) years. | Where a membrane process is proposed, the Project Company shall demonstrate membrane replacement provisions in the lifecycle plan and shall warrant a membrane life of not less than seven (7) years. | shall warrant a membrane life of not less than seven (7) years | VOL-II 3.2 p3 | VOL-II 3.2 p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 3.2 p3 | VOL-II 3.2 p3 | VOL-II 3.2 p3 | VOL-II 3.2 p3 | none stated in the documents |  |  | high: verbatim text-layer clause | Applies only where a membrane process is proposed. | unchanged since BASE; value as read: 'shall warrant a membrane life of not less than seven (7) years' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:3.2 (VOL-II p3; text layer)
VOL-II-3.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:3.3 | technical_design; process; disinfection | Disinfection by chlorination with dechlorination provision, by UV with a validated dose, or both; ozonation alone not acceptable | Disinfection shall be by chlorination with provision for dechlorination, or by ultraviolet irradiation with a validated dose, or by a combination. Ozonation alone is not acceptable. | Disinfection shall be by chlorination with provision for dechlorination, or by ultraviolet irradiation with a validated dose, or by a combination. Ozonation alone is not acceptable. | Disinfection shall be by chlorination with provision for dechlorination, or by ultraviolet irradiation with a validated dose, or by a combination. | VOL-II 3.3 p3 | VOL-II 3.3 p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 3.3 p3 | VOL-II 3.3 p3 | VOL-II 3.3 p3 | VOL-II 3.3 p3 | none stated in the documents |  |  | high: verbatim text-layer clause; the tension with Table 2-4 is recorded as an issue | 'Ozonation alone is not acceptable.' Table 2-4 (image) sets residual chlorine 0.5-1.0 mg/l continuous at outlet; how that sits with UV-only disinfection or dechlorination is for a person. | unchanged since BASE; value as read: 'Disinfection shall be by chlorination with provision for dechlorination, or by ultraviolet irradiation with a validated…' | decided (recorded): I-VOL-II-T24-TENSIONS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:3.3 (VOL-II p3; text layer) | I-VOL-II-T24-TENSIONS
VOL-II-3.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:3.4 | environmental_performance; odour | Odour at the site boundary of no more than 5 OU/m3 as a 98th percentile hourly value | Odour control shall achieve not more than 5 OU/m³ at the site boundary, assessed as a 98th percentile hourly value. | Odour control shall achieve not more than 5 OU/m³ at the site boundary, assessed as a 98th percentile hourly value. | Odour control shall achieve not more than 5 OU/m³ at the site boundary, assessed as a 98th percentile hourly value. | VOL-II 3.4 p3 | VOL-II 3.4 p3 | scored | Environmental | Environmental lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 3.4 p3 | VOL-II 3.4 p3 | VOL-II 3.4 p3 | VOL-II 3.4 p3 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'Odour control shall achieve not more than 5 OU/m³ at the site boundary, assessed as a 98th percentile hourly value.' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:3.4 (VOL-II p3; text layer)
VOL-II-3.5-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:3.5 | environmental_performance; noise | Noise at the nearest sensitive receptor of no more than 55 dB(A) by day and 45 dB(A) by night | Noise at the nearest sensitive receptor shall not exceed 55 dB(A) by day and 45 dB(A) by night. | Noise at the nearest sensitive receptor shall not exceed 55 dB(A) by day and 45 dB(A) by night. | Noise at the nearest sensitive receptor shall not exceed 55 dB(A) by day and 45 dB(A) by night. | VOL-II 3.5 p3 | VOL-II 3.5 p3 | scored | Environmental | Environmental lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 3.5 p3 | VOL-II 3.5 p3 | VOL-II 3.5 p3 | VOL-II 3.5 p3 | none stated in the documents |  |  | high: verbatim text-layer clause | The receptor and the day and night periods are not identified in the extract. | unchanged since BASE; value as read: 'Noise at the nearest sensitive receptor shall not exceed 55 dB(A) by day and 45 dB(A) by night.' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:3.5 (VOL-II p3; text layer)
VOL-II-4.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:4.1 | technical_design; hydraulics | Hydraulic profile to pass the Table 2-6 flows without surcharging any structure or relying on pumped bypass | The hydraulic profile shall accommodate the flows in Table 2-6 without surcharge of any structure and without reliance on pumped bypass. | The hydraulic profile shall accommodate the flows in Table 2-6 without surcharge of any structure and without reliance on pumped bypass. | The hydraulic profile shall accommodate the flows in Table 2-6 without surcharge of any structure and without reliance on pumped bypass. | VOL-II 4.1 p3 | VOL-II 4.1 p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 4.1 p3 | VOL-II 4.1 p3 | VOL-II 4.1 p3 | VOL-II 4.1 p3 | none stated in the documents |  |  | medium: verbatim; the Table 2-6 peak hourly and storm flows are questioned and ADD-02 Q11 did not resolve them | The flows are rows VOL-II-T2-6-*. | unchanged since BASE; value as read: 'The hydraulic profile shall accommodate the flows in Table 2-6 without surcharge of any structure and without reliance …' | decided (recorded): I-FLOWS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:4.1 (VOL-II p3; text layer) | I-FLOWS
VOL-II-T2-6-1 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:T2-6 | technical_design; hydraulics; design_flow | Hydraulic design criterion 2-6.1: average daily flow of 120,000 m3/day | Ref: 2-6.1 ¦ Criterion: Average daily flow ¦ Value: 120,000 ¦ Unit: m³/day | Ref: 2-6.1 ¦ Criterion: Average daily flow ¦ Value: 120,000 ¦ Unit: m³/day | Value: 120,000 | VOL-II T2-6/2-6.1 p3 | VOL-II T2-6/2-6.1 p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II T2-6/2-6.1 p3 | VOL-II T2-6/2-6.1 p3 | VOL-II T2-6/2-6.1 p3 | VOL-II T2-6/2-6.1 p3 | none stated in the documents |  |  | medium: verbatim table row; the consistency of the Table 2-6 flows is questioned (I-FLOWS) | The same figure as the nominal capacity in VOL-II 2.1. | unchanged since BASE; value as read: 'Value: 120,000' | decided (recorded): I-FLOWS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:T2-6/2-6.1 (VOL-II p3; text layer) | I-FLOWS
VOL-II-T2-6-2 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:T2-6 | technical_design; hydraulics; design_flow | Hydraulic design criterion 2-6.2: peak hourly flow (design) of 7,500 m3/h | Ref: 2-6.2 ¦ Criterion: Peak hourly flow (design) ¦ Value: 7,500 ¦ Unit: m³/h | Ref: 2-6.2 ¦ Criterion: Peak hourly flow (design) ¦ Value: 7,500 ¦ Unit: m³/h | Value: 7,500 | VOL-II T2-6/2-6.2 p3 | VOL-II T2-6/2-6.2 p3 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II T2-6/2-6.2 p3 | VOL-II T2-6/2-6.2 p3 | VOL-II T2-6/2-6.2 p3 | VOL-II T2-6/2-6.2 p3 | none stated in the documents |  |  | medium: verbatim table row; questioned in ADD-02 Q11 against the 120,000 m3/day average, and not answered (I-FLOWS) | Also the design flow of the transmission main (VOL-II 5.2). | unchanged since BASE; value as read: 'Value: 7,500' | decided (recorded): I-FLOWS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:T2-6/2-6.2 (VOL-II p3; text layer) | I-FLOWS
VOL-II-T2-6-3 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:T2-6 | technical_design; hydraulics; design_flow | Hydraulic design criterion 2-6.3: minimum night flow of 1,800 m3/h | Ref: 2-6.3 ¦ Criterion: Minimum night flow ¦ Value: 1,800 ¦ Unit: m³/h | Ref: 2-6.3 ¦ Criterion: Minimum night flow ¦ Value: 1,800 ¦ Unit: m³/h | Value: 1,800 | VOL-II T2-6/2-6.3 p4 | VOL-II T2-6/2-6.3 p4 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II T2-6/2-6.3 p4 | VOL-II T2-6/2-6.3 p4 | VOL-II T2-6/2-6.3 p4 | VOL-II T2-6/2-6.3 p4 | none stated in the documents |  |  | high: verbatim table row |  | unchanged since BASE; value as read: 'Value: 1,800' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:T2-6/2-6.3 (VOL-II p4; text layer)
VOL-II-T2-6-4 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:T2-6 | technical_design; hydraulics; design_flow; storm | Hydraulic design criterion 2-6.4: pass storm flow of 3 x dry weather flow to full treatment | Ref: 2-6.4 ¦ Criterion: Storm flow to be passed to full treatment ¦ Value: 3 x dry weather flow ¦ Unit: — | Ref: 2-6.4 ¦ Criterion: Storm flow to be passed to full treatment ¦ Value: 3 x dry weather flow ¦ Unit: — | Value: 3 x dry weather flow | VOL-II T2-6/2-6.4 p4 | VOL-II T2-6/2-6.4 p4 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II T2-6/2-6.4 p4 | VOL-II T2-6/2-6.4 p4 | VOL-II T2-6/2-6.4 p4 | VOL-II T2-6/2-6.4 p4 | none stated in the documents |  |  | medium: verbatim table row; dry weather flow is undefined and 3 x DWF may exceed the 7,500 m3/h design peak (I-FLOWS) | 'Dry weather flow' is not defined in the pack. | unchanged since BASE; value as read: 'Value: 3 x dry weather flow' | decided (recorded): I-FLOWS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:T2-6/2-6.4 (VOL-II p4; text layer) | I-FLOWS
VOL-II-T2-6-5 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:T2-6 | technical_design; hydraulics | Hydraulic design criterion 2-6.5: inlet works design head of 1.8 m | Ref: 2-6.5 ¦ Criterion: Inlet works design head ¦ Value: 1.8 ¦ Unit: m | Ref: 2-6.5 ¦ Criterion: Inlet works design head ¦ Value: 1.8 ¦ Unit: m | Value: 1.8 | VOL-II T2-6/2-6.5 p4 | VOL-II T2-6/2-6.5 p4 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II T2-6/2-6.5 p4 | VOL-II T2-6/2-6.5 p4 | VOL-II T2-6/2-6.5 p4 | VOL-II T2-6/2-6.5 p4 | none stated in the documents |  |  | high: verbatim table row |  | unchanged since BASE; value as read: 'Value: 1.8' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:T2-6/2-6.5 (VOL-II p4; text layer)
VOL-II-T2-6-6 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:T2-6 | technical_design; hydraulics | Hydraulic design criterion 2-6.6: maximum velocity in channels of 1.2 m/s | Ref: 2-6.6 ¦ Criterion: Maximum velocity in channels ¦ Value: 1.2 ¦ Unit: m/s | Ref: 2-6.6 ¦ Criterion: Maximum velocity in channels ¦ Value: 1.2 ¦ Unit: m/s | Value: 1.2 | VOL-II T2-6/2-6.6 p4 | VOL-II T2-6/2-6.6 p4 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II T2-6/2-6.6 p4 | VOL-II T2-6/2-6.6 p4 | VOL-II T2-6/2-6.6 p4 | VOL-II T2-6/2-6.6 p4 | none stated in the documents |  |  | high: verbatim table row |  | unchanged since BASE; value as read: 'Value: 1.2' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:T2-6/2-6.6 (VOL-II p4; text layer)
VOL-II-4.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:4.2 | clarification; hydraulics; design_flow | Check the consistency of the Volume II flow figures and raise any inconsistency as a clarification under VOL-I 5.1 | The Project Company shall satisfy itself as to the consistency of the flow figures stated in this Volume and shall raise any inconsistency as a clarification under Volume I Clause 5.1. | The Project Company shall satisfy itself as to the consistency of the flow figures stated in this Volume and shall raise any inconsistency as a clarification under Volume I Clause 5.1. | shall satisfy itself as to the consistency of the flow figures stated in this Volume and shall raise any inconsistency as a clarification under Volume I Clause 5.1 | VOL-II 4.2 p4 | VOL-II 4.2 p4 | procedural | Technical | Process engineer | EV-CLARIFICATIONS | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q11 (p2), asked about a peak hourly flow of 7,500 m3/h against a daily average of 120,000 m3/day, answers: 'Bidders shall design to the figures stated in Volume II. Volume II Clause 4.2 applies.' It settles the question asked (design to the Volume II figures; this clause applies) and does not comment on their consistency, which this clause leaves to the Bidder, or define 'dry weather flow' (CQ-DWF-STORM-FLOW). Engineering reading, for the process engineer to confirm (not the Authority's words): 120,000 m3/day is 5,000 m3/h on average and 7,500 m3/h a peaking factor of 1.5, so the two figures are not contradictory (I-FLOWS). by ADD-02/Q11 [ADD-02; proposed; annotates VOL-II:4.2 (confirms)] <- ADD-02:Q11 (ADD-02 p2) |  | VOL-II 4.2 p4 | VOL-II 4.2 p4 | VOL-II 4.2 p4 | VOL-II 4.2 p4 | none stated in the documents |  |  | medium: verbatim; the ADD-02 Q11 answer refers back to this clause without resolving the figures | ADD-02 Q11 (p2), asked about a peak hourly flow of 7,500 m3/h against a daily average of 120,000 m3/day, answers: 'Bidders shall design to the figures stated in Volume II. Volume II Clause 4.2 applies.' It settles the question asked (design to the Volume II figures; this clause applies) and does not comment on their consistency, which this clause leaves to the Bidder, or define 'dry weather flow' (CQ-DWF-STORM-FLOW). Engineering reading, for the process engineer to confirm (not the Authority's words): 120,000 m3/day is 5,000 m3/h on average and 7,500 m3/h a peaking factor of 1.5, so the two figures are not contradictory (I-FLOWS). | unchanged since BASE; re-read by ADD-02/Q11 (confirms; accepted by a person; not counted as a confirmation); value as read: 'shall satisfy itself as to the consistency of the flow figures stated in this Volume and shall raise any inconsistency …' | decided (recorded): I-FLOWS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/Q11: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:4.2 (VOL-II p4; text layer); ADD-02/Q11 [ADD-02; proposed; annotates VOL-II:4.2 (confirms)] <- ADD-02:Q11 (ADD-02 p2) | I-FLOWS
VOL-II-4.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:4.3 | technical_design; reliability; redundancy | Each treatment stage arranged in at least four parallel streams | Each treatment stage shall be arranged in not fewer than four (4) parallel streams, such that the Facility can meet Table 2-4 with any one stream out of service. | Each treatment stage shall be arranged in not fewer than four (4) parallel streams, such that the Facility can meet Table 2-4 with any one stream out of service. | Each treatment stage shall be arranged in not fewer than four (4) parallel streams | VOL-II 4.3 p4 | VOL-II 4.3 p4 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 4.3 p4 | VOL-II 4.3 p4 | VOL-II 4.3 p4 | VOL-II 4.3 p4 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'Each treatment stage shall be arranged in not fewer than four (4) parallel streams' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:4.3 (VOL-II p4; text layer)
VOL-II-4.3-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:4.3 | technical_design; reliability; redundancy; effluent | Facility able to meet Table 2-4 with any one stream out of service | Each treatment stage shall be arranged in not fewer than four (4) parallel streams, such that the Facility can meet Table 2-4 with any one stream out of service. | Each treatment stage shall be arranged in not fewer than four (4) parallel streams, such that the Facility can meet Table 2-4 with any one stream out of service. | such that the Facility can meet Table 2-4 with any one stream out of service | VOL-II 4.3 p4 | VOL-II 4.3 p4 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 4.3 p4 | VOL-II 4.3 p4 | VOL-II 4.3 p4 | VOL-II 4.3 p4 | none stated in the documents |  |  | medium: verbatim; the Table 2-4 limits it refers to are an image reading (transcription confirmed by the owner, 3 Oct 2026) | Table 2-4 limits: rows VOL-II-T2-4-*. | own words unchanged at ADD-02, but what it depends on changed (dependency; see A2); value as read: 'such that the Facility can meet Table 2-4 with any one stream out of service' | decided (recorded): I-READING-T24, I-VOL-II-T24-TENSIONS, I-VOL-II-AT-ALL-TIMES, I-VOL-II-COMPLIANCE-POINT, I-PERMIT | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:4.3 (VOL-II p4; text layer) | I-READING-T24; I-VOL-II-T24-TENSIONS (via REL-T24-COMPLIANCE-MONITORING-STREAMS (confirmed)); I-VOL-II-AT-ALL-TIMES (via REL-T24-COMPLIANCE-MONITORING-STREAMS (confirmed)); I-VOL-II-COMPLIANCE-POINT (via REL-T24-COMPLIANCE-MONITORING-STREAMS (confirmed)); I-PERMIT (via REL-MISSING-ENVIRONMENTAL-PERMIT > REL-T24-COMPLIANCE-MONITORING-STREAMS (confirmed)) | <- REL-T24-COMPLIANCE-MONITORING-STREAMS [confirmed limit_applies] from VOL-II:T2-4; REACHED at ADD-02 (confirmed dependency): from VOL-II:T2-4 via REL-T24-COMPLIANCE-MONITORING-STREAMS
VOL-II-4.4-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:4.4 | technical_design; reliability; redundancy | N+1 standby provision for all rotating equipment | Standby provision for all rotating equipment shall be N+1. Standby power shall be sized to carry the full inlet works, the disinfection stage and the effluent pumping station for not less than seventy-two (72) hours. | Standby provision for all rotating equipment shall be N+1. Standby power shall be sized to carry the full inlet works, the disinfection stage and the effluent pumping station for not less than ninety-six (96) hours. | Standby provision for all rotating equipment shall be N+1. | VOL-II 4.4 p4 as amended by ADD-02 4.1 p1 | VOL-II 4.4 p4 <- ADD-02/4.1 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE (unit amended by ADD-02/4.1; the row's words unchanged) | ACTIVE (unit amended by ADD-02/4.1; the row's words unchanged) |  | status ACTIVE -> ACTIVE (unit amended by ADD-02/4.1; the row's words unchanged). reading re-made at ADD-02: ADD-02 4.1 changes the standby power duration in this clause (72 to 96 hours, row VOL-II-4.4-01); the N+1 requirement is unchanged. by ADD-02/4.1 [ADD-02; proposed] <- ADD-02:4.1 (ADD-02 p1) |  | VOL-II 4.4 p4 | VOL-II 4.4 p4 | VOL-II 4.4 p4 as amended by ADD-02 4.1 p1 | VOL-II 4.4 p4 as amended by ADD-02 4.1 p1 | none stated in the documents |  |  | high: verbatim text-layer clause | ADD-02 4.1 changes the standby power duration in this clause (72 to 96 hours, row VOL-II-4.4-01); the N+1 requirement is unchanged. | unchanged since BASE (unit amended elsewhere at ADD-02 by ADD-02/4.1; the row's words unchanged); value as read: 'Standby provision for all rotating equipment shall be N+1.' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/4.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-02/4.1: accepted | VOL-II:4.4 (VOL-II p4; text layer); ADD-02/4.1 [ADD-02; proposed] <- ADD-02:4.1 (ADD-02 p1)
VOL-II-4.5-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:4.5 | technical_design; transmission_main; surge | Surge protection on the transmission main for the full range of operating scenarios, including simultaneous pump trip | The transmission main shall be provided with surge protection designed for the full range of operating scenarios including simultaneous pump trip. | The transmission main shall be provided with surge protection designed for the full range of operating scenarios including simultaneous pump trip. | The transmission main shall be provided with surge protection designed for the full range of operating scenarios including simultaneous pump trip. | VOL-II 4.5 p4 | VOL-II 4.5 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 4.5 p4 | VOL-II 4.5 p4 | VOL-II 4.5 p4 | VOL-II 4.5 p4 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'The transmission main shall be provided with surge protection designed for the full range of operating scenarios includ…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:4.5 (VOL-II p4; text layer)
VOL-II-5.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:5.1 | technical_design; transmission_main; route | Treated effluent main of about 18 km from the Facility outlet chamber to the delivery point shown on Drawing 03-C-114 | The treated effluent transmission main shall be approximately eighteen (18) kilometres in length between the Facility outlet chamber and the delivery point shown on Drawing 03-C-114. | The treated effluent transmission main shall be approximately eighteen (18) kilometres in length between the Facility outlet chamber and the delivery point shown on Drawing 03-C-114. | approximately eighteen (18) kilometres in length between the Facility outlet chamber and the delivery point shown on Drawing 03-C-114 | VOL-II 5.1 p4 | VOL-II 5.1 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 5.1 p4 | VOL-II 5.1 p4 | VOL-II 5.1 p4 | VOL-II 5.1 p4 | none stated in the documents |  |  | low: the delivery point is shown only on Drawing 03-C-114 (Volume III), which is not supplied; route and end point cannot be established | The delivery point is also where VOL-II 5.2 sets the residual head and where VOL-V 31.1(c) measures delivery. | unchanged since BASE; value as read: 'approximately eighteen (18) kilometres in length between the Facility outlet chamber and the delivery point shown on Dr…' | decided (recorded): I-VOL-III, I-VOL-II-COMPLIANCE-POINT | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:5.1 (VOL-II p4; text layer) | I-VOL-III; I-VOL-II-COMPLIANCE-POINT
VOL-II-5.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:5.2 | technical_design; transmission_main; hydraulics | Size the main for the Table 2-6 peak hourly flow at a velocity of no more than 2.0 m/s | [VOL-II 5.2 p4] The main shall be sized for the peak hourly flow in Table 2-6 with a maximum velocity of 2.0 m/s and a minimum residual head of 15 m at the delivery point. [VOL-II T2-6/2-6.2 p3] Ref: 2-6.2 ¦ Criterion: Peak hourly flow (design) ¦ Value: 7,500 ¦ Unit: m³/h | [VOL-II 5.2 p4] The main shall be sized for the peak hourly flow in Table 2-6 with a maximum velocity of 2.0 m/s and a minimum residual head of 15 m at the delivery point. [VOL-II T2-6/2-6.2 p3] Ref: 2-6.2 ¦ Criterion: Peak hourly flow (design) ¦ Value: 7,500 ¦ Unit: m³/h | The main shall be sized for the peak hourly flow in Table 2-6 with a maximum velocity of 2.0 m/s | VOL-II 5.2 p4 | VOL-II 5.2 p4; VOL-II T2-6/2-6.2 p3 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 5.2 p4 | VOL-II 5.2 p4 | VOL-II 5.2 p4 | VOL-II 5.2 p4 | none stated in the documents |  |  | medium: verbatim; the peak hourly flow it is sized for is questioned (I-FLOWS) | Table 2-6 row 2-6.2 is listed as a unit. | unchanged since BASE; value as read: 'The main shall be sized for the peak hourly flow in Table 2-6 with a maximum velocity of 2.0 m/s' | decided (recorded): I-FLOWS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:5.2 (VOL-II p4; text layer); VOL-II:T2-6/2-6.2 (VOL-II p3; text layer) | I-FLOWS
VOL-II-5.2-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:5.2 | technical_design; transmission_main; hydraulics | Minimum residual head of 15 m at the delivery point | The main shall be sized for the peak hourly flow in Table 2-6 with a maximum velocity of 2.0 m/s and a minimum residual head of 15 m at the delivery point. | The main shall be sized for the peak hourly flow in Table 2-6 with a maximum velocity of 2.0 m/s and a minimum residual head of 15 m at the delivery point. | a minimum residual head of 15 m at the delivery point | VOL-II 5.2 p4 | VOL-II 5.2 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 5.2 p4 | VOL-II 5.2 p4 | VOL-II 5.2 p4 | VOL-II 5.2 p4 | none stated in the documents |  |  | medium: verbatim; the delivery point is shown only on Drawing 03-C-114, which is not supplied | After award, failing to deliver at the required residual head is an Unavailability Event (VOL-V 31.1(c), row VOL-V-31.1-03). | unchanged since BASE; value as read: 'a minimum residual head of 15 m at the delivery point' | decided (recorded): I-VOL-III | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:5.2 (VOL-II p4; text layer) | I-VOL-III
VOL-II-5.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:5.3 | technical_design; transmission_main; materials | Main of internally lined, externally protected ductile iron; other materials only with a whole-life cost comparison | The main shall be of ductile iron to the relevant international standard, internally lined and externally protected, with a minimum nominal diameter of DN1200. Alternative materials will be considered only where supported by a whole-life cost comparison. | The main shall be of ductile iron to the relevant international standard, internally lined and externally protected, with a minimum nominal diameter of DN1200. Alternative materials will be considered only where supported by a whole-life cost comparison. Glass reinforced plastic pipe of an equivalent pressure class is acceptable for the buried sections of the transmission main, subject to the whole-life cost comparison required by this Clause. | Glass reinforced plastic pipe of an equivalent pressure class is acceptable for the buried sections of the transmission main, subject to the whole-life cost comparison required by this Clause. | ADD-01 5.1 p1 (amending VOL-II 5.3) | VOL-II 5.3 p4 <- ADD-01/5.1 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | AMENDED (ADD-01/5.1) | ACTIVE (as amended by ADD-01/5.1) | ACTIVE (as amended by ADD-01/5.1) | status ACTIVE -> AMENDED (ADD-01/5.1). reading re-made at ADD-01: ADD-01 5.1 appends this sentence: GRP of an equivalent pressure class is acceptable for buried sections, subject to the whole-life cost comparison. by ADD-01/5.1 [ADD-01; proposed] <- ADD-01:5.1 (ADD-01 p1) | status AMENDED (ADD-01/5.1) -> ACTIVE (as amended by ADD-01/5.1) |  | VOL-II 5.3 p4 | ADD-01 5.1 p1 (amending VOL-II 5.3) | ADD-01 5.1 p1 (amending VOL-II 5.3) | ADD-01 5.1 p1 (amending VOL-II 5.3) | none stated in the documents |  |  | high: verbatim at each stage; the applicable international standard is not named | ADD-01 5.1 appends this sentence: GRP of an equivalent pressure class is acceptable for buried sections, subject to the whole-life cost comparison. | changed at ADD-01 by ADD-01/5.1 (the quoted value); value as read: 'Glass reinforced plastic pipe of an equivalent pressure class is acceptable for the buried sections of the transmission…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/5.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-01/5.1: accepted | VOL-II:5.3 (VOL-II p4; text layer); ADD-01/5.1 [ADD-01; proposed] <- ADD-01:5.1 (ADD-01 p1)
VOL-II-5.3-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:5.3 | technical_design; transmission_main | Main of minimum nominal diameter DN1200 | The main shall be of ductile iron to the relevant international standard, internally lined and externally protected, with a minimum nominal diameter of DN1200. Alternative materials will be considered only where supported by a whole-life cost comparison. | The main shall be of ductile iron to the relevant international standard, internally lined and externally protected, with a minimum nominal diameter of DN1200. Alternative materials will be considered only where supported by a whole-life cost comparison. Glass reinforced plastic pipe of an equivalent pressure class is acceptable for the buried sections of the transmission main, subject to the whole-life cost comparison required by this Clause. | with a minimum nominal diameter of DN1200 | VOL-II 5.3 p4 as amended by ADD-01 5.1 p1 | VOL-II 5.3 p4 <- ADD-01/5.1 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE (unit amended by ADD-01/5.1; the row's words unchanged) | ACTIVE (unit amended by ADD-01/5.1; the row's words unchanged) | ACTIVE (unit amended by ADD-01/5.1; the row's words unchanged) | status ACTIVE -> ACTIVE (unit amended by ADD-01/5.1; the row's words unchanged). reading re-made at ADD-01: ADD-01 5.1 appends the GRP sentence to this clause; the minimum diameter is unchanged. by ADD-01/5.1 [ADD-01; proposed] <- ADD-01:5.1 (ADD-01 p1) |  |  | VOL-II 5.3 p4 | VOL-II 5.3 p4 as amended by ADD-01 5.1 p1 | VOL-II 5.3 p4 as amended by ADD-01 5.1 p1 | VOL-II 5.3 p4 as amended by ADD-01 5.1 p1 | none stated in the documents |  |  | high: verbatim text-layer clause | ADD-01 5.1 appends the GRP sentence to this clause; the minimum diameter is unchanged. | unchanged since BASE (unit amended elsewhere at ADD-01 by ADD-01/5.1; the row's words unchanged); value as read: 'with a minimum nominal diameter of DN1200' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/5.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-01/5.1: accepted | VOL-II:5.3 (VOL-II p4; text layer); ADD-01/5.1 [ADD-01; proposed] <- ADD-01:5.1 (ADD-01 p1)
VOL-II-5.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:5.4 | technical_design; transmission_main; crossings | Execute the three road crossings and the wadi crossing by trenchless methods | Three (3) road crossings and one (1) wadi crossing shall be executed by trenchless methods. Crossing permits shall be obtained by the Project Company. | Three (3) road crossings and one (1) wadi crossing shall be executed by trenchless methods. Crossing permits shall be obtained by the Project Company. | Three (3) road crossings and one (1) wadi crossing shall be executed by trenchless methods. | VOL-II 5.4 p4 | VOL-II 5.4 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 5.4 p4 | VOL-II 5.4 p4 | VOL-II 5.4 p4 | VOL-II 5.4 p4 | none stated in the documents |  |  | high: verbatim; ground conditions at the wadi crossing are the Bidder's risk (ADD-01 Q4) and the geotechnical report is in the data room, not the pack |  | unchanged since BASE; value as read: 'Three (3) road crossings and one (1) wadi crossing shall be executed by trenchless methods.' | decided (recorded): I-VOL-II-MISSING | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:5.4 (VOL-II p4; text layer) | I-VOL-II-MISSING
VOL-II-5.4-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:5.4 | permits; transmission_main; crossings | Obtain the crossing permits | Three (3) road crossings and one (1) wadi crossing shall be executed by trenchless methods. Crossing permits shall be obtained by the Project Company. | Three (3) road crossings and one (1) wadi crossing shall be executed by trenchless methods. Crossing permits shall be obtained by the Project Company. | Crossing permits shall be obtained by the Project Company. | VOL-II 5.4 p4 | VOL-II 5.4 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 5.4 p4 | VOL-II 5.4 p4 | VOL-II 5.4 p4 | VOL-II 5.4 p4 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'Crossing permits shall be obtained by the Project Company.' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:5.4 (VOL-II p4; text layer)
VOL-II-5.5-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:5.5 | technical_design; civil; seismic | Design permanent civil structures for a seismic event with a 475-year return period | All permanent civil structures shall be designed for a seismic event with a return period of 475 years and for a flood with a return period of 100 years. | All permanent civil structures shall be designed for a seismic event with a return period of 475 years and for a flood with a return period of 100 years. | designed for a seismic event with a return period of 475 years | VOL-II 5.5 p4 | VOL-II 5.5 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 5.5 p4 | VOL-II 5.5 p4 | VOL-II 5.5 p4 | VOL-II 5.5 p4 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'designed for a seismic event with a return period of 475 years' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:5.5 (VOL-II p4; text layer)
VOL-II-5.5-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:5.5 | technical_design; civil; flood | Design permanent civil structures for a flood with a 100-year return period | All permanent civil structures shall be designed for a seismic event with a return period of 475 years and for a flood with a return period of 100 years. | All permanent civil structures shall be designed for a seismic event with a return period of 475 years and for a flood with a return period of 100 years. | for a flood with a return period of 100 years | VOL-II 5.5 p4 | VOL-II 5.5 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 5.5 p4 | VOL-II 5.5 p4 | VOL-II 5.5 p4 | VOL-II 5.5 p4 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'for a flood with a return period of 100 years' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:5.5 (VOL-II p4; text layer)
VOL-II-6.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:6.1 | technical_design; scada | SCADA system capable of unattended operation of the whole Facility | The Facility shall be provided with a SCADA system capable of unattended operation of the whole Facility, with a permanently manned central control room. | The Facility shall be provided with a SCADA system capable of unattended operation of the whole Facility, with a permanently manned central control room. | The Facility shall be provided with a SCADA system capable of unattended operation of the whole Facility | VOL-II 6.1 p4 | VOL-II 6.1 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 6.1 p4 | VOL-II 6.1 p4 | VOL-II 6.1 p4 | VOL-II 6.1 p4 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'The Facility shall be provided with a SCADA system capable of unattended operation of the whole Facility' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:6.1 (VOL-II p4; text layer)
VOL-II-6.1-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:6.1 | technical_design; scada; staffing | A permanently manned central control room | The Facility shall be provided with a SCADA system capable of unattended operation of the whole Facility, with a permanently manned central control room. | The Facility shall be provided with a SCADA system capable of unattended operation of the whole Facility, with a permanently manned central control room. | with a permanently manned central control room | VOL-II 6.1 p4 | VOL-II 6.1 p4 | scored | Operations | O&M lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 6.1 p4 | VOL-II 6.1 p4 | VOL-II 6.1 p4 | VOL-II 6.1 p4 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'with a permanently manned central control room' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:6.1 (VOL-II p4; text layer)
VOL-II-6.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:6.2 | technical_design; cyber_security | Control system segregated from any business network by a DMZ, with one-way data flow to the Authority's monitoring interface | The industrial control system shall be segregated from any business network by a demilitarised zone with unidirectional data flow to the Authority's monitoring interface. | The industrial control system shall be segregated from any business network by a demilitarised zone with unidirectional data flow to the Authority's monitoring interface. | The industrial control system shall be segregated from any business network by a demilitarised zone with unidirectional data flow to the Authority's monitoring interface. | VOL-II 6.2 p4 | VOL-II 6.2 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 6.2 p4 | VOL-II 6.2 p4 | VOL-II 6.2 p4 | VOL-II 6.2 p4 | none stated in the documents |  |  | high: verbatim text-layer clause; Form 4-G undertaking 1 (ADD-02) restates this segregation |  | unchanged since BASE; value as read: 'The industrial control system shall be segregated from any business network by a demilitarised zone with unidirectional…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:6.2 (VOL-II p4; text layer)
VOL-II-6.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:6.3 | technical_design; cyber_security | Implement and maintain an information security management system covering the operational technology environment | The Project Company shall implement and maintain an information security management system covering the operational technology environment, and shall submit its security architecture for the Authority's review prior to commissioning. | The Project Company shall implement and maintain an information security management system covering the operational technology environment, and shall submit its security architecture for the Authority's review prior to commissioning. | shall implement and maintain an information security management system covering the operational technology environment | VOL-II 6.3 p4 | VOL-II 6.3 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 6.3 p4 | VOL-II 6.3 p4 | VOL-II 6.3 p4 | VOL-II 6.3 p4 | none stated in the documents |  |  | high: verbatim text-layer clause; Form 4-G undertakings 3-6 (ADD-02) add cyber obligations not in this clause (I-F4G-NO) |  | unchanged since BASE; value as read: 'shall implement and maintain an information security management system covering the operational technology environment' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:6.3 (VOL-II p4; text layer)
VOL-II-6.3-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:6.3 | cyber_security; submission_to_authority | Submit the security architecture for the Authority's review before commissioning | The Project Company shall implement and maintain an information security management system covering the operational technology environment, and shall submit its security architecture for the Authority's review prior to commissioning. | The Project Company shall implement and maintain an information security management system covering the operational technology environment, and shall submit its security architecture for the Authority's review prior to commissioning. | shall submit its security architecture for the Authority's review prior to commissioning | VOL-II 6.3 p4 | VOL-II 6.3 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 6.3 p4 | VOL-II 6.3 p4 | VOL-II 6.3 p4 | VOL-II 6.3 p4 | none stated in the documents |  | VOL-II-SECURITY-ARCHITECTURE-DUE: None (unknown_anchor) | high: verbatim text-layer clause | A post-award submission; commissioning is not a pack event. | unchanged since BASE; value as read: 'shall submit its security architecture for the Authority's review prior to commissioning' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:6.3 (VOL-II p4; text layer)
VOL-II-6.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:6.4 | operations; data_retention | Retain all process data for at least seven years | All process data shall be retained for not less than seven (7) years and shall be made available to the Authority on demand in a non-proprietary format. | All process data shall be retained for not less than seven (7) years and shall be made available to the Authority on demand in a non-proprietary format. | All process data shall be retained for not less than seven (7) years | VOL-II 6.4 p4 | VOL-II 6.4 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 6.4 p4 | VOL-II 6.4 p4 | VOL-II 6.4 p4 | VOL-II 6.4 p4 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'All process data shall be retained for not less than seven (7) years' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:6.4 (VOL-II p4; text layer)
VOL-II-6.4-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:6.4 | operations; data_access | Make process data available to the Authority on demand in a non-proprietary format | All process data shall be retained for not less than seven (7) years and shall be made available to the Authority on demand in a non-proprietary format. | All process data shall be retained for not less than seven (7) years and shall be made available to the Authority on demand in a non-proprietary format. | shall be made available to the Authority on demand in a non-proprietary format | VOL-II 6.4 p4 | VOL-II 6.4 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 6.4 p4 | VOL-II 6.4 p4 | VOL-II 6.4 p4 | VOL-II 6.4 p4 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'shall be made available to the Authority on demand in a non-proprietary format' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:6.4 (VOL-II p4; text layer)
VOL-II-7.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:7.1 | commissioning; testing | Carry out FAT, SAT and integrated process commissioning under a commissioning plan approved by the Authority | The Project Company shall carry out factory acceptance testing, site acceptance testing, and integrated process commissioning in accordance with a commissioning plan approved by the Authority. | The Project Company shall carry out factory acceptance testing, site acceptance testing, and integrated process commissioning in accordance with a commissioning plan approved by the Authority. | shall carry out factory acceptance testing, site acceptance testing, and integrated process commissioning in accordance with a commissioning plan approved by the Authority | VOL-II 7.1 p4 | VOL-II 7.1 p4 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 7.1 p4 | VOL-II 7.1 p4 | VOL-II 7.1 p4 | VOL-II 7.1 p4 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'shall carry out factory acceptance testing, site acceptance testing, and integrated process commissioning in accordance…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:7.1 (VOL-II p4; text layer)
VOL-II-7.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:7.2 | commissioning; pcod; reliability_run; effluent | Before PCOD: a 30-day continuous reliability run at 90% or more of nominal capacity meeting every Table 2-4 parameter | PCOD shall not be certified until the Facility has completed a continuous reliability run of thirty (30) days at not less than 90% of nominal capacity, during which every parameter in Table 2-4 has been met. | PCOD shall not be certified until the Facility has completed a continuous reliability run of thirty (30) days at not less than 90% of nominal capacity, during which every parameter in Table 2-4 has been met. | PCOD shall not be certified until the Facility has completed a continuous reliability run of thirty (30) days at not less than 90% of nominal capacity, during which every parameter in Table 2-4 has been met. | VOL-II 7.2 p4 | VOL-II 7.2 p4 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 7.2 p4 | VOL-II 7.2 p4 | VOL-II 7.2 p4 | VOL-II 7.2 p4 | contractual remedy (post-award): "A failure of any Table 2-4 parameter during the reliability run shall restart the run in full." | VOL-II 7.3 p4 |  | medium: verbatim; every Table 2-4 parameter is an image reading (transcription confirmed by the owner, 3 Oct 2026), and TN is amended by ADD-02 5.1 (row VOL-II-T2-4-TN) | PCOD is certified by the Independent Engineer against this clause (VOL-V 1.5). How a 30-day rolling-average limit is 'met' within a 30-day run is not stated. Late PCOD: VOL-V 18.1 and 18.3. | own words unchanged at ADD-02, but what it depends on changed (dependency; see A2); value as read: 'PCOD shall not be certified until the Facility has completed a continuous reliability run of thirty (30) days at not le…' | decided (recorded): I-READING-T24, I-PERMIT, I-VOL-II-T24-TENSIONS, I-VOL-II-AT-ALL-TIMES, I-VOL-II-COMPLIANCE-POINT | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:7.2 (VOL-II p4; text layer) | I-READING-T24; I-PERMIT; I-VOL-II-T24-TENSIONS (via REL-T24-RELIABILITY-RUN (confirmed)); I-VOL-II-AT-ALL-TIMES (via REL-T24-RELIABILITY-RUN (confirmed)); I-VOL-II-COMPLIANCE-POINT (via REL-T24-RELIABILITY-RUN (confirmed)) | <- REL-T24-RELIABILITY-RUN [confirmed limit_applies] from VOL-II:T2-4; <- REL-AI-001 [proposed depends_on] from VOL-II:2.1; -> REL-AI-007 [proposed depends_on] to VOL-II:2.1; REACHED at ADD-02 (confirmed dependency): from VOL-II:T2-4 via REL-T24-RELIABILITY-RUN; REACHED at ADD-02 (proposed relationship): from VOL-II:T2-4 via REL-T24-RELIABILITY-RUN > REL-AI-007 > REL-AI-001
VOL-II-7.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:7.4 | commissioning; documentation; post_pcod | Provide as-built documents, O&M manuals and an asset register in the Authority's standard format within 60 days after PCOD | The Project Company shall provide as-built documentation, operation and maintenance manuals, and an asset register in the Authority's standard format not later than sixty (60) days after PCOD. | The Project Company shall provide as-built documentation, operation and maintenance manuals, and an asset register in the Authority's standard format not later than sixty (60) days after PCOD. | shall provide as-built documentation, operation and maintenance manuals, and an asset register in the Authority's standard format not later than sixty (60) days after PCOD | VOL-II 7.4 p5 | VOL-II 7.4 p5 | scored | Technical | Technical lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 7.4 p5 | VOL-II 7.4 p5 | VOL-II 7.4 p5 | VOL-II 7.4 p5 | none stated in the documents |  | VOL-II-AS-BUILT-DUE: None (unknown_anchor) | medium: verbatim; the Authority's standard format is not in the pack; PCOD is not a pack event |  | unchanged since BASE; value as read: 'shall provide as-built documentation, operation and maintenance manuals, and an asset register in the Authority's stand…' | decided (recorded): I-VOL-II-MISSING | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:7.4 (VOL-II p5; text layer) | I-VOL-II-MISSING
VOL-II-8.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:8.1 | operations; maintenance; spares | Hold spares for two years of normal operation for all items with a lead time over 12 weeks | The Project Company shall hold a spare parts inventory sufficient for two (2) years of normal operation for all items with a lead time exceeding twelve (12) weeks. | The Project Company shall hold a spare parts inventory sufficient for two (2) years of normal operation for all items with a lead time exceeding twelve (12) weeks. | shall hold a spare parts inventory sufficient for two (2) years of normal operation for all items with a lead time exceeding twelve (12) weeks | VOL-II 8.1 p5 | VOL-II 8.1 p5 | scored | Operations | O&M lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 8.1 p5 | VOL-II 8.1 p5 | VOL-II 8.1 p5 | VOL-II 8.1 p5 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'shall hold a spare parts inventory sufficient for two (2) years of normal operation for all items with a lead time exce…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:8.1 (VOL-II p5; text layer)
VOL-II-8.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:8.2 | operations; maintenance; cmms | Implement a computerised maintenance management system before PCOD and keep it in use for the concession period | A computerised maintenance management system shall be implemented before PCOD and shall remain in use for the concession period. | A computerised maintenance management system shall be implemented before PCOD and shall remain in use for the concession period. | A computerised maintenance management system shall be implemented before PCOD and shall remain in use for the concession period. | VOL-II 8.2 p5 | VOL-II 8.2 p5 | scored | Operations | O&M lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 8.2 p5 | VOL-II 8.2 p5 | VOL-II 8.2 p5 | VOL-II 8.2 p5 | none stated in the documents |  | VOL-II-CMMS-BY-PCOD: None (unknown_anchor) | high: verbatim text-layer clause; PCOD is not a pack event |  | unchanged since BASE; value as read: 'A computerised maintenance management system shall be implemented before PCOD and shall remain in use for the concessio…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:8.2 (VOL-II p5; text layer)
VOL-II-8.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:8.3 | operations; staffing | Employ a suitably qualified plant manager | The Project Company shall employ a suitably qualified plant manager and shall maintain a minimum of two (2) certified operators on shift at all times. | The Project Company shall employ a suitably qualified plant manager and shall maintain a minimum of two (2) certified operators on shift at all times. | shall employ a suitably qualified plant manager | VOL-II 8.3 p5 | VOL-II 8.3 p5 | scored | Operations | O&M lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 8.3 p5 | VOL-II 8.3 p5 | VOL-II 8.3 p5 | VOL-II 8.3 p5 | none stated in the documents |  |  | high: verbatim text-layer clause; 'suitably qualified' is not defined |  | unchanged since BASE; value as read: 'shall employ a suitably qualified plant manager' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:8.3 (VOL-II p5; text layer)
VOL-II-8.3-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:8.3 | operations; staffing | At least two certified operators on shift at all times | The Project Company shall employ a suitably qualified plant manager and shall maintain a minimum of two (2) certified operators on shift at all times. | The Project Company shall employ a suitably qualified plant manager and shall maintain a minimum of two (2) certified operators on shift at all times. | shall maintain a minimum of two (2) certified operators on shift at all times | VOL-II 8.3 p5 | VOL-II 8.3 p5 | scored | Operations | O&M lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 8.3 p5 | VOL-II 8.3 p5 | VOL-II 8.3 p5 | VOL-II 8.3 p5 | none stated in the documents |  |  | high: verbatim text-layer clause | The certification scheme is not named. | unchanged since BASE; value as read: 'shall maintain a minimum of two (2) certified operators on shift at all times' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:8.3 (VOL-II p5; text layer)
VOL-II-8.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:8.4 | operations; sludge | Dewater sludge to at least 22% dry solids | Sludge shall be dewatered to not less than 22% dry solids and shall be disposed of or reused in accordance with the applicable regulations. Disposal to landfill of sludge exceeding 500 tonnes per annum shall require the Authority's prior written consent. | Sludge shall be dewatered to not less than 22% dry solids and shall be disposed of or reused in accordance with the applicable regulations. Disposal to landfill of sludge exceeding 500 tonnes per annum shall require the Authority's prior written consent. | Sludge shall be dewatered to not less than 22% dry solids | VOL-II 8.4 p5 | VOL-II 8.4 p5 | scored | Technical | Process engineer | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 8.4 p5 | VOL-II 8.4 p5 | VOL-II 8.4 p5 | VOL-II 8.4 p5 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'Sludge shall be dewatered to not less than 22% dry solids' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:8.4 (VOL-II p5; text layer)
VOL-II-8.4-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:8.4 | operations; sludge; environmental_compliance | Dispose of or reuse sludge under the applicable regulations; landfill over 500 t/a only with the Authority's prior written consent | Sludge shall be dewatered to not less than 22% dry solids and shall be disposed of or reused in accordance with the applicable regulations. Disposal to landfill of sludge exceeding 500 tonnes per annum shall require the Authority's prior written consent. | Sludge shall be dewatered to not less than 22% dry solids and shall be disposed of or reused in accordance with the applicable regulations. Disposal to landfill of sludge exceeding 500 tonnes per annum shall require the Authority's prior written consent. | shall be disposed of or reused in accordance with the applicable regulations | VOL-II 8.4 p5 | VOL-II 8.4 p5 | scored | Environmental | Environmental lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 8.4 p5 | VOL-II 8.4 p5 | VOL-II 8.4 p5 | VOL-II 8.4 p5 | none stated in the documents |  |  | high: verbatim text-layer clause | 'Disposal to landfill of sludge exceeding 500 tonnes per annum shall require the Authority's prior written consent.' The applicable regulations are not identified. | unchanged since BASE; value as read: 'shall be disposed of or reused in accordance with the applicable regulations' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:8.4 (VOL-II p5; text layer)
VOL-II-8.5-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:8.5 | handback; survey | Carry out a handback condition survey in the final two years of the concession | A handback condition survey shall be carried out in the final two (2) years of the concession, and any remedial works identified shall be completed before transfer. | A handback condition survey shall be carried out in the final two (2) years of the concession, and any remedial works identified shall be completed before transfer. | A handback condition survey shall be carried out in the final two (2) years of the concession | VOL-II 8.5 p5 | VOL-II 8.5 p5 | scored | Operations | O&M lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 8.5 p5 | VOL-II 8.5 p5 | VOL-II 8.5 p5 | VOL-II 8.5 p5 | none stated in the documents |  | VOL-II-HANDBACK-SURVEY-WINDOW: None (unknown_anchor) | medium: verbatim; when the concession ends depends on whether the term runs from the Effective Date or PCOD | Handback condition: VOL-V 42.1 refers to this clause. | unchanged since BASE; value as read: 'A handback condition survey shall be carried out in the final two (2) years of the concession' | decided (recorded): I-CONCESSION | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:8.5 (VOL-II p5; text layer) | I-CONCESSION
VOL-II-8.5-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:8.5 | handback; remedial_works | Complete the remedial works the handback survey identifies before transfer | A handback condition survey shall be carried out in the final two (2) years of the concession, and any remedial works identified shall be completed before transfer. | A handback condition survey shall be carried out in the final two (2) years of the concession, and any remedial works identified shall be completed before transfer. | any remedial works identified shall be completed before transfer | VOL-II 8.5 p5 | VOL-II 8.5 p5 | scored | Operations | O&M lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 8.5 p5 | VOL-II 8.5 p5 | VOL-II 8.5 p5 | VOL-II 8.5 p5 | none stated in the documents |  | VOL-II-HANDBACK-REMEDIALS-DUE: None (unknown_anchor) | medium: verbatim; the transfer date depends on the concession term start |  | unchanged since BASE; value as read: 'any remedial works identified shall be completed before transfer' | decided (recorded): I-CONCESSION | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:8.5 (VOL-II p5; text layer) | I-CONCESSION
VOL-II-9.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:9.1 | environmental_social; esia | Comply with the Environmental and Social Impact Assessment for the site (in the data room) | The Project Company shall comply with the Environmental and Social Impact Assessment prepared for the site and available in the data room, and shall prepare an Environmental and Social Management Plan aligned with the International Finance Corporation Performance Standards. | The Project Company shall comply with the Environmental and Social Impact Assessment prepared for the site and available in the data room, and shall prepare an Environmental and Social Management Plan aligned with the International Finance Corporation Performance Standards. | shall comply with the Environmental and Social Impact Assessment prepared for the site and available in the data room | VOL-II 9.1 p5 | VOL-II 9.1 p5 | scored | Environmental | Environmental lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 9.1 p5 | VOL-II 9.1 p5 | VOL-II 9.1 p5 | VOL-II 9.1 p5 | none stated in the documents |  |  | medium: verbatim; the ESIA is in the data room, not in the pack, so what compliance requires cannot be read here |  | unchanged since BASE; value as read: 'shall comply with the Environmental and Social Impact Assessment prepared for the site and available in the data room' | decided (recorded): I-VOL-II-MISSING | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:9.1 (VOL-II p5; text layer) | I-VOL-II-MISSING
VOL-II-9.1-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:9.1 | environmental_social; esmp | Prepare an Environmental and Social Management Plan aligned with the IFC Performance Standards | The Project Company shall comply with the Environmental and Social Impact Assessment prepared for the site and available in the data room, and shall prepare an Environmental and Social Management Plan aligned with the International Finance Corporation Performance Standards. | The Project Company shall comply with the Environmental and Social Impact Assessment prepared for the site and available in the data room, and shall prepare an Environmental and Social Management Plan aligned with the International Finance Corporation Performance Standards. | shall prepare an Environmental and Social Management Plan aligned with the International Finance Corporation Performance Standards | VOL-II 9.1 p5 | VOL-II 9.1 p5 | scored | Environmental | Environmental lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 9.1 p5 | VOL-II 9.1 p5 | VOL-II 9.1 p5 | VOL-II 9.1 p5 | none stated in the documents |  |  | high: verbatim text-layer clause | VOL-I Table 1-1 criterion D (environmental and social management) is also scored. | unchanged since BASE; value as read: 'shall prepare an Environmental and Social Management Plan aligned with the International Finance Corporation Performanc…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:9.1 (VOL-II p5; text layer)
VOL-II-9.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:9.2 | environmental_social; permits | Obtain environmental clearance from the national environmental regulator before construction starts | Environmental clearance shall be obtained from the competent national environmental regulator before commencement of construction. | Environmental clearance shall be obtained from the competent national environmental regulator before commencement of construction. | Environmental clearance shall be obtained from the competent national environmental regulator before commencement of construction. | VOL-II 9.2 p5 | VOL-II 9.2 p5 | scored | Environmental | Environmental lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 9.2 p5 | VOL-II 9.2 p5 | VOL-II 9.2 p5 | VOL-II 9.2 p5 | none stated in the documents |  | VOL-II-ENV-CLEARANCE-DUE: None (unknown_anchor) | high: verbatim text-layer clause; the regulator is not named |  | unchanged since BASE; value as read: 'Environmental clearance shall be obtained from the competent national environmental regulator before commencement of co…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:9.2 (VOL-II p5; text layer)
VOL-II-9.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:9.3 | environmental_social; grievance | Set up a grievance mechanism for the affected community before construction and keep it for the concession period | A grievance mechanism accessible to the affected community shall be established before construction and maintained for the concession period. | A grievance mechanism accessible to the affected community shall be established before construction and maintained for the concession period. | A grievance mechanism accessible to the affected community shall be established before construction and maintained for the concession period. | VOL-II 9.3 p5 | VOL-II 9.3 p5 | scored | Environmental | Environmental lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 9.3 p5 | VOL-II 9.3 p5 | VOL-II 9.3 p5 | VOL-II 9.3 p5 | none stated in the documents |  | VOL-II-GRIEVANCE-DUE: None (unknown_anchor) | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'A grievance mechanism accessible to the affected community shall be established before construction and maintained for …' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:9.3 (VOL-II p5; text layer)
VOL-II-9.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:9.4 | environmental_social; water | Do not abstract construction water from the local aquifer; use tankered supply or treated effluent | Construction water shall not be abstracted from the local aquifer. The Project Company shall source construction water from tankered supply or treated effluent. | Construction water shall not be abstracted from the local aquifer. The Project Company shall source construction water from tankered supply or treated effluent. | Construction water shall not be abstracted from the local aquifer. | VOL-II 9.4 p5 | VOL-II 9.4 p5 | scored | Environmental | Environmental lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 9.4 p5 | VOL-II 9.4 p5 | VOL-II 9.4 p5 | VOL-II 9.4 p5 | none stated in the documents |  |  | high: verbatim text-layer clause | 'The Project Company shall source construction water from tankered supply or treated effluent.' | unchanged since BASE; value as read: 'Construction water shall not be abstracted from the local aquifer.' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:9.4 (VOL-II p5; text layer)
VOL-II-9.5-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-II:9.5 | environmental_social; reporting | Report environmental and social performance to the Authority quarterly during construction and annually after | The Project Company shall report environmental and social performance to the Authority quarterly during construction and annually thereafter. | The Project Company shall report environmental and social performance to the Authority quarterly during construction and annually thereafter. | shall report environmental and social performance to the Authority quarterly during construction and annually thereafter | VOL-II 9.5 p5 | VOL-II 9.5 p5 | scored | Environmental | Environmental lead | EV-TECH-PROPOSAL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-II 9.5 p5 | VOL-II 9.5 p5 | VOL-II 9.5 p5 | VOL-II 9.5 p5 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'shall report environmental and social performance to the Authority quarterly during construction and annually thereafter' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-II:9.5 (VOL-II p5; text layer)
VOL-IV-FORMS-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:cover/para5 | forms; wording | Reproduce every Form without alteration to its wording | Forms shall be reproduced without alteration to their wording. A Bidder that alters the wording of a Form does so at its own risk. | Forms shall be reproduced without alteration to their wording. A Bidder that alters the wording of a Form does so at its own risk. | Forms shall be reproduced without alteration to their wording. | VOL-IV cover/para5 p2 | VOL-IV cover/para5 p2 | procedural | Bid management | Bid manager | none: a rule on how each Form is reproduced; the Forms themselves are the deliverables of their own rows | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-IV cover/para5 p2 | VOL-IV cover/para5 p2 | VOL-IV cover/para5 p2 | VOL-IV cover/para5 p2 | lesser consequence: "A Bidder that alters the wording of a Form does so at its own risk." | VOL-IV cover/para5 p2 |  | high: verbatim; 'at its own risk' does not say what the Authority will do | Bears on the reissued Form 4-A, which prints the old Proposal Due Date (VOL-IV-F4A-01, I-F4A-FIELDS), and on Form 4-D, which VOL-I 8.7 requires only 'substantially in the form'. | unchanged since BASE; value as read: 'Forms shall be reproduced without alteration to their wording.' | decided (recorded): I-F4A-FIELDS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:cover/para5 (VOL-IV p2; text layer) | I-F4A-FIELDS
VOL-IV-F4A-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-A | envelope_A; forms; reissued_form | Complete Form 4-A (Envelope A, mandatory) in the form reissued by ADD-01 App A; VOL-I states no consequence for a blank field. Execution and its consequence (unsigned or improperly executed: non-responsive) are row VOL-I-9.3-01 | [VOL-IV F4-A/name-of-bidder-lead-member p3] Name of Bidder / lead member: [VOL-IV cover/T1/4-A p2] Form: 4-A ¦ Title: Proposal Submission Letter ¦ Envelope: A ¦ Status: Mandatory [VOL-IV F4-A/tender-reference p3] Tender reference: NUPA/ISTP/2026/014 [VOL-IV F4-A/project p3] Project: Wadi Sirhan Independent Sewage Treatment Plant [VOL-IV F4-A/proposal-due-date p3] Proposal Due Date: 12 November 2026, 14:00 Riyadh time [VOL-IV F4-A/commercial-registration-number p3] Commercial registration number: [VOL-IV F4-A/registered-address p3] Registered address: [VOL-IV F4-A/single-point-of-contact-name-title p3] Single point of contact (name, title): [VOL-IV F4-A/contact-email-and-telephone p3] Contact email and telephone: [VOL-IV F4-A/signature p3] Signature: [VOL-IV F4-A/name-of-signatory p3] Name of signatory: [VOL-IV F4-A/capacity p3] Capacity: [VOL-IV F4-A/power-of-attorney-reference-and-date p3] Power of Attorney reference and date: [VOL-IV F4-A/date p3] Date: [VOL-IV F4-A/company-seal p3] Company seal: [ADD-01 AppA/para1 p3; issued by ADD-01] Form 4-A is reissued below to add the acknowledgement of Addenda at paragraph 1. Bidders shall use this version. [ADD-01 AppA/single-point-of-contact p3; issued by ADD-01] Single point of contact: [ADD-01 AppA/signature-name-capacity p3; issued by ADD-01] Signature / name / capacity: | [ADD-01 AppA/name-of-bidder-lead-member p3] Name of Bidder / lead member: [VOL-IV cover/T1/4-A p2] Form: 4-A ¦ Title: Proposal Submission Letter ¦ Envelope: A ¦ Status: Mandatory [ADD-01 AppA/tender-reference p3] Tender reference: NUPA/ISTP/2026/014 [ADD-01 AppA/project p3] Project: Wadi Sirhan Independent Sewage Treatment Plant [ADD-01 AppA/proposal-due-date p3] Proposal Due Date: 12 November 2026, 14:00 Riyadh time [VOL-IV F4-A/commercial-registration-number p3] (SUPERSEDED) [VOL-IV F4-A/registered-address p3] (SUPERSEDED) [VOL-IV F4-A/single-point-of-contact-name-title p3] (SUPERSEDED) [VOL-IV F4-A/contact-email-and-telephone p3] (SUPERSEDED) [VOL-IV F4-A/signature p3] (SUPERSEDED) [VOL-IV F4-A/name-of-signatory p3] (SUPERSEDED) [VOL-IV F4-A/capacity p3] (SUPERSEDED) [VOL-IV F4-A/power-of-attorney-reference-and-date p3] (SUPERSEDED) [ADD-01 AppA/date p3] Date: [VOL-IV F4-A/company-seal p3] (SUPERSEDED) [ADD-01 AppA/para1 p3] Form 4-A is reissued below to add the acknowledgement of Addenda at paragraph 1. Bidders shall use this version. [ADD-01 AppA/single-point-of-contact p3] Single point of contact: [ADD-01 AppA/signature-name-capacity p3] Signature / name / capacity: | Name of Bidder / lead member: | ADD-01 AppA/name-of-bidder-lead-member p3 (replacing VOL-IV F4-A/name-of-bidder-lead-member p3, ADD-01/AppA/para1) | ADD-01 AppA/name-of-bidder-lead-member p3 (issued as VOL-IV:F4-A/name-of-bidder-lead-member) <- ADD-01/AppA/para1; VOL-IV cover/T1/4-A p2; ADD-01 AppA/tender-reference p3 (issued as VOL-IV:F4-A/tender-reference) <- ADD-01/AppA/para1; ADD-01 AppA/project p3 (issued as VOL-IV:F4-A/project) <- ADD-01/AppA/para1; ADD-01 AppA/proposal-due-date p3 (issued as VOL-IV:F4-A/proposal-due-date) <- ADD-01/AppA/para1; VOL-IV F4-A/commercial-registration-number p3 <- ADD-01/AppA/para1; VOL-IV F4-A/registered-address p3 <- ADD-01/AppA/para1; VOL-IV F4-A/single-point-of-contact-name-title p3 <- ADD-01/AppA/para1; VOL-IV F4-A/contact-email-and-telephone p3 <- ADD-01/AppA/para1; VOL-IV F4-A/signature p3 <- ADD-01/AppA/para1; VOL-IV F4-A/name-of-signatory p3 <- ADD-01/AppA/para1; VOL-IV F4-A/capacity p3 <- ADD-01/AppA/para1; VOL-IV F4-A/power-of-attorney-reference-and-date p3 <- ADD-01/AppA/para1; ADD-01 AppA/date p3 (issued as VOL-IV:F4-A/date) <- ADD-01/AppA/para1; VOL-IV F4-A/company-seal p3 <- ADD-01/AppA/para1; ADD-01 AppA/para1 p3; ADD-01 AppA/single-point-of-contact p3 <- ADD-01/AppA/para1; ADD-01 AppA/signature-name-capacity p3 <- ADD-01/AppA/para1 | pass_fail | Legal | Bid manager | EV-FORM-4A | ACTIVE | AMENDED (ADD-01/AppA/para1) | ACTIVE (as amended by ADD-01/AppA/para1) | ACTIVE (as amended by ADD-01/AppA/para1) | status ACTIVE -> AMENDED (ADD-01/AppA/para1). reading re-made at ADD-01: No consequence is stated for a blank field; VOL-I 9.3's 'unsigned or improperly executed' trigger is row VOL-I-9.3-01. ADD-01 App A reissues Form 4-A ('Bidders shall use this version'). It keeps tender reference, project, PDD, name, single point of contact, 'Signature / name / capacity' and date; it drops the CR number, registered address, contact email/telephone, Power of Attorney reference and date, and company seal. Not resolved: I-F4A-FIELDS. by ADD-01/AppA/para1 [ADD-01; proposed] <- ADD-01:AppA/para1 (ADD-01 p3) | status AMENDED (ADD-01/AppA/para1) -> ACTIVE (as amended by ADD-01/AppA/para1) |  | VOL-IV F4-A/name-of-bidder-lead-member p3 | ADD-01 AppA/name-of-bidder-lead-member p3 (replacing VOL-IV F4-A/name-of-bidder-lead-member p3, ADD-01/AppA/para1) | ADD-01 AppA/name-of-bidder-lead-member p3 (replacing VOL-IV F4-A/name-of-bidder-lead-member p3, ADD-01/AppA/para1) | ADD-01 AppA/name-of-bidder-lead-member p3 (replacing VOL-IV F4-A/name-of-bidder-lead-member p3, ADD-01/AppA/para1) | none stated in the documents |  |  | medium: verbatim fields; the reissued form drops fields and still prints the old PDD (a decision for a person) | No consequence is stated for a blank field; VOL-I 9.3's 'unsigned or improperly executed' trigger is row VOL-I-9.3-01. ADD-01 App A reissues Form 4-A ('Bidders shall use this version'). It keeps tender reference, project, PDD, name, single point of contact, 'Signature / name / capacity' and date; it drops the CR number, registered address, contact email/telephone, Power of Attorney reference and date, and company seal. Not resolved: I-F4A-FIELDS. | amended at ADD-01 by ADD-01/AppA/para1 (the unit reissued; the quoted words unchanged); value as read: 'Name of Bidder / lead member:' | decided (recorded): I-F4A-FIELDS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/AppA/para1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-01/AppA/para1: accepted | VOL-IV:F4-A/name-of-bidder-lead-member (VOL-IV p3; text layer); VOL-IV:cover/T1/4-A (VOL-IV p2; text layer); VOL-IV:F4-A/tender-reference (VOL-IV p3; text layer); VOL-IV:F4-A/project (VOL-IV p3; text layer); VOL-IV:F4-A/proposal-due-date (VOL-IV p3; text layer); VOL-IV:F4-A/commercial-registration-number (VOL-IV p3; text layer); VOL-IV:F4-A/registered-address (VOL-IV p3; text layer); VOL-IV:F4-A/single-point-of-contact-name-title (VOL-IV p3; text layer); VOL-IV:F4-A/contact-email-and-telephone (VOL-IV p3; text layer); VOL-IV:F4-A/signature (VOL-IV p3; text layer); VOL-IV:F4-A/name-of-signatory (VOL-IV p3; text layer); VOL-IV:F4-A/capacity (VOL-IV p3; text layer); VOL-IV:F4-A/power-of-attorney-reference-and-date (VOL-IV p3; text layer); VOL-IV:F4-A/date (VOL-IV p3; text layer); VOL-IV:F4-A/company-seal (VOL-IV p3; text layer); ADD-01:AppA/para1 (ADD-01 p3; text layer; issued by ADD-01); ADD-01:AppA/single-point-of-contact (ADD-01 p3; text layer; issued by ADD-01); ADD-01:AppA/signature-name-capacity (ADD-01 p3; text layer; issued by ADD-01); ADD-01/AppA/para1 [ADD-01; proposed] <- ADD-01:AppA/para1 (ADD-01 p3) | I-F4A-FIELDS
VOL-IV-F4A-03 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-A | envelope_A; forms; confirmation; addenda_acknowledgement; dropped_in_reissue | Form 4-A para 1: acknowledge receipt of the Addenda by number and offer the Project in conformity with the RFP Documents | 1. Having examined the RFP Documents, including Addenda numbered ______ to ______, the receipt of which is hereby acknowledged, we offer to design, finance, construct, own, operate, maintain and transfer the Project in conformity with the RFP Documents. | 1. Having examined the RFP Documents, including Addenda numbered ______ to ______, the receipt of which is hereby acknowledged, we offer to design, finance, construct, own, operate, maintain and transfer the Project in conformity with the RFP Documents. | the receipt of which is hereby acknowledged, we offer to design, finance, construct, own, operate, maintain and transfer the Project in conformity with the RFP Documents | VOL-IV F4-A/item1 p3 | VOL-IV F4-A/item1 p3 | pass_fail | Legal | Bid manager | EV-FORM-4A | ACTIVE | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | status ACTIVE -> REPLACED (by ADD-01:AppA). by ADD-01/AppA/para1 [ADD-01; proposed] <- ADD-01:AppA/para1 (ADD-01 p3) |  |  | VOL-IV F4-A/item1 p3 | VOL-IV F4-A/item1 p3 as amended by ADD-01 AppA/para1 p3 | VOL-IV F4-A/item1 p3 as amended by ADD-01 AppA/para1 p3 | VOL-IV F4-A/item1 p3 as amended by ADD-01 AppA/para1 p3 | none stated in the documents |  |  | medium: verbatim; dropped by the reissued form from ADD-01 (whether to give it anyway is for a person) | No consequence stated in the form. The reissued Form 4-A (ADD-01 App A) has no paragraph 1 and no offer wording; it has an 'Addenda acknowledged (numbers)' field (row ADD-01-AppA-01). | not in force at ADD-02 (REPLACED (by ADD-01:AppA)) | decided (recorded): I-F4A-FIELDS, I-NO-CONSEQUENCE | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/AppA/para1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-01/AppA/para1: accepted | VOL-IV:F4-A/item1 (VOL-IV p3; text layer); ADD-01/AppA/para1 [ADD-01; proposed] <- ADD-01:AppA/para1 (ADD-01 p3) | I-F4A-FIELDS; I-NO-CONSEQUENCE
VOL-IV-F4A-04 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-A | envelope_A; forms; confirmation; validity; dropped_in_reissue | Form 4-A para 2: confirm the Proposal is valid for 150 days from the Proposal Due Date | 2. We confirm that this Proposal is valid for one hundred and fifty (150) days from the Proposal Due Date. | 2. We confirm that this Proposal is valid for one hundred and fifty (150) days from the Proposal Due Date. | We confirm that this Proposal is valid for one hundred and fifty (150) days from the Proposal Due Date. | VOL-IV F4-A/item2 p3 | VOL-IV F4-A/item2 p3 | pass_fail | Commercial | Bid manager | EV-FORM-4A | ACTIVE | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | status ACTIVE -> REPLACED (by ADD-01:AppA). by ADD-01/AppA/para1 [ADD-01; proposed] <- ADD-01:AppA/para1 (ADD-01 p3); ADD-01/2.1 [ADD-01; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-01:2.1 (ADD-01 p1) |  |  | VOL-IV F4-A/item2 p3 | VOL-IV F4-A/item2 p3 as amended by ADD-01 AppA/para1 p3 | VOL-IV F4-A/item2 p3 as amended by ADD-01 AppA/para1 p3 | VOL-IV F4-A/item2 p3 as amended by ADD-01 AppA/para1 p3 | none stated in the documents |  |  | medium: verbatim; dropped by the reissued form from ADD-01; day 0 / day 1 not stated | Confirms VOL-I 7.1 (row VOL-I-7.1-01). No consequence stated. Dropped by the reissued Form 4-A from ADD-01. | not in force at ADD-02 (REPLACED (by ADD-01:AppA)) | decided (recorded): I-F4A-FIELDS, I-NO-CONSEQUENCE | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/AppA/para1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-01/AppA/para1: accepted | VOL-IV:F4-A/item2 (VOL-IV p3; text layer); ADD-01/AppA/para1 [ADD-01; proposed] <- ADD-01:AppA/para1 (ADD-01 p3); ADD-01/2.1 [ADD-01; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-01:2.1 (ADD-01 p1); ADD-03/2.1 [ADD-03; proposed; moves the date anchor PDD (VOL-I:6.1)] <- ADD-03:2.1 (ADD-03 p1) | I-F4A-FIELDS; I-NO-CONSEQUENCE
VOL-IV-F4A-05 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-A | envelope_A; forms; confirmation; bid_security; dropped_in_reissue | Form 4-A para 3: confirm the Bid Bond required by VOL-I 6.4 accompanies the Proposal | 3. We confirm that the Bid Bond required by Volume I Clause 6.4 accompanies this Proposal. | 3. We confirm that the Bid Bond required by Volume I Clause 6.4 accompanies this Proposal. | We confirm that the Bid Bond required by Volume I Clause 6.4 accompanies this Proposal. | VOL-IV F4-A/item3 p3 | VOL-IV F4-A/item3 p3 | pass_fail | Commercial | Bid manager | EV-FORM-4A | ACTIVE | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | status ACTIVE -> REPLACED (by ADD-01:AppA). by ADD-01/AppA/para1 [ADD-01; proposed] <- ADD-01:AppA/para1 (ADD-01 p3) |  |  | VOL-IV F4-A/item3 p3 | VOL-IV F4-A/item3 p3 as amended by ADD-01 AppA/para1 p3 | VOL-IV F4-A/item3 p3 as amended by ADD-01 AppA/para1 p3 | VOL-IV F4-A/item3 p3 as amended by ADD-01 AppA/para1 p3 | none stated in the documents |  |  | medium: verbatim; dropped by the reissued form from ADD-01 | The Bid Bond itself is VOL-I-6.3-01, VOL-I-6.4-01 and VOL-I-6.4-02. No consequence stated. Dropped by the reissued Form 4-A from ADD-01. | not in force at ADD-02 (REPLACED (by ADD-01:AppA)) | decided (recorded): I-F4A-FIELDS, I-NO-CONSEQUENCE | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/AppA/para1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-01/AppA/para1: accepted | VOL-IV:F4-A/item3 (VOL-IV p3; text layer); ADD-01/AppA/para1 [ADD-01; proposed] <- ADD-01:AppA/para1 (ADD-01 p3) | I-F4A-FIELDS; I-NO-CONSEQUENCE
VOL-IV-F4A-06 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-A | envelope_A; forms; confirmation; multiple_participation; dropped_in_reissue | Form 4-A para 4: confirm no consortium member participates in any other Proposal for the Project | 4. We confirm that no member of our consortium participates in any other Proposal for this Project. | 4. We confirm that no member of our consortium participates in any other Proposal for this Project. | We confirm that no member of our consortium participates in any other Proposal for this Project. | VOL-IV F4-A/item4 p3 | VOL-IV F4-A/item4 p3 | pass_fail | Legal | Bid manager | EV-FORM-4A | ACTIVE | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | status ACTIVE -> REPLACED (by ADD-01:AppA). by ADD-01/AppA/para1 [ADD-01; proposed] <- ADD-01:AppA/para1 (ADD-01 p3) |  |  | VOL-IV F4-A/item4 p3 | VOL-IV F4-A/item4 p3 as amended by ADD-01 AppA/para1 p3 | VOL-IV F4-A/item4 p3 as amended by ADD-01 AppA/para1 p3 | VOL-IV F4-A/item4 p3 as amended by ADD-01 AppA/para1 p3 | none stated in the documents |  |  | medium: verbatim; dropped by the reissued form from ADD-01; the confirmation rests on bidder facts | No consequence stated in the form; multiple participation itself leads to rejection under VOL-I 8.2 (row VOL-I-8.2-01). Also declared in Form 4-C (VOL-IV-F4C-02). Dropped by the reissued Form 4-A from ADD-01. | not in force at ADD-02 (REPLACED (by ADD-01:AppA)) | decided (recorded): I-F4A-FIELDS, I-NO-CONSEQUENCE, I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/AppA/para1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-01/AppA/para1: accepted | VOL-IV:F4-A/item4 (VOL-IV p3; text layer); ADD-01/AppA/para1 [ADD-01; proposed] <- ADD-01:AppA/para1 (ADD-01 p3) | I-F4A-FIELDS; I-NO-CONSEQUENCE; I-BIDDER-FACTS
VOL-IV-F4A-07 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-A | envelope_A; forms; confirmation; pre_bid; dropped_in_reissue | Form 4-A para 5: confirm attendance at the Pre-Bid Conference held under VOL-I 5.4 | 5. We confirm that we attended the Pre-Bid Conference held under Volume I Clause 5.4. | 5. We confirm that we attended the Pre-Bid Conference held under Volume I Clause 5.4. | We confirm that we attended the Pre-Bid Conference held under Volume I Clause 5.4. | VOL-IV F4-A/item5 p3 | VOL-IV F4-A/item5 p3 | pass_fail | Bid management | Bid manager | EV-FORM-4A | ACTIVE | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | REPLACED (by ADD-01:AppA) | status ACTIVE -> REPLACED (by ADD-01:AppA). by ADD-01/AppA/para1 [ADD-01; proposed] <- ADD-01:AppA/para1 (ADD-01 p3) |  |  | VOL-IV F4-A/item5 p3 | VOL-IV F4-A/item5 p3 as amended by ADD-01 AppA/para1 p3 | VOL-IV F4-A/item5 p3 as amended by ADD-01 AppA/para1 p3 | VOL-IV F4-A/item5 p3 as amended by ADD-01 AppA/para1 p3 | none stated in the documents |  |  | medium: verbatim; dropped by the reissued form from ADD-01; attendance is a bidder fact | No consequence stated in the form; non-attendance itself leads to disqualification under VOL-I 5.4 (row VOL-I-5.4-01). Dropped by the reissued Form 4-A from ADD-01. | not in force at ADD-02 (REPLACED (by ADD-01:AppA)) | decided (recorded): I-F4A-FIELDS, I-NO-CONSEQUENCE, I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/AppA/para1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-01/AppA/para1: accepted | VOL-IV:F4-A/item5 (VOL-IV p3; text layer); ADD-01/AppA/para1 [ADD-01; proposed] <- ADD-01:AppA/para1 (ADD-01 p3) | I-F4A-FIELDS; I-NO-CONSEQUENCE; I-BIDDER-FACTS
VOL-IV-F4B-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-B | envelope_A; forms; references | Form 4-B, one per reference project (Envelope A): complete every field, incl. the completion certificate question | [VOL-IV cover/T1/4-B p2] Form: 4-B ¦ Title: Reference Projects Schedule ¦ Envelope: A ¦ Status: Mandatory (one per project) [VOL-IV F4-B/reference-project-number p4] Reference project number: _____ of _____ [VOL-IV F4-B/project-name p4] Project name: [VOL-IV F4-B/country-and-location p4] Country and location: [VOL-IV F4-B/client-owner p4] Client / owner: [VOL-IV F4-B/role-of-the-consortium-member p4] Role of the consortium member: [VOL-IV F4-B/nominal-treatment-capacity-m3-day p4] Nominal treatment capacity (m³/day): [VOL-IV F4-B/process-type p4] Process type: [VOL-IV F4-B/date-of-commercial-operation-dd-mm-yyyy p4] Date of commercial operation (dd/mm/yyyy): [VOL-IV F4-B/was-the-member-responsible-for-design p4] Was the member responsible for design?: Yes / No [VOL-IV F4-B/was-the-member-responsible-for-construction p4] Was the member responsible for construction?: Yes / No [VOL-IV F4-B/was-the-member-responsible-for-operation p4] Was the member responsible for operation?: Yes / No [VOL-IV F4-B/years-of-operation-by-the-member p4] Years of operation by the member: [VOL-IV F4-B/contract-value-sar-equivalent p4] Contract value (SAR equivalent): [VOL-IV F4-B/client-contact-for-verification p4] Client contact for verification: [VOL-IV F4-B/completion-certificate-attached p4] Completion certificate attached?: Yes / No | [VOL-IV cover/T1/4-B p2] Form: 4-B ¦ Title: Reference Projects Schedule ¦ Envelope: A ¦ Status: Mandatory (one per project) [VOL-IV F4-B/reference-project-number p4] Reference project number: _____ of _____ [VOL-IV F4-B/project-name p4] Project name: [VOL-IV F4-B/country-and-location p4] Country and location: [VOL-IV F4-B/client-owner p4] Client / owner: [VOL-IV F4-B/role-of-the-consortium-member p4] Role of the consortium member: [VOL-IV F4-B/nominal-treatment-capacity-m3-day p4] Nominal treatment capacity (m³/day): [VOL-IV F4-B/process-type p4] Process type: [VOL-IV F4-B/date-of-commercial-operation-dd-mm-yyyy p4] Date of commercial operation (dd/mm/yyyy): [VOL-IV F4-B/was-the-member-responsible-for-design p4] Was the member responsible for design?: Yes / No [VOL-IV F4-B/was-the-member-responsible-for-construction p4] Was the member responsible for construction?: Yes / No [VOL-IV F4-B/was-the-member-responsible-for-operation p4] Was the member responsible for operation?: Yes / No [VOL-IV F4-B/years-of-operation-by-the-member p4] Years of operation by the member: [VOL-IV F4-B/contract-value-sar-equivalent p4] Contract value (SAR equivalent): [VOL-IV F4-B/client-contact-for-verification p4] Client contact for verification: [VOL-IV F4-B/completion-certificate-attached p4] Completion certificate attached?: Yes / No | Envelope: A ¦ Status: Mandatory (one per project) | VOL-IV cover/T1/4-B p2 | VOL-IV cover/T1/4-B p2; VOL-IV F4-B/reference-project-number p4; VOL-IV F4-B/project-name p4; VOL-IV F4-B/country-and-location p4; VOL-IV F4-B/client-owner p4; VOL-IV F4-B/role-of-the-consortium-member p4; VOL-IV F4-B/nominal-treatment-capacity-m3-day p4; VOL-IV F4-B/process-type p4; VOL-IV F4-B/date-of-commercial-operation-dd-mm-yyyy p4; VOL-IV F4-B/was-the-member-responsible-for-design p4; VOL-IV F4-B/was-the-member-responsible-for-construction p4; VOL-IV F4-B/was-the-member-responsible-for-operation p4; VOL-IV F4-B/years-of-operation-by-the-member p4; VOL-IV F4-B/contract-value-sar-equivalent p4; VOL-IV F4-B/client-contact-for-verification p4; VOL-IV F4-B/completion-certificate-attached p4 | pass_fail | Technical | Technical lead | EV-FORM-4B | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-IV cover/T1/4-B p2 | VOL-IV cover/T1/4-B p2 | VOL-IV cover/T1/4-B p2 | VOL-IV cover/T1/4-B p2 | none stated in the documents |  |  | medium: verbatim fields; the contract value field conflicts with VOL-I 6.2 (no commercial information in Envelope A) | No consequence stated for an incomplete form. A reference without a completion certificate is disregarded (VOL-I 9.5, row VOL-I-9.5-01, restated in the form's note); fewer than two qualifying plants leads to rejection (VOL-I-8.5-01). The 'Contract value (SAR equivalent)' field sits in Envelope A (I-VOL-I-ENV-A-PRICES). | unchanged since BASE; value as read: 'Envelope: A ¦ Status: Mandatory (one per project)' | decided (recorded): I-NO-CONSEQUENCE, I-VOL-I-ENV-A-PRICES, I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:cover/T1/4-B (VOL-IV p2; text layer); VOL-IV:F4-B/reference-project-number (VOL-IV p4; text layer); VOL-IV:F4-B/project-name (VOL-IV p4; text layer); VOL-IV:F4-B/country-and-location (VOL-IV p4; text layer); VOL-IV:F4-B/client-owner (VOL-IV p4; text layer); VOL-IV:F4-B/role-of-the-consortium-member (VOL-IV p4; text layer); VOL-IV:F4-B/nominal-treatment-capacity-m3-day (VOL-IV p4; text layer); VOL-IV:F4-B/process-type (VOL-IV p4; text layer); VOL-IV:F4-B/date-of-commercial-operation-dd-mm-yyyy (VOL-IV p4; text layer); VOL-IV:F4-B/was-the-member-responsible-for-design (VOL-IV p4; text layer); VOL-IV:F4-B/was-the-member-responsible-for-construction (VOL-IV p4; text layer); VOL-IV:F4-B/was-the-member-responsible-for-operation (VOL-IV p4; text layer); VOL-IV:F4-B/years-of-operation-by-the-member (VOL-IV p4; text layer); VOL-IV:F4-B/contract-value-sar-equivalent (VOL-IV p4; text layer); VOL-IV:F4-B/client-contact-for-verification (VOL-IV p4; text layer); VOL-IV:F4-B/completion-certificate-attached (VOL-IV p4; text layer) | I-NO-CONSEQUENCE; I-VOL-I-ENV-A-PRICES; I-BIDDER-FACTS
VOL-IV-F4C-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-C | envelope_A; forms; arabic; declaration; image | Form 4-C declaration 1 (Arabic only): no actual or potential conflict of interest with the Authority or its advisers on this project | أولاً: أنه لا يوجد أي تضارب في المصالح، فعلي أو محتمل، بيننا وبين الهيئة أو أي من مستشاريها فيما يتعلق بهذا المشروع. | أولاً: أنه لا يوجد أي تضارب في المصالح، فعلي أو محتمل، بيننا وبين الهيئة أو أي من مستشاريها فيما يتعلق بهذا المشروع. | أنه لا يوجد أي تضارب في المصالح، فعلي أو محتمل، بيننا وبين الهيئة أو أي من مستشاريها فيما يتعلق بهذا المشروع | VOL-IV F4-C/image/decl1 p6 | VOL-IV F4-C/image/decl1 p6 | pass_fail | Legal | Legal counsel | EV-FORM-4C | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q9 (Form 4-C completed in Arabic; English translation for convenience only) reviewed: no change to this declaration. by ADD-02/Q9 [ADD-02; proposed; annotates VOL-IV:F4-C/image (confirms)] <- ADD-02:Q9 (ADD-02 p2) |  | VOL-IV F4-C/image/decl1 p6 | VOL-IV F4-C/image/decl1 p6 | VOL-IV F4-C/image/decl1 p6 | VOL-IV F4-C/image/decl1 p6 | none stated in the documents |  |  | medium: from an image reading (transcription and displayed translations confirmed by the owner, 3 Oct 2026, VOL-IV-p6-r1; the consequence category mapping stays open: I-F4C-EXCLUSION) | ADD-02 Q9 (Form 4-C completed in Arabic; English translation for convenience only) reviewed: no change to this declaration. | unchanged since BASE; re-read by ADD-02/Q9 (confirms; accepted by a person; not counted as a confirmation); value as read: 'أنه لا يوجد أي تضارب في المصالح، فعلي أو محتمل، بيننا وبين الهيئة أو أي من مستشاريها فيما يتعلق بهذا المشروع' | decided (recorded): I-READING-F4C, I-NO-CONSEQUENCE, I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/Q9: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:F4-C/image/decl1 (VOL-IV p6; image reading); ADD-02/Q9 [ADD-02; proposed; annotates VOL-IV:F4-C/image (confirms)] <- ADD-02:Q9 (ADD-02 p2) | I-READING-F4C; I-NO-CONSEQUENCE; I-BIDDER-FACTS
VOL-IV-F4C-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-C | envelope_A; forms; arabic; declaration; image; multiple_participation | Form 4-C declaration 2 (Arabic): the member has not taken part, directly or indirectly, in more than one proposal for this tender | ثانياً: أن الشركة لم تشارك، بصورة مباشرة أو غير مباشرة، في أكثر من عرض واحد لهذه المناقصة. | ثانياً: أن الشركة لم تشارك، بصورة مباشرة أو غير مباشرة، في أكثر من عرض واحد لهذه المناقصة. | أن الشركة لم تشارك، بصورة مباشرة أو غير مباشرة، في أكثر من عرض واحد لهذه المناقصة | VOL-IV F4-C/image/decl2 p6 | VOL-IV F4-C/image/decl2 p6 | pass_fail | Legal | Legal counsel | EV-FORM-4C | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q9 (Form 4-C in Arabic) reviewed: no change to this declaration. by ADD-02/Q9 [ADD-02; proposed; annotates VOL-IV:F4-C/image (confirms)] <- ADD-02:Q9 (ADD-02 p2) |  | VOL-IV F4-C/image/decl2 p6 | VOL-IV F4-C/image/decl2 p6 | VOL-IV F4-C/image/decl2 p6 | VOL-IV F4-C/image/decl2 p6 | none stated in the documents |  |  | medium: from an image reading (transcription and displayed translations confirmed by the owner, 3 Oct 2026, VOL-IV-p6-r1; the consequence category mapping stays open: I-F4C-EXCLUSION) | ADD-02 Q9 (Form 4-C in Arabic) reviewed: no change to this declaration. | unchanged since BASE; re-read by ADD-02/Q9 (confirms; accepted by a person; not counted as a confirmation); value as read: 'أن الشركة لم تشارك، بصورة مباشرة أو غير مباشرة، في أكثر من عرض واحد لهذه المناقصة' | decided (recorded): I-READING-F4C, I-NO-CONSEQUENCE, I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/Q9: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:F4-C/image/decl2 (VOL-IV p6; image reading); ADD-02/Q9 [ADD-02; proposed; annotates VOL-IV:F4-C/image (confirms)] <- ADD-02:Q9 (ADD-02 p2) | I-READING-F4C; I-NO-CONSEQUENCE; I-BIDDER-FACTS | <- REL-MEMBER-MULTIPLE-PARTICIPATION [confirmed member_scope] from VOL-I:8.1, words:member of the Bidder, words:consortium member, words:member of the consortium
VOL-IV-F4C-03 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-C | envelope_A; forms; arabic; declaration; image; debarment | Form 4-C declaration 3 (Arabic): the member is not, and in the previous five years was not, on any Kingdom government debarment list | ثالثاً: أن الشركة غير مدرجة، ولم تكن مدرجة خلال الخمس سنوات السابقة، في أي قائمة حظر صادرة عن جهة حكومية في المملكة. | ثالثاً: أن الشركة غير مدرجة، ولم تكن مدرجة خلال الخمس سنوات السابقة، في أي قائمة حظر صادرة عن جهة حكومية في المملكة. | أن الشركة غير مدرجة، ولم تكن مدرجة خلال الخمس سنوات السابقة، في أي قائمة حظر صادرة عن جهة حكومية في المملكة | VOL-IV F4-C/image/decl3 p6 | VOL-IV F4-C/image/decl3 p6 | pass_fail | Legal | Legal counsel | EV-FORM-4C | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q9 (Form 4-C in Arabic) reviewed: no change to this declaration. by ADD-02/Q9 [ADD-02; proposed; annotates VOL-IV:F4-C/image (confirms)] <- ADD-02:Q9 (ADD-02 p2) |  | VOL-IV F4-C/image/decl3 p6 | VOL-IV F4-C/image/decl3 p6 | VOL-IV F4-C/image/decl3 p6 | VOL-IV F4-C/image/decl3 p6 | none stated in the documents |  |  | medium: from an image reading (transcription and displayed translations confirmed by the owner, 3 Oct 2026); wording differs from VOL-I 8.10 | ADD-02 Q9 (Form 4-C in Arabic) reviewed: no change to this declaration. | unchanged since BASE; re-read by ADD-02/Q9 (confirms; accepted by a person; not counted as a confirmation); value as read: 'أن الشركة غير مدرجة، ولم تكن مدرجة خلال الخمس سنوات السابقة، في أي قائمة حظر صادرة عن جهة حكومية في المملكة' | decided (recorded): I-READING-F4C, I-NO-CONSEQUENCE, I-BIDDER-FACTS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/Q9: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:F4-C/image/decl3 (VOL-IV p6; image reading); ADD-02/Q9 [ADD-02; proposed; annotates VOL-IV:F4-C/image (confirms)] <- ADD-02:Q9 (ADD-02 p2) | I-READING-F4C; I-NO-CONSEQUENCE; I-BIDDER-FACTS | <- REL-MEMBER-DEBARMENT [confirmed member_scope] from VOL-I:8.1, words:member of the Bidder, words:consortium member, words:member of the consortium
VOL-IV-F4C-05 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-C | envelope_A; forms; arabic; declaration; image; communications | Form 4-C declaration 5 (Arabic): undertake to comply with the communication rules of Volume I clause 4.2 (blackout) | خامساً: نلتزم بقواعد الاتصال المنصوص عليها في البند ٤-٢ من المجلد الأول. | خامساً: نلتزم بقواعد الاتصال المنصوص عليها في البند ٤-٢ من المجلد الأول. | نلتزم بقواعد الاتصال المنصوص عليها في البند ٤-٢ من المجلد الأول | VOL-IV F4-C/image/decl5 p6 | VOL-IV F4-C/image/decl5 p6 | pass_fail | Legal | Legal counsel | EV-FORM-4C | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q9 (Form 4-C in Arabic) reviewed: no change to this declaration. by ADD-02/Q9 [ADD-02; proposed; annotates VOL-IV:F4-C/image (confirms)] <- ADD-02:Q9 (ADD-02 p2) |  | VOL-IV F4-C/image/decl5 p6 | VOL-IV F4-C/image/decl5 p6 | VOL-IV F4-C/image/decl5 p6 | VOL-IV F4-C/image/decl5 p6 | none stated in the documents |  |  | medium: transcription and displayed translations confirmed by the owner, 3 Oct 2026, including the clause numeral (4.2); the interpretation is proposed | ADD-02 Q9 (Form 4-C in Arabic) reviewed: no change to this declaration. | unchanged since BASE; re-read by ADD-02/Q9 (confirms; accepted by a person; not counted as a confirmation); value as read: 'نلتزم بقواعد الاتصال المنصوص عليها في البند ٤-٢ من المجلد الأول' | decided (recorded): I-READING-F4C, I-NO-CONSEQUENCE | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/Q9: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:F4-C/image/decl5 (VOL-IV p6; image reading); ADD-02/Q9 [ADD-02; proposed; annotates VOL-IV:F4-C/image (confirms)] <- ADD-02:Q9 (ADD-02 p2) | I-READING-F4C; I-NO-CONSEQUENCE
VOL-IV-F4D-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-D | envelope_A; forms; guarantee | Form 4-D (Envelope A, EPC parent): name guarantor, jurisdiction and EPC Contractor; execute with name, capacity, date, authority reference | [VOL-IV cover/T1/4-D p2] Form: 4-D ¦ Title: Parent Company Guarantee — pro forma ¦ Envelope: A ¦ Status: Mandatory (EPC parent) [VOL-IV F4-D/guarantor-ultimate-parent-of-epc-contractor p7] Guarantor (ultimate parent of EPC Contractor): [VOL-IV F4-D/jurisdiction-of-incorporation p7] Jurisdiction of incorporation: [VOL-IV F4-D/epc-contractor-guaranteed p7] EPC Contractor guaranteed: [VOL-IV F4-D/guaranteed-obligations p7] Guaranteed obligations: All obligations of the EPC Contractor under the EPC Contract during the construction period, including the payment of liquidated damages. [VOL-IV F4-D/limit-of-liability p7] Limit of liability: Unlimited as to the guaranteed obligations [VOL-IV F4-D/expiry p7] Expiry: The later of the issue of the final completion certificate under the EPC Contract and the expiry of the defects notification period [VOL-IV F4-D/governing-law p7] Governing law: Laws of the Kingdom [VOL-IV F4-D/signature p7] Signature: [VOL-IV F4-D/name-and-capacity p7] Name and capacity: [VOL-IV F4-D/date p7] Date: [VOL-IV F4-D/corporate-authority-reference p7] Corporate authority reference: | [VOL-IV cover/T1/4-D p2] Form: 4-D ¦ Title: Parent Company Guarantee — pro forma ¦ Envelope: A ¦ Status: Mandatory (EPC parent) [VOL-IV F4-D/guarantor-ultimate-parent-of-epc-contractor p7] Guarantor (ultimate parent of EPC Contractor): [VOL-IV F4-D/jurisdiction-of-incorporation p7] Jurisdiction of incorporation: [VOL-IV F4-D/epc-contractor-guaranteed p7] EPC Contractor guaranteed: [VOL-IV F4-D/guaranteed-obligations p7] Guaranteed obligations: All obligations of the EPC Contractor under the EPC Contract during the construction period, including the payment of liquidated damages. [VOL-IV F4-D/limit-of-liability p7] Limit of liability: Unlimited as to the guaranteed obligations [VOL-IV F4-D/expiry p7] Expiry: The later of the issue of the final completion certificate under the EPC Contract and the expiry of the defects notification period [VOL-IV F4-D/governing-law p7] Governing law: Laws of the Kingdom [VOL-IV F4-D/signature p7] Signature: [VOL-IV F4-D/name-and-capacity p7] Name and capacity: [VOL-IV F4-D/date p7] Date: [VOL-IV F4-D/corporate-authority-reference p7] Corporate authority reference: | Envelope: A ¦ Status: Mandatory (EPC parent) | VOL-IV cover/T1/4-D p2 | VOL-IV cover/T1/4-D p2; VOL-IV F4-D/guarantor-ultimate-parent-of-epc-contractor p7; VOL-IV F4-D/jurisdiction-of-incorporation p7; VOL-IV F4-D/epc-contractor-guaranteed p7; VOL-IV F4-D/guaranteed-obligations p7; VOL-IV F4-D/limit-of-liability p7; VOL-IV F4-D/expiry p7; VOL-IV F4-D/governing-law p7; VOL-IV F4-D/signature p7; VOL-IV F4-D/name-and-capacity p7; VOL-IV F4-D/date p7; VOL-IV F4-D/corporate-authority-reference p7 | pass_fail | Legal | Legal counsel | EV-FORM-4D | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-IV cover/T1/4-D p2 | VOL-IV cover/T1/4-D p2 | VOL-IV cover/T1/4-D p2 | VOL-IV cover/T1/4-D p2 | none stated in the documents |  |  | high: verbatim fields; no consequence stated | Executed by the ultimate parent of the EPC Contractor, 'substantially in the form' (VOL-I 8.7, row VOL-I-8.7-01; ADD-02 Q10: not from the O&M Operator). No consequence stated. The guarantee terms are separate rows (VOL-IV-F4D-02 to -08). | unchanged since BASE; value as read: 'Envelope: A ¦ Status: Mandatory (EPC parent)' | decided (recorded): I-NO-CONSEQUENCE, I-F4D-WORDING | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:cover/T1/4-D (VOL-IV p2; text layer); VOL-IV:F4-D/guarantor-ultimate-parent-of-epc-contractor (VOL-IV p7; text layer); VOL-IV:F4-D/jurisdiction-of-incorporation (VOL-IV p7; text layer); VOL-IV:F4-D/epc-contractor-guaranteed (VOL-IV p7; text layer); VOL-IV:F4-D/guaranteed-obligations (VOL-IV p7; text layer); VOL-IV:F4-D/limit-of-liability (VOL-IV p7; text layer); VOL-IV:F4-D/expiry (VOL-IV p7; text layer); VOL-IV:F4-D/governing-law (VOL-IV p7; text layer); VOL-IV:F4-D/signature (VOL-IV p7; text layer); VOL-IV:F4-D/name-and-capacity (VOL-IV p7; text layer); VOL-IV:F4-D/date (VOL-IV p7; text layer); VOL-IV:F4-D/corporate-authority-reference (VOL-IV p7; text layer) | I-NO-CONSEQUENCE; I-F4D-WORDING
VOL-IV-F4D-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-D | forms; guarantee; post_award | Guarantee covers all EPC Contractor obligations under the EPC Contract during construction, incl. payment of liquidated damages | Guaranteed obligations: All obligations of the EPC Contractor under the EPC Contract during the construction period, including the payment of liquidated damages. | Guaranteed obligations: All obligations of the EPC Contractor under the EPC Contract during the construction period, including the payment of liquidated damages. | All obligations of the EPC Contractor under the EPC Contract during the construction period, including the payment of liquidated damages. | VOL-IV F4-D/guaranteed-obligations p7 | VOL-IV F4-D/guaranteed-obligations p7 | contractual_post_award | Legal | Legal counsel | EV-FORM-4D | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-IV F4-D/guaranteed-obligations p7 | VOL-IV F4-D/guaranteed-obligations p7 | VOL-IV F4-D/guaranteed-obligations p7 | VOL-IV F4-D/guaranteed-obligations p7 | none stated in the documents |  |  | high: verbatim pre-printed term | A pre-printed term of the pro forma; the executed guarantee is submitted with Envelope A and binds the guarantor after award. | unchanged since BASE; value as read: 'All obligations of the EPC Contractor under the EPC Contract during the construction period, including the payment of l…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:F4-D/guaranteed-obligations (VOL-IV p7; text layer)
VOL-IV-F4D-03 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-D | forms; guarantee; post_award; liability | Guarantor's liability unlimited as to the guaranteed obligations | Limit of liability: Unlimited as to the guaranteed obligations | Limit of liability: Unlimited as to the guaranteed obligations | Limit of liability: Unlimited as to the guaranteed obligations | VOL-IV F4-D/limit-of-liability p7 | VOL-IV F4-D/limit-of-liability p7 | contractual_post_award | Legal | Legal counsel | EV-FORM-4D | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-IV F4-D/limit-of-liability p7 | VOL-IV F4-D/limit-of-liability p7 | VOL-IV F4-D/limit-of-liability p7 | VOL-IV F4-D/limit-of-liability p7 | none stated in the documents |  |  | high: verbatim pre-printed term |  | unchanged since BASE; value as read: 'Limit of liability: Unlimited as to the guaranteed obligations' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:F4-D/limit-of-liability (VOL-IV p7; text layer)
VOL-IV-F4D-04 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-D | forms; guarantee; post_award; expiry | Guarantee expires at the later of the final completion certificate and the end of the defects notification period | Expiry: The later of the issue of the final completion certificate under the EPC Contract and the expiry of the defects notification period | Expiry: The later of the issue of the final completion certificate under the EPC Contract and the expiry of the defects notification period | The later of the issue of the final completion certificate under the EPC Contract and the expiry of the defects notification period | VOL-IV F4-D/expiry p7 | VOL-IV F4-D/expiry p7 | contractual_post_award | Legal | Legal counsel | EV-FORM-4D | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-IV F4-D/expiry p7 | VOL-IV F4-D/expiry p7 | VOL-IV F4-D/expiry p7 | VOL-IV F4-D/expiry p7 | none stated in the documents |  |  | high: verbatim pre-printed term | Both events are under the EPC Contract, which is not in the pack; no date can be computed. | unchanged since BASE; value as read: 'The later of the issue of the final completion certificate under the EPC Contract and the expiry of the defects notific…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:F4-D/expiry (VOL-IV p7; text layer)
VOL-IV-F4D-05 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-D | forms; guarantee; post_award; governing_law | Guarantee governed by the laws of the Kingdom | Governing law: Laws of the Kingdom | Governing law: Laws of the Kingdom | Governing law: Laws of the Kingdom | VOL-IV F4-D/governing-law p7 | VOL-IV F4-D/governing-law p7 | contractual_post_award | Legal | Legal counsel | EV-FORM-4D | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-IV F4-D/governing-law p7 | VOL-IV F4-D/governing-law p7 | VOL-IV F4-D/governing-law p7 | VOL-IV F4-D/governing-law p7 | none stated in the documents |  |  | high: verbatim pre-printed term |  | unchanged since BASE; value as read: 'Governing law: Laws of the Kingdom' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:F4-D/governing-law (VOL-IV p7; text layer)
VOL-IV-F4D-06 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-D | forms; guarantee; post_award | Irrevocable, unconditional guarantee of the EPC Contractor's performance to the Project Company and, by collateral warranty, the Authority | 1. The Guarantor irrevocably and unconditionally guarantees to the Project Company and, by way of collateral warranty, to the Authority, the due and punctual performance by the EPC Contractor of the guaranteed obligations. | 1. The Guarantor irrevocably and unconditionally guarantees to the Project Company and, by way of collateral warranty, to the Authority, the due and punctual performance by the EPC Contractor of the guaranteed obligations. | The Guarantor irrevocably and unconditionally guarantees to the Project Company and, by way of collateral warranty, to the Authority, the due and punctual performance by the EPC Contractor of the guaranteed obligations. | VOL-IV F4-D/item1 p7 | VOL-IV F4-D/item1 p7 | contractual_post_award | Legal | Legal counsel | EV-FORM-4D | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-IV F4-D/item1 p7 | VOL-IV F4-D/item1 p7 | VOL-IV F4-D/item1 p7 | VOL-IV F4-D/item1 p7 | none stated in the documents |  |  | high: verbatim pre-printed term |  | unchanged since BASE; value as read: 'The Guarantor irrevocably and unconditionally guarantees to the Project Company and, by way of collateral warranty, to …' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:F4-D/item1 (VOL-IV p7; text layer)
VOL-IV-F4D-07 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-D | forms; guarantee; post_award | Guarantor liable as primary obligor; not discharged by any amendment, indulgence or waiver granted to the EPC Contractor | 2. The Guarantor's liability is that of a primary obligor and is not discharged by any amendment, indulgence or waiver granted to the EPC Contractor. | 2. The Guarantor's liability is that of a primary obligor and is not discharged by any amendment, indulgence or waiver granted to the EPC Contractor. | The Guarantor's liability is that of a primary obligor and is not discharged by any amendment, indulgence or waiver granted to the EPC Contractor. | VOL-IV F4-D/item2 p7 | VOL-IV F4-D/item2 p7 | contractual_post_award | Legal | Legal counsel | EV-FORM-4D | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-IV F4-D/item2 p7 | VOL-IV F4-D/item2 p7 | VOL-IV F4-D/item2 p7 | VOL-IV F4-D/item2 p7 | none stated in the documents |  |  | high: verbatim pre-printed term |  | unchanged since BASE; value as read: 'The Guarantor's liability is that of a primary obligor and is not discharged by any amendment, indulgence or waiver gra…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:F4-D/item2 (VOL-IV p7; text layer)
VOL-IV-F4D-08 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-D | forms; guarantee; post_award | Guarantee not conditional on any demand first being made of the EPC Contractor | 3. This guarantee is not conditional on any demand first being made of the EPC Contractor. | 3. This guarantee is not conditional on any demand first being made of the EPC Contractor. | This guarantee is not conditional on any demand first being made of the EPC Contractor. | VOL-IV F4-D/item3 p7 | VOL-IV F4-D/item3 p7 | contractual_post_award | Legal | Legal counsel | EV-FORM-4D | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-IV F4-D/item3 p7 | VOL-IV F4-D/item3 p7 | VOL-IV F4-D/item3 p7 | VOL-IV F4-D/item3 p7 | none stated in the documents |  |  | high: verbatim pre-printed term |  | unchanged since BASE; value as read: 'This guarantee is not conditional on any demand first being made of the EPC Contractor.' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:F4-D/item3 (VOL-IV p7; text layer)
VOL-IV-F4E-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-E | envelope_A; forms; deviations | Form 4-E (Envelope A, mandatory): one line per deviation (Volume/Clause, nature, proposed wording, rationale), total declared, signed, dated | [VOL-IV cover/T1/4-E p2] Form: 4-E ¦ Title: Schedule of Deviations ¦ Envelope: A ¦ Status: Mandatory [VOL-IV F4-E/T1/1 p8] No: 1 [VOL-IV F4-E/T1/2 p8] No: 2 [VOL-IV F4-E/T1/3 p8] No: 3 [VOL-IV F4-E/T1/4 p8] No: 4 [VOL-IV F4-E/T1/5 p8] No: 5 [VOL-IV F4-E/T1/6 p8] No: 6 [VOL-IV F4-E/total-number-of-deviations-declared p8] Total number of deviations declared: [VOL-IV F4-E/signature-of-authorised-signatory p8] Signature of authorised signatory: [VOL-IV F4-E/date p8] Date: | [VOL-IV cover/T1/4-E p2] Form: 4-E ¦ Title: Schedule of Deviations ¦ Envelope: A ¦ Status: Mandatory [VOL-IV F4-E/T1/1 p8] No: 1 [VOL-IV F4-E/T1/2 p8] No: 2 [VOL-IV F4-E/T1/3 p8] No: 3 [VOL-IV F4-E/T1/4 p8] No: 4 [VOL-IV F4-E/T1/5 p8] No: 5 [VOL-IV F4-E/T1/6 p8] No: 6 [VOL-IV F4-E/total-number-of-deviations-declared p8] Total number of deviations declared: [VOL-IV F4-E/signature-of-authorised-signatory p8] Signature of authorised signatory: [VOL-IV F4-E/date p8] Date: | Title: Schedule of Deviations ¦ Envelope: A ¦ Status: Mandatory | VOL-IV cover/T1/4-E p2 | VOL-IV cover/T1/4-E p2; VOL-IV F4-E/T1/1 p8; VOL-IV F4-E/T1/2 p8; VOL-IV F4-E/T1/3 p8; VOL-IV F4-E/T1/4 p8; VOL-IV F4-E/T1/5 p8; VOL-IV F4-E/T1/6 p8; VOL-IV F4-E/total-number-of-deviations-declared p8; VOL-IV F4-E/signature-of-authorised-signatory p8; VOL-IV F4-E/date p8 | pass_fail | Legal | Legal counsel | EV-FORM-4E | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-IV cover/T1/4-E p2 | VOL-IV cover/T1/4-E p2 | VOL-IV cover/T1/4-E p2 | VOL-IV cover/T1/4-E p2 | none stated in the documents |  |  | high: verbatim; no consequence stated for the form itself | No consequence stated for completing the form. What it must list, and the non-responsive consequence of 'no deviations' with a qualification elsewhere, are VOL-I-9.6-01 (restated in the form's note). VOL-V's note: a deviation not listed is taken as accepted. | own words unchanged at ADD-02, but what it depends on changed (dependency; see A2); value as read: 'Title: Schedule of Deviations ¦ Envelope: A ¦ Status: Mandatory' | decided (recorded): I-NO-CONSEQUENCE, I-VOL-V-MISSING, I-VOL-V-PERSISTENT-BREACH, I-FORM-4E-COMMERCIAL-QUALIFICATION, I-FORM-4E-CROSS-CHECK | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:cover/T1/4-E (VOL-IV p2; text layer); VOL-IV:F4-E/T1/1 (VOL-IV p8; text layer); VOL-IV:F4-E/T1/2 (VOL-IV p8; text layer); VOL-IV:F4-E/T1/3 (VOL-IV p8; text layer); VOL-IV:F4-E/T1/4 (VOL-IV p8; text layer); VOL-IV:F4-E/T1/5 (VOL-IV p8; text layer); VOL-IV:F4-E/T1/6 (VOL-IV p8; text layer); VOL-IV:F4-E/total-number-of-deviations-declared (VOL-IV p8; text layer); VOL-IV:F4-E/signature-of-authorised-signatory (VOL-IV p8; text layer); VOL-IV:F4-E/date (VOL-IV p8; text layer) | I-NO-CONSEQUENCE; I-VOL-V-MISSING (via REL-MISSING-SCHEDULE-11-LATE-COMPLETION > REL-VOL-V-FORM-4E (confirmed); via REL-MISSING-SCHEDULE-11-PERSISTENT-BREACH > REL-VOL-V-FORM-4E (proposed)); I-VOL-V-PERSISTENT-BREACH (via REL-MISSING-SCHEDULE-11-PERSISTENT-BREACH > REL-VOL-V-FORM-4E (proposed)); I-FORM-4E-COMMERCIAL-QUALIFICATION (the issue names the row (curated, PROPOSED)); I-FORM-4E-CROSS-CHECK (the issue names the row (curated, PROPOSED)) | <- REL-VOL-V-FORM-4E [confirmed depends_on] from VOL-V:1.1, VOL-V:1.2, VOL-V:1.3, VOL-V:1.4, VOL-V:1.5, VOL-V:1.6, VOL-V:3.1, VOL-V:3.2, VOL-V:3.3, VOL-V:12.1, VOL-V:12.2, VOL-V:12.3, VOL-V:12.4, VOL-V:18.1, VOL-V:18.2, VOL-V:18.3, VOL-V:18.4, VOL-V:24.1, VOL-V:24.2, VOL-V:24.3, VOL-V:24.4, VOL-V:29.1, VOL-V:29.2, VOL-V:29.3, VOL-V:29.4, VOL-V:29.5, VOL-V:31.1, VOL-V:31.2, VOL-V:31.3, VOL-V:31.4, VOL-V:31.5, VOL-V:34.1, VOL-V:34.2, VOL-V:34.3, VOL-V:36.1, VOL-V:36.2, VOL-V:36.3, VOL-V:39.1, VOL-V:39.2, VOL-V:39.3, VOL-V:39.4, VOL-V:39.5, VOL-V:40.1, VOL-V:40.2, VOL-V:40.3, VOL-V:42.1, VOL-V:42.2, VOL-V:44.1, VOL-V:44.2, VOL-V:44.3; REACHED at ADD-02 (confirmed dependency): from VOL-V:3.1, VOL-V:36.2 via REL-VOL-V-FORM-4E
VOL-IV-F4F-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-F | envelope_B; forms; commercial | Form 4-F (Envelope B, mandatory): complete every field (Availability Payment in figures and words, cost, financing, IRRs, model audit) and sign | [VOL-IV cover/T1/4-F p2] Form: 4-F ¦ Title: Financial Proposal Schedule ¦ Envelope: B ¦ Status: Mandatory [VOL-IV F4-F/bidder p9] Bidder: [VOL-IV F4-F/availability-payment-sar-per-annum-year-1-of-operations p9] Availability Payment (SAR per annum, year 1 of operations): [VOL-IV F4-F/availability-payment-in-words p9] Availability Payment in words: [VOL-IV F4-F/estimated-project-cost-sar p9] Estimated Project Cost (SAR): [VOL-IV F4-F/assumed-senior-debt-tenor-years-from-financial-close p9] Assumed senior debt tenor (years from Financial Close): [VOL-IV F4-F/assumed-senior-debt-margin-bps p9] Assumed senior debt margin (bps): [VOL-IV F4-F/assumed-gearing-debt-equity p9] Assumed gearing (debt : equity): [VOL-IV F4-F/project-irr-nominal-post-tax p9] Project IRR (%, nominal, post-tax): [VOL-IV F4-F/equity-irr-nominal-post-tax p9] Equity IRR (%, nominal, post-tax): [VOL-IV F4-F/indexation-basis-assumed p9] Indexation basis assumed: Per Volume V Clause 29.2 [VOL-IV F4-F/model-auditor p9] Model auditor: [VOL-IV F4-F/date-of-model-audit-opinion p9] Date of model audit opinion: [VOL-IV F4-F/signature p9] Signature: [VOL-IV F4-F/name-and-capacity p9] Name and capacity: [VOL-IV F4-F/date p9] Date: | [VOL-IV cover/T1/4-F p2] Form: 4-F ¦ Title: Financial Proposal Schedule ¦ Envelope: B ¦ Status: Mandatory [VOL-IV F4-F/bidder p9] Bidder: [VOL-IV F4-F/availability-payment-sar-per-annum-year-1-of-operations p9] Availability Payment (SAR per annum, year 1 of operations): [VOL-IV F4-F/availability-payment-in-words p9] Availability Payment in words: [VOL-IV F4-F/estimated-project-cost-sar p9] Estimated Project Cost (SAR): [VOL-IV F4-F/assumed-senior-debt-tenor-years-from-financial-close p9] Assumed senior debt tenor (years from Financial Close): [VOL-IV F4-F/assumed-senior-debt-margin-bps p9] Assumed senior debt margin (bps): [VOL-IV F4-F/assumed-gearing-debt-equity p9] Assumed gearing (debt : equity): [VOL-IV F4-F/project-irr-nominal-post-tax p9] Project IRR (%, nominal, post-tax): [VOL-IV F4-F/equity-irr-nominal-post-tax p9] Equity IRR (%, nominal, post-tax): [VOL-IV F4-F/indexation-basis-assumed p9] Indexation basis assumed: Per Volume V Clause 29.2 [VOL-IV F4-F/model-auditor p9] Model auditor: [VOL-IV F4-F/date-of-model-audit-opinion p9] Date of model audit opinion: [VOL-IV F4-F/signature p9] Signature: [VOL-IV F4-F/name-and-capacity p9] Name and capacity: [VOL-IV F4-F/date p9] Date: | Title: Financial Proposal Schedule ¦ Envelope: B ¦ Status: Mandatory | VOL-IV cover/T1/4-F p2 | VOL-IV cover/T1/4-F p2; VOL-IV F4-F/bidder p9; VOL-IV F4-F/availability-payment-sar-per-annum-year-1-of-operations p9; VOL-IV F4-F/availability-payment-in-words p9; VOL-IV F4-F/estimated-project-cost-sar p9; VOL-IV F4-F/assumed-senior-debt-tenor-years-from-financial-close p9; VOL-IV F4-F/assumed-senior-debt-margin-bps p9; VOL-IV F4-F/assumed-gearing-debt-equity p9; VOL-IV F4-F/project-irr-nominal-post-tax p9; VOL-IV F4-F/equity-irr-nominal-post-tax p9; VOL-IV F4-F/indexation-basis-assumed p9; VOL-IV F4-F/model-auditor p9; VOL-IV F4-F/date-of-model-audit-opinion p9; VOL-IV F4-F/signature p9; VOL-IV F4-F/name-and-capacity p9; VOL-IV F4-F/date p9 | pass_fail | Commercial | Commercial lead | EV-FORM-4F | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-IV cover/T1/4-F p2 | VOL-IV cover/T1/4-F p2 | VOL-IV cover/T1/4-F p2 | VOL-IV cover/T1/4-F p2 | none stated in the documents |  |  | high: verbatim fields; where the 10.3 and 10.6 documents go is an open issue | No consequence stated for an incomplete form. Envelope B holds only this Form and the Financial Model (VOL-I-10.1-01); its tenor, margin, gearing, model auditor and opinion-date fields partly overlap VOL-I 10.3 and 10.6 (I-VOL-I-ENV-B). Indexation basis printed as 'Per Volume V Clause 29.2'. | unchanged since BASE; value as read: 'Title: Financial Proposal Schedule ¦ Envelope: B ¦ Status: Mandatory' | decided (recorded): I-NO-CONSEQUENCE, I-VOL-I-ENV-B, I-ADD03-Q17-AP-CAPACITY | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:cover/T1/4-F (VOL-IV p2; text layer); VOL-IV:F4-F/bidder (VOL-IV p9; text layer); VOL-IV:F4-F/availability-payment-sar-per-annum-year-1-of-operations (VOL-IV p9; text layer); VOL-IV:F4-F/availability-payment-in-words (VOL-IV p9; text layer); VOL-IV:F4-F/estimated-project-cost-sar (VOL-IV p9; text layer); VOL-IV:F4-F/assumed-senior-debt-tenor-years-from-financial-close (VOL-IV p9; text layer); VOL-IV:F4-F/assumed-senior-debt-margin-bps (VOL-IV p9; text layer); VOL-IV:F4-F/assumed-gearing-debt-equity (VOL-IV p9; text layer); VOL-IV:F4-F/project-irr-nominal-post-tax (VOL-IV p9; text layer); VOL-IV:F4-F/equity-irr-nominal-post-tax (VOL-IV p9; text layer); VOL-IV:F4-F/indexation-basis-assumed (VOL-IV p9; text layer); VOL-IV:F4-F/model-auditor (VOL-IV p9; text layer); VOL-IV:F4-F/date-of-model-audit-opinion (VOL-IV p9; text layer); VOL-IV:F4-F/signature (VOL-IV p9; text layer); VOL-IV:F4-F/name-and-capacity (VOL-IV p9; text layer); VOL-IV:F4-F/date (VOL-IV p9; text layer) | I-NO-CONSEQUENCE; I-VOL-I-ENV-B; I-ADD03-Q17-AP-CAPACITY (via REL-AI-004 (proposed)) | <- REL-PAY-FORM-4F [confirmed feeds_calculation] from calc:availability-payment; <- REL-AI-004 [proposed depends_on] from ADD-03-Q17-01
VOL-IV-F4F-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-IV:F4-F | envelope_B; forms; confirmation; commercial | Form 4-F: confirm the Availability Payment is unconditional, unqualified and derived from the Financial Model submitted with the Form | We confirm that the Availability Payment stated above is unconditional, is not subject to any qualification, and has been derived from the Financial Model submitted with this Form. | We confirm that the Availability Payment stated above is unconditional, is not subject to any qualification, and has been derived from the Financial Model submitted with this Form. | We confirm that the Availability Payment stated above is unconditional, is not subject to any qualification, and has been derived from the Financial Model submitted with this Form. | VOL-IV F4-F/para1 p9 | VOL-IV F4-F/para1 p9 | pass_fail | Commercial | Commercial lead | EV-FORM-4F; EV-FIN-MODEL | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-IV F4-F/para1 p9 | VOL-IV F4-F/para1 p9 | VOL-IV F4-F/para1 p9 | VOL-IV F4-F/para1 p9 | none stated in the documents |  |  | high: verbatim | No consequence stated in the confirmation; a conditional or alternative price is non-responsive under VOL-I 10.5 (row VOL-I-10.5-01). | unchanged since BASE; value as read: 'We confirm that the Availability Payment stated above is unconditional, is not subject to any qualification, and has be…' | decided (recorded): I-NO-CONSEQUENCE, I-ADD03-Q17-AP-CAPACITY, I-FORM-4E-COMMERCIAL-QUALIFICATION | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-IV:F4-F/para1 (VOL-IV p9; text layer) | I-NO-CONSEQUENCE; I-ADD03-Q17-AP-CAPACITY (via REL-AI-004 (proposed)); I-FORM-4E-COMMERCIAL-QUALIFICATION (the issue names the row (curated, PROPOSED)) | <- REL-MODEL-FORM-4F [confirmed feeds_calculation] from VOL-I-10.3-01; <- REL-AI-004 [proposed depends_on] from ADD-03-Q17-01; REACHED at ADD-02 (possible impact): from VOL-V:36.2 via REL-CHANGE-IN-LAW-FINANCIAL-MODEL > REL-MODEL-FORM-4F
VOL-V-NOTE-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:cover/note-to-bidders | contract; deviations; bid_submission | List every deviation from the Volume V clauses in Form 4-E; a deviation not listed is taken as accepted | Note to Bidders. This extract contains the clauses of the draft Project Agreement on which the Authority invites comment through Form 4-E. Clause numbering follows the full draft; omitted clauses are not reproduced. A deviation not listed in Form 4-E will be taken as accepted. | Note to Bidders. This extract contains the clauses of the draft Project Agreement on which the Authority invites comment through Form 4-E. Clause numbering follows the full draft; omitted clauses are not reproduced. A deviation not listed in Form 4-E will be taken as accepted. | This extract contains the clauses of the draft Project Agreement on which the Authority invites comment through Form 4-E. | VOL-V cover/note-to-bidders p2 | VOL-V cover/note-to-bidders p2 | procedural | Legal | Legal counsel | EV-FORM-4E | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V cover/note-to-bidders p2 | VOL-V cover/note-to-bidders p2 | VOL-V cover/note-to-bidders p2 | VOL-V cover/note-to-bidders p2 | lesser consequence: "A deviation not listed in Form 4-E will be taken as accepted." | VOL-V cover/note-to-bidders p2 |  | high: verbatim text-layer note | VOL-I 9.6 (row VOL-I-9.6-01) requires Form 4-E to list every deviation, qualification or reservation to Volume V, and treats 'no deviations' with a qualification elsewhere as non-responsive. 'Omitted clauses are not reproduced' (I-VOL-V-MISSING). The concession-term conflict (I-CONCESSION) turns on this Note. | unchanged since BASE; value as read: 'This extract contains the clauses of the draft Project Agreement on which the Authority invites comment through Form 4-…' | decided (recorded): I-VOL-V-MISSING, I-CONCESSION | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:cover/note-to-bidders (VOL-V p2; text layer) | I-VOL-V-MISSING; I-CONCESSION
VOL-V-3.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:3.1 | contract; post_award; term | Agreement in force from the Effective Date for 25 years from the Effective Date, unless terminated earlier | This Agreement shall come into force on the Effective Date and shall continue for a period of twenty-five (25) years from the Effective Date, unless terminated earlier in accordance with its terms. | This Agreement shall come into force on the Effective Date and shall continue for a period of twenty-five (25) years from the Effective Date, unless terminated earlier in accordance with its terms. | shall continue for a period of twenty-five (25) years from the Effective Date | VOL-V 3.1 p2 | VOL-V 3.1 p2 | contractual_post_award | Legal | Legal counsel | Post-award (proposed requirement): to be obtained on execution, the Project Agreement executed by both parties, whose date of execution is the Effective Date (VOL-V 1.2) from which VOL-V 3.1 runs the 25-year term. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q7 (p2) was asked 'Which applies?' and answers: 'The Authority notes the question. The order of precedence at Volume I Clause 3.2 applies. The Authority does not consider further amendment necessary at this stage.' It does not say which clause applies, and it amends neither. Two readings: this clause, 'twenty-five (25) years from the Effective Date'; VOL-I 12.1 (p6), 'twenty-five (25) years commencing on the Project Commercial Operation Date' (row VOL-I-12.1-01). VOL-I 3.2 (p2) orders the RFP Documents '(a) the Addenda, a later Addendum prevailing over an earlier one;' '(b) Volume I (Instructions to Bidders);' '(c) Volume V (Draft Project Agreement);' 'the first named prevailing'; VOL-I 3.3 (p2): 'A Bidder that resolves such a conflict unilaterally does so at its own risk'; and 'A deviation not listed in Form 4-E will be taken as accepted.' (VOL-V Note to Bidders, p2). Which clause governs the term, what to record in Form 4-E and which term start the Financial Model assumes are a decision for a person (Legal; I-CONCESSION, CQ-CONCESSION-TERM); no decision recorded. by ADD-02/Q7 [ADD-02; proposed; annotates VOL-V:3.1 (interprets)] <- ADD-02:Q7 (ADD-02 p2) |  | VOL-V 3.1 p2 | VOL-V 3.1 p2 | VOL-V 3.1 p2 | VOL-V 3.1 p2 | none stated in the documents |  | VOL-V-TERM-END: None (unknown_anchor) | medium: verbatim; conflicts with VOL-I 12.1 (from PCOD); ADD-02 Q7 refers to the order of precedence at VOL-I 3.2 without saying which clause applies; which clause governs is a decision for a person (Legal, I-CONCESSION); no decision recorded; the Effective Date is not a pack event | ADD-02 Q7 (p2) was asked 'Which applies?' and answers: 'The Authority notes the question. The order of precedence at Volume I Clause 3.2 applies. The Authority does not consider further amendment necessary at this stage.' It does not say which clause applies, and it amends neither. Two readings: this clause, 'twenty-five (25) years from the Effective Date'; VOL-I 12.1 (p6), 'twenty-five (25) years commencing on the Project Commercial Operation Date' (row VOL-I-12.1-01). VOL-I 3.2 (p2) orders the RFP Documents '(a) the Addenda, a later Addendum prevailing over an earlier one;' '(b) Volume I (Instructions to Bidders);' '(c) Volume V (Draft Project Agreement);' 'the first named prevailing'; VOL-I 3.3 (p2): 'A Bidder that resolves such a conflict unilaterally does so at its own risk'; and 'A deviation not listed in Form 4-E will be taken as accepted.' (VOL-V Note to Bidders, p2). Which clause governs the term, what to record in Form 4-E and which term start the Financial Model assumes are a decision for a person (Legal; I-CONCESSION, CQ-CONCESSION-TERM); no decision recorded. | unchanged since BASE; re-read by ADD-02/Q7 (interprets; accepted by a person; not counted as a confirmation); value as read: 'shall continue for a period of twenty-five (25) years from the Effective Date' | decided (recorded): I-CONCESSION | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/Q7: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:3.1 (VOL-V p2; text layer); ADD-02/Q7 [ADD-02; proposed; annotates VOL-V:3.1 (interprets)] <- ADD-02:Q7 (ADD-02 p2) | I-CONCESSION
VOL-V-3.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:3.2 | contract; post_award; handback | On expiry, transfer the Facility to the Authority under Clause 42 for nil consideration | On expiry, the Facility shall transfer to the Authority in accordance with Clause 42 for nil consideration. | On expiry, the Facility shall transfer to the Authority in accordance with Clause 42 for nil consideration. | On expiry, the Facility shall transfer to the Authority in accordance with Clause 42 for nil consideration. | VOL-V 3.2 p2 | VOL-V 3.2 p2 | contractual_post_award | Legal | Legal counsel | Post-award (proposed requirement): to be produced on expiry, a record of the transfer of the Facility to the Authority for nil consideration in accordance with Clause 42 (the extract prescribes no form of transfer document), supported by the handback records proposed under row VOL-V-42.1-01. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 3.2 p2 | VOL-V 3.2 p2 | VOL-V 3.2 p2 | VOL-V 3.2 p2 | none stated in the documents |  |  | high: verbatim; the expiry date depends on the term start (I-CONCESSION) |  | unchanged since BASE; value as read: 'On expiry, the Facility shall transfer to the Authority in accordance with Clause 42 for nil consideration.' | decided (recorded): I-CONCESSION | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:3.2 (VOL-V p2; text layer) | I-CONCESSION
VOL-V-12.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-15) | VOL-V:12.1 | contract; post_award; programme; pcod | Achieve PCOD within 36 months of the Notice to Proceed (the Scheduled PCOD) | The Project Company shall achieve PCOD within thirty-six (36) months of the Notice to Proceed (the Scheduled PCOD). | The Project Company shall achieve PCOD within thirty-six (36) months of the Notice to Proceed (the Scheduled PCOD). | shall achieve PCOD within thirty-six (36) months of the Notice to Proceed (the Scheduled PCOD) | VOL-V 12.1 p2 | VOL-V 12.1 p2 | contractual_post_award | Technical | Technical lead | Post-award (proposed requirement): to be obtained at PCOD, the Independent Engineer's certification that the Facility has satisfied Volume II Clause 7.2 (which fixes PCOD under VOL-V 1.5), dated within 36 months of the Notice to Proceed, with the Notice to Proceed itself kept to fix the Scheduled PCOD. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  | reading re-made at ADD-03: Re-read at ADD-03. ADD-03 Q15 asks 'Following the capacity increase, will the Authority extend the construction period in Volume V Clause 12.1?' The Authority answers 'No. The period of thirty-six (36) months is unchanged.' (op ADD-03/Q15, confirms, PROPOSED). The clause text is unchanged. The programme in the Technical Proposal must now reach PCOD within the same 36 months for the 150,000 m³/day capacity of VOL-II 2.1 as amended by ADD-03/4.1(a). PCOD also requires the VOL-II 7.2 reliability run at 90% of nominal capacity. Delay liquidated damages, their cap (VOL-V 18.4) and the date rule (Notice to Proceed, not a pack event) are unchanged. What the answer means for programme risk and pricing is for the Technical and Commercial leads. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed]. by ADD-03/Q15 [ADD-03; proposed; annotates VOL-V:12.1 (confirms)] <- ADD-03:Q15 (ADD-03 p2) | VOL-V 12.1 p2 | VOL-V 12.1 p2 | VOL-V 12.1 p2 | VOL-V 12.1 p2 | contractual remedy (post-award): "the Project Company shall pay to the Authority delay liquidated damages at the rate of SAR 180,000 for each day of delay" | VOL-V 18.1 p2 | VOL-V-SCHEDULED-PCOD: None (unknown_anchor) | high: verbatim; the Notice to Proceed is not a pack event, so the Scheduled PCOD cannot be dated | Delay liquidated damages are the Authority's sole financial remedy for late completion, without prejudice to termination (18.2). Cap: their aggregate 'shall not exceed ten per cent (10%) of the Estimated Project Cost' (VOL-V 18.4, p2). PCOD: certified by the Independent Engineer against VOL-II 7.2 (VOL-V 1.5). The date rule records 36 months as 3 years (date rules have no month unit). | unchanged since BASE; value as read: 'shall achieve PCOD within thirty-six (36) months of the Notice to Proceed (the Scheduled PCOD)' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:12.1 (VOL-V p2; text layer); ADD-03/Q15 [ADD-03; proposed; annotates VOL-V:12.1 (confirms)] <- ADD-03:Q15 (ADD-03 p2)
VOL-V-18.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:18.3 | contract; post_award; programme; pcod; termination | Achieve PCOD within 365 days after the Scheduled PCOD, failing which the Authority may terminate under Clause 39.2 | If PCOD has not been achieved within three hundred and sixty-five (365) days after the Scheduled PCOD, the Authority may terminate under Clause 39.2. | If PCOD has not been achieved within three hundred and sixty-five (365) days after the Scheduled PCOD, the Authority may terminate under Clause 39.2. | If PCOD has not been achieved within three hundred and sixty-five (365) days after the Scheduled PCOD | VOL-V 18.3 p2 | VOL-V 18.3 p2 | contractual_post_award | Legal | Legal counsel | Post-award (proposed requirement): to be obtained, the Independent Engineer's PCOD certification (VOL-V 1.5) dated within 365 days after the Scheduled PCOD, the same record as row VOL-V-12.1-01, showing that the Authority's termination right under Clause 39.2 has not arisen. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 18.3 p2 | VOL-V 18.3 p2 | VOL-V 18.3 p2 | VOL-V 18.3 p2 | contractual remedy (post-award): "the Authority may terminate under Clause 39.2" | VOL-V 18.3 p2 | VOL-V-PCOD-LONG-STOP: None (unknown_anchor) | high: verbatim; the Scheduled PCOD depends on the Notice to Proceed, not a pack event | Restated as an Authority termination right in 39.2. | unchanged since BASE; value as read: 'If PCOD has not been achieved within three hundred and sixty-five (365) days after the Scheduled PCOD' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:18.3 (VOL-V p2; text layer)
VOL-V-12.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:12.2 | contract; post_award; epc | Have the EPC Contractor build on a fixed price, lump sum, date certain, turnkey basis with single point responsibility | The Project Company shall procure that the EPC Contractor performs the construction works on a fixed price, lump sum, date certain, turnkey basis with single point responsibility. | The Project Company shall procure that the EPC Contractor performs the construction works on a fixed price, lump sum, date certain, turnkey basis with single point responsibility. | shall procure that the EPC Contractor performs the construction works on a fixed price, lump sum, date certain, turnkey basis with single point responsibility | VOL-V 12.2 p2 | VOL-V 12.2 p2 | contractual_post_award | Commercial | Commercial lead | Post-award (proposed requirement): to be produced, the executed EPC Contract, showing that the construction works are let on a fixed price, lump sum, date certain, turnkey basis with single point responsibility (VOL-V 12.2). | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 12.2 p2 | VOL-V 12.2 p2 | VOL-V 12.2 p2 | VOL-V 12.2 p2 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'shall procure that the EPC Contractor performs the construction works on a fixed price, lump sum, date certain, turnkey…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:12.2 (VOL-V p2; text layer)
VOL-V-12.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:12.3 | contract; post_award; independent_engineer; cost | Bear half of the Independent Engineer's reasonable costs (the Authority appoints the Independent Engineer) | The Authority shall appoint an Independent Engineer whose reasonable costs shall be borne equally by the parties. | The Authority shall appoint an Independent Engineer whose reasonable costs shall be borne equally by the parties. | whose reasonable costs shall be borne equally by the parties | VOL-V 12.3 p2 | VOL-V 12.3 p2 | contractual_post_award | Commercial | Commercial lead | Post-award (proposed requirement): to be produced for each period in which Independent Engineer costs are incurred, a record of those reasonable costs and of payment of the Project Company's equal share (VOL-V 12.3); the extract does not say how the costs are invoiced or shared between the parties. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 12.3 p2 | VOL-V 12.3 p2 | VOL-V 12.3 p2 | VOL-V 12.3 p2 | none stated in the documents |  |  | high: verbatim text-layer clause | The appointment itself is an Authority duty. | unchanged since BASE; value as read: 'whose reasonable costs shall be borne equally by the parties' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:12.3 (VOL-V p2; text layer)
VOL-V-12.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:12.4 | contract; post_award; reporting | Submit monthly progress reports | The Project Company shall submit monthly progress reports and shall permit the Authority access to the site at all reasonable times. | The Project Company shall submit monthly progress reports and shall permit the Authority access to the site at all reasonable times. | shall submit monthly progress reports | VOL-V 12.4 p2 | VOL-V 12.4 p2 | contractual_post_award | Technical | Technical lead | Post-award (proposed requirement): to be produced each month, the monthly progress report that VOL-V 12.4 requires, with a record of the date it was submitted; the extract does not state the report's content, its recipient, or when reporting starts and ends. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 12.4 p2 | VOL-V 12.4 p2 | VOL-V 12.4 p2 | VOL-V 12.4 p2 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'shall submit monthly progress reports' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:12.4 (VOL-V p2; text layer)
VOL-V-12.4-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:12.4 | contract; post_award; site_access | Permit the Authority access to the site at all reasonable times | The Project Company shall submit monthly progress reports and shall permit the Authority access to the site at all reasonable times. | The Project Company shall submit monthly progress reports and shall permit the Authority access to the site at all reasonable times. | shall permit the Authority access to the site at all reasonable times | VOL-V 12.4 p2 | VOL-V 12.4 p2 | contractual_post_award | Technical | Technical lead | Post-award (proposed requirement): to be kept, a site access log recording each Authority request for access and each visit, with the time and the access given, to show that access was permitted at all reasonable times (VOL-V 12.4); the clause itself prescribes no record. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 12.4 p2 | VOL-V 12.4 p2 | VOL-V 12.4 p2 | VOL-V 12.4 p2 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'shall permit the Authority access to the site at all reasonable times' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:12.4 (VOL-V p2; text layer)
VOL-V-24.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:24.1 | contract; post_award; finance; accounts | Open and keep the project accounts the Financing Documents require, with an account bank acceptable to the Senior Lenders | The Project Company shall open and maintain the project accounts required by the Financing Documents with an account bank acceptable to the Senior Lenders. | The Project Company shall open and maintain the project accounts required by the Financing Documents with an account bank acceptable to the Senior Lenders. | shall open and maintain the project accounts required by the Financing Documents with an account bank acceptable to the Senior Lenders | VOL-V 24.1 p2 | VOL-V 24.1 p2 | contractual_post_award | Finance | Financial modeller | Post-award (proposed requirement): to be produced when the Financing Documents require the project accounts, the account bank's confirmation that each required project account is open and the Senior Lenders' acceptance of the account bank, with continued maintenance shown by the quarterly statements under VOL-V 24.4 (row VOL-V-24.4-01). | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 24.1 p2 | VOL-V 24.1 p2 | VOL-V 24.1 p2 | VOL-V 24.1 p2 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'shall open and maintain the project accounts required by the Financing Documents with an account bank acceptable to the…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:24.1 (VOL-V p2; text layer)
VOL-V-24.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:24.2 | contract; post_award; finance; reserves | Establish, maintain and fund the reserve accounts the Financing Documents require | The Project Company shall establish and maintain such reserve accounts, and shall fund them to such levels and at such times, as are required under the Financing Documents. The Authority takes no position on the sizing of any reserve account. | The Project Company shall establish and maintain such reserve accounts, and shall fund them to such levels and at such times, as are required under the Financing Documents. The Authority takes no position on the sizing of any reserve account. | shall establish and maintain such reserve accounts, and shall fund them to such levels and at such times, as are required under the Financing Documents | VOL-V 24.2 p3 | VOL-V 24.2 p3 | contractual_post_award | Finance | Financial modeller | Post-award (proposed requirement): to be produced, account statements showing each reserve account required by the Financing Documents established and funded to the level and at the time they require, cross-referenced to the Financing Documents' requirement (VOL-V 24.2). | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 24.2 p3 | VOL-V 24.2 p3 | VOL-V 24.2 p3 | VOL-V 24.2 p3 | none stated in the documents |  |  | high: verbatim text-layer clause | 'The Authority takes no position on the sizing of any reserve account.' | unchanged since BASE; value as read: 'shall establish and maintain such reserve accounts, and shall fund them to such levels and at such times, as are requir…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:24.2 (VOL-V p3; text layer)
VOL-V-24.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:24.3 | contract; post_award; finance; distributions | No shareholder distribution unless the Financing Documents' conditions are met and no Unavailability Event is continuing | The Project Company shall not make a distribution to its shareholders unless the conditions to distribution in the Financing Documents are satisfied and no Unavailability Event is continuing. | The Project Company shall not make a distribution to its shareholders unless the conditions to distribution in the Financing Documents are satisfied and no Unavailability Event is continuing. | shall not make a distribution to its shareholders unless the conditions to distribution in the Financing Documents are satisfied and no Unavailability Event is continuing | VOL-V 24.3 p3 | VOL-V 24.3 p3 | contractual_post_award | Finance | Financial modeller | Post-award (proposed requirement): to be produced before each shareholder distribution, a record showing that the conditions to distribution in the Financing Documents are satisfied and that no Unavailability Event is continuing at the time (VOL-V 24.3). | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 24.3 p3 | VOL-V 24.3 p3 | VOL-V 24.3 p3 | VOL-V 24.3 p3 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'shall not make a distribution to its shareholders unless the conditions to distribution in the Financing Documents are …' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:24.3 (VOL-V p3; text layer)
VOL-V-24.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:24.4 | contract; post_award; finance; reporting | Give the Authority quarterly statements of each project account | The Project Company shall provide the Authority with quarterly statements of each project account. | The Project Company shall provide the Authority with quarterly statements of each project account. | shall provide the Authority with quarterly statements of each project account | VOL-V 24.4 p3 | VOL-V 24.4 p3 | contractual_post_award | Finance | Financial modeller | Post-award (proposed requirement): to be produced each quarter, a statement of each project account provided to the Authority, as VOL-V 24.4 requires, with a record of when it was provided. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 24.4 p3 | VOL-V 24.4 p3 | VOL-V 24.4 p3 | VOL-V 24.4 p3 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'shall provide the Authority with quarterly statements of each project account' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:24.4 (VOL-V p3; text layer)
VOL-V-29.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-15) | VOL-V:29.3 | contract; post_award; payment; ramp_up; image | Ramp-Up Period (12 months after PCOD): payment at 90%; no availability deduction for Table 2-4 parameters assessed on a rolling average (a payment exception only: not an exemption from technical compliance or commissioning requirements) | [VOL-V 29.3 p3] During the first twelve (12) months after PCOD (the Ramp-Up Period) the Availability Payment shall be paid at ninety per cent (90%) of the full rate, and no availability deduction shall apply to a parameter listed in Table 2-4 as assessed on a rolling average basis. [VOL-II T2-4/BOD5 p3] Parameter: Biochemical Oxygen Demand (BOD5) ¦ Unit: mg/l ¦ Limit: 10 ¦ Basis of assessment: 30-day rolling average [VOL-II T2-4/COD p3] Parameter: Chemical Oxygen Demand (COD) ¦ Unit: mg/l ¦ Limit: 50 ¦ Basis of assessment: 30-day rolling average [VOL-II T2-4/TSS p3] Parameter: Total Suspended Solids (TSS) ¦ Unit: mg/l ¦ Limit: 10 ¦ Basis of assessment: 30-day rolling average [VOL-II T2-4/TN p3] Parameter: Total Nitrogen (TN) ¦ Unit: mg/l ¦ Limit: 5 ¦ Basis of assessment: 30-day rolling average [VOL-II T2-4/TP p3] Parameter: Total Phosphorus (TP) ¦ Unit: mg/l ¦ Limit: 1 ¦ Basis of assessment: 30-day rolling average | [VOL-V 29.3 p3] During the first twelve (12) months after PCOD (the Ramp-Up Period) the Availability Payment shall be paid at ninety per cent (90%) of the full rate, and no availability deduction shall apply to a parameter listed in Table 2-4 as assessed on a rolling average basis. [VOL-II T2-4/BOD5 p3] Parameter: Biochemical Oxygen Demand (BOD5) ¦ Unit: mg/l ¦ Limit: 10 ¦ Basis of assessment: 30-day rolling average [VOL-II T2-4/COD p3] Parameter: Chemical Oxygen Demand (COD) ¦ Unit: mg/l ¦ Limit: 50 ¦ Basis of assessment: 30-day rolling average [VOL-II T2-4/TSS p3] Parameter: Total Suspended Solids (TSS) ¦ Unit: mg/l ¦ Limit: 10 ¦ Basis of assessment: 30-day rolling average [VOL-II T2-4/TN p3] Parameter: Total Nitrogen (TN) ¦ Unit: mg/l ¦ Limit: 3 ¦ Basis of assessment: 30-day rolling average [VOL-II T2-4/TP p3] Parameter: Total Phosphorus (TP) ¦ Unit: mg/l ¦ Limit: 1 ¦ Basis of assessment: 30-day rolling average | During the first twelve (12) months after PCOD (the Ramp-Up Period) the Availability Payment shall be paid at ninety per cent (90%) of the full rate | VOL-V 29.3 p3 | VOL-V 29.3 p3; VOL-II T2-4/BOD5 p3; VOL-II T2-4/COD p3; VOL-II T2-4/TSS p3; VOL-II T2-4/TN p3 <- ADD-02/5.1; VOL-II T2-4/TP p3 | contractual_post_award | Commercial | Commercial lead | Not applicable: the Ramp-Up Period terms (payment at 90% of the full rate and no availability deduction for Table 2-4 parameters assessed on a rolling average) are a payment term and a limit on the Authority's deductions, not an act the Project Company evidences, and they do not exempt the Facility from Table 2-4 compliance or the commissioning requirements, which are evidenced under their own rows. | ACTIVE | ACTIVE | ACTIVE | ACTIVE | reading re-made at ADD-01: ADD-01 Q6: offtake volume is not guaranteed; the payment mechanism is availability based and does not depend on volume delivered. No change to this row. by ADD-01/Q6 [ADD-01; proposed; annotates VOL-V:29.3 (interprets)] <- ADD-01:Q6 (ADD-01 p2) | reading re-made at ADD-02: ADD-02 5.1 amends the TN limit to 3 mg/l 'assessed on the same basis' (30-day rolling average as read) and states 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED), so the rolling-average parameters as read stay BOD5, COD, TSS, TN and TP; the payment terms of this clause are unchanged. by ADD-02/5.1 [ADD-02; proposed] <- ADD-02:5.1 (ADD-02 p1); ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/BOD5 (confirms)] <- ADD-02:5.1 (ADD-02 p1) | reading re-made at ADD-03: Re-read at ADD-03. ADD-03 7.1 (op ADD-03/7.1, PROPOSED) amends the TP limit to 0.5 mg/l 'assessed on the same basis'. The TP Basis of assessment stays '30-day rolling average', so the rolling-average parameters as read stay BOD5, COD, TSS, TN and TP. The payment terms of this clause are not amended by ADD-03. The exception covers availability deductions only: the effluent must still comply 'at all times' with Table 2-4, now including TP at 0.5 mg/l (VOL-II 2.4), and the commissioning requirements still apply. The basis column remains an image reading (I-READING-T24). [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed]. by ADD-03/7.1 [ADD-03; proposed] <- ADD-03:7.1 (ADD-03 p2) | VOL-V 29.3 p3 | VOL-V 29.3 p3 | VOL-V 29.3 p3 | VOL-V 29.3 p3 | none stated in the documents |  | VOL-V-RAMP-UP-END: None (unknown_anchor) | medium: verbatim clause; the parameters exempt from Ramp-Up deductions come from an image reading (transcription confirmed by the owner, 3 Oct 2026); PCOD is not a pack event | ADD-02 5.1 amends the TN limit to 3 mg/l 'assessed on the same basis' (30-day rolling average as read) and states 'All other parameters in Table 2-4 are unchanged.' (ADD-02 5.1, p1; op ADD-02/5.1/unchanged, confirms, PROPOSED), so the rolling-average parameters as read stay BOD5, COD, TSS, TN and TP; the payment terms of this clause are unchanged. Printed table title: 'Table 2-4 Minimum Effluent Quality Parameters at the Point of Discharge'. | own words unchanged at ADD-02, but what it depends on changed (cited units; see A2); re-read by ADD-01/Q6 (interprets; accepted by a person; not counted as a confirmation), ADD-02/5.1/unchanged (confirms; accepted by a person; not counted as a confirmation); value as read: 'During the first twelve (12) months after PCOD (the Ramp-Up Period) the Availability Payment shall be paid at ninety pe…' | decided (recorded): I-READING-T24, I-VOL-II-AT-ALL-TIMES, I-VOL-II-COMPLIANCE-POINT, I-PERMIT | row: ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/Q6: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/5.1/unchanged: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; image transcription approved by the owner (the transcription and its displayed translation only; not an approval of the interpretation) | approved | ASSUMED APPROVED FOR DEMO (2026-10-15); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:29.3 (VOL-V p3; text layer); VOL-II:T2-4/BOD5 (VOL-II p3; image reading); VOL-II:T2-4/COD (VOL-II p3; image reading); VOL-II:T2-4/TSS (VOL-II p3; image reading); VOL-II:T2-4/TN (VOL-II p3; image reading); VOL-II:T2-4/TP (VOL-II p3; image reading); ADD-01/Q6 [ADD-01; proposed; annotates VOL-V:29.3 (interprets)] <- ADD-01:Q6 (ADD-01 p2); ADD-02/5.1 [ADD-02; proposed] <- ADD-02:5.1 (ADD-02 p1); ADD-02/5.1/unchanged [ADD-02; proposed; annotates VOL-II:T2-4/BOD5 (confirms)] <- ADD-02:5.1 (ADD-02 p1); ADD-03/7.1 [ADD-03; proposed] <- ADD-03:7.1 (ADD-03 p2) | I-READING-T24; I-VOL-II-AT-ALL-TIMES (via REL-T24-RAMP-UP-DEDUCTIONS (confirmed)); I-VOL-II-COMPLIANCE-POINT (via REL-T24-RAMP-UP-DEDUCTIONS (confirmed)); I-PERMIT (via REL-MISSING-ENVIRONMENTAL-PERMIT > REL-T24-RAMP-UP-DEDUCTIONS (confirmed)) | <- REL-T24-RAMP-UP-DEDUCTIONS [confirmed limit_applies] from VOL-II:T2-4; issue I-VOL-II-T24-TENSIONS not carried by REL-T24-RAMP-UP-DEDUCTIONS: the relationship's scope is the members of VOL-II:T2-4 whose words carry 'rolling average' (its evidence: 'no availability deduction shall apply to a parameter listed in Table 2-4 as assessed on a rolling average basis'): BOD5, COD, TN, TP, TSS; the issue's subject is ResidualChlorine, pH (scope PROPOSED, not reviewed; the owner may keep the issue on the row); REACHED at ADD-02 (confirmed dependency): from VOL-II:T2-4 via REL-T24-RAMP-UP-DEDUCTIONS
VOL-V-29.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:29.4 | contract; post_award; payment; invoicing | Submit invoices within 10 Working Days of each month end (the Authority pays within 30 days of receipt) | Invoices shall be submitted within ten (10) Working Days of each month end and shall be paid within thirty (30) days of receipt. | Invoices shall be submitted within ten (10) Working Days of each month end and shall be paid within thirty (30) days of receipt. | Invoices shall be submitted within ten (10) Working Days of each month end | VOL-V 29.4 p3 | VOL-V 29.4 p3 | contractual_post_award | Commercial | Commercial lead | Post-award (proposed requirement): to be produced each month from PCOD, an invoice submitted within ten Working Days of the month end, as VOL-V 29.4 requires, with proof of the submission and receipt dates (receipt starts the Authority's 30-day payment period). | ACTIVE | ACTIVE | ACTIVE | ACTIVE | reading re-made at ADD-01: ADD-01 Q6 (payment availability based, volume not guaranteed) reviewed for this row: no change. by ADD-01/Q6 [ADD-01; proposed; annotates VOL-V:29.4 (interprets)] <- ADD-01:Q6 (ADD-01 p2) |  |  | VOL-V 29.4 p3 | VOL-V 29.4 p3 | VOL-V 29.4 p3 | VOL-V 29.4 p3 | none stated in the documents |  | VOL-V-INVOICE-DUE: None (unknown_anchor) | high: verbatim text-layer clause | ADD-01 Q6 (payment availability based, volume not guaranteed) reviewed for this row: no change. | unchanged since BASE; re-read by ADD-01/Q6 (interprets; accepted by a person; not counted as a confirmation); value as read: 'Invoices shall be submitted within ten (10) Working Days of each month end' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-01/Q6: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:29.4 (VOL-V p3; text layer); ADD-01/Q6 [ADD-01; proposed; annotates VOL-V:29.4 (interprets)] <- ADD-01:Q6 (ADD-01 p2)
VOL-V-31.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:31.1 | contract; post_award; availability; deductions | Treat the flow delivered to the Facility (failure is an Unavailability Event under 31.1(a)) | An Unavailability Event occurs where (a) the Facility is unable to treat the flow delivered to it, (b) the treated effluent fails any parameter in Volume II Table 2-4, or (c) the Facility fails to deliver treated effluent to the delivery point at the required residual head. | An Unavailability Event occurs where (a) the Facility is unable to treat the flow delivered to it, (b) the treated effluent fails any parameter in Volume II Table 2-4, or (c) the Facility fails to deliver treated effluent to the delivery point at the required residual head. | (a) the Facility is unable to treat the flow delivered to it | VOL-V 31.1 p3 | VOL-V 31.1 p3 | contractual_post_award | Operations | O&M lead | Post-award (proposed requirement): to be kept continuously from PCOD, metered records of the flow delivered to the Facility and the flow treated, with a timestamped log of any period in which delivered flow was not treated, so that any Unavailability Event under VOL-V 31.1(a) can be established; the extract prescribes no monitoring or reporting format. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q12 (are the deductions capped?) refers Bidders to the wording of 31.2: deductions are not subject to any cap. by ADD-02/Q12 [ADD-02; proposed; annotates VOL-V:31.2 (confirms)] <- ADD-02:Q12 (ADD-02 p2) |  | VOL-V 31.1 p3 | VOL-V 31.1 p3 | VOL-V 31.1 p3 | VOL-V 31.1 p3 | contractual remedy (post-award): "the Authority shall deduct from the Availability Payment the amounts calculated under Schedule 7" | VOL-V 31.2 p3 |  | medium: verbatim; the deduction amounts are in Schedule 7, not supplied; how 'the flow delivered' relates to the design flows is open | ADD-02 Q12 (are the deductions capped?) refers Bidders to the wording of 31.2: deductions are not subject to any cap. | unchanged since BASE; value as read: '(a) the Facility is unable to treat the flow delivered to it' | decided (recorded): I-VOL-V-MISSING, I-FLOWS | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:31.1 (VOL-V p3; text layer); ADD-02/Q12 [ADD-02; proposed; annotates VOL-V:31.2 (confirms)] <- ADD-02:Q12 (ADD-02 p2) | I-VOL-V-MISSING; I-FLOWS | NOT SUPPLIED: Volume V Schedule 7 (deductions) (REL-MISSING-SCHEDULE-7-DEDUCTIONS, link confirmed): cannot be established: the amount of the deduction for each Unavailability Event under 31.1(a), (b) and (c), so the price risk of each
VOL-V-31.1-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:31.1 | contract; post_award; availability; deductions; effluent | Treated effluent to meet every parameter in VOL-II Table 2-4 (failure is an Unavailability Event under 31.1(b)) | An Unavailability Event occurs where (a) the Facility is unable to treat the flow delivered to it, (b) the treated effluent fails any parameter in Volume II Table 2-4, or (c) the Facility fails to deliver treated effluent to the delivery point at the required residual head. | An Unavailability Event occurs where (a) the Facility is unable to treat the flow delivered to it, (b) the treated effluent fails any parameter in Volume II Table 2-4, or (c) the Facility fails to deliver treated effluent to the delivery point at the required residual head. | (b) the treated effluent fails any parameter in Volume II Table 2-4 | VOL-V 31.1 p3 | VOL-V 31.1 p3 | contractual_post_award | Operations | O&M lead | Post-award (proposed requirement): to be kept continuously from PCOD, treated-effluent sampling and analysis records for every Table 2-4 parameter, each on its stated basis of assessment and against the limits as amended (TN 3 mg/l, ADD-02 5.1), so that any Unavailability Event under VOL-V 31.1(b) can be established; these records would not show compliance with the Environmental Permit, which is not supplied. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q12 refers Bidders to the wording of 31.2: deductions are not subject to any cap. ADD-02 5.1 tightens the TN limit to 3 mg/l (row VOL-II-T2-4-TN), which this event applies to. by ADD-02/Q12 [ADD-02; proposed; annotates VOL-V:31.2 (confirms)] <- ADD-02:Q12 (ADD-02 p2) |  | VOL-V 31.1 p3 | VOL-V 31.1 p3 | VOL-V 31.1 p3 | VOL-V 31.1 p3 | contractual remedy (post-award): "the Authority shall deduct from the Availability Payment the amounts calculated under Schedule 7" | VOL-V 31.2 p3 |  | medium: verbatim; Table 2-4 is an image reading (transcription confirmed by the owner, 3 Oct 2026), the Permit that prevails over it in VOL-II is not supplied, and Schedule 7 is not supplied | ADD-02 Q12 refers Bidders to the wording of 31.2: deductions are not subject to any cap. ADD-02 5.1 tightens the TN limit to 3 mg/l (row VOL-II-T2-4-TN), which this event applies to. | own words unchanged at ADD-02, but what it depends on changed (dependency; see A2); value as read: '(b) the treated effluent fails any parameter in Volume II Table 2-4' | decided (recorded): I-READING-T24, I-PERMIT, I-VOL-V-MISSING, I-VOL-II-T24-TENSIONS, I-VOL-II-AT-ALL-TIMES, I-VOL-II-COMPLIANCE-POINT | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:31.1 (VOL-V p3; text layer); ADD-02/Q12 [ADD-02; proposed; annotates VOL-V:31.2 (confirms)] <- ADD-02:Q12 (ADD-02 p2) | I-READING-T24; I-PERMIT; I-VOL-V-MISSING; I-VOL-II-T24-TENSIONS (via REL-T24-UNAVAILABILITY (confirmed)); I-VOL-II-AT-ALL-TIMES (via REL-T24-UNAVAILABILITY (confirmed)); I-VOL-II-COMPLIANCE-POINT (via REL-T24-UNAVAILABILITY (confirmed)) | <- REL-T24-UNAVAILABILITY [confirmed limit_applies] from VOL-II:T2-4; NOT SUPPLIED: Volume V Schedule 7 (deductions) (REL-MISSING-SCHEDULE-7-DEDUCTIONS, link confirmed): cannot be established: the amount of the deduction for each Unavailability Event under 31.1(a), (b) and (c), so the price risk of each; REACHED at ADD-02 (confirmed dependency): from VOL-II:T2-4 via REL-T24-UNAVAILABILITY
VOL-V-31.1-03 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:31.1 | contract; post_award; availability; deductions; transmission_main | Deliver treated effluent to the delivery point at the required residual head (failure is an Unavailability Event under 31.1(c)) | An Unavailability Event occurs where (a) the Facility is unable to treat the flow delivered to it, (b) the treated effluent fails any parameter in Volume II Table 2-4, or (c) the Facility fails to deliver treated effluent to the delivery point at the required residual head. | An Unavailability Event occurs where (a) the Facility is unable to treat the flow delivered to it, (b) the treated effluent fails any parameter in Volume II Table 2-4, or (c) the Facility fails to deliver treated effluent to the delivery point at the required residual head. | (c) the Facility fails to deliver treated effluent to the delivery point at the required residual head | VOL-V 31.1 p3 | VOL-V 31.1 p3 | contractual_post_award | Operations | O&M lead | Post-award (proposed requirement): to be kept continuously from PCOD, residual head records at the delivery point, with a timestamped log of any period below the required residual head (VOL-II 5.2 states a minimum of 15 m at the delivery point), so that any Unavailability Event under VOL-V 31.1(c) can be established; the delivery point is shown only on Drawing 03-C-114, which is not supplied. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q12 refers Bidders to the wording of 31.2: deductions are not subject to any cap. by ADD-02/Q12 [ADD-02; proposed; annotates VOL-V:31.2 (confirms)] <- ADD-02:Q12 (ADD-02 p2) |  | VOL-V 31.1 p3 | VOL-V 31.1 p3 | VOL-V 31.1 p3 | VOL-V 31.1 p3 | contractual remedy (post-award): "the Authority shall deduct from the Availability Payment the amounts calculated under Schedule 7" | VOL-V 31.2 p3 |  | medium: verbatim; the delivery point (Drawing 03-C-114) and the deduction amounts (Schedule 7) are not supplied | ADD-02 Q12 refers Bidders to the wording of 31.2: deductions are not subject to any cap. | unchanged since BASE; value as read: '(c) the Facility fails to deliver treated effluent to the delivery point at the required residual head' | decided (recorded): I-VOL-III, I-VOL-V-MISSING | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:31.1 (VOL-V p3; text layer); ADD-02/Q12 [ADD-02; proposed; annotates VOL-V:31.2 (confirms)] <- ADD-02:Q12 (ADD-02 p2) | I-VOL-III; I-VOL-V-MISSING | NOT SUPPLIED: Volume V Schedule 7 (deductions) (REL-MISSING-SCHEDULE-7-DEDUCTIONS, link confirmed): cannot be established: the amount of the deduction for each Unavailability Event under 31.1(a), (b) and (c), so the price risk of each
VOL-V-31.3-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:31.3 | contract; post_award; availability; cure_period | Cure period of 24 hours for an Unavailability Event under VOL-V 31.1(a) | A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a) and of seventy-two (72) hours to an event under Clause 31.1(c). No cure period applies to an event under Clause 31.1(b). | A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a) and of seventy-two (72) hours to an event under Clause 31.1(c). No cure period applies to an event under Clause 31.1(b). | A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a) | VOL-V 31.3 p3 | VOL-V 31.3 p3 | contractual_post_award | Legal | Legal counsel | Unresolved: the record that would show a VOL-V 31.1(a) event was cured within the 24-hour cure period cannot be specified from the extract, which states the length of the period but not when it starts or what a cure changes, and the deductions are calculated under Schedule 7 (VOL-V 31.2), which is not supplied. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 31.3 p3 | VOL-V 31.3 p3 | VOL-V 31.3 p3 | VOL-V 31.3 p3 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a)' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:31.3 (VOL-V p3; text layer)
VOL-V-31.3-03 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:31.3 | contract; post_award; availability; cure_period; effluent | No cure period for an Unavailability Event under VOL-V 31.1(b) (a Table 2-4 failure) | A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a) and of seventy-two (72) hours to an event under Clause 31.1(c). No cure period applies to an event under Clause 31.1(b). | A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a) and of seventy-two (72) hours to an event under Clause 31.1(c). No cure period applies to an event under Clause 31.1(b). | No cure period applies to an event under Clause 31.1(b). | VOL-V 31.3 p3 | VOL-V 31.3 p3 | contractual_post_award | Legal | Legal counsel | Not applicable: VOL-V 31.3 states that no cure period applies to a 31.1(b) event (a Table 2-4 failure), which gives the Project Company no period to use and requires no act of it; effluent compliance itself is to be evidenced under row VOL-V-31.1-02. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 31.3 p3 | VOL-V 31.3 p3 | VOL-V 31.3 p3 | VOL-V 31.3 p3 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'No cure period applies to an event under Clause 31.1(b).' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:31.3 (VOL-V p3; text layer)
VOL-V-31.4-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:31.4 | contract; post_award; availability; persistent_breach; termination | Persistent breach (3+ Unavailability Events in a rolling 90 days): remediation plan on request; a second occurrence allows termination | Persistent breach, being three (3) or more Unavailability Events in any rolling ninety (90) day period, entitles the Authority to require a remediation plan and, on a second occurrence, to terminate under Clause 39.3. | Persistent breach, being three (3) or more Unavailability Events in any rolling ninety (90) day period, entitles the Authority to require a remediation plan and, on a second occurrence, to terminate under Clause 39.3. | Persistent breach, being three (3) or more Unavailability Events in any rolling ninety (90) day period, entitles the Authority to require a remediation plan | VOL-V 31.4 p3 | VOL-V 31.4 p3 | contractual_post_award | Operations | O&M lead | Post-award (proposed requirement): to be kept continuously from PCOD, a rolling 90-day count of Unavailability Events, and to be produced when the Authority requires one after a persistent breach, a remediation plan (VOL-V 31.4); the extract states no content or deadline for the plan. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 31.4 p3 | VOL-V 31.4 p3 | VOL-V 31.4 p3 | VOL-V 31.4 p3 | contractual remedy (post-award): "on a second occurrence, to terminate under Clause 39.3" | VOL-V 31.4 p3 |  | medium: verbatim; the trigger for termination ('a second occurrence') is not defined | Restated as an Authority termination right in 39.3. What 'a second occurrence' refers to is not stated. | unchanged since BASE; value as read: 'Persistent breach, being three (3) or more Unavailability Events in any rolling ninety (90) day period, entitles the Au…' | decided (recorded): I-VOL-V-PERSISTENT-BREACH, I-VOL-V-MISSING | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:31.4 (VOL-V p3; text layer) | I-VOL-V-PERSISTENT-BREACH; I-VOL-V-MISSING (via REL-MISSING-SCHEDULE-11-PERSISTENT-BREACH (proposed)) | NOT SUPPLIED: Volume V Schedule 11 (Project Company Events of Default) (REL-MISSING-SCHEDULE-11-PERSISTENT-BREACH, link proposed): cannot be established: whether persistent breach (three or more Unavailability Events in a rolling 90 days) is also an Event of Default listed in Schedule 11, giving a termination right under 39.1 independent of 31.4 and 39.3; so an amendment or deletion of 31.4 or 39.3 cannot be concluded to remove that exposure
VOL-V-34.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:34.3 | contract; post_award; relief_events; notice | Notify a Relief Event within 5 Working Days of becoming aware of it, or no relief is granted | The Project Company shall notify a Relief Event within five (5) Working Days of becoming aware of it, failing which no relief shall be granted. | The Project Company shall notify a Relief Event within five (5) Working Days of becoming aware of it, failing which no relief shall be granted. | shall notify a Relief Event within five (5) Working Days of becoming aware of it | VOL-V 34.3 p3 | VOL-V 34.3 p3 | contractual_post_award | Legal | Legal counsel | Post-award (proposed requirement): to be produced for each Relief Event, a written notification given within five Working Days of becoming aware of it, as VOL-V 34.3 requires, with a record of the date of awareness and proof of the date of notice; the extract prescribes no form of notice or recipient. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 34.3 p3 | VOL-V 34.3 p3 | VOL-V 34.3 p3 | VOL-V 34.3 p3 | contractual remedy (post-award): "failing which no relief shall be granted" | VOL-V 34.3 p3 | VOL-V-RELIEF-EVENT-NOTICE: None (unknown_anchor) | high: verbatim text-layer clause | A Relief Event gives an extension of time but no compensation (34.1). Forward Working Day counting is not defined in the pack. | unchanged since BASE; value as read: 'shall notify a Relief Event within five (5) Working Days of becoming aware of it' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:34.3 (VOL-V p3; text layer)
VOL-V-36.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:36.2 | contract; post_award; change_in_law; threshold | General Change in Law: compensation only for the capital expenditure it requires, and only above the stated aggregate threshold | A General Change in Law entitles the Project Company to compensation only in respect of capital expenditure required by that change and only to the extent that such expenditure exceeds SAR 5,000,000 in aggregate over the term. | A General Change in Law entitles the Project Company to compensation only in respect of capital expenditure required by that change and only to the extent that such expenditure exceeds SAR 2,500,000 in aggregate over the term. | SAR 2,500,000 | ADD-02 8.1 p3 (amending VOL-V 36.2) | VOL-V 36.2 p4 <- ADD-02/8.1 | contractual_post_award | Commercial | Commercial lead | Post-award (proposed requirement): to be kept over the term, a cumulative register of the capital expenditure required by each General Change in Law, showing when the aggregate exceeds SAR 2,500,000 (VOL-V 36.2 as amended by ADD-02 8.1), as support for any compensation claim; the extract states no claim procedure. | ACTIVE | ACTIVE | AMENDED (ADD-02/8.1) | ACTIVE (as amended by ADD-02/8.1) |  | status ACTIVE -> AMENDED (ADD-02/8.1). reading re-made at ADD-02: ADD-02 8.1 deletes 'SAR 5,000,000' and substitutes 'SAR 2,500,000'. by ADD-02/8.1 [ADD-02; proposed] <- ADD-02:8.1 (ADD-02 p3) | status AMENDED (ADD-02/8.1) -> ACTIVE (as amended by ADD-02/8.1) | VOL-V 36.2 p4 | VOL-V 36.2 p4 | ADD-02 8.1 p3 (amending VOL-V 36.2) | ADD-02 8.1 p3 (amending VOL-V 36.2) | none stated in the documents |  |  | high: verbatim at each stage | ADD-02 8.1 deletes 'SAR 5,000,000' and substitutes 'SAR 2,500,000'. | changed at ADD-02 by ADD-02/8.1 (the quoted value); value as read: 'SAR 2,500,000' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review.; ADD-02/8.1: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | ADD-02/8.1: accepted | VOL-V:36.2 (VOL-V p4; text layer); ADD-02/8.1 [ADD-02; proposed] <- ADD-02:8.1 (ADD-02 p3)
VOL-V-39.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:39.1 | contract; post_award; termination; events_of_default | Avoid the Project Company Events of Default listed in Schedule 11 (not supplied); the Authority may terminate for them | The Authority may terminate for a Project Company Event of Default, being the events listed in Schedule 11. | The Authority may terminate for a Project Company Event of Default, being the events listed in Schedule 11. | being the events listed in Schedule 11 | VOL-V 39.1 p4 | VOL-V 39.1 p4 | contractual_post_award | Legal | Legal counsel | Unresolved: the evidence of avoiding the Project Company Events of Default cannot be specified, because they are listed in Schedule 11, which is not supplied; the Senior Lenders' notice and cure period before termination is in the Direct Agreement, also not supplied. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 39.1 p4 | VOL-V 39.1 p4 | VOL-V 39.1 p4 | VOL-V 39.1 p4 | contractual remedy (post-award): "The Authority may terminate for a Project Company Event of Default" | VOL-V 39.1 p4 |  | low: the events of default themselves (Schedule 11) are not in the pack | Schedule 11 is not supplied. Before terminating under 39.1 the Authority must give the Senior Lenders the notice and cure period of the Direct Agreement (39.5; not supplied). Compensation on termination for Project Company default: 40.2. | unchanged since BASE; value as read: 'being the events listed in Schedule 11' | decided (recorded): I-VOL-V-MISSING | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:39.1 (VOL-V p4; text layer) | I-VOL-V-MISSING | NOT SUPPLIED: Volume V Schedule 11 (Project Company Events of Default) (REL-MISSING-SCHEDULE-11-DEFAULTS, link confirmed): cannot be established: which events are Project Company Events of Default, so how to avoid them and whether to reserve the position in Form 4-E
VOL-V-42.1-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:42.1 | contract; post_award; handback | On expiry, transfer the Facility in the condition required by VOL-II 8.5, free of encumbrance | The Project Company shall transfer the Facility to the Authority on expiry in the condition required by Volume II Clause 8.5, free of encumbrance and with a remaining design life of not less than five (5) years for all major assets. | The Project Company shall transfer the Facility to the Authority on expiry in the condition required by Volume II Clause 8.5, free of encumbrance and with a remaining design life of not less than five (5) years for all major assets. | shall transfer the Facility to the Authority on expiry in the condition required by Volume II Clause 8.5, free of encumbrance | VOL-V 42.1 p4 | VOL-V 42.1 p4 | contractual_post_award | Operations | O&M lead | Post-award (proposed requirement): to be produced before transfer on expiry, the handback condition survey report from the final two years of the concession and records of completion of the remedial works it identifies (VOL-II 8.5), with releases of any security or other encumbrance over the Facility (VOL-V 42.1). | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 42.1 p4 | VOL-V 42.1 p4 | VOL-V 42.1 p4 | VOL-V 42.1 p4 | none stated in the documents |  |  | high: verbatim; the expiry date depends on the term start (I-CONCESSION) | VOL-II 8.5: handback survey and remedial works (rows VOL-II-8.5-01, VOL-II-8.5-02). | unchanged since BASE; value as read: 'shall transfer the Facility to the Authority on expiry in the condition required by Volume II Clause 8.5, free of encum…' | decided (recorded): I-CONCESSION | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:42.1 (VOL-V p4; text layer) | I-CONCESSION
VOL-V-42.1-02 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:42.1 | contract; post_award; handback; design_life | At handback, at least 5 years of remaining design life for all major assets | The Project Company shall transfer the Facility to the Authority on expiry in the condition required by Volume II Clause 8.5, free of encumbrance and with a remaining design life of not less than five (5) years for all major assets. | The Project Company shall transfer the Facility to the Authority on expiry in the condition required by Volume II Clause 8.5, free of encumbrance and with a remaining design life of not less than five (5) years for all major assets. | with a remaining design life of not less than five (5) years for all major assets | VOL-V 42.1 p4 | VOL-V 42.1 p4 | contractual_post_award | Operations | O&M lead | Unresolved: the evidence of at least five years' remaining design life for all major assets at handback cannot be fully specified, because the extract does not define 'major assets' or say how, or by whom, remaining design life is assessed; a remaining-life assessment per major asset, drawn from the VOL-II 7.4 asset register, is the likely record once that is settled. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 42.1 p4 | VOL-V 42.1 p4 | VOL-V 42.1 p4 | VOL-V 42.1 p4 | none stated in the documents |  |  | medium: verbatim; 'major assets' is not defined | 'major assets' is not defined in the extract. | unchanged since BASE; value as read: 'with a remaining design life of not less than five (5) years for all major assets' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:42.1 (VOL-V p4; text layer)
VOL-V-42.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:42.2 | contract; post_award; handback; reserves | Fund a handback reserve from the start of year 20 of the term, in the amount the Independent Engineer certifies | A handback reserve shall be funded from the start of year twenty (20) of the term in an amount certified by the Independent Engineer. | A handback reserve shall be funded from the start of year twenty (20) of the term in an amount certified by the Independent Engineer. | A handback reserve shall be funded from the start of year twenty (20) of the term in an amount certified by the Independent Engineer. | VOL-V 42.2 p4 | VOL-V 42.2 p4 | contractual_post_award | Finance | Financial modeller | Post-award (proposed requirement): to be produced from the start of year 20 of the term, the Independent Engineer's certification of the handback reserve amount and account statements showing the reserve funded to that amount (VOL-V 42.2). | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  | reading re-made at ADD-02: ADD-02 Q7 (p2) was asked 'Which applies?' (VOL-I 12.1: from PCOD; VOL-V 3.1: from the Effective Date) and answers: 'The Authority notes the question. The order of precedence at Volume I Clause 3.2 applies. The Authority does not consider further amendment necessary at this stage.' It does not say which clause applies, and it amends neither, so when year 20 of the term starts is not settled: a decision for a person (Legal; I-CONCESSION, CQ-CONCESSION-TERM); no decision recorded. The date rule records the start of year 20 as 19 years after the term starts. by ADD-02/Q7 [ADD-02; proposed; cited by the reading made at ADD-02 (interprets)] <- ADD-02:Q7 (ADD-02 p2) |  | VOL-V 42.2 p4 | VOL-V 42.2 p4 | VOL-V 42.2 p4 | VOL-V 42.2 p4 | none stated in the documents |  | VOL-V-HANDBACK-RESERVE-START: None (unknown_anchor) | medium: verbatim; when year 20 starts depends on the term start: VOL-I 12.1 (from PCOD) or VOL-V 3.1 (from the Effective Date); ADD-02 Q7 answers 'The order of precedence at Volume I Clause 3.2 applies.' without saying which applies; which clause governs is a decision for a person (Legal, I-CONCESSION); no decision recorded | ADD-02 Q7 (p2) was asked 'Which applies?' (VOL-I 12.1: from PCOD; VOL-V 3.1: from the Effective Date) and answers: 'The Authority notes the question. The order of precedence at Volume I Clause 3.2 applies. The Authority does not consider further amendment necessary at this stage.' It does not say which clause applies, and it amends neither, so when year 20 of the term starts is not settled: a decision for a person (Legal; I-CONCESSION, CQ-CONCESSION-TERM); no decision recorded. The date rule records the start of year 20 as 19 years after the term starts. | unchanged since BASE; value as read: 'A handback reserve shall be funded from the start of year twenty (20) of the term in an amount certified by the Indepen…' | decided (recorded): I-CONCESSION | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:42.2 (VOL-V p4; text layer); ADD-02/Q7 [ADD-02; proposed; cited by the reading made at ADD-02 (interprets)] <- ADD-02:Q7 (ADD-02 p2) | I-CONCESSION
VOL-V-44.2-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:44.2 | contract; post_award; disputes | Refer disputes first to senior representatives, then an expert if technical, then arbitration seated in Riyadh in English | The parties shall first refer a dispute to senior representatives, then to an expert where the dispute is technical, and failing resolution to arbitration seated in Riyadh conducted in the English language before three arbitrators under the arbitration rules applicable in the Kingdom. | The parties shall first refer a dispute to senior representatives, then to an expert where the dispute is technical, and failing resolution to arbitration seated in Riyadh conducted in the English language before three arbitrators under the arbitration rules applicable in the Kingdom. | The parties shall first refer a dispute to senior representatives, then to an expert where the dispute is technical, and failing resolution to arbitration seated in Riyadh conducted in the English language before three arbitrators | VOL-V 44.2 p4 | VOL-V 44.2 p4 | contractual_post_award | Legal | Legal counsel | Post-award (proposed requirement): to be produced for each dispute, written records of its referral first to senior representatives, then to an expert where the dispute is technical, before any reference to arbitration (VOL-V 44.2); the extract states no time limit for any stage. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 44.2 p4 | VOL-V 44.2 p4 | VOL-V 44.2 p4 | VOL-V 44.2 p4 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'The parties shall first refer a dispute to senior representatives, then to an expert where the dispute is technical, an…' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:44.2 (VOL-V p4; text layer)
VOL-V-44.3-01 | DECIDED: accepted by Interview demo assumption (2026-10-11) | VOL-V:44.3 | contract; post_award; disputes | Continue performing the Agreement during any dispute | Performance of this Agreement shall continue during any dispute. | Performance of this Agreement shall continue during any dispute. | Performance of this Agreement shall continue during any dispute. | VOL-V 44.3 p4 | VOL-V 44.3 p4 | contractual_post_award | Legal | Legal counsel | Post-award (proposed requirement): for the period of any dispute, the routine performance records proposed under the other VOL-V rows (for example monthly progress reports, operating records and invoices) to be kept up without interruption, showing that performance continued (VOL-V 44.3); the clause requires no separate document. | ACTIVE | ACTIVE | ACTIVE | ACTIVE |  |  |  | VOL-V 44.3 p4 | VOL-V 44.3 p4 | VOL-V 44.3 p4 | VOL-V 44.3 p4 | none stated in the documents |  |  | high: verbatim text-layer clause |  | unchanged since BASE; value as read: 'Performance of this Agreement shall continue during any dispute.' | no open issue on the reading | row: ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a (text layer) | ASSUMED APPROVED FOR DEMO (2026-10-11); no observed human review — note: Assumed approved for an interview demonstration on the owner's instruction; no observed human review. | n/a | VOL-V:44.3 (VOL-V p4; text layer)

## Assumptions
Key | Value | Basis | Owner
lead_times.poa_board_resolutions | 5 WD | PROVISIONAL ASSUMPTION: board resolutions of each member authorising its signatories, members in parallel; not stated in the pack | Legal
lead_times.poa_notarisation | 5 WD | PROVISIONAL ASSUMPTION: typical notarisation of a Power of Attorney, signatories in parallel; not stated in the pack | Legal
lead_times.form_4a_preparation | 1 WD | PROVISIONAL ASSUMPTION: prepare the content of Form 4-A as reissued by ADD-01 Appendix A (Bidder and lead member, Addenda acknowledged, single point of contact); not stated | Legal
lead_times.form_4a_signature | 1 WD | PROVISIONAL ASSUMPTION: finalise the printed form and signature by the lead member's PoA holder; not stated | Legal
lead_times.spoc_confirmation | 1 WD | PROVISIONAL ASSUMPTION: confirm the single point of contact named in Form 4-A; not stated | Bid management
lead_times.form_4b_preparation | 3 WD | PROVISIONAL ASSUMPTION: prepare one Form 4-B per reference project from the reference evidence; not stated | Technical
lead_times.form_4b_finalise | 1 WD | PROVISIONAL ASSUMPTION: finalise each Form 4-B, including the 'Contract value (SAR equivalent)' field as the decision on I-VOL-I-ENV-A-PRICES directs; not stated | Technical
lead_times.completion_certificate | 15 WD | PROVISIONAL ASSUMPTION: obtain a client completion certificate for each reference plant from a third-party client; none is assumed to be held already; not stated | Technical
lead_times.form_4c_arabic_prep | 2 WD | PROVISIONAL ASSUMPTION: prepare the Arabic form text for the members; not stated | Legal
lead_times.form_4c_member_sign | 3 WD | PROVISIONAL ASSUMPTION: signature and stamp at each member's office, members in parallel; not stated | Legal
lead_times.pcg_wording | 10 WD | PROVISIONAL ASSUMPTION: agree the Parent Company Guarantee wording (substantially Form 4-D) with the EPC Contractor's ultimate parent; not stated | Legal
lead_times.pcg_execution | 10 WD | PROVISIONAL ASSUMPTION: parent board approval and execution of the guarantee; not stated | Legal
lead_times.deviations_review | 10 WD | PROVISIONAL ASSUMPTION: review Volume V and list every deviation, qualification or reservation; not stated | Legal
lead_times.form_4e_finalise | 2 WD | PROVISIONAL ASSUMPTION: finalise and sign Form 4-E, cross-check that no qualification appears elsewhere (VOL-I 9.6); not stated | Legal
lead_times.form_4g_review | 5 WD | PROVISIONAL ASSUMPTION: review the six cybersecurity undertakings with the O&M and OT teams; not stated | Technical
lead_times.form_4g_signature | 1 WD | PROVISIONAL ASSUMPTION: signature for the Bidder; not stated | Technical
lead_times.technical_proposal | 20 WD | PROVISIONAL ASSUMPTION: remaining work on the narrative incl. process design to the amended TN limit and standby power; not stated | Technical
lead_times.investment_licence | 5 WD | PROVISIONAL ASSUMPTION: copy of a current licence or a signed undertaking per foreign member (VOL-I 8.9); not stated | Legal
lead_times.consortium_confirmation | 1 WD | PROVISIONAL ASSUMPTION: confirm against the prequalification record (VOL-I Appendix 1) that the Bidder, its members, shareholdings and lead member are unchanged, or that the Authority's prior written consent to a change is held (VOL-I 1.4, 8.1); not stated in the pack | Legal
lead_times.bid_bond_bank_approval | 10 WD | PROVISIONAL ASSUMPTION: bank credit approval for a SAR 4.5m first-demand bond; not stated | Commercial
lead_times.bid_bond_issue | 3 WD | PROVISIONAL ASSUMPTION: issue of the bond after approval; not stated | Commercial
lead_times.lcc_ratio_calc | 5 WD | PROVISIONAL ASSUMPTION: compute the construction-phase local content ratio; not stated | Commercial
lead_times.lcc_certificate | 30 WD | PROVISIONAL ASSUMPTION: issuing authority not named and no lead time stated; the (non-binding) minutes record bidders' difficulty obtaining it 'within the programme'; set deliberately long until the owner confirms | Commercial
lead_times.iso_certificate_copy | 2 WD | PROVISIONAL ASSUMPTION: copy of the EPC Contractor's certificate, if it holds one; not stated | Technical
lead_times.reference_evidence | 10 WD | PROVISIONAL ASSUMPTION: commercial-operation evidence for the reference plants, plants in parallel; not stated | Technical
lead_times.fin_statements_collection | 5 WD | PROVISIONAL ASSUMPTION: collect each member's most recent audited financial statements, members in parallel; not stated | Commercial
lead_times.fin_standing_calc | 3 WD | PROVISIONAL ASSUMPTION: combined net worth and turnover weighted by shareholding (VOL-I 8.4); not stated | Commercial
lead_times.om_experience_evidence | 10 WD | PROVISIONAL ASSUMPTION: operating-experience evidence from the O&M Operator; not stated | Technical
lead_times.fin_model_build | 15 WD | PROVISIONAL ASSUMPTION: remaining build of a Financial Model already in development (unlocked, formula-linked, no macros); not stated | Commercial
lead_times.fin_model_freeze | 1 WD | PROVISIONAL ASSUMPTION: freeze inputs and version for audit and Form 4-F; not stated | Commercial
lead_times.lender_terms | 10 WD | PROVISIONAL ASSUMPTION: indicative financing terms (tenor, margin, gearing) from lenders; not stated | Commercial
lead_times.fin_assumptions_schedule | 2 WD | PROVISIONAL ASSUMPTION: schedule of principal financing assumptions from the frozen model (VOL-I 10.6); not stated | Commercial
lead_times.model_auditor_appointment | 5 WD | PROVISIONAL ASSUMPTION: engage an independent model auditor (opinion addressed to the Authority); not stated | Commercial
lead_times.model_audit_review | 10 WD | PROVISIONAL ASSUMPTION: rolling review of the draft model by the auditor; not stated | Commercial
lead_times.model_audit_opinion | 5 WD | PROVISIONAL ASSUMPTION: final review of the frozen model and issue of the opinion; not stated | Commercial
lead_times.form_4f_preparation | 2 WD | PROVISIONAL ASSUMPTION: complete and sign Form 4-F from the frozen model; not stated | Commercial
lead_times.ground_due_diligence | 10 WD | PROVISIONAL ASSUMPTION: review of the data-room geotechnical report and any own investigation needed to price ground risk; not stated | Technical
lead_times.clarification_drafting | 2 WD | PROVISIONAL ASSUMPTION: draft and submit requests or notices through the Portal; not stated | Bid management
lead_times.envelope_assembly | 1 WD | PROVISIONAL ASSUMPTION: assemble the marked original of one envelope in the required order with numbered dividers; not stated | Bid management
lead_times.copies_and_usb | 1 WD | PROVISIONAL ASSUMPTION: three hard copies of each envelope and the encrypted searchable USB copy named per Appendix 2; not stated | Bid management
lead_times.seal_and_mark | 0 WD | PROVISIONAL ASSUMPTION: a few hours at the end of the day the copies are finished (0 = no separate Working Day); not stated | Bid management
lead_times.delivery | 1 WD | PROVISIONAL ASSUMPTION: courier to the Appendix 3 address before the Proposal Due Date time stated in VOL-I 6.1 as amended (the time is derived, not assumed); not stated | Bid management
bidder.name | Unnamed consortium (the Bidder) | configurable assumption (owner's email of 1 Oct; confirmed by the hiring team's reply of 2 Oct) | Bid manager
bidder.members | 3 | PROVISIONAL ASSUMPTION: owner's instruction (assumed scenario: an unnamed three-member consortium, editable); VOL-I Appendix 1 lists one two-member consortium | Bid manager
bidder.foreign_members | 1 | PROVISIONAL ASSUMPTION: owner's instruction (one foreign member in the assumed consortium, editable); VOL-I 8.9 is the only clause found that ties a document to foreign members (an investment licence or a signed undertaking for each foreign consortium member); no legalisation or apostille is assumed because no clause requires one | Bid manager
bidder.signatories_per_member | 1 | PROVISIONAL ASSUMPTION: one authorised signatory per member (signs Form 4-C; the lead member's also signs Form 4-A) | Legal
bidder.reference_plants_offered | 2 | PROVISIONAL ASSUMPTION: the minimum of two reference plants in VOL-I 8.5 footnote 12; no actual reference plant of the Bidder is known or assumed to qualify | Technical
bidder.epc_contractors | 1 | PROVISIONAL ASSUMPTION: one proposed EPC Contractor | Bid manager
bidder.om_operators | 1 | PROVISIONAL ASSUMPTION: one proposed O&M Operator | Bid manager
resources.bid_manager | capacity 2 | PROVISIONAL ASSUMPTION: bid manager plus one coordinator (2 staff per Working Day); not stated in the pack | Bid manager
resources.document_controller | capacity 2 | PROVISIONAL ASSUMPTION: two document controllers for assembly, copies, sealing and delivery (2 staff per Working Day); not stated | Bid manager
resources.legal_counsel | capacity 2 | PROVISIONAL ASSUMPTION: two lawyers on PoAs, forms, guarantees and the licence evidence (2 staff per Working Day); not stated | Legal
resources.commercial_manager | capacity 2 | PROVISIONAL ASSUMPTION: two commercial staff on the bond, financial standing, lenders, auditor and Form 4-F (2 staff per Working Day); not stated | Commercial
resources.financial_modeller | capacity 1 | PROVISIONAL ASSUMPTION: one financial modeller for build, freeze and auditor queries (1 staff per Working Day); not stated | Commercial
resources.technical_lead | capacity 2 | PROVISIONAL ASSUMPTION: technical lead plus one engineer for certificates, references, ground review and Form 4-G (2 staff per Working Day); not stated | Technical
resources.proposal_writers | capacity 3 | PROVISIONAL ASSUMPTION: a writing team of three engineers for the Technical Proposal narrative (3 staff per Working Day); not stated | Technical
submission.marked_originals | 1 | stated in VOL-I 6.5 | Bid manager
submission.hard_copies | 3 | stated in VOL-I 6.5 | Bid manager
submission.electronic_copy | one searchable electronic copy on encrypted USB media, files named per Appendix 2 | stated in VOL-I 6.5 | Bid manager
submission.source | VOL-I:6.5; VOL-I:App2/para1; VOL-I:6.2 | stated in VOL-I 6.5 | Bid manager
submission.usb_per_envelope | 1 | PROVISIONAL ASSUMPTION (config/assumptions.yaml): ASSUMPTION (reading, PROVISIONAL): VOL-I 6.5 asks for one electronic copy per Proposal and VOL-I 6.2 forbids commercial information in Envelope A, so one USB per envelope is assumed; owner Bid manager; to confirm by clarification (I-VOL-I-COPIES) | Bid manager
submission.delivery_buffer_wd | 0 | PROVISIONAL ASSUMPTION: Working Days between delivery and the Proposal Due Date; 0 = delivered on the PDD itself, before the time VOL-I 6.1 (as amended) states; late Proposals are rejected unopened (VOL-I 6.6); not stated in the pack; owner Bid manager | Bid manager
planning.status_date | latest_validated_addendum_issue_date | configurable planning choice | Bid manager
planning.counting_policy | conservative | configurable planning choice | Bid manager
calendar.holidays | none | the pack declares none (VOL-I 2.4 excludes declared public holidays) | Bid manager

## Date coverage
Unit | Phrase | Treatment | By | Sentence
VOL-I:cover/para3 | 14 September 2026 | disposition | informational: tender reference and date of issue (14 September 2026, the start of the VOL-I 4.2 blackout) | 14 September 2026
VOL-I:4.3 | two (2) Working Days | rule | VOL-I-4.3-01 SPOC-CHANGE-NOTICE | Each Bidder shall nominate a single point of contact and shall notify the Authority of any change within two (2) Working Days.
VOL-I:5.2 | ten (10) Working Days | rule | VOL-I-5.2-01 CLARIFICATION-CUTOFF | Requests for clarification shall be submitted no later than ten (10) Working Days before the Proposal Due Date.
VOL-I:5.4 | 30 September 2026 | rule | VOL-I-5.4-01 PRE-BID | A Pre-Bid Conference will be held on Wednesday 30 September 2026 at 10:00 Riyadh time at the Authority's offices.
VOL-I:6.1 | 00 hours | rule | VOL-I-6.1-01 PDD | Proposals shall be received by the Authority not later than 14:00 hours Riyadh time on Thursday 26 November 2026 at the address given in Appendix 3.
VOL-I:6.1 | 26 November 2026 | anchor | defines PDD | Proposals shall be received by the Authority not later than 14:00 hours Riyadh time on Thursday 26 November 2026 at the address given in Appendix 3.
VOL-I:6.3 | eighty (180) days | rule | VOL-I-6.3-01 BID-BOND-VALIDITY | Envelope A shall be accompanied by a Bid Bond which shall remain valid for one hundred and eighty (180) days from the Proposal Due Date and shall be extended on demand where the Authority extends the period of Proposal v
VOL-I:7.1 | fifty (150) days | rule | VOL-I-7.1-01 PROPOSAL-VALIDITY | Each Proposal shall remain open for acceptance for one hundred and fifty (150) days from the Proposal Due Date.
VOL-I:8.5#fn12 | ten (10) years | rule | VOL-I-8.5-01 REFERENCE-LOOKBACK | For the avoidance of doubt, a Bidder that does not evidence at least two (2) reference sewage treatment plants, each of nominal capacity not less than 80,000 m³/day and each having achieved commercial operation within th
VOL-I:8.8 | five (5) years | duration | VOL-I-8.8-01 quotes it as part of the requirement | The proposed O&M Operator shall evidence not less than five (5) years of continuous operation of at least one (1) wastewater treatment facility of nominal capacity not less than 50,000 m³/day.
VOL-I:8.10 | five (5) years | rule | VOL-I-8.10-01 DEBARMENT-LOOKBACK | No member of the Bidder shall be the subject of, or have been the subject of within the preceding five (5) years, any debarment by a public authority in the Kingdom.
VOL-I:12.1 | twenty-five (25) years | rule | VOL-I-12.1-01 CONCESSION-END-PCOD | The concession period shall be twenty-five (25) years commencing on the Project Commercial Operation Date, following which the Project shall transfer to the Authority in accordance with Volume V.
VOL-I:12.2 | twenty (120) days | rule | VOL-I-12.2-01 PB-COMMERCIAL-CLOSE | The Preferred Bidder shall achieve Commercial Close within one hundred and twenty (120) days, and Financial Close within two hundred and seventy (270) days, of the date of the Preferred Bidder Notification.
VOL-I:12.2 | seventy (270) days | rule | VOL-I-12.2-02 PB-FINANCIAL-CLOSE | The Preferred Bidder shall achieve Commercial Close within one hundred and twenty (120) days, and Financial Close within two hundred and seventy (270) days, of the date of the Preferred Bidder Notification.
VOL-I:12.3 | ten (10) Working Days | disposition | authority: standstill of ten Working Days before the Authority executes the Project Agreement; no bidder action | A standstill period of ten (10) Working Days shall apply between the Preferred Bidder Notification and execution of the Project Agreement.
VOL-I:12.4 | twenty (20) Working Days | disposition | informational: an optional right of unsuccessful Bidders to request a debrief; not an obligation | Unsuccessful Bidders may request a debrief within twenty (20) Working Days of notification.
VOL-II:cover/para3 | 14 September 2026 | disposition | informational: tender reference and date of issue (14 September 2026, fixed) | 14 September 2026
VOL-II:2.2 | fifty (50) years | duration | VOL-II-2.2-01 quotes it as part of the requirement | The design life of all civil structures shall be not less than fifty (50) years.
VOL-II:2.2 | twenty (20) years | duration | VOL-II-2.2-02 quotes it as part of the requirement | The design life of mechanical and electrical equipment shall be not less than twenty (20) years or the manufacturer's rated life, whichever is the shorter, with lifecycle replacement provided for in the Project Company's
VOL-II:3.2 | seven (7) years | duration | VOL-II-3.2-02 quotes it as part of the requirement | Where a membrane process is proposed, the Project Company shall demonstrate membrane replacement provisions in the lifecycle plan and shall warrant a membrane life of not less than seven (7) years.
VOL-II:4.4 | ninety-six (96) hours | duration | VOL-II-4.4-01 quotes it as part of the requirement | Standby power shall be sized to carry the full inlet works, the disinfection stage and the effluent pumping station for not less than ninety-six (96) hours.
VOL-II:5.5 | 475 years | duration | VOL-II-5.5-01 quotes it as part of the requirement | All permanent civil structures shall be designed for a seismic event with a return period of 475 years and for a flood with a return period of 100 years.
VOL-II:5.5 | 100 years | duration | VOL-II-5.5-02 quotes it as part of the requirement | All permanent civil structures shall be designed for a seismic event with a return period of 475 years and for a flood with a return period of 100 years.
VOL-II:6.4 | seven (7) years | duration | VOL-II-6.4-01 quotes it as part of the requirement | All process data shall be retained for not less than seven (7) years and shall be made available to the Authority on demand in a non-proprietary format.
VOL-II:7.2 | thirty (30) days | duration | VOL-II-7.2-01 quotes it as part of the requirement | PCOD shall not be certified until the Facility has completed a continuous reliability run of thirty (30) days at not less than 90% of nominal capacity, during which every parameter in Table 2-4 has been met.
VOL-II:7.4 | sixty (60) days | rule | VOL-II-7.4-01 VOL-II-AS-BUILT-DUE | The Project Company shall provide as-built documentation, operation and maintenance manuals, and an asset register in the Authority's standard format not later than sixty (60) days after PCOD.
VOL-II:8.1 | two (2) years | duration | VOL-II-8.1-01 quotes it as part of the requirement | The Project Company shall hold a spare parts inventory sufficient for two (2) years of normal operation for all items with a lead time exceeding twelve (12) weeks.
VOL-II:8.1 | twelve (12) weeks | duration | VOL-II-8.1-01 quotes it as part of the requirement | The Project Company shall hold a spare parts inventory sufficient for two (2) years of normal operation for all items with a lead time exceeding twelve (12) weeks.
VOL-II:8.5 | two (2) years | rule | VOL-II-8.5-01 VOL-II-HANDBACK-SURVEY-WINDOW | A handback condition survey shall be carried out in the final two (2) years of the concession, and any remedial works identified shall be completed before transfer.
VOL-IV:cover/para3 | 14 September 2026 | disposition | informational: tender reference and issue date (14 September 2026, a fixed date); no bidder obligation | 14 September 2026
VOL-V:cover/para3 | 14 September 2026 | disposition | informational: tender reference and date of issue (14 September 2026, fixed) | 14 September 2026
VOL-V:3.1 | twenty-five (25) years | rule | VOL-V-3.1-01 VOL-V-TERM-END | This Agreement shall come into force on the Effective Date and shall continue for a period of twenty-five (25) years from the Effective Date, unless terminated earlier in accordance with its terms.
VOL-V:12.1 | thirty-six (36) months | rule | VOL-V-12.1-01 VOL-V-SCHEDULED-PCOD | The Project Company shall achieve PCOD within thirty-six (36) months of the Notice to Proceed (the Scheduled PCOD).
VOL-V:18.3 | sixty-five (365) days | rule | VOL-V-18.3-01 VOL-V-PCOD-LONG-STOP | If PCOD has not been achieved within three hundred and sixty-five (365) days after the Scheduled PCOD, the Authority may terminate under Clause 39.2.
VOL-V:29.3 | twelve (12) months | rule | VOL-V-29.3-01 VOL-V-RAMP-UP-END | During the first twelve (12) months after PCOD (the Ramp-Up Period) the Availability Payment shall be paid at ninety per cent (90%) of the full rate, and no availability deduction shall apply to a parameter listed in Tab
VOL-V:29.4 | ten (10) Working Days | rule | VOL-V-29.4-01 VOL-V-INVOICE-DUE | Invoices shall be submitted within ten (10) Working Days of each month end and shall be paid within thirty (30) days of receipt.
VOL-V:29.4 | thirty (30) days | rule | VOL-V-29.4-01 VOL-V-INVOICE-DUE | Invoices shall be submitted within ten (10) Working Days of each month end and shall be paid within thirty (30) days of receipt.
VOL-V:31.3 | twenty-four (24) hours | duration | VOL-V-31.3-02 quotes it as part of the requirement | A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a) and of seventy-two (72) hours to an event under Clause 31.1(c).
VOL-V:31.3 | seventy-two (72) hours | duration | VOL-V-31.3-01 quotes it as part of the requirement | A cure period of twenty-four (24) hours applies to an Unavailability Event under Clause 31.1(a) and of seventy-two (72) hours to an event under Clause 31.1(c).
VOL-V:31.4 | ninety (90) day | duration | VOL-V-31.4-01 quotes it as part of the requirement | Persistent breach, being three (3) or more Unavailability Events in any rolling ninety (90) day period, entitles the Authority to require a remediation plan and, on a second occurrence, to terminate under Clause 39.3.
VOL-V:34.3 | five (5) Working Days | rule | VOL-V-34.3-01 VOL-V-RELIEF-EVENT-NOTICE | The Project Company shall notify a Relief Event within five (5) Working Days of becoming aware of it, failing which no relief shall be granted.
VOL-V:39.4 | sixty (60) days | disposition | informational: the Project Company's right to terminate for an Authority Event of Default (unpaid undisputed sum over SAR 20,000,000 for 60 days after notice); | The Project Company may terminate for an Authority Event of Default, being a failure to pay an undisputed sum exceeding SAR 20,000,000 that continues for sixty (60) days after notice.
VOL-V:42.1 | five (5) years | duration | VOL-V-42.1-02 quotes it as part of the requirement | The Project Company shall transfer the Facility to the Authority on expiry in the condition required by Volume II Clause 8.5, free of encumbrance and with a remaining design life of not less than five (5) years for all m
ADD-01:3.1 | five (5) Working Days | rule | ADD-01-3.1-01 ATTENDANCE-NOTICE | A Bidder that considers its attendance to have been incorrectly recorded shall notify the Authority through the Portal within five (5) Working Days of this Addendum.
ADD-01:AppA/proposal-due-date | 12 November 2026 | printed | prints the PDD as 2026-11-12; the effective date is 2026-11-26 (raised as an issue, C31; not corrected) | 12 November 2026, 14:00 Riyadh time
ADD-02:F4-G/T1/4 | twenty-four (24) hours | post_award | ADD-02-F4G-05: undertaking 4: an event-driven post-award period (from detection of each incident), not a bid-stage date | Security incidents affecting the Facility will be notified to the Authority within twenty-four (24) hours of detection.

## Dates
Row | Stage | Rule | Text | Anchor | Readings | Planning | Readings differ
VOL-I-6.1-01 | BASE | PDD | not later than 14:00 hours Riyadh time on <date> | PDD = 2026-11-12 | as_stated: 2026-11-12 (stated in VOL-I:6.1) | 2026-11-12 (as_stated, policy conservative) | FALSE
VOL-I-6.1-01 | ADD-01 | PDD | not later than 14:00 hours Riyadh time on <date> | PDD = 2026-11-26 | as_stated: 2026-11-26 (stated in VOL-I:6.1) | 2026-11-26 (as_stated, policy conservative) | FALSE
VOL-I-6.1-01 | ADD-02 | PDD | not later than 14:00 hours Riyadh time on <date> | PDD = 2026-11-26 | as_stated: 2026-11-26 (stated in VOL-I:6.1) | 2026-11-26 (as_stated, policy conservative) | FALSE
VOL-I-6.1-01 | ADD-03 | PDD | not later than 14:00 hours Riyadh time on <date> | PDD = 2026-12-10 | as_stated: 2026-12-10 (stated in VOL-I:6.1) | 2026-12-10 (as_stated, policy conservative) | FALSE
VOL-I-5.2-01 | BASE | CLARIFICATION-CUTOFF | no later than ten (10) Working Days before the Proposal Due Date | PDD = 2026-11-12 | stated_date_excluded: 2026-10-29 (VOL-I §2.4) | 2026-10-29 (stated_date_excluded, policy conservative) | FALSE
VOL-I-5.2-01 | ADD-01 | CLARIFICATION-CUTOFF | no later than ten (10) Working Days before the Proposal Due Date | PDD = 2026-11-26 | stated_date_excluded: 2026-11-12 (VOL-I §2.4) | 2026-11-12 (stated_date_excluded, policy conservative) | FALSE
VOL-I-5.2-01 | ADD-02 | CLARIFICATION-CUTOFF | no later than ten (10) Working Days before the Proposal Due Date | PDD = 2026-11-26 | stated_date_excluded: 2026-11-12 (VOL-I §2.4) | 2026-11-12 (stated_date_excluded, policy conservative) | FALSE
VOL-I-5.2-01 | ADD-03 | CLARIFICATION-CUTOFF | no later than ten (10) Working Days before the Proposal Due Date | PDD = 2026-12-10 | stated_date_excluded: 2026-11-26 (VOL-I §2.4) | 2026-11-26 (stated_date_excluded, policy conservative) | FALSE
VOL-I-6.3-01 | BASE | BID-BOND-VALIDITY | valid for one hundred and eighty (180) days from the Proposal Due Date | PDD = 2026-11-12 | day0: 2027-05-11 (not stated in the pack); day1: 2027-05-10 (not stated in the pack) | 2027-05-11 (day0, policy conservative) | TRUE
VOL-I-6.3-01 | ADD-01 | BID-BOND-VALIDITY | valid for one hundred and eighty (180) days from the Proposal Due Date | PDD = 2026-11-26 | day0: 2027-05-25 (not stated in the pack); day1: 2027-05-24 (not stated in the pack) | 2027-05-25 (day0, policy conservative) | TRUE
VOL-I-6.3-01 | ADD-02 | BID-BOND-VALIDITY | valid for one hundred and eighty (180) days from the Proposal Due Date | PDD = 2026-11-26 | day0: 2027-05-25 (not stated in the pack); day1: 2027-05-24 (not stated in the pack) | 2027-05-25 (day0, policy conservative) | TRUE
VOL-I-6.3-01 | ADD-03 | BID-BOND-VALIDITY | valid for one hundred and eighty (180) days from the Proposal Due Date | PDD = 2026-12-10 | day0: 2027-07-08 (not stated in the pack); day1: 2027-07-07 (not stated in the pack) | 2027-07-08 (day0, policy conservative) | TRUE
VOL-I-7.1-01 | BASE | PROPOSAL-VALIDITY | one hundred and fifty (150) days from the Proposal Due Date | PDD = 2026-11-12 | day0: 2027-04-11 (not stated in the pack); day1: 2027-04-10 (not stated in the pack) | 2027-04-11 (day0, policy conservative) | TRUE
VOL-I-7.1-01 | ADD-01 | PROPOSAL-VALIDITY | one hundred and fifty (150) days from the Proposal Due Date | PDD = 2026-11-26 | day0: 2027-04-25 (not stated in the pack); day1: 2027-04-24 (not stated in the pack) | 2027-04-25 (day0, policy conservative) | TRUE
VOL-I-7.1-01 | ADD-02 | PROPOSAL-VALIDITY | one hundred and fifty (150) days from the Proposal Due Date | PDD = 2026-11-26 | day0: 2027-04-25 (not stated in the pack); day1: 2027-04-24 (not stated in the pack) | 2027-04-25 (day0, policy conservative) | TRUE
VOL-I-7.1-01 | ADD-03 | PROPOSAL-VALIDITY | one hundred and fifty (150) days from the Proposal Due Date | PDD = 2026-12-10 | day0: 2027-05-09 (not stated in the pack); day1: 2027-05-08 (not stated in the pack) | 2027-05-09 (day0, policy conservative) | TRUE
VOL-I-8.3-01 | BASE | ISO-CURRENT-AT | current as at the Proposal Due Date | PDD = 2026-11-12 | as_stated: 2026-11-12 (stated in VOL-I:8.3) | 2026-11-12 (as_stated, policy conservative) | FALSE
VOL-I-8.3-01 | ADD-01 | ISO-CURRENT-AT | current as at the Proposal Due Date | PDD = 2026-11-26 | as_stated: 2026-11-26 (stated in VOL-I:8.3) | 2026-11-26 (as_stated, policy conservative) | FALSE
VOL-I-8.3-01 | ADD-02 | ISO-CURRENT-AT | current as at the Proposal Due Date | PDD = 2026-11-26 | as_stated: 2026-11-26 (stated in VOL-I:8.3) | 2026-11-26 (as_stated, policy conservative) | FALSE
VOL-I-8.3-01 | ADD-03 | ISO-CURRENT-AT | current as at the Proposal Due Date | PDD = 2026-12-10 | as_stated: 2026-12-10 (stated in VOL-I:8.3) | 2026-12-10 (as_stated, policy conservative) | FALSE
VOL-I-8.5-01 | BASE | REFERENCE-LOOKBACK | within the ten (10) years preceding the Proposal Due Date | PDD = 2026-11-12 | boundary_inclusive: 2016-11-12 (not stated in the pack); boundary_exclusive: 2016-11-13 (not stated in the pack) | 2016-11-13 (boundary_exclusive, policy conservative) | TRUE
VOL-I-8.5-01 | ADD-01 | REFERENCE-LOOKBACK | within the ten (10) years preceding the Proposal Due Date | PDD = 2026-11-26 | boundary_inclusive: 2016-11-26 (not stated in the pack); boundary_exclusive: 2016-11-27 (not stated in the pack) | 2016-11-27 (boundary_exclusive, policy conservative) | TRUE
VOL-I-8.5-01 | ADD-02 | REFERENCE-LOOKBACK | within the ten (10) years preceding the Proposal Due Date | PDD = 2026-11-26 | boundary_inclusive: 2016-11-26 (not stated in the pack); boundary_exclusive: 2016-11-27 (not stated in the pack) | 2016-11-27 (boundary_exclusive, policy conservative) | TRUE
VOL-I-8.5-01 | ADD-03 | REFERENCE-LOOKBACK | within the ten (10) years preceding the Proposal Due Date | PDD = 2026-12-10 | boundary_inclusive: 2016-12-10 (not stated in the pack); boundary_exclusive: 2016-12-11 (not stated in the pack) | 2016-12-11 (boundary_exclusive, policy conservative) | TRUE
VOL-I-5.4-01 | BASE | PRE-BID | Wednesday 30 September 2026 at 10:00 Riyadh time |  | as_stated: 2026-09-30 (stated in VOL-I:5.4) | 2026-09-30 (as_stated, policy conservative) | FALSE
VOL-I-5.4-01 | ADD-01 | PRE-BID | Wednesday 30 September 2026 at 10:00 Riyadh time |  | as_stated: 2026-09-30 (stated in VOL-I:5.4) | 2026-09-30 (as_stated, policy conservative) | FALSE
VOL-I-5.4-01 | ADD-02 | PRE-BID | Wednesday 30 September 2026 at 10:00 Riyadh time |  | as_stated: 2026-09-30 (stated in VOL-I:5.4) | 2026-09-30 (as_stated, policy conservative) | FALSE
VOL-I-5.4-01 | ADD-03 | PRE-BID | Wednesday 30 September 2026 at 10:00 Riyadh time |  | as_stated: 2026-09-30 (stated in VOL-I:5.4) | 2026-09-30 (as_stated, policy conservative) | FALSE
ADD-01-3.1-01 | ADD-01 | ATTENDANCE-NOTICE | within five (5) Working Days of this Addendum | ADD-01-issue = 2026-10-08 | event_day_excluded: 2026-10-15 (not stated in the pack (VOL-I §2.4 covers backward counting only)); event_day_counted: 2026-10-14 (not stated in the pack (VOL-I §2.4 covers backward counting only)) | 2026-10-14 (event_day_counted, policy conservative) (calc deadline: ambiguous, the counting rules state nothing for Working Days counted after a date (VOL-I 2.4 covers Working Days counted backwards): not stated, so every reading is kept and a person decides) | TRUE
ADD-01-3.1-01 | ADD-02 | ATTENDANCE-NOTICE | within five (5) Working Days of this Addendum | ADD-01-issue = 2026-10-08 | event_day_excluded: 2026-10-15 (not stated in the pack (VOL-I §2.4 covers backward counting only)); event_day_counted: 2026-10-14 (not stated in the pack (VOL-I §2.4 covers backward counting only)) | 2026-10-14 (event_day_counted, policy conservative) | TRUE
ADD-01-3.1-01 | ADD-03 | ATTENDANCE-NOTICE | within five (5) Working Days of this Addendum | ADD-01-issue = 2026-10-08 | event_day_excluded: 2026-10-15 (not stated in the pack (VOL-I §2.4 covers backward counting only)); event_day_counted: 2026-10-14 (not stated in the pack (VOL-I §2.4 covers backward counting only)) | 2026-10-14 (event_day_counted, policy conservative) | TRUE
VOL-I-3.4-01 | BASE | OMISSION-CLAIM-CUTOFF | No claim arising from an alleged omission shall be entertained after the Proposal Due Date. | PDD = 2026-11-12 | as_stated: 2026-11-12 (stated in VOL-I:3.4) | 2026-11-12 (as_stated, policy conservative) | FALSE
VOL-I-3.4-01 | ADD-01 | OMISSION-CLAIM-CUTOFF | No claim arising from an alleged omission shall be entertained after the Proposal Due Date. | PDD = 2026-11-26 | as_stated: 2026-11-26 (stated in VOL-I:3.4) | 2026-11-26 (as_stated, policy conservative) | FALSE
VOL-I-3.4-01 | ADD-02 | OMISSION-CLAIM-CUTOFF | No claim arising from an alleged omission shall be entertained after the Proposal Due Date. | PDD = 2026-11-26 | as_stated: 2026-11-26 (stated in VOL-I:3.4) | 2026-11-26 (as_stated, policy conservative) | FALSE
VOL-I-3.4-01 | ADD-03 | OMISSION-CLAIM-CUTOFF | No claim arising from an alleged omission shall be entertained after the Proposal Due Date. | PDD = 2026-12-10 | as_stated: 2026-12-10 (stated in VOL-I:3.4) | 2026-12-10 (as_stated, policy conservative) | FALSE
VOL-I-4.2-01 | BASE | BLACKOUT-START | From the date of issue of this Volume |  | as_stated: 2026-09-14 (stated in VOL-I:4.2) | 2026-09-14 (as_stated, policy conservative) | FALSE
VOL-I-4.2-01 | BASE | BLACKOUT-END | until the issue of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-4.2-01 | ADD-01 | BLACKOUT-START | From the date of issue of this Volume |  | as_stated: 2026-09-14 (stated in VOL-I:4.2) | 2026-09-14 (as_stated, policy conservative) | FALSE
VOL-I-4.2-01 | ADD-01 | BLACKOUT-END | until the issue of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-4.2-01 | ADD-02 | BLACKOUT-START | From the date of issue of this Volume |  | as_stated: 2026-09-14 (stated in VOL-I:4.2) | 2026-09-14 (as_stated, policy conservative) | FALSE
VOL-I-4.2-01 | ADD-02 | BLACKOUT-END | until the issue of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-4.2-01 | ADD-03 | BLACKOUT-START | From the date of issue of this Volume |  | as_stated: 2026-09-14 (stated in VOL-I:4.2) | 2026-09-14 (as_stated, policy conservative) | FALSE
VOL-I-4.2-01 | ADD-03 | BLACKOUT-END | until the issue of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-4.3-01 | BASE | SPOC-CHANGE-NOTICE | notify the Authority of any change within two (2) Working Days | SPOC-CHANGE = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-4.3-01 | ADD-01 | SPOC-CHANGE-NOTICE | notify the Authority of any change within two (2) Working Days | SPOC-CHANGE = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-4.3-01 | ADD-02 | SPOC-CHANGE-NOTICE | notify the Authority of any change within two (2) Working Days | SPOC-CHANGE = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-4.3-01 | ADD-03 | SPOC-CHANGE-NOTICE | notify the Authority of any change within two (2) Working Days | SPOC-CHANGE = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-6.7-01 | BASE | MODIFY-CUTOFF | at any time before the Proposal Due Date | PDD = 2026-11-12 | as_stated: 2026-11-12 (stated in VOL-I:6.7) | 2026-11-12 (as_stated, policy conservative) | FALSE
VOL-I-6.7-01 | ADD-01 | MODIFY-CUTOFF | at any time before the Proposal Due Date | PDD = 2026-11-26 | as_stated: 2026-11-26 (stated in VOL-I:6.7) | 2026-11-26 (as_stated, policy conservative) | FALSE
VOL-I-6.7-01 | ADD-02 | MODIFY-CUTOFF | at any time before the Proposal Due Date | PDD = 2026-11-26 | as_stated: 2026-11-26 (stated in VOL-I:6.7) | 2026-11-26 (as_stated, policy conservative) | FALSE
VOL-I-6.7-01 | ADD-03 | MODIFY-CUTOFF | at any time before the Proposal Due Date | PDD = 2026-12-10 | as_stated: 2026-12-10 (stated in VOL-I:6.7) | 2026-12-10 (as_stated, policy conservative) | FALSE
VOL-I-8.9-01 | BASE | INVESTMENT-LICENCE-BY-FC | a signed undertaking to obtain such licence prior to Financial Close | FC = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-8.9-01 | ADD-01 | INVESTMENT-LICENCE-BY-FC | a signed undertaking to obtain such licence prior to Financial Close | FC = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-8.9-01 | ADD-02 | INVESTMENT-LICENCE-BY-FC | a signed undertaking to obtain such licence prior to Financial Close | FC = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-8.9-01 | ADD-03 | INVESTMENT-LICENCE-BY-FC | a signed undertaking to obtain such licence prior to Financial Close | FC = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-8.10-01 | BASE | DEBARMENT-LOOKBACK | within the preceding five (5) years |  | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-8.10-01 | ADD-01 | DEBARMENT-LOOKBACK | within the preceding five (5) years |  | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-8.10-01 | ADD-02 | DEBARMENT-LOOKBACK | within the preceding five (5) years |  | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-8.10-01 | ADD-03 | DEBARMENT-LOOKBACK | within the preceding five (5) years |  | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.1-01 | BASE | CONCESSION-END-PCOD | twenty-five (25) years commencing on the Project Commercial Operation Date | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.1-01 | ADD-01 | CONCESSION-END-PCOD | twenty-five (25) years commencing on the Project Commercial Operation Date | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.1-01 | ADD-02 | CONCESSION-END-PCOD | twenty-five (25) years commencing on the Project Commercial Operation Date | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.1-01 | ADD-03 | CONCESSION-END-PCOD | twenty-five (25) years commencing on the Project Commercial Operation Date | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.2-01 | BASE | PB-COMMERCIAL-CLOSE | Commercial Close within one hundred and twenty (120) days ... of the date of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.2-01 | ADD-01 | PB-COMMERCIAL-CLOSE | Commercial Close within one hundred and twenty (120) days ... of the date of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.2-01 | ADD-02 | PB-COMMERCIAL-CLOSE | Commercial Close within one hundred and twenty (120) days ... of the date of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.2-01 | ADD-03 | PB-COMMERCIAL-CLOSE | Commercial Close within one hundred and twenty (120) days ... of the date of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.2-02 | BASE | PB-FINANCIAL-CLOSE | Financial Close within two hundred and seventy (270) days, of the date of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.2-02 | ADD-01 | PB-FINANCIAL-CLOSE | Financial Close within two hundred and seventy (270) days, of the date of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.2-02 | ADD-02 | PB-FINANCIAL-CLOSE | Financial Close within two hundred and seventy (270) days, of the date of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-I-12.2-02 | ADD-03 | PB-FINANCIAL-CLOSE | Financial Close within two hundred and seventy (270) days, of the date of the Preferred Bidder Notification | PBN = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-6.3-02 | BASE | VOL-II-SECURITY-ARCHITECTURE-DUE | prior to commissioning | Commissioning = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-6.3-02 | ADD-01 | VOL-II-SECURITY-ARCHITECTURE-DUE | prior to commissioning | Commissioning = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-6.3-02 | ADD-02 | VOL-II-SECURITY-ARCHITECTURE-DUE | prior to commissioning | Commissioning = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-6.3-02 | ADD-03 | VOL-II-SECURITY-ARCHITECTURE-DUE | prior to commissioning | Commissioning = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-7.4-01 | BASE | VOL-II-AS-BUILT-DUE | not later than sixty (60) days after PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-7.4-01 | ADD-01 | VOL-II-AS-BUILT-DUE | not later than sixty (60) days after PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-7.4-01 | ADD-02 | VOL-II-AS-BUILT-DUE | not later than sixty (60) days after PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-7.4-01 | ADD-03 | VOL-II-AS-BUILT-DUE | not later than sixty (60) days after PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.2-01 | BASE | VOL-II-CMMS-BY-PCOD | implemented before PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.2-01 | ADD-01 | VOL-II-CMMS-BY-PCOD | implemented before PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.2-01 | ADD-02 | VOL-II-CMMS-BY-PCOD | implemented before PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.2-01 | ADD-03 | VOL-II-CMMS-BY-PCOD | implemented before PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.5-01 | BASE | VOL-II-HANDBACK-SURVEY-WINDOW | in the final two (2) years of the concession | End of the concession period = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.5-01 | ADD-01 | VOL-II-HANDBACK-SURVEY-WINDOW | in the final two (2) years of the concession | End of the concession period = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.5-01 | ADD-02 | VOL-II-HANDBACK-SURVEY-WINDOW | in the final two (2) years of the concession | End of the concession period = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.5-01 | ADD-03 | VOL-II-HANDBACK-SURVEY-WINDOW | in the final two (2) years of the concession | End of the concession period = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.5-02 | BASE | VOL-II-HANDBACK-REMEDIALS-DUE | completed before transfer | Transfer of the Facility = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.5-02 | ADD-01 | VOL-II-HANDBACK-REMEDIALS-DUE | completed before transfer | Transfer of the Facility = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.5-02 | ADD-02 | VOL-II-HANDBACK-REMEDIALS-DUE | completed before transfer | Transfer of the Facility = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-8.5-02 | ADD-03 | VOL-II-HANDBACK-REMEDIALS-DUE | completed before transfer | Transfer of the Facility = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-9.2-01 | BASE | VOL-II-ENV-CLEARANCE-DUE | before commencement of construction | Commencement of construction = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-9.2-01 | ADD-01 | VOL-II-ENV-CLEARANCE-DUE | before commencement of construction | Commencement of construction = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-9.2-01 | ADD-02 | VOL-II-ENV-CLEARANCE-DUE | before commencement of construction | Commencement of construction = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-9.2-01 | ADD-03 | VOL-II-ENV-CLEARANCE-DUE | before commencement of construction | Commencement of construction = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-9.3-01 | BASE | VOL-II-GRIEVANCE-DUE | established before construction | Commencement of construction = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-9.3-01 | ADD-01 | VOL-II-GRIEVANCE-DUE | established before construction | Commencement of construction = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-9.3-01 | ADD-02 | VOL-II-GRIEVANCE-DUE | established before construction | Commencement of construction = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-II-9.3-01 | ADD-03 | VOL-II-GRIEVANCE-DUE | established before construction | Commencement of construction = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-IV-F4A-04 | BASE | PROPOSAL-VALIDITY-F4A | valid for one hundred and fifty (150) days from the Proposal Due Date | PDD = 2026-11-12 | day0: 2027-04-11 (not stated in the pack); day1: 2027-04-10 (not stated in the pack) | 2027-04-11 (day0, policy conservative) | TRUE
VOL-V-3.1-01 | BASE | VOL-V-TERM-END | twenty-five (25) years from the Effective Date | Effective Date = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-3.1-01 | ADD-01 | VOL-V-TERM-END | twenty-five (25) years from the Effective Date | Effective Date = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-3.1-01 | ADD-02 | VOL-V-TERM-END | twenty-five (25) years from the Effective Date | Effective Date = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-3.1-01 | ADD-03 | VOL-V-TERM-END | twenty-five (25) years from the Effective Date | Effective Date = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-12.1-01 | BASE | VOL-V-SCHEDULED-PCOD | within thirty-six (36) months of the Notice to Proceed | Notice to Proceed = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-12.1-01 | ADD-01 | VOL-V-SCHEDULED-PCOD | within thirty-six (36) months of the Notice to Proceed | Notice to Proceed = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-12.1-01 | ADD-02 | VOL-V-SCHEDULED-PCOD | within thirty-six (36) months of the Notice to Proceed | Notice to Proceed = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-12.1-01 | ADD-03 | VOL-V-SCHEDULED-PCOD | within thirty-six (36) months of the Notice to Proceed | Notice to Proceed = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-18.3-01 | BASE | VOL-V-PCOD-LONG-STOP | within three hundred and sixty-five (365) days after the Scheduled PCOD | Scheduled PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-18.3-01 | ADD-01 | VOL-V-PCOD-LONG-STOP | within three hundred and sixty-five (365) days after the Scheduled PCOD | Scheduled PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-18.3-01 | ADD-02 | VOL-V-PCOD-LONG-STOP | within three hundred and sixty-five (365) days after the Scheduled PCOD | Scheduled PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-18.3-01 | ADD-03 | VOL-V-PCOD-LONG-STOP | within three hundred and sixty-five (365) days after the Scheduled PCOD | Scheduled PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-29.3-01 | BASE | VOL-V-RAMP-UP-END | the first twelve (12) months after PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-29.3-01 | ADD-01 | VOL-V-RAMP-UP-END | the first twelve (12) months after PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-29.3-01 | ADD-02 | VOL-V-RAMP-UP-END | the first twelve (12) months after PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-29.3-01 | ADD-03 | VOL-V-RAMP-UP-END | the first twelve (12) months after PCOD | PCOD = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-29.4-01 | BASE | VOL-V-INVOICE-DUE | within ten (10) Working Days of each month end | Each month end = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-29.4-01 | ADD-01 | VOL-V-INVOICE-DUE | within ten (10) Working Days of each month end | Each month end = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-29.4-01 | ADD-02 | VOL-V-INVOICE-DUE | within ten (10) Working Days of each month end | Each month end = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-29.4-01 | ADD-03 | VOL-V-INVOICE-DUE | within ten (10) Working Days of each month end | Each month end = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-34.3-01 | BASE | VOL-V-RELIEF-EVENT-NOTICE | within five (5) Working Days of becoming aware of it | Becoming aware of a Relief Event = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-34.3-01 | ADD-01 | VOL-V-RELIEF-EVENT-NOTICE | within five (5) Working Days of becoming aware of it | Becoming aware of a Relief Event = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-34.3-01 | ADD-02 | VOL-V-RELIEF-EVENT-NOTICE | within five (5) Working Days of becoming aware of it | Becoming aware of a Relief Event = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-34.3-01 | ADD-03 | VOL-V-RELIEF-EVENT-NOTICE | within five (5) Working Days of becoming aware of it | Becoming aware of a Relief Event = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-42.2-01 | BASE | VOL-V-HANDBACK-RESERVE-START | from the start of year twenty (20) of the term | Start of the term = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-42.2-01 | ADD-01 | VOL-V-HANDBACK-RESERVE-START | from the start of year twenty (20) of the term | Start of the term = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-42.2-01 | ADD-02 | VOL-V-HANDBACK-RESERVE-START | from the start of year twenty (20) of the term | Start of the term = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE
VOL-V-42.2-01 | ADD-03 | VOL-V-HANDBACK-RESERVE-START | from the start of year twenty (20) of the term | Start of the term = None | unknown_anchor: None (not stated in the pack) | None (unknown_anchor, policy conservative) | FALSE

## Evidence
Code | Name | Issuer | Envelope | Per | Source
EV-ATTENDANCE | Pre-Bid Conference attendance; notice if the attendance record is wrong | Bidder | none | proposal | VOL-I:5.4; ADD-01:3.1
EV-BID-BOND | Bid Bond (SAR 4,500,000, first demand) | Bank licensed in the Kingdom meeting the VOL-I 6.4 rating | A | proposal | VOL-I:9.1(g); VOL-I:6.3; VOL-I:6.4
EV-CLARIFICATIONS | Clarification requests through the Portal (each citing Volume, Clause and page) | Bidder | none | proposal | VOL-I:5.1; VOL-I:5.2
EV-COMPLETION-CERT | Client completion certificate for each reference project | Client of each reference plant | A | reference | VOL-I:9.5
EV-COPIES | One marked original, three hard copies and an encrypted searchable USB copy, files named per Appendix 2 | Bidder | A+B | proposal | VOL-I:6.5; VOL-I:App2/para1
EV-DELIVERY | Delivery of both sealed, marked envelopes to the Appendix 3 address before the deadline | Bidder (courier) | A+B | proposal | VOL-I:6.1; VOL-I:6.2; VOL-I:App3/para1
EV-FIN-ASSUMPTIONS | Schedule of principal financing assumptions (tenor, margin, gearing) | Bidder | B | proposal | VOL-I:10.6
EV-FIN-MODEL | Financial Model (unlocked Excel, no macros, no hard-coded calculation cells) | Bidder | B | proposal | VOL-I:10.1; VOL-I:10.3
EV-FIN-STANDING | Evidence of financial standing (net worth and other VOL-I 8.4 tests) | Each member (audited accounts) | A | member | VOL-I:8.4; VOL-I:9.1(i)
EV-FORM-4A | Form 4-A Proposal Submission Letter (signed by the lead member's PoA holder) | PoA holder of the lead member | A | proposal | VOL-I:9.1(a); VOL-I:9.3
EV-FORM-4B | Form 4-B Reference Projects Schedule (one per reference project) | Bidder | A | reference | VOL-I:9.1(b); VOL-I:9.5
EV-FORM-4C | Form 4-C Conflict of Interest and Debarment Declaration (Arabic, per member) | Authorised signatory of each member | A | member | VOL-I:9.1(c); VOL-I:9.4
EV-FORM-4D | Form 4-D Parent Company Guarantee (executed) | Ultimate parent of the EPC Contractor | A | epc_contractor | VOL-I:9.1(d); VOL-I:8.7
EV-FORM-4E | Form 4-E Schedule of Deviations | Bidder | A | proposal | VOL-I:9.1(e); VOL-I:9.6
EV-FORM-4F | Form 4-F Financial Proposal Schedule (single Availability Payment, SAR p.a.) | Bidder | B | proposal | VOL-I:10.1; VOL-I:10.2
EV-FORM-4G | Form 4-G Cybersecurity Compliance Undertaking | Bidder | A | proposal | ADD-02:7.1; ADD-02:7.2
EV-GROUND-DD | Ground-condition due diligence (Bidders satisfy themselves; the data-room geotechnical report is for information) | Bidder | none | proposal | ADD-01:Q4
EV-INVESTMENT-LICENCE | Investment licence or signed undertaking for each foreign member | Licensing authority / each foreign member | A | foreign_member | VOL-I:8.9
EV-ISO | EPC Contractor's ISO 9001:2015 certificate | Accredited certification body | A | epc_contractor | VOL-I:8.3; VOL-I:9.1(i)
EV-LCC | Local Content Certificate | Competent authority (not named in the pack) | A | proposal | VOL-I:8.6 as amended
EV-MODEL-AUDIT | Independent model auditor's opinion on the Financial Model | Independent model auditor | B | proposal | VOL-I:10.3
EV-OM-EXPERIENCE | Evidence of the O&M Operator's operating experience | O&M Operator | A | om_operator | VOL-I:8.8
EV-POA | Notarised Power of Attorney for each signatory | Notary | A | signatory | VOL-I:9.1(h); VOL-I:9.3
EV-REFERENCES | Evidence of commercial operation of the reference plants | Reference plant owners | A | reference | VOL-I:8.5; VOL-I:8.5#fn12
EV-SPOC | Single point of contact nominated, changes notified within 2 Working Days | Bidder | none | proposal | VOL-I:4.3
EV-TECH-PROPOSAL | Technical Proposal narrative (page limit per VOL-I 9.2) | Bidder | A | proposal | VOL-I:9.1(f); VOL-I:9.2; VOL-I:9.7

## Issues
Id | Text | Owner | Source | Rows | Clarification
I-NO-CONSEQUENCE | The clause states no consequence of its own. A mandatory requirement is subject to the responsiveness and mandatory compliance check on a pass or fail basis (VOL-I 11.1(i)); only Proposals that pass it go on to technical evaluation (11.1(ii)). The pack gives no clause-specific label and does not say whether a failure is curable; none is implied | Bid manager | curated (proposed wording) | VOL-I-6.3-01; VOL-I-6.4-01; VOL-I-6.4-02; VOL-I-7.1-01; VOL-I-8.3-01; ADD-01-AppA-01; ADD-02-F4G-04; VOL-I-6.2-01; VOL-I-6.5-01; VOL-I-8.4-01; VOL-I-8.4-02; VOL-I-8.7-01; VOL-I-8.8-01; VOL-I-8.9-01; VOL-I-8.10-01; VOL-I-9.1-01; VOL-I-9.1h-01; VOL-I-9.7-01; VOL-I-10.1-01; VOL-I-10.2-01; VOL-I-10.3-01; VOL-I-10.3-02; VOL-I-10.4-01; VOL-I-10.5-02; VOL-I-10.6-01; VOL-I-App3-01; VOL-IV-F4A-02; VOL-IV-F4B-01; VOL-IV-F4C-01; VOL-IV-F4C-02; VOL-IV-F4C-03; VOL-IV-F4C-05; VOL-IV-F4D-01; VOL-IV-F4E-01; VOL-IV-F4F-01; VOL-IV-F4F-02
I-LCC-ISSUER | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): Local Content Certificate: issuing 'competent authority' not named and no lead time stated; the minutes (non-binding) record bidders' difficulty obtaining it in time | Commercial | curated (proposed wording) | VOL-I-8.6-01 | CQ-LCC-ISSUER
I-BIDDER-FACTS | Bidder facts are configurable assumptions about an assumed bidder (config/assumptions.yaml), not facts: the consortium members and how many are foreign, the reference plants offered, the signatories per member, and attendance at the Pre-Bid Conference; confirm them | Bid manager | curated (proposed wording) | VOL-I-5.4-01; VOL-I-9.4-01; VOL-I-1.4-01; VOL-I-8.1-01; VOL-I-8.2-01; VOL-I-8.4-01; VOL-I-8.4-02; VOL-I-8.8-01; VOL-I-8.9-01; VOL-I-8.10-01; VOL-I-9.1h-01; VOL-I-9.5-01; VOL-IV-F4A-06; VOL-IV-F4A-07; VOL-IV-F4B-01; VOL-IV-F4C-01; VOL-IV-F4C-02; VOL-IV-F4C-03; VOL-IV-F4C-N1 (via REL-MEMBER-FORM-4C (confirmed))
I-F4A-FIELDS | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): Reissued Form 4-A (ADD-01 App A) drops fields and the numbered confirmations of the original and states a purpose ('acknowledgement of Addenda at paragraph 1') it has no paragraph for; what to print and sign, and whether to seek clarification before the cut-off | Legal | curated (proposed wording) | VOL-I-9.3-01; VOL-IV-F4A-01; ADD-03-cover-para3-01; ADD-01-AppA-01; VOL-IV-FORMS-01; VOL-IV-F4A-02; VOL-IV-F4A-03; VOL-IV-F4A-04; VOL-IV-F4A-05; VOL-IV-F4A-06; VOL-IV-F4A-07; VOL-I-7.1-01 (evidence field not on the reissued form (VOL-IV-F4A-04)) | CQ-F4A-REISSUE
I-READING-F4C | Form 4-C (image, Arabic): the visible Arabic text and displayed translations were confirmed by the owner (Ahmad, 3 Oct 2026; approval of VOL-IV-p6-r1), and declaration 5 refers to VOL-I 4.2. Still open: the exact placement of diacritics. The approval covers that version of the reading only, not the register's interpretations or bidder compliance | Owner (Arabic reviewer) | curated (proposed wording) | VOL-IV-F4C-04; VOL-IV-F4C-N1; VOL-IV-F4C-01; VOL-IV-F4C-02; VOL-IV-F4C-03; VOL-IV-F4C-05 | CQ-F4C-EXCLUSION
I-F4C-EXCLUSION | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): Form 4-C declaration 4 says any incorrect statement 'leads to the exclusion of the proposal' (يؤدي إلى استبعاد العرض). The English volumes never use 'exclusion'; it is kept as its own category and not treated as equivalent to rejection, disqualification or non-responsiveness. Which, if any, it corresponds to is a legal question (clarification register CQ-F4C-EXCLUSION) | Legal | curated (proposed wording) | VOL-IV-F4C-04 | CQ-F4C-EXCLUSION
I-READING-T24 | Table 2-4 (image): the visible transcription (rows, headings, units, limits, assessment bases, the qualifier and Note 1) was confirmed by the owner (Ahmad, 3 Oct 2026; approval of VOL-II-p3-r1). TN = 5 mg/l is the original reading; 3 mg/l is ADD-02 5.1's separate amended value. Still open: anything outside the visible image (e.g. whether a further note was cut off below Note 1) | Owner | curated (proposed wording) | VOL-II-T2-4-TN; ADD-02-5.2-01; VOL-II-2.4-01; VOL-II-2.5-01; VOL-II-T2-4-BOD5; VOL-II-T2-4-COD; VOL-II-T2-4-TSS; VOL-II-T2-4-TP; VOL-II-T2-4-Turbidity; VOL-II-T2-4-FaecalColiforms; VOL-II-T2-4-ResidualChlorine; VOL-II-T2-4-pH; VOL-II-T2-4-OilGrease; VOL-II-T2-4-NOTE1; VOL-II-3.1-01; VOL-II-4.3-02; VOL-II-7.2-01; VOL-V-29.3-01; VOL-V-31.1-02 | CQ-ENV-PERMIT
I-F4G-LETTERING | Form 4-G is inserted after item (e) of VOL-I 9.1; the re-lettering of items (f)-(i) is not stated | Bid manager | curated (proposed wording) | ADD-02-7.2-01; VOL-I-9.1-01
I-F4G-NO | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): Form 4-G undertakings are answered Yes/No; the effect of 'No' is not stated, and undertakings 3-6 add post-award obligations not in VOL-II 6 | Technical | curated (proposed wording) | ADD-02-F4G-01; ADD-02-F4G-05; ADD-02-F4G-06; ADD-02-F4G-07; ADD-02-F4G-02; ADD-02-F4G-03
I-F4D-WORDING | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): Form 4-D wording latitude: VOL-I 8.7 (p4) requires the guarantee 'substantially in the form set out in Form 4-D'; Volume IV (p2) states 'A Bidder that alters the wording of a Form does so at its own risk.' Whether a change to the Form 4-D wording stays within 'substantially in the form' is a decision for Legal; no decision recorded (the scope and expiry point is drafted as CQ-F4D-GUARANTEE-SCOPE) | Legal | curated (proposed wording) | VOL-IV-F4D-01
I-PERMIT | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): Table 2-4 is reproduced from an Environmental Permit that is not in the pack. The precedence language is in the VOL-II p3 reproduction preamble ('the Environmental Permit shall prevail'; VOL-II 2.4 incorporates the table by reference); the owner confirmed that location on 3 Oct 2026. Not confirmed, and not claimed: the Permit's contents and compliance with the Permit, including after the TN amendment (ADD-02 5.1, 3 mg/l). Context, not binding: the pre-bid minutes record that 'the permit was under review by the regulator and that any change would be issued by Addendum.' (ADD-01 Appendix B item 5, p4); the minutes do not bind the Authority (ADD-01 3.2, p1) | Technical | curated (proposed wording) | VOL-II-T2-4-TN; ADD-02-5.2-01; VOL-II-2.4-01; VOL-II-T2-4-BOD5; VOL-II-T2-4-COD; VOL-II-T2-4-TSS; VOL-II-T2-4-TP; VOL-II-T2-4-Turbidity; VOL-II-T2-4-FaecalColiforms; VOL-II-T2-4-ResidualChlorine; VOL-II-T2-4-pH; VOL-II-T2-4-OilGrease; VOL-II-T2-4-NOTE1; VOL-II-3.1-01; VOL-II-7.2-01; VOL-V-31.1-02; VOL-V-29.3-01 (via REL-MISSING-ENVIRONMENTAL-PERMIT > REL-T24-RAMP-UP-DEDUCTIONS (confirmed)); VOL-II-4.3-02 (via REL-MISSING-ENVIRONMENTAL-PERMIT > REL-T24-COMPLIANCE-MONITORING-STREAMS (confirmed)); VOL-II-2.5-01 (via REL-MISSING-ENVIRONMENTAL-PERMIT > REL-T24-CONTINUOUS-MONITORING (confirmed)) | CQ-ENV-PERMIT
I-CONCESSION | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): Concession term: VOL-I 12.1 (p6) 'twenty-five (25) years commencing on the Project Commercial Operation Date'; VOL-V 3.1 (p2) 'twenty-five (25) years from the Effective Date'. ADD-02 Q7 (p2), asked 'Which applies?': 'The Authority notes the question. The order of precedence at Volume I Clause 3.2 applies. The Authority does not consider further amendment necessary at this stage.' The answer does not say which clause applies, and neither clause is amended. VOL-I 3.2 (p2) orders (a) the Addenda, (b) Volume I, (c) Volume V, 'the first named prevailing'; VOL-I 3.3 (p2): 'A Bidder that resolves such a conflict unilaterally does so at its own risk'. Which clause governs the term is a decision for a person (Legal); no decision recorded. It sets the term start in the Financial Model, what to record in Form 4-E ('A deviation not listed in Form 4-E will be taken as accepted.', VOL-V Note to Bidders) and how 'the term' in VOL-V 3.2 and 42.2 reads (draft question CQ-CONCESSION-TERM). A legal and commercial question | Legal | curated (proposed wording) | VOL-I-3.3-01; VOL-I-9.6-01; VOL-I-12.1-01; VOL-II-1.1-01; VOL-II-8.5-01; VOL-II-8.5-02; VOL-V-NOTE-01; VOL-V-3.1-01; VOL-V-3.2-01; VOL-V-42.1-01; VOL-V-42.2-01 | CQ-CONCESSION-TERM
I-FLOWS | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): Design flows: ADD-02 Q11 (p2), asked about a peak hourly flow of 7,500 m3/h against a daily average of 120,000 m3/day, answers 'Bidders shall design to the figures stated in Volume II. Volume II Clause 4.2 applies.': design to the Volume II figures. It does not comment on their consistency (VOL-II 4.2 leaves that to the Bidder) and does not define 'dry weather flow'. Engineering reading, for the process engineer to confirm (not the Authority's words): 120,000 m3/day is 5,000 m3/h on average and 7,500 m3/h a peaking factor of 1.5, so the two figures are not contradictory. Open: 'dry weather flow' in Table 2-6 row 2-6.4 is undefined, so the storm flow to be passed to full treatment is unclear (draft question CQ-DWF-STORM-FLOW). An engineering question | Process engineer | curated (proposed wording) | VOL-II-4.1-01; VOL-II-T2-6-1; VOL-II-T2-6-2; VOL-II-T2-6-4; VOL-II-4.2-01; VOL-II-5.2-01; VOL-V-31.1-01 | CQ-DWF-STORM-FLOW
I-VOL-III | Volume III referenced (VOL-I 3.1), not supplied; pack confirmed complete (2 Oct). Only Drawing 03-C-114 shows the effluent main's delivery point (VOL-II 5.1). No omission claim after the PDD (VOL-I 3.4) | Technical | curated (proposed wording) | ADD-01-Q4-01; VOL-I-3.4-01; VOL-I-5.5-01; VOL-II-5.1-01; VOL-II-5.2-02; VOL-V-31.1-03 | CQ-VOL-III-DRAWINGS
I-ADD03-F4G-SCOPE | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): ADD-03 3.1 says: 'Form 4-G (Cybersecurity Compliance Undertaking), added by Addendum No. 2 Section 7, is withdrawn. Bidders shall disregard it and shall not submit it. Section 7.2 of Addendum No. 2 ceases to have effect.' The proposed op ADD-03/3.1(a) revokes only ADD-02:7.2. Row ADD-02-7.2-01 is therefore REVOKED and needs no new reading. Two things stay ACTIVE at ADD-03: the form itself (ADD-02:F4-G, meaning undertakings 1-6 and the signature line) and its entry in the Envelope A list (VOL-I:9.1(e)+ADD-02, 'FORM 4-G — CYBERSECURITY COMPLIANCE UNDERTAKING'). They stay active because the op engine cannot revoke the form as a group, and it rejects the form's member units as targets the provision does not name (dry run, C22). A person needs to decide: (1) whether rows ADD-02-F4G-01 to -05, and any rows on undertakings 5 and 6, stop applying from ADD-03; (2) whether the ADD-02 item list of row VOL-I-9.1-01, which includes Form 4-G, should be re-read without it; (3) whether evidence item EV-FORM-4G and A5 activities form-4g-review and form-4g-sign should come off the programme; (4) whether issues I-F4G-NO and I-F4G-LETTERING lapse. Those two issues were accepted only under an interview_demo assumption, which acknowledges them and nothing more. No handling instruction is recorded for any of these points, and none is inferred. The interview_demo 'changed' review status of the Form 4-G rows is kept as it is. [the same question was raised by the analysis phase as I-ADD-03-3-1-ISSUE-ANA: PROPOSED by the analysis phase (ISS-ADD03-3.1, ADD-03:3.1; interpretation_pending): ambiguous: ADD-03:3.1 says Form 4-G 'is withdrawn' and that 'Section 7.2 of Addendum No. 2 ceases to have effect', but says nothing of ADD-02:7.1 ('A new Form 4-G is added to Volume IV and to the list at Volume I Cl…] [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Bid management | curated (proposed wording)
I-ADD03-F4G-UNITS | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): ADD-03 3.1 withdraws Form 4-G ('is withdrawn. Bidders shall disregard it and shall not submit it. Section 7.2 of Addendum No. 2 ceases to have effect.'). The proposed op ADD-03/3.1(a) revokes only ADD-02:7.2. The form's units stay active at ADD-03: the heading VOL-I:9.1(e)+ADD-02 'FORM 4-G — CYBERSECURITY COMPLIANCE UNDERTAKING' and undertakings ADD-02:F4-G/T1/1-6, inserted by ADD-02/7.1. As a result, rows ADD-02-F4G-06 and ADD-02-F4G-07 (post-award undertakings 5 and 6) and any other Form 4-G undertaking rows remain in force. Open questions for people: (1) Document control: should the amendment record also withdraw the Form 4-G units and the VOL-I 9.1 list entry? That is amendment-phase work and is not done here. (2) Technical: do the post-award duties in undertakings 5 and 6 survive? ADD-03 3.2 says 'The substantive requirements of Volume II Section 6 are unchanged and shall be addressed in the Technical Proposal narrative', and the register records these undertakings as not in VOL-II 6. Once these are decided, review the dependent work: evidence item EV-FORM-4G, A5 activities form-4g-review and form-4g-sign, and issues I-F4G-NO and I-F4G-LETTERING (their interview_demo acceptances are kept as recorded and are not resolutions). Pending a human decision. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Document control | curated (proposed wording)
I-ADD03-BOND-AMOUNT-FOLLOW-ON | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): ADD-03 5.1 (op ADD-03/5.1, proposed) changes the Bid Bond amount in VOL-I 6.4 to 'SAR 5,600,000 (five million six hundred thousand Saudi Riyals)'. Some follow-on records still restate or rest on the earlier amount. (1) The evidence item EV-BID-BOND is named 'Bid Bond (SAR 4,500,000, first demand)'. Document control needs to correct the label. No new evidence item is proposed because the instrument is the same. (2) The A5 activities bond-approval and bond-issue (lead times bid_bond_bank_approval and bid_bond_issue) produce EV-BID-BOND. Any bank approval or draft prepared on the earlier amount would need to be revisited. The pack does not say whether any such approval exists; that is a bidder fact. (3) ADD-03 5.2 (op ADD-03/5.2(a)) also changes the Bid Bond validity in VOL-I 6.3 to two hundred and ten (210) days from the Proposal Due Date. This affects the same instrument and is read with the Proposal Due Date as amended by ADD-03/2.1. Nothing here decides how the bond is procured. Decision owner: Commercial. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Commercial | curated (proposed wording)
I-ADD03-PDD-OWNER-DIRECTIONS | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): ADD-03 2.1 (op ADD-03/2.1, proposed) changes the Proposal Due Date in VOL-I 6.1 to 'Thursday 10 December 2026'; the time '14:00 hours Riyadh time' is unchanged. The owner's directions of 3 Oct 2026 (session 08 §3) are recorded on two rows: VOL-I-6.7-01 (the cut-off in VOL-I 6.7) and VOL-I-8.3-01 (ISO 9001:2015 certificate current as at the Proposal Due Date). Both directions name the amended date that applied then, 26 November 2026. The ADD-03 re-readings carry their substance and read the Proposal Due Date from VOL-I 6.1 as amended. Open question for a person: do the session-08 directions apply unchanged to the Proposal Due Date as amended by ADD-03? The current reviews of these rows are interview_demo assumptions ('no observed human review'), not observed approvals. Rows VOL-I-7.1-01 (validity) and VOL-I-8.5-01 (reference look-back) are anchored on the same date. Decision owner: Bid management. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Bid management | curated (proposed wording)
I-ADD03-REFERENCE-THRESHOLD | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): ADD-03 4.2 (op ADD-03/4.2(a), proposed) raises the reference plant threshold in footnote 12 to VOL-I 8.5 to 'not less than 100,000 m³/day'. The stated consequence of not evidencing two such plants is unchanged: 'shall be rejected without further evaluation'. Follow-on work rests on this change: the reference evidence (EV-REFERENCES, activity references), the Form 4-B schedules (EV-FORM-4B) and the completion certificates (EV-COMPLETION-CERT) for the plants relied on under 8.5. Any reference selection made against the earlier threshold (80,000 m³/day) needs re-checking against the amended threshold. It also needs re-checking against the ten-year look-back, counted from the Proposal Due Date as amended by ADD-03/2.1. The pack does not say which plants the Bidder holds or what their capacities are; these are bidder facts, and nothing is asserted about them. Decision owner: Technical. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Technical | curated (proposed wording)
I-ADD03-TIE-BAND | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): ambiguous: new VOL-I 11.6 (ADD-03 6.1, p2) reads 'Where, on completion of the combined evaluation, two or more Proposals are within two per cent (2%) of one another, the Authority may apply such further criteria as it considers appropriate to determine the Preferred Bidder, and its determination shall be final.' The combined evaluation ranks Proposals 'on a combined score calculated on a weighting of sixty per cent (60%) technical and forty per cent (40%) commercial' (VOL-I 11.2, p5). Readings: (A) within 2 points of combined score; (B) within a relative 2% of the higher combined score; (C) within 2% on another measure, such as the Availability Payment. The 'further criteria' are not stated, and what 'its determination shall be final' means is a legal question. The clause bears on bid strategy and pricing near the margin. Whether to seek clarification before the VOL-I 5.2 cut-off (draft CQ-ADD03-TIE-BAND) is for a person. HUMAN DECISION PENDING; nothing decided. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Bid management | curated (proposed wording) | ADD-03-6.1-01 | CQ-ADD03-TIE-BAND
I-ADD03-Q17-AP-CAPACITY | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): ambiguous: ADD-03 Q17 asks 'Will the Availability Payment be adjusted for the increased capacity?' and the Authority responds 'Bidders shall price the Project as amended by this Addendum.' Reading (a): no adjustment is offered and the single Availability Payment quoted under VOL-I 10.2 on Form 4-F (confirmed 'unconditional' and 'not subject to any qualification') must itself reflect the Project as amended by ADD-03, including its capacity change. Reading (b): the response states only the pricing basis and does not say whether the Availability Payment mechanism (VOL-V Clause 29, adjusted under Clause 31 per VOL-V 1.1) changes for capacity. Which reading holds, and whether a follow-up clarification is sought, is a Commercial decision; the Financial Model and Form 4-F rest on it (rows VOL-I-10.2-01, VOL-IV-F4F-01, VOL-IV-F4F-02, VOL-V-29.2-01, ADD-03-Q17-01). [the same question was raised by the analysis phase as I-ADD-03-Q17-Q17-ISSUE-ANA: PROPOSED by the analysis phase (ADD-03/Q17-issue, ADD-03:Q17; interpretation_pending): ambiguous: Clarification request 17 asks 'Will the Availability Payment be adjusted for the increased capacity?'; the Authority responds 'Bidders shall price the Project as amended by this Addendum.' Reading A: e…] [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Commercial | curated (proposed wording) | ADD-03-Q17-01; VOL-I-10.2-01 (via REL-AI-004 (proposed)); VOL-IV-F4F-01 (via REL-AI-004 (proposed)); VOL-IV-F4F-02 (via REL-AI-004 (proposed))
I-ADD03-F4G-UNITS-ACTIVE | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): ADD-03 3.1 states that Form 4-G 'is withdrawn' and that Bidders 'shall not submit it'; the promoted op ADD-03/3.1(a) revokes only ADD-02:7.2. After the ops the Envelope A list entry inserted in VOL-I 9.1 by ADD-02 ('FORM 4-G — CYBERSECURITY COMPLIANCE UNDERTAKING', VOL-I:9.1(e)+ADD-02) and the Form 4-G units (ADD-02:F4-G/T1/1 to T1/6, ADD-02:F4-G/para1) are still active, so rows ADD-02-F4G-01 to -07 are still evaluated ACTIVE and A5 still plans form-4g-review and form-4g-sign, whose output 3.1 forbids submitting. Open for Document control: whether further ops on those units are needed to give effect to 'is withdrawn' (amendment phase), and for Technical: re-reading of rows ADD-02-F4G-01 to -07 and the A5 activities. Not decided here; the existing issues I-F4G-LETTERING and I-F4G-NO are not changed. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Document control | curated (proposed wording) | ADD-03-3.1-01
I-ADD03-BOND-210 | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): Existing issue I-VOL-I-BOND-LONGSTOP (and the 'gap' of CQ-BOND-FC-COVERAGE as previously recorded) refers to 'the Bid Bond's 180-day validity from the PDD (VOL-I 6.3)'; after ADD-03/5.2(a) VOL-I 6.3 prints 'two hundred and ten (210) days from the Proposal Due Date'. The existing issue is not changed by a proposal; whether its open question still stands at 210 days, and whether CQ-BOND-FC-COVERAGE is still to be sent, is a Commercial decision. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Commercial | curated (proposed wording)
I-ADD03-F4G-EFFECTIVE-TEXT | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): ADD-03 3.1 (p1): 'Form 4-G (Cybersecurity Compliance Undertaking), added by Addendum No. 2 Section 7, is withdrawn. Bidders shall disregard it and shall not submit it. Section 7.2 of Addendum No. 2 ceases to have effect.' The promoted ops act only on ADD-02:7.2 (op ADD-03/3.1(a): set_status 'revoked'). ADD-02 7.1 (p3), 'A new Form 4-G is added to Volume IV and to the list at Volume I Clause 9.1, to be inserted after item (e).', and the Form 4-G units (ADD-02:F4-G/T1/1-6, F4-G/para1) are still active in the effective text at ADD-03. As a result, row VOL-I-9.1-01 (whose ADD-02 reading lists Form 4-G after item (e)), rows ADD-02-F4G-01 to -07, evidence item EV-FORM-4G and activities form-4g-review and form-4g-sign still stand. Open question for Document control: should the withdrawal be represented in the amendment record for ADD-02 7.1 and the Form 4-G units, and how should those rows, the evidence item and the activities be treated? HUMAN DECISION PENDING. Activity 'assemble-envelope-a' is proposed to drop its Form 4-G instruction on the words of ADD-03 3.1. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Document control | curated (proposed wording)
I-ADD03-F4A-PDD | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): ADD-03:2.1 amends VOL-I 6.1 to 'Thursday 10 December 2026', 14:00 Riyadh time. The reissued Form 4-A still prints 'Proposal Due Date: 12 November 2026, 14:00 Riyadh time' (row VOL-IV-F4A-01). VOL-IV cover paragraph 5 says 'Forms shall be reproduced without alteration to their wording.' The open question on I-F4A-FIELDS (how to correct the out-of-date printed date) is the same kind of question, but it now follows a second amendment of the Proposal Due Date. I-F4A-FIELDS has only an interview_demo acceptance and no handling instruction, so nothing says what to print and sign. Activity form-4a stays gated. Open question for Legal: how should Form 4-A's printed Proposal Due Date be handled after ADD-03, and should clarification be sought before the cut-off? HUMAN DECISION PENDING. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Legal | curated (proposed wording)
I-ADD03-ISO-DATE | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): Row VOL-I-8.3-01 (reading at ADD-01) records the owner's direction of 3 Oct 2026: the EPC Contractor's ISO 9001:2015 certificate must be current at '26 November 2026, 14:00 Riyadh time'. ADD-03:2.1 deletes 'Thursday 26 November 2026' from VOL-I 6.1 and substitutes 'Thursday 10 December 2026'. VOL-I 8.3 ties currency to 'the Proposal Due Date'. So the date that recorded decision rests on has changed. The owner (Technical) should restate whether the direction now applies at the amended Proposal Due Date. The certificate's expiry date is a bidder fact that is not in the pack, and it must be checked against the amended date. Nothing is re-decided here. HUMAN DECISION PENDING. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Technical | curated (proposed wording)
I-ADD03-REF-THRESHOLD | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): ADD-03/4.2(a) raises the reference-plant threshold in footnote 12 to VOL-I 8.5 from '80,000 m³/day' to '100,000 m³/day'. The footnote states that a Bidder that does not evidence two such plants 'shall be rejected without further evaluation'. The reference plants offered are bidder facts, held only as configurable assumptions (I-BIDDER-FACTS). The pack cannot show whether they meet the new threshold, or whether they fall within the ten-year window counted from the amended Proposal Due Date. The Technical lead must confirm both before the references activity relies on those plants. HUMAN DECISION PENDING. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Technical | curated (proposed wording)
I-ADD03-F4G-TAKEN-OUT | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): ADD-03 3.1 (p1) takes Form 4-G out of the RFP Documents: 'Bidders shall disregard it and shall not submit it. Section 7.2 of Addendum No. 2 ceases to have effect.' Only ADD-02 7.2 is revoked in the tool. The form units, the VOL-I 9.1 Envelope A entry ('FORM 4-G — CYBERSECURITY COMPLIANCE UNDERTAKING'), rows ADD-02-F4G-01 to -07, evidence item EV-FORM-4G and activities form-4g-review and form-4g-sign remain. Open: (1) how to record the remaining form units as no longer in force and retire the rows, evidence item and activities (Document control); (2) ambiguous: whether undertakings 3 to 6, which had no counterpart in VOL-II 6, survive in any other form, or fall away with the form (Technical). VOL-II 6.2 and 6.3 stand on their own words. Earlier records that rest on Form 4-G: I-F4G-NO and I-F4G-LETTERING (interview_demo acceptances; no handling instruction recorded). No decision recorded; pending a human decision. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Document control | curated (proposed wording)
I-ADD03-FLOWS-BASIS | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): ADD-03 4.1 (p1) raises the average daily flow in VOL-II 2.1 to '150,000 m³/day' (and names Table 2-6 row 2-6.1, which the tool has not yet changed). It also says 'The peak hourly flow in Table 2-6 row 2-6.2 is unchanged.' (Table 2-6: 'Value: 7,500', m³/h). The engineering reading recorded in I-FLOWS, that 7,500 m³/h is a peaking factor of 1.5 on an average of 5,000 m³/h, was based on 120,000 m³/day. The Authority's ADD-02 Q11 response ('Bidders shall design to the figures stated in Volume II.') was given when the figures read 120,000. Open (Technical, Process engineer): whether the peak, storm (3 x dry weather flow) and transmission main sizing (VOL-II 5.2) figures remain consistent with the new average, and whether to raise a clarification before the VOL-I 5.2 cut-off. No figure is recomputed here; no decision recorded. [the same question was raised by the analysis phase as I-ADD-03-4-1-ISSUE-ANA: PROPOSED by the analysis phase (ISS-ADD03-4.1, ADD-03:4.1; interpretation_pending): ADD-03:4.1 raises the average daily flow ('‘120,000 m³/day’ is deleted and ‘150,000 m³/day’ is substituted') but states 'The peak hourly flow in Table 2-6 row 2-6.2 is unchanged.' (row 2-6.2: 'Peak hourly flow (desi…] [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Technical | curated (proposed wording)
I-ADD03-CAPACITY-VOLI-1-3-COND | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): CONDITIONAL on disposition DISP-ADD03-4.3 (unresolved; nothing applied) and proposed issue ISS-ADD03-4.3. ambiguous: ADD-03:4.3 prints only 'Volume I Clause 1.3 is amended correspondingly.' At ADD-03 the effective texts disagree: VOL-I:1.3 still reads 'nominal capacity one hundred and twenty thousand cubic metres per day (120,000 m³/day)', while VOL-II:2.1 reads 'nominal treatment capacity of 150,000 m³/day average daily flow'. Reading (a): VOL-I:1.3 is amended in both words and figures to correspond to 150,000 m³/day. The new words are not printed anywhere. Reading (b): only the figure is amended. Downstream reach if either reading were applied: no A1 row quotes VOL-I:1.3 in the scope found. The activity technical-proposal (EV-TECH-PROPOSAL, through row VOL-II-2.1-01) designs to the capacity. ADD-03:Q17 tells Bidders to 'price the Project as amended by this Addendum', so the pricing basis depends on which capacity text is in force. Nothing is applied and no reading is chosen. Open question: what is the effective text of VOL-I:1.3 at ADD-03? Pending a human decision. [the same question was raised by the analysis phase as I-ADD-03-4-3-ISSUE-ANA: PROPOSED by the analysis phase (ISS-ADD03-4.3, ADD-03:4.3; interpretation_pending): ambiguous: 'Volume I Clause 1.3 is amended correspondingly.' (ADD-03:4.3) gives no new words for 'nominal capacity one hundred and twenty thousand cubic metres per day (120,000 m³/day)' (VOL-I:1.3). Reading (a): wor…] [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Document control | curated (proposed wording)
I-ADD03-FLOWS-REREAD-COND | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): CONDITIONAL on proposed issue ISS-ADD03-4.1 and escalation ESC-ADD-03:4.1-table. ADD-03:4.1 raises the average daily flow in VOL-II:2.1 to 150,000 m³/day and states 'The peak hourly flow in Table 2-6 row 2-6.2 is unchanged.' Row 2-6.2 still reads 'Peak hourly flow (design) ¦ Value: 7,500 ¦ Unit: m³/h'. Several earlier records compare 7,500 m³/h with a daily average of 120,000 m³/day: issue I-FLOWS (accepted, interview_demo origin; acceptance is not a resolution), the ADD-02 note of row VOL-II-4.2-01, and the ADD-02 Q11 answer recorded there. They rest on a figure ADD-03:4.1 replaced in VOL-II:2.1 and should be re-read by the Process engineer. VOL-II:5.2 sizes the transmission main 'for the peak hourly flow in Table 2-6' (row VOL-II-5.2-01). VOL-II:4.2 requires that the Project Company 'shall raise any inconsistency as a clarification under Volume I Clause 5.1'. No peaking factor, conversion or consistency conclusion is computed or stated here, and I-FLOWS is not changed. Open question: does the earlier engineering reading still hold against 150,000 m³/day, and should a clarification be drafted before the clarification cut-off? Pending a human decision. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Technical | curated (proposed wording)
I-ADD03-F4G-LIST-ENTRY-COND | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): CONDITIONAL on issue ISS-ADD03-3.1 (held, blocked by ESC-ADD-03:3.1-form). ambiguous: ADD-03:3.1 says Form 4-G 'is withdrawn' and that 'Section 7.2 of Addendum No. 2 ceases to have effect', but says nothing of ADD-02:7.1 ('A new Form 4-G is added to Volume IV and to the list at Volume I Clause 9.1, to be inserted after item (e).'). ADD-02:7.1 and the inserted list unit VOL-I:9.1(e)+ADD-02 ('FORM 4-G — CYBERSECURITY COMPLIANCE UNDERTAKING') remain active at ADD-03. Reading (a): the list entry falls with the withdrawal. Reading (b): it stays as printed, for a form that Bidders 'shall not submit'. Records that rest on the answer: the ADD-02 reading of row VOL-I-9.1-01 (accepted, interview_demo origin), whose parameters list 'Form 4-G' between Form 4-E and the Technical Proposal narrative; issue I-F4G-LETTERING (re-lettering after item (e)); and issue I-F4G-NO (effect of a 'No' answer on the form). Under reading (a) these would need re-reading. Under reading (b) the Envelope A order would include an entry Bidders are told not to submit. Nothing is decided here, no existing issue is changed or closed, and no handling instruction is recorded or inferred. Open question: does the Volume I Clause 9.1 list still include a Form 4-G entry from ADD-03? Pending a human decision. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Document control | curated (proposed wording)
I-ADD03-11-6-BAND-COND | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): CONDITIONAL on proposed issue ISS-ADD03-6.1. ambiguous: new Volume I Clause 11.6 reads 'two or more Proposals are within two per cent (2%) of one another, the Authority may apply such further criteria as it considers appropriate to determine the Preferred Bidder, and its determination shall be final.' Reading 1: the 2% is two percentage points of the combined score under VOL-I:11.2 ('ranked on a combined score'). Reading 2: the 2% is relative to a Proposal's combined score, and the clause does not say which Proposal's. Downstream reach if either reading held: row VOL-I-11.2-01 (accepted, interview_demo origin; no_deliverable) would gain a tie-break stage after the combined score. This affects bid strategy but not deliverables. insufficient evidence: the 'further criteria' are not stated in units_after or in any unit read for this task, so no A5 activity or evidence item can be proposed for them. No bid-out consequence is stated. What 'its determination shall be final' means is a Legal question and is not answered here. Open questions for Bid management, with Legal on the finality words: which reading of the 2% band applies, and whether to draft a clarification asking for the further criteria before the clarification cut-off. Pending a human decision. [the same question was raised by the analysis phase as I-ADD-03-6-1-ISSUE-ANA: PROPOSED by the analysis phase (ISS-ADD03-6.1, ADD-03:6.1; interpretation_pending): ambiguous: new Volume I Clause 11.6 (ADD-03:6.1) reads 'two or more Proposals are within two per cent (2%) of one another, the Authority may apply such further criteria as it considers appropriate to determine the P…] [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Bid management | curated (proposed wording) | VOL-I-11.2-01 (via REL-AI-010 (possible))
I-ADD03-Q17-PRICING-COND | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): CONDITIONAL on proposed issue ADD-03/Q17-issue. ambiguous: clarification request 17 asks 'Will the Availability Payment be adjusted for the increased capacity?' and the Authority responds 'Bidders shall price the Project as amended by this Addendum.' Reading A: the Bidder's single Availability Payment under VOL-I:10.2 reflects the Project as amended, including the capacity change, with no adjustment by the Authority. Reading B: the response does not answer whether the payment mechanism at Volume V Clause 29 is adjusted, so a further clarification may be needed. Downstream reach: row VOL-I-10.2-01 (accepted, interview_demo origin; evidence EV-FORM-4F, activity form-4f) and the Financial Model activities under EV-FIN-MODEL (fin-model-build, fin-model-freeze) price the Project. Row VOL-V-29.3-01 records the Ramp-Up payment at 90% of the full rate. The 'Project as amended by this Addendum' is itself not settled: VOL-I:1.3 still reads 120,000 m³/day (disposition DISP-ADD03-4.3 unresolved), and Table 2-6 row 2-6.1 still reads 120,000 (escalation ESC-ADD-03:4.1-table). Prices therefore rest on those open points as well. No price, figure or Bidder fact is stated or assumed. Open question (Commercial): which reading governs the pricing of the Financial Proposal, and should a further clarification be drafted? Pending a human decision. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Commercial | curated (proposed wording) | VOL-I-10.2-01 (via REL-AI-011 (possible))
I-ADD03-T26-AVG-FLOW | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): ADD-03:4.1 reads: 'In Volume II Clause 2.1 and in Table 2-6 row 2-6.1, ‘120,000 m³/day’ is deleted and ‘150,000 m³/day’ is substituted.' The promoted ops supplied to the downstream phase include ADD-03/4.1(a) on VOL-II:2.1 only. None targets Table 2-6 row 2-6.1, whose Value cell reads '120,000' (Unit 'm³/day') at ADD-03 in the evidence tools. Earlier clarification ADD-02 Q11 quotes this table figure. Open question for Document control: is the provision's change to Table 2-6 row 2-6.1 accounted for by an op or a disposition? Until a person confirms it, the Table 2-6 average daily flow at ADD-03 is unconfirmed. HUMAN DECISION PENDING; nothing is resolved by this issue. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Document control | curated (proposed wording)
I-ADD-03-2-2-2-2-ISSUE-ANA | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): PROPOSED by the analysis phase (ADD-03/2.2-issue, ADD-03:2.2; interpretation_pending): ambiguous: ADD-03:2.2 reads 'Every period calculated by reference to the Proposal Due Date is adjusted accordingly.' without naming any clause. Open question: which periods does it adjust - (A) those ADD-01:2.2 listed (VOL-I 5.2 clarification cut-off, 6.3 Bid Bond validity, 7.1 Proposal validity, 8.5 footnote 12 look-back) or (B) every PDD-referenced period at ADD-03, including periods that other ADD-03 provisions amend (Bid Bond; Q18 'One hundred and fifty (150) days from the Proposal Due Date as amended.')? Pending a human decision. [AI workflow run ADD-03-run-host-20261015T140902Z-ab89 (route host, model claude-code headless (claude-opus-5-5)); PROPOSED; not reviewed] | Bid management | curated (proposed wording)
I-VOL-I-ENV-B | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): VOL-I 10.1: Envelope B holds 'only' Form 4-F and the Financial Model, yet 10.3 (model auditor's opinion) and 10.6 (financing assumptions schedule) need more documents; where they go is unstated | Legal | curated (proposed wording) | VOL-I-3.3-01; VOL-I-10.1-01; VOL-I-10.3-02; VOL-I-10.6-01; VOL-IV-F4F-01 | CQ-ENV-B-CONTENTS
I-VOL-I-ENV-A-PRICES | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): VOL-I 6.2 makes any price, rate or other commercial information in Envelope A non-responsive, but Form 4-B (Envelope A) asks for each reference's contract value in SAR | Legal | curated (proposed wording) | VOL-I-3.3-01; VOL-I-6.2-02; VOL-I-9.5-01; VOL-IV-F4B-01 | CQ-F4B-CONTRACT-VALUE
I-VOL-I-COPIES | Copy quantities are per Proposal (VOL-I 6.5: 'Each Proposal shall be submitted as' one marked original, three hard copies and one encrypted USB copy); settled. Open: how the single USB copy relates to the two separately sealed envelopes and how its means of decryption is given (draft question CQ-USB-PACKAGING) | Bid manager | curated (proposed wording) | VOL-I-6.5-01 | CQ-USB-PACKAGING
I-VOL-I-FILE-NAMES | The Financial Model must be in Microsoft Excel (VOL-I 10.3); settled. Open: how the Appendix 2 naming convention, which ends in '.pdf' and does not define [BIDDER] or the date in [YYYYMMDD], applies to it (draft question CQ-FILENAMES) | Bid manager | curated (proposed wording) | VOL-I-6.5-02; VOL-I-10.3-01 | CQ-FILENAMES
I-VOL-I-BOND-LONGSTOP | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): The VOL-I 12.2 periods (Commercial Close 120 days, Financial Close 270 days from the Preferred Bidder Notification) are unchanged: settled by ADD-02 Q13. Open: the Bid Bond's 180-day validity from the PDD (VOL-I 6.3) may end before the Financial Close long-stop, on which 12.2 lets the Authority call it; whether it must be extended to cover that period, and 'long-stop date' is undefined (draft question CQ-BOND-FC-COVERAGE) | Commercial lead | curated (proposed wording) | VOL-I-12.2-02 | CQ-BOND-FC-COVERAGE
I-VOL-I-APPENDICES | VOL-I 9.2 excludes 'the appendices expressly permitted by Volume II' from the page limit; none was found in the Volume II extract | Bid manager | curated (proposed wording) | VOL-I-9.2-01 | CQ-PAGE-LIMIT-APPENDICES
I-VOL-I-PAGE-LIMIT-Q2 | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): applied rule: VOL-I 9.2 as amended by ADD-02 2.1 'The Technical Proposal narrative shall not exceed one hundred and fifty (150) pages of A4, excluding the Form Sheets and the appendices expressly permitted by Volume II.'; a person confirms the application VOL-I 9.2 as amended by ADD-02 2.1 provides: 'The Technical Proposal narrative shall not exceed one hundred and fifty (150) pages of A4, excluding the Form Sheets and the appendices expressly permitted by Volume II.' (applied, not decided) Page limit: ADD-02 2.1 (p1) substitutes 'one hundred and fifty (150) pages' and leaves the other words of VOL-I 9.2 (p5) as printed (ADD-02 p1: 'All other terms of the RFP Documents remain unchanged.'). ADD-01 Q2 (p1), asked about the '120-page limit', answered 'The limit applies to the Technical Proposal narrative only. Form Sheets and the appendices permitted by Volume II are excluded.', words VOL-I 9.2 as amended still prints. Proposed basis: Q2's answer restates the clause's unchanged words, so it still holds at 150 pages; the Bid manager confirms the application (no decision recorded; A2 lists 9.2 for review after ADD-02 2.1; the undefined permitted appendices stay raised as CQ-PAGE-LIMIT-APPENDICES) | Bid manager | curated (proposed wording) | VOL-I-9.2-01
I-FORM-4E-COMMERCIAL-QUALIFICATION | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): Form 4-E and a qualification of a commercial term of Volume V. VOL-I 9.6 (p5): 'Form 4-E shall list every deviation, qualification or reservation to Volume V. A Proposal that states ‘no deviations’ in Form 4-E while containing a qualification elsewhere in the Proposal shall be treated as non-responsive.' Form 4-E is in Envelope A (VOL-I 9.1, p4: '(e) Form 4-E — Schedule of Deviations;'), and VOL-I 6.2 (p3): 'The appearance of any price, rate, or other commercial information within Envelope A shall render the Proposal non-responsive.' Stated in Envelope B instead, a qualification of a price meets VOL-I 10.5 (p5): 'Any conditional price, price subject to adjustment other than as provided in Volume V, or alternative price shall render the Proposal non-responsive.' and Form 4-F (VOL-IV p9): 'is not subject to any qualification'. Whether a qualification of a commercial term of Volume V can be made at all, and how Form 4-E words it without commercial information, is a decision for Legal counsel, with Commercial; no decision recorded and no question drafted. Raised by the Form 4-E check (A5 form_4e_checks, its commercial-qualification finding) | Legal counsel | curated (proposed wording) | VOL-IV-F4F-02 (the issue names the row (curated, PROPOSED)); VOL-IV-F4E-01 (the issue names the row (curated, PROPOSED)); VOL-I-9.6-01 (the issue names the row (curated, PROPOSED)); VOL-I-10.5-01 (the issue names the row (curated, PROPOSED)); VOL-I-6.2-02 (the issue names the row (curated, PROPOSED))
I-FORM-4E-CROSS-CHECK | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): How Form 4-E is cross-checked against the rest of the Proposal. VOL-I 9.6 (p5): 'A Proposal that states ‘no deviations’ in Form 4-E while containing a qualification elsewhere in the Proposal shall be treated as non-responsive.' The Form 4-E check (A5 form_4e_checks, its cross-check finding) lists the Proposal documents that are final only after Form 4-E starts, so a qualification in them cannot be checked against its declaration, and computes whether making Form 4-E wait for all of them is feasible on the assumed durations (INFEASIBLE on the programme of 7 Oct 2026). How the cross-check is done (a later final read of every document, a different order, or a change of a lead time) is a decision for the Bid manager, with Legal; no decision recorded; no duration, setting or dependency is changed | Bid manager | curated (proposed wording) | VOL-IV-F4E-01 (the issue names the row (curated, PROPOSED)); VOL-I-9.6-01 (the issue names the row (curated, PROPOSED))
I-VOL-II-MISSING | Not in the pack: the Environmental and Social Impact Assessment (ESIA; VOL-II 9.1) and the geotechnical report (ADD-01 Q4), both 'in the data room'; tie-in points (1.3); asset register format (7.4). ESIA compliance and ground risk unverifiable | Technical lead | curated (proposed wording) | VOL-II-1.3-01; VOL-II-5.4-01; VOL-II-7.4-01; VOL-II-9.1-01 | CQ-VOL-III-DRAWINGS
I-VOL-II-T24-TENSIONS | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): The printed qualifier is confirmed (owner, 3 Oct 2026): 'all values are maxima; compliance assessed as a 30-day rolling average unless stated'. Unresolved: how it interacts with the chlorine (0.5-1.0 mg/l) and pH (6.0-9.0) ranges, and a chlorine residual 'continuous at outlet' vs UV-only disinfection or dechlorination allowed by VOL-II 3.3 (draft question CQ-T24-RANGES). Each parameter keeps its own printed basis of assessment; the 'at all times' reading is I-VOL-II-AT-ALL-TIMES, and the point at which compliance is assessed is I-VOL-II-COMPLIANCE-POINT | Process engineer | curated (proposed wording) | VOL-II-2.4-01; VOL-II-T2-4-ResidualChlorine; VOL-II-T2-4-pH; VOL-II-3.3-01; VOL-II-3.1-01 (via REL-T24-PROCESS-DESIGN (confirmed)); VOL-II-7.2-01 (via REL-T24-RELIABILITY-RUN (confirmed)); VOL-V-31.1-02 (via REL-T24-UNAVAILABILITY (confirmed)); VOL-II-4.3-02 (via REL-T24-COMPLIANCE-MONITORING-STREAMS (confirmed)); VOL-II-2.5-01 (via REL-T24-CONTINUOUS-MONITORING (confirmed)) | CQ-T24-RANGES
I-VOL-V-MISSING | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): VOL-V is an extract: omitted clauses, Schedules 7 (deductions), 9 (indexation), 11 (defaults), 12 (termination sums) and the Direct Agreement are not supplied, yet unlisted deviations are accepted | Legal counsel | curated (proposed wording) | VOL-V-NOTE-01; VOL-V-31.1-01; VOL-V-31.1-02; VOL-V-31.1-03; VOL-V-39.1-01; VOL-V-31.4-01 (via REL-MISSING-SCHEDULE-11-PERSISTENT-BREACH (proposed)); VOL-IV-F4E-01 (via REL-MISSING-SCHEDULE-11-LATE-COMPLETION > REL-VOL-V-FORM-4E (confirmed); via REL-MISSING-SCHEDULE-11-PERSISTENT-BREACH > REL-VOL-V-FORM-4E (proposed)) | CQ-VOL-V-SCHEDULES
I-VOL-V-PERSISTENT-BREACH | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): VOL-V 31.4: 'on a second occurrence' is not defined (a second persistent breach, or a further event after the remediation plan); the termination right in 39.3 turns on it | Legal counsel | curated (proposed wording) | VOL-V-31.4-01; VOL-IV-F4E-01 (via REL-MISSING-SCHEDULE-11-PERSISTENT-BREACH > REL-VOL-V-FORM-4E (proposed)) | CQ-PERSISTENT-BREACH
I-VOL-II-AT-ALL-TIMES | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): 'at all times' (VOL-II 2.4) vs Table 2-4 assessment bases. Proposed reading (not decided): Table 2-4 gives a basis of assessment for each parameter and a general qualifier, and VOL-II 2.4 requires that the treated effluent 'shall at all times comply with the parameters set out in Table 2-4'; the assistant reads the two together as continuous compliance on each parameter's printed basis. Whether that reading holds is for the Process engineer; no decision recorded (the ranges and the reliability run are raised separately: CQ-T24-RANGES, CQ-PCOD-RELIABILITY-RUN) | Process engineer | curated (proposed wording) | VOL-II-2.4-01; VOL-II-3.1-01 (via REL-T24-PROCESS-DESIGN (confirmed)); VOL-II-7.2-01 (via REL-T24-RELIABILITY-RUN (confirmed)); VOL-V-31.1-02 (via REL-T24-UNAVAILABILITY (confirmed)); VOL-V-29.3-01 (via REL-T24-RAMP-UP-DEDUCTIONS (confirmed)); VOL-II-4.3-02 (via REL-T24-COMPLIANCE-MONITORING-STREAMS (confirmed)); VOL-II-2.5-01 (via REL-T24-CONTINUOUS-MONITORING (confirmed))
I-VOL-II-COMPLIANCE-POINT | OPEN — REVIEW ASSUMED FOR DEMO (no observed human decision): The point at which Table 2-4 compliance is assessed. The pack prints three candidates: the table title 'Minimum Effluent Quality Parameters at the Point of Discharge' (VOL-II p3, the Table 2-4 image); 'Continuous at outlet' (the basis of assessment of Residual Chlorine and pH, VOL-II p3); and 'the delivery point shown on Drawing 03-C-114' (VOL-II 5.1, p4; the end of the 18 km treated effluent main), on a drawing of Volume III, which is not supplied. Which point governs, and whether to raise it with the Authority before the clarification cut-off, is for the Process engineer; no decision recorded and no question drafted | Process engineer | curated (proposed wording) | VOL-II-T2-4-TN; VOL-II-T2-4-BOD5; VOL-II-T2-4-COD; VOL-II-T2-4-TSS; VOL-II-T2-4-TP; VOL-II-T2-4-Turbidity; VOL-II-T2-4-FaecalColiforms; VOL-II-T2-4-ResidualChlorine; VOL-II-T2-4-pH; VOL-II-T2-4-OilGrease; VOL-II-5.1-01; VOL-II-3.1-01 (via REL-T24-PROCESS-DESIGN (confirmed)); VOL-II-7.2-01 (via REL-T24-RELIABILITY-RUN (confirmed)); VOL-V-31.1-02 (via REL-T24-UNAVAILABILITY (confirmed)); VOL-V-29.3-01 (via REL-T24-RAMP-UP-DEDUCTIONS (confirmed)); VOL-II-2.4-01 (via REL-T24-COMPLIANCE-MONITORING-STREAMS (confirmed)); VOL-II-4.3-02 (via REL-T24-COMPLIANCE-MONITORING-STREAMS (confirmed)); VOL-II-2.5-01 (via REL-T24-CONTINUOUS-MONITORING (confirmed))
I-VOL-IV-SCALE | ADD-02 note (3) to Table 1-1: marks on the Authority's 'standard five-point scale' multiplied by 'the weight shown'; the scale is not in the pack and the table shows Marks, not weights | Bid manager | curated (proposed wording) | ADD-02-T1-1-N3-01 | CQ-SCORING-METHOD
I-AUTO-NOT-SUPPLIED-ENVIRONMENTAL-PERMIT | the Environmental Permit issued for the site is referenced but not supplied (referenced in VOL-II 2.4, VOL-II T2-4-heading/para1). Without it these conclusions cannot be established: VOL-II-2.4-01, VOL-II-T2-4-BOD5, VOL-II-T2-4-COD, VOL-II-T2-4-TSS, VOL-II-T2-4-TN, VOL-II-T2-4-TP, VOL-II-T2-4-Turbidity, VOL-II-T2-4-FaecalColiforms, VOL-II-T2-4-ResidualChlorine, VOL-II-T2-4-pH, VOL-II-T2-4-OilGrease, VOL-II-T2-4-NOTE1 (REL-MISSING-ENVIRONMENTAL-PERMIT, link confirmed): that the reproduced Table 2-4 limits, as amended by the addenda, are the limits that govern (the Permit prevails over the reproduction), and the limit of any parameter not listed (Note 1); Permit compliance is not claimed [context (not binding): ADD-01:AppB/item-5-effluent-standards p4 'the permit was under review by the regulator and that any change would be issued by Addendum.' (pre-bid minutes; they do not bind the Authority (ADD-01 3.2, p1))]. Linked open issues: I-PERMIT. Not a prerequisite for completing the bid; a person decides whether to raise a clarification or reserve the position | Technical | relationships (automatic) | VOL-II-2.4-01; VOL-II-T2-4-BOD5; VOL-II-T2-4-COD; VOL-II-T2-4-FaecalColiforms; VOL-II-T2-4-NOTE1; VOL-II-T2-4-OilGrease; VOL-II-T2-4-ResidualChlorine; VOL-II-T2-4-TN; VOL-II-T2-4-TP; VOL-II-T2-4-TSS; VOL-II-T2-4-Turbidity; VOL-II-T2-4-pH
I-AUTO-NOT-SUPPLIED-VOL-V-SCHEDULE-11 | Volume V Schedule 11 (Project Company Events of Default) is referenced but not supplied (referenced in VOL-V 39.1). Without it these conclusions cannot be established: VOL-V-39.1-01 (REL-MISSING-SCHEDULE-11-DEFAULTS, link confirmed): which events are Project Company Events of Default, so how to avoid them and whether to reserve the position in Form 4-E; VOL-V:18.2 (REL-MISSING-SCHEDULE-11-LATE-COMPLETION, link confirmed): whether late completion short of the VOL-V 18.3 long-stop is itself an Event of Default giving a termination right under 39.1, so whether delay liquidated damages are in practice the only remedy for late completion; VOL-V-31.4-01, VOL-V:39.3 (REL-MISSING-SCHEDULE-11-PERSISTENT-BREACH, link proposed): whether persistent breach (three or more Unavailability Events in a rolling 90 days) is also an Event of Default listed in Schedule 11, giving a termination right under 39.1 independent of 31.4 and 39.3; so an amendment or deletion of 31.4 or 39.3 cannot be concluded to remove that exposure. Linked open issues: I-VOL-V-MISSING, I-VOL-V-PERSISTENT-BREACH. Not a prerequisite for completing the bid; a person decides whether to raise a clarification or reserve the position | Legal counsel | relationships (automatic) | VOL-V-31.4-01; VOL-V-39.1-01
I-AUTO-NOT-SUPPLIED-VOL-V-SCHEDULE-7 | Volume V Schedule 7 (deductions) is referenced but not supplied (referenced in VOL-V 31.2). Without it these conclusions cannot be established: VOL-V-31.1-01, VOL-V-31.1-02, VOL-V-31.1-03 (REL-MISSING-SCHEDULE-7-DEDUCTIONS, link confirmed): the amount of the deduction for each Unavailability Event under 31.1(a), (b) and (c), so the price risk of each. Linked open issues: I-VOL-V-MISSING. Not a prerequisite for completing the bid; a person decides whether to raise a clarification or reserve the position | Legal counsel | relationships (automatic) | VOL-V-31.1-01; VOL-V-31.1-02; VOL-V-31.1-03
I-AUTO-PRINTED-AppA-proposal-due-date | ADD-01:AppA/proposal-due-date prints the Proposal Due Date as 2026-11-12; the effective date (VOL-I:6.1) is 2026-11-26. Not corrected: a person decides what to print and sign, and whether to seek clarification | Legal | C31 (automatic)
I-OP-ADD-01/Q4 | ADD-01/Q4: the geotechnical report and the wadi-crossing drawing (Volume III) are referenced but not supplied | Bid manager | amendment op
I-OP-ADD-01/AppA/para1 | ADD-01/AppA/para1: the reissued form may differ from the original in more than its stated purpose; compare. It prints 'Proposal Due Date: 12 November 2026, 14:00 Riyadh time' (ADD-01 App A p3) while ADD-01 2.1 (p1) substitutes 'Thursday 26 November 2026' in VOL-I 6.1; not corrected (a person decides: I-F4A-FIELDS) | Bid manager | amendment op
I-OP-ADD-02/T1-1-rev/note(2) | ADD-02/T1-1-rev/note(2): the addendum restates the value without quoting the old words; the old words were located in the target by shape and need a person's check | Bid manager | amendment op
I-OP-ADD-02/T1-1-rev/note(3) | ADD-02/T1-1-rev/note(3): the 'standard five-point scale' is not defined in the pack and the table shows Marks, not weights | Bid manager | amendment op
I-OP-ADD-02/Q7 | ADD-02/Q7: which clause governs the concession term is not stated by the Authority and is a decision for a person (Legal, I-CONCESSION; draft question CQ-CONCESSION-TERM), with what to record in Form 4-E under the Volume V note and how 'the term' in VOL-V 3.2 and 42.2 reads; no decision recorded | Bid manager | amendment op
I-OP-ADD-02/Q11 | ADD-02/Q11: follow-up only (clarification CQ-DWF-STORM-FLOW): 'dry weather flow' in Table 2-6 row 2-6.4 is not defined, so the storm flow to be passed to full treatment is unclear | Bid manager | amendment op
I-OP-ADD-02/7.1 | ADD-02/7.1: re-lettering of the items after (e) is not stated | Bid manager | amendment op
I-PARTIAL-ADD-03 | ADD-03 is PARTIAL: unresolved provisions ['ADD-03:2.2', 'ADD-03:4.3']; invalid ops none; ops withheld after a person's rejection none. The validated state stays at ADD-02 | Bid manager | C20/C21-C27 and review decisions (automatic)
I-AUTO-SUMMARY-ADD-01 | ADD-01's cover summary does not match its provisions (C28): [omitted] ADD-01/3.1 adds an obligation (ADD-01:3.1); the summary does not mention it: 'The attendance record is held by the Authority. A Bidder that considers its attendance to have been incorrectly recorded shall notify the Authority through the Portal within five (5) Working Days of this Addendum.'; [omitted] ADD-01/AppA/para1 replaces VOL-IV:F4-A; the summary does not mention it: 'Form 4-A is reissued below to add the acknowledgement of Addenda at paragraph 1. Bidders shall use this version.'. The summary is never applied; a person decides whether to raise a clarification | Bid manager | C28 (automatic)
I-AUTO-SUMMARY-ADD-02 | ADD-02's cover summary does not match its provisions (C28): [consequence not mentioned] ADD-02:7.2 states 'Failure to submit Form 4-G shall render the Proposal non-responsive.'; the summary says only 'adds Form 4-G'; [understated] 'reinstates Volume I Clause 8.6', but ADD-02/9.1 reinstates it in an amended form: 'The Bidder shall submit a Local Content Certificate issued by the competent authority evidencing a local content ratio of not less than thirty-five per cent (35%) for the construction phase. Failure …' (as issued: 'The Bidder shall submit a Local Content Certificate issued by the competent authority evidencing a local content ratio of not less than thirty per cent (30%) f…'); [consequence not mentioned] ADD-02:9.1 states 'Failure to submit the certificate shall render the Proposal non-responsive.'; the summary says only 'reinstates Volume I Clause 8.6'; [omitted] ADD-02/T1-1-rev/note(2) amends VOL-I:11.2; the summary does not mention it: '(2) The combined score weighting stated in Volume I Clause 11.2 is amended to sixty-five per cent (65%) technical and thirty-five per cent (35%) commercial.'; [omitted] ADD-02/5.2 adds an obligation (VOL-II:S3); the summary does not mention it: 'Bidders shall reflect the amended limit in the process design submitted under Volume II Section 3.'; [omitted] ADD-02/9.2 ends the effect of ADD-01:4.2; the summary does not mention it: 'Section 4.2 of Addendum No. 1 ceases to have effect.'. The summary is never applied; a person decides whether to raise a clarification | Bid manager | C28 (automatic)
I-AUTO-SUMMARY-ADD-03 | ADD-03's cover summary does not match its provisions (C28): [not found] 'withdraws Form 4-G': no provision of ADD-03 does this; [not found] 'adds a new Clause 11.6': no provision of ADD-03 does this; [understated] 'responds to clarification requests 15 to 18', but ADD-03/Q17 adds an obligation (ADD-03:Q17): 'Bidders shall price the Project as amended by this Addendum.'; [omitted] ADD-03/3.1(a) ends the effect of ADD-02:7.2; the summary does not mention it: 'Form 4-G (Cybersecurity Compliance Undertaking), added by Addendum No. 2 Section 7, is withdrawn. Bidders shall disregard it and shall not submit it. Section 7.2 of Addendum No. 2 ceases to have effect.'; [omitted] ADD-03/5.1 amends VOL-I:6.4; the summary does not mention it: 'In Volume I Clause 6.4, ‘SAR 4,500,000 (four million five hundred thousand Saudi Riyals)’ is deleted and ‘SAR 5,600,000 (five million six hundred thousand Saudi Riyals)’ is substituted.'; [omitted] ADD-03/5.2(a) amends VOL-I:6.3; the summary does not mention it: 'In Volume I Clause 6.3, ‘one hundred and eighty (180) days’ is deleted and ‘two hundred and ten (210) days’ is substituted. The Proposal validity period in Clause 7.1 is unchanged.'; [omitted] ADD-03/5.2(b) confirms VOL-I:7.1; the summary does not mention it: 'In Volume I Clause 6.3, ‘one hundred and eighty (180) days’ is deleted and ‘two hundred and ten (210) days’ is substituted. The Proposal validity period in Clause 7.1 is unchanged.'; [omitted] ADD-03/6.1 inserts new text after VOL-I:11.5; the summary does not mention it: 'A new Clause 11.6 is added to Volume I: ‘11.6 Where, on completion of the combined evaluation, two or more Proposals are within two per cent (2%) of one another, the Authority may apply such further criteria as it considers appropriate to …'. The summary is never applied; a person decides whether to raise a clarification | Bid manager | C28 (automatic)
I-AUTO-COUNTING | Counting conventions not stated in the pack for ATTENDANCE-NOTICE (ADD-01 3.1), BID-BOND-VALIDITY (VOL-I 6.3), PROPOSAL-VALIDITY (VOL-I 7.1), PROPOSAL-VALIDITY-F4A (Form 4-A), REFERENCE-LOOKBACK (VOL-I 8.5): every reading is shown (A1 Dates); planning uses the conservative reading (config/assumptions.yaml) | Bid manager | D4 (automatic)
I-A5-lcc-ratio | A5 lcc-ratio: INFEASIBLE by 12 WD (total float -12 WD: latest start 2026-10-06 is before the planning date 2026-10-22; not compressed) (VOL-I-8.6-01; duration 5 WD is an ASSUMPTION: lcc_ratio_calc) | Commercial | A5 (automatic) | VOL-I-8.6-01
I-A5-attendance-notice | A5 attendance-notice: CONDITIONAL — window elapsed 2026-10-14; whether the condition arose is not known (ATTENDANCE-NOTICE = 2026-10-14 is before the planning date 2026-10-22; needed only if the Bidder considers its attendance at the Pre-Bid Conference to have been incorrectly recorded (ADD-01 3.1); an elapsed window alone does not establish a missed duty: a person records whether the condition arose and, if it did, what was done) (ADD-01-3.1-01, VOL-I-5.4-01; duration 2 WD is an ASSUMPTION: clarification_drafting) | Bid management | A5 (automatic) | ADD-01-3.1-01; VOL-I-5.4-01
I-A5-lcc-certificate | A5 lcc-certificate: INFEASIBLE by 12 WD (total float -12 WD: latest start 2026-10-13 is before the planning date 2026-10-22; not compressed) (VOL-I-8.6-01; duration 30 WD is an ASSUMPTION: lcc_certificate) | Commercial | A5 (automatic) | VOL-I-8.6-01
I-A5-assemble-envelope-a | A5 assemble-envelope-a: INFEASIBLE by 12 WD (total float -12 WD: earliest start 2026-12-10 (after lcc-certificate) is after the latest start 2026-11-24; not compressed) (VOL-I-6.1-01, VOL-I-6.2-01, VOL-I-6.2-02, VOL-I-9.1-01, VOL-I-App3-01; duration 1 WD is an ASSUMPTION: envelope_assembly) | Bid management | A5 (automatic) | VOL-I-6.1-01; VOL-I-6.2-01; VOL-I-6.2-02; VOL-I-9.1-01; VOL-I-App3-01
I-A5-copies | A5 copies: INFEASIBLE by 12 WD (total float -12 WD: earliest start 2026-12-13 (after assemble-envelope-a) is after the latest start 2026-11-25; not compressed) (VOL-I-6.1-01, VOL-I-6.2-01, VOL-I-6.5-01, VOL-I-6.5-02, VOL-I-9.1-01, VOL-I-App3-01; duration 1 WD is an ASSUMPTION: copies_and_usb) | Bid management | A5 (automatic) | VOL-I-6.1-01; VOL-I-6.2-01; VOL-I-6.5-01; VOL-I-6.5-02; VOL-I-9.1-01; VOL-I-App3-01
I-A5-seal-and-mark | A5 seal-and-mark: INFEASIBLE by 12 WD (total float -12 WD: earliest start 2026-12-13 (after copies) is after the latest start 2026-11-25; not compressed) (VOL-I-6.1-01, VOL-I-6.2-01, VOL-I-9.1-01, VOL-I-App3-01; duration 0 WD is an ASSUMPTION: seal_and_mark) | Bid management | A5 (automatic) | VOL-I-6.1-01; VOL-I-6.2-01; VOL-I-9.1-01; VOL-I-App3-01
I-A5-deliver | A5 deliver: INFEASIBLE by 12 WD (total float -12 WD: earliest start 2026-12-14 (after seal-and-mark) is after the latest start 2026-11-26; not compressed) (VOL-I-6.1-01, VOL-I-6.2-01, VOL-I-9.1-01, VOL-I-App3-01; duration 1 WD is an ASSUMPTION: delivery) | Bid management | A5 (automatic) | VOL-I-6.1-01; VOL-I-6.2-01; VOL-I-9.1-01; VOL-I-App3-01
I-A5-FEASIBILITY | A5 at the status date: lcc-ratio INFEASIBLE by 12 WD; lcc-certificate INFEASIBLE by 12 WD; assemble-envelope-a INFEASIBLE by 12 WD; copies INFEASIBLE by 12 WD; seal-and-mark INFEASIBLE by 12 WD; deliver INFEASIBLE by 12 WD. Lead times are PROVISIONAL assumptions (A5 drivers) | Bid manager | A5 (automatic) | VOL-I-6.1-01; VOL-I-6.2-01; VOL-I-6.2-02; VOL-I-6.5-01; VOL-I-6.5-02; VOL-I-8.6-01; VOL-I-9.1-01; VOL-I-App3-01

## Relationships
Relationship status: confirmed = stated in the documents (the entry quotes the cross-reference), not confirmed by a person; proposed = inferred by a curator or a model, a person decides; possible = a weaker inference.
Id | Kind | Status | Class | From | To | Scope | Evidence | Basis | Note | Document | Blocks | Issues | Origin | Review | Reached
REL-MEMBER-FIN-STANDING | member_scope | confirmed | confirmed dependency | VOL-I:8.1; words:member of the Bidder; words:consortium member; words:member of the consortium | VOL-I-8.4-01; VOL-I-8.4-02; calc:financial-standing |  | VOL-I:8.4 p4: “on a combined basis across consortium members weighted by shareholding”; VOL-I:8.1 p4: “No change to the composition, shareholding or lead member of a prequalified consortium shall be effective without the prior written consent of the Authority.” |  | The financial standing is combined across the members and weighted by shareholding: a member added, removed or re-weighted changes the calculation (the members and their shares are bidder facts, I-BIDDER-FACTS). |  |  | I-BIDDER-FACTS | curator | proposed
REL-MEMBER-FORM-4C | member_scope | confirmed | confirmed dependency | VOL-I:8.1; words:member of the Bidder; words:consortium member; words:member of the consortium | VOL-I-9.4-01; VOL-IV-F4C-N1 |  | VOL-I:9.4 p5: “signed and stamped by an authorised signatory of each member of the Bidder”; VOL-I:9.4 p5: “Failure to submit a complete and properly executed Form 4-C for each member shall render the Proposal non-responsive.”; VOL-IV:F4-C/image/note p6: “يجب تقديم هذا النموذج باللغة العربية عن كل عضو من أعضاء الائتلاف” |  | One Form 4-C per member: a new member gives its own (in Arabic, signed and stamped by its authorised signatory). |  |  | I-BIDDER-FACTS | curator | proposed
REL-MEMBER-MULTIPLE-PARTICIPATION | member_scope | confirmed | confirmed dependency | VOL-I:8.1; words:member of the Bidder; words:consortium member; words:member of the consortium | VOL-I-8.2-01; VOL-IV-F4C-02 |  | VOL-I:8.2 p4: “No firm, and no affiliate of a firm, shall participate in more than one Proposal.”; VOL-IV:F4-C/image/intro p6: “بصفتنا ممثلين مفوضين عن العضو المذكور أدناه في ائتلاف مقدم العرض”; VOL-IV:F4-C/image/decl2 p6: “أن الشركة لم تشارك، بصورة مباشرة أو غير مباشرة، في أكثر من عرض واحد لهذه المناقصة” |  | Each member declares in its Form 4-C (declaration 2, given for 'the member named below') that it has not taken part in more than one proposal: a new member, and its affiliates, must be checked against VOL-I 8.2. |  |  | I-BIDDER-FACTS | curator | proposed
REL-MEMBER-DEBARMENT | member_scope | confirmed | confirmed dependency | VOL-I:8.1; words:member of the Bidder; words:consortium member; words:member of the consortium | VOL-I-8.10-01; VOL-IV-F4C-03 |  | VOL-I:8.10 p4: “No member of the Bidder shall be the subject of, or have been the subject of within the preceding five (5) years, any debarment by a public authority in the Kingdom.”; VOL-I:8.10 p4: “A declaration to this effect shall be given in Form 4-C.” |  |  |  |  | I-BIDDER-FACTS | curator | proposed
REL-MEMBER-INVESTMENT-LICENCE | member_scope | confirmed | confirmed dependency | VOL-I:8.1; words:member of the Bidder; words:consortium member; words:member of the consortium | VOL-I-8.9-01 |  | VOL-I:8.9 p4: “evidence of a current investment licence for each foreign consortium member” |  | Whether a new member is foreign is a bidder fact (bidder.foreign_members is a labelled assumption). |  |  | I-BIDDER-FACTS | curator | proposed
REL-T24-PROCESS-DESIGN | limit_applies | confirmed | confirmed dependency | VOL-II:T2-4 | VOL-II-3.1-01 |  | VOL-II:3.1 p3: “The treatment process shall be capable of achieving the effluent quality in Table 2-4 under all design influent conditions in Table 2-2.” |  | A changed limit, unit or basis of assessment changes what the process design must achieve. The qualifier 'all values are maxima' and the chlorine and pH ranges stay an open question (I-VOL-II-T24-TENSIONS). |  |  | I-VOL-II-T24-TENSIONS | curator | proposed | ADD-02; ADD-03
REL-T24-RELIABILITY-RUN | limit_applies | confirmed | confirmed dependency | VOL-II:T2-4 | VOL-II-7.2-01 |  | VOL-II:7.2 p4: “during which every parameter in Table 2-4 has been met”; VOL-II:7.3 p4: “A failure of any Table 2-4 parameter during the reliability run shall restart the run in full.” |  | The 30-day reliability run before PCOD must meet every Table 2-4 parameter as amended; a failure restarts it in full. |  |  | I-VOL-II-T24-TENSIONS | curator | proposed | ADD-02; ADD-03
REL-T24-UNAVAILABILITY | limit_applies | confirmed | confirmed dependency | VOL-II:T2-4 | VOL-V-31.1-02 |  | VOL-V:31.1 p3: “(b) the treated effluent fails any parameter in Volume II Table 2-4” |  | After PCOD a failure of any Table 2-4 parameter is an Unavailability Event (VOL-V 31.1(b)), with deductions and no cure period. |  |  | I-VOL-II-T24-TENSIONS | curator | proposed | ADD-02; ADD-03
REL-T24-RAMP-UP-DEDUCTIONS | limit_applies | confirmed | confirmed dependency | VOL-II:T2-4 | VOL-V-29.3-01 | rolling average (verbatim in its evidence; members in scope: BOD5, COD, TN, TP, TSS) (scope PROPOSED, not reviewed; the owner may keep the issue on the row) | VOL-V:29.3 p3: “no availability deduction shall apply to a parameter listed in Table 2-4 as assessed on a rolling average basis” |  | The second limb of 29.3 turns on which parameters Table 2-4 assesses on a rolling average: a changed basis of assessment changes the Ramp-Up relief. |  |  | I-VOL-II-T24-TENSIONS | curator | proposed | ADD-02; ADD-03
REL-T24-COMPLIANCE-MONITORING-STREAMS | limit_applies | confirmed | confirmed dependency | VOL-II:T2-4 | VOL-II-2.4-01; VOL-II-4.3-02 |  | VOL-II:2.4 p2: “The treated effluent shall at all times comply with the parameters set out in Table 2-4.”; VOL-II:4.3 p4: “such that the Facility can meet Table 2-4 with any one stream out of service” |  |  |  |  | I-VOL-II-T24-TENSIONS | curator | proposed | ADD-02; ADD-03
REL-T24-CONTINUOUS-MONITORING | limit_applies | confirmed | confirmed dependency | VOL-II:T2-4 | VOL-II-2.5-01 | continuous (verbatim in its evidence; members in scope: ResidualChlorine, pH) (scope PROPOSED, not reviewed; the owner may keep the issue on the row) | VOL-II:2.5 p2: “continuous online monitoring for those parameters identified in Table 2-4 as assessed on a continuous basis” |  | VOL-II 2.5 monitors the parameters Table 2-4 assesses on a continuous basis: a changed basis of assessment, or a changed limit of a continuously assessed parameter, changes what is monitored online. |  |  | I-VOL-II-T24-TENSIONS | curator | proposed
REL-PAY-MECHANISM | feeds_calculation | confirmed | confirmed dependency | VOL-V:29.1; VOL-V:29.2; VOL-V:29.3; VOL-V:29.4; VOL-V:29.5 | calc:availability-payment |  | VOL-V:1.1 p2: “Availability Payment means the annual payment calculated under Clause 29 and adjusted under Clause 31.”; VOL-V:H:C29 p3: “CLAUSE 29 — PAYMENT MECHANISM” |  | Every sub-clause of Clause 29 is part of the payment mechanism the Availability Payment is calculated under (the Ramp-Up payment of 29.3 included). |  |  |  | curator | proposed | ADD-01
REL-PAY-DEDUCTIONS | depends_on | proposed | proposed relationship | VOL-V:31.1; VOL-V:31.2; VOL-V:31.3; VOL-V:31.4; VOL-V:31.5 | calc:availability-payment |  | VOL-V:1.1 p2: “Availability Payment means the annual payment calculated under Clause 29 and adjusted under Clause 31.”; VOL-I:10.2 p5: “calculated in accordance with the payment mechanism at Volume V Clause 29” | The definition says the Availability Payment is adjusted under Clause 31, but the price quoted under VOL-I 10.2 is calculated under Clause 29 only: whether a change to the deductions changes the quoted price, or only the risk priced into it, is a commercial judgement (inferred, not stated). |  |  |  |  | curator | proposed
REL-PAY-QUOTED-PRICE | feeds_calculation | confirmed | confirmed dependency | calc:availability-payment | VOL-I-10.2-01 |  | VOL-I:10.2 p5: “The Bidder shall quote a single Availability Payment expressed in Saudi Riyals per annum, calculated in accordance with the payment mechanism at Volume V Clause 29.” | [5 empty] | curator | proposed | ADD-01
REL-PAY-FORM-4F | feeds_calculation | confirmed | confirmed dependency | calc:availability-payment | VOL-IV-F4F-01 |  | VOL-IV:F4-F/availability-payment-sar-per-annum-year-1-of-operations p9: “Availability Payment (SAR per annum, year 1 of operations):”; VOL-IV:F4-F/indexation-basis-assumed p9: “Indexation basis assumed: Per Volume V Clause 29.2” | [5 empty] | curator | proposed | ADD-01
REL-PAY-FINANCIAL-MODEL | depends_on | proposed | proposed relationship | calc:availability-payment | VOL-I-10.3-01 |  | VOL-IV:F4-F/para1 p9: “has been derived from the Financial Model submitted with this Form”; VOL-I:10.2 p5: “calculated in accordance with the payment mechanism at Volume V Clause 29” | Form 4-F states that the Availability Payment is derived from the Financial Model, and VOL-I 10.2 that it is calculated under the payment mechanism of Volume V Clause 29; so the model must reproduce Clause 29 (the Ramp-Up payment of 29.3 included). That a change to Clause 29 requires the model to be re-run is the curator's inference, not a stated link. | Reaches the Envelope B modelling activities (fin-model-build, fin-model-freeze) through the row's evidence item (EV-FIN-MODEL). |  |  |  | curator | proposed | ADD-01
REL-MODEL-FORM-4F | feeds_calculation | confirmed | confirmed dependency | VOL-I-10.3-01 | VOL-IV-F4F-02 |  | VOL-IV:F4-F/para1 p9: “We confirm that the Availability Payment stated above is unconditional, is not subject to any qualification, and has been derived from the Financial Model submitted with this Form.” | [5 empty] | curator | proposed | ADD-01; ADD-02
REL-PAY-FINANCING-ASSUMPTIONS | depends_on | possible | possible impact | calc:availability-payment | VOL-I-10.6-01 |  | VOL-I:10.6 p5: “a schedule of the principal financing assumptions underlying the Availability Payment” | The schedule states the financing assumptions underlying the Availability Payment; whether a change to the payment mechanism changes them (for example debt sized on the Ramp-Up revenue) is a commercial judgement. |  |  |  |  | curator | proposed | ADD-01
REL-LCC-ENVELOPE-A | cites | confirmed | confirmed dependency | VOL-I:8.6 | VOL-I:9.1(i) |  | VOL-I:9.1(i) p4: “(i) the certificates and evidence required under Section 8.”; VOL-I:8.6 p4: “The Bidder shall submit a Local Content Certificate issued by the competent authority” |  | Item (i) of the Envelope A list is whatever Section 8 requires: the Local Content Certificate leaves it when ADD-01 4.1 deletes VOL-I 8.6 and returns when ADD-02 9.1 reinstates 8.6 at 35%. |  |  | I-LCC-ISSUER | curator | proposed | ADD-01; ADD-02
REL-VOL-V-FORM-4E | depends_on | confirmed | confirmed dependency | VOL-V:1.1; VOL-V:1.2; VOL-V:1.3; VOL-V:1.4; VOL-V:1.5; VOL-V:1.6; VOL-V:3.1; VOL-V:3.2; VOL-V:3.3; VOL-V:12.1; VOL-V:12.2; VOL-V:12.3; VOL-V:12.4; VOL-V:18.1; VOL-V:18.2; VOL-V:18.3; VOL-V:18.4; VOL-V:24.1; VOL-V:24.2; VOL-V:24.3; VOL-V:24.4; VOL-V:29.1; VOL-V:29.2; VOL-V:29.3; VOL-V:29.4; VOL-V:29.5; VOL-V:31.1; VOL-V:31.2; VOL-V:31.3; VOL-V:31.4; VOL-V:31.5; VOL-V:34.1; VOL-V:34.2; VOL-V:34.3; VOL-V:36.1; VOL-V:36.2; VOL-V:36.3; VOL-V:39.1; VOL-V:39.2; VOL-V:39.3; VOL-V:39.4; VOL-V:39.5; VOL-V:40.1; VOL-V:40.2; VOL-V:40.3; VOL-V:42.1; VOL-V:42.2; VOL-V:44.1; VOL-V:44.2; VOL-V:44.3 | VOL-IV-F4E-01 |  | VOL-V:cover/note-to-bidders p2: “This extract contains the clauses of the draft Project Agreement on which the Authority invites comment through Form 4-E.”; VOL-V:cover/note-to-bidders p2: “A deviation not listed in Form 4-E will be taken as accepted.” |  | A changed Volume V clause (ADD-02 8.1: VOL-V 36.2, SAR 5,000,000 to SAR 2,500,000) is a clause on which Form 4-E invites comment: whether to list a deviation from it is re-read; what to list is for Legal. |  |  |  | curator | proposed | ADD-01; ADD-02
REL-CHANGE-IN-LAW-FINANCIAL-MODEL | depends_on | possible | possible impact | VOL-V:36.2 | VOL-I-10.3-01 |  |  | VOL-V 36.2 sets the capital expenditure a General Change in Law must exceed before the Project Company is compensated (SAR 2,500,000 after ADD-02 8.1); no clause links it to the Financial Model, and whether the model prices the retained Change in Law risk is a commercial judgement (inferred, not stated). |  |  |  |  | curator | proposed | ADD-02
REL-MISSING-SCHEDULE-11-DEFAULTS | missing_document | confirmed | confirmed dependency | VOL-V:39.1 | VOL-V-39.1-01 |  | VOL-V:39.1 p4: “The Authority may terminate for a Project Company Event of Default, being the events listed in Schedule 11.” |  |  | Volume V Schedule 11 (Project Company Events of Default) | which events are Project Company Events of Default, so how to avoid them and whether to reserve the position in Form 4-E | I-VOL-V-MISSING | curator | proposed
REL-MISSING-SCHEDULE-11-LATE-COMPLETION | missing_document | confirmed | confirmed dependency | VOL-V:39.1 | VOL-V:18.2 |  | VOL-V:18.2 p2: “without prejudice to its termination rights under Clause 39”; VOL-V:39.1 p4: “being the events listed in Schedule 11” |  |  | Volume V Schedule 11 (Project Company Events of Default) | whether late completion short of the VOL-V 18.3 long-stop is itself an Event of Default giving a termination right under 39.1, so whether delay liquidated damages are in practice the only remedy for late completion | I-VOL-V-MISSING | curator | proposed
REL-MISSING-SCHEDULE-11-PERSISTENT-BREACH | missing_document | proposed | proposed relationship | VOL-V:39.1 | VOL-V-31.4-01; VOL-V:39.3 |  | VOL-V:39.1 p4: “being the events listed in Schedule 11”; VOL-V:31.4 p3: “on a second occurrence, to terminate under Clause 39.3”; VOL-V:39.3 p4: “The Authority may terminate for persistent breach in the circumstances described in Clause 31.4.” | 31.4 and 39.3 give a termination right for persistent breach; 39.1 gives one for the Events of Default in Schedule 11, which is not supplied. The documents do not say whether persistent breach is also listed there: that it may be is the curator's inference. |  | Volume V Schedule 11 (Project Company Events of Default) | whether persistent breach (three or more Unavailability Events in a rolling 90 days) is also an Event of Default listed in Schedule 11, giving a termination right under 39.1 independent of 31.4 and 39.3; so an amendment or deletion of 31.4 or 39.3 cannot be concluded to remove that exposure | I-VOL-V-MISSING; I-VOL-V-PERSISTENT-BREACH | curator | proposed
REL-MISSING-SCHEDULE-7-DEDUCTIONS | missing_document | confirmed | confirmed dependency | VOL-V:31.2 | VOL-V-31.1-01; VOL-V-31.1-02; VOL-V-31.1-03 |  | VOL-V:31.2 p3: “the Authority shall deduct from the Availability Payment the amounts calculated under Schedule 7” |  |  | Volume V Schedule 7 (deductions) | the amount of the deduction for each Unavailability Event under 31.1(a), (b) and (c), so the price risk of each | I-VOL-V-MISSING | curator | proposed | ADD-02
REL-MISSING-ENVIRONMENTAL-PERMIT | missing_document | confirmed | confirmed dependency | VOL-II:2.4; VOL-II:T2-4-heading/para1 | VOL-II-2.4-01; VOL-II-T2-4-BOD5; VOL-II-T2-4-COD; VOL-II-T2-4-TSS; VOL-II-T2-4-TN; VOL-II-T2-4-TP; VOL-II-T2-4-Turbidity; VOL-II-T2-4-FaecalColiforms; VOL-II-T2-4-ResidualChlorine; VOL-II-T2-4-pH; VOL-II-T2-4-OilGrease; VOL-II-T2-4-NOTE1 |  | VOL-II:2.4 p2: “Table 2-4 is reproduced overleaf from the Environmental Permit issued for the site”; VOL-II:T2-4-heading/para1 p3: “In the event of any discrepancy between this reproduction and the Environmental Permit, the Environmental Permit shall prevail.”; VOL-II:T2-4/note1 p3: “Where a parameter is not listed above, the limit stated in the Environmental Permit shall apply.” |  | context (not binding): ADD-01:AppB/item-5-effluent-standards p4 'the permit was under review by the regulator and that any change would be issued by Addendum.' (pre-bid minutes; they do not bind the Authority (ADD-01 3.2, p1)) | the Environmental Permit issued for the site | that the reproduced Table 2-4 limits, as amended by the addenda, are the limits that govern (the Permit prevails over the reproduction), and the limit of any parameter not listed (Note 1); Permit compliance is not claimed | I-PERMIT | curator | proposed | ADD-02; ADD-03
REL-AI-001 | depends_on | proposed | proposed relationship | VOL-II:2.1 | VOL-II-7.2-01 |  | VOL-II:7.2 p4: “continuous reliability run of thirty (30) days at not less than 90% of nominal capacity” | VOL-II 7.2 sets the reliability run 'at not less than 90% of nominal capacity'. VOL-II 2.1 states the nominal capacity, which ADD-03/4.1(a) (PROPOSED) changes to 150,000 m³/day. The run threshold therefore follows VOL-II 2.1. | Quoted from the text as amended (not as issued): VOL-II:2.1 p2: 'nominal treatment capacity of 150,000 m³/day' |  |  |  | ai:workflow ADD-03-run-host-20261015T140902Z-ab89 | proposed | ADD-02; ADD-03
REL-AI-002 | depends_on | proposed | proposed relationship | ADD-03-cover-para3-01 | ADD-01-AppA-01 |  | ADD-03:cover/para3 p1: “Bidders shall acknowledge receipt in Form 4-A.”; ADD-01:cover/para3 p1: “Bidders shall acknowledge receipt in Form 4-A.” | The ADD-01, ADD-02 and ADD-03 covers all print 'Bidders shall acknowledge receipt in Form 4-A.' The acknowledgement is made in the field of the Form 4-A reissued by ADD-01 App A, which row ADD-01-AppA-01 holds. |  |  |  | I-F4A-FIELDS | ai:workflow ADD-03-run-host-20261015T140902Z-ab89 | proposed | ADD-01; ADD-03
REL-AI-003 | depends_on | proposed | proposed relationship | VOL-I:11.5+ADD-03 | VOL-I-12.1-01 |  | VOL-I:12.1 p6: “The Authority will notify the successful Bidder as Preferred Bidder.” | New VOL-I 11.6 is how the Authority may 'determine the Preferred Bidder' among close Proposals. VOL-I 12.1 provides 'The Authority will notify the successful Bidder as Preferred Bidder', and the Preferred Bidder Notification starts the VOL-I 12.2 and 12.3 periods and ends the VOL-I 4.2 blackout. | Quoted from the text as amended (not as issued): VOL-I:11.5+ADD-03 p2: 'the Authority may apply such further criteria as it considers appropriate to determine the Preferred Bidder' |  |  |  | ai:workflow ADD-03-run-host-20261015T140902Z-ab89 | proposed | ADD-03
REL-AI-004 | depends_on | proposed | proposed relationship | ADD-03-Q17-01 | VOL-I-10.2-01; VOL-IV-F4F-01; VOL-IV-F4F-02 |  | VOL-I:10.2 p5: “The Bidder shall quote a single Availability Payment expressed in Saudi Riyals per annum, calculated in accordance with the payment mechanism at Volume V Clause 29.”; ADD-03:Q17 p2: “Bidders shall price the Project as amended by this Addendum.” | ADD-03 Q17 instructs 'Bidders shall price the Project as amended by this Addendum.' in answer to a question on the Availability Payment; the Availability Payment is quoted under VOL-I 10.2 ('The Bidder shall quote a single Availability Payment expressed in Saudi Riyals per annum') on Form 4-F, which confirms it is 'derived from the Financial Model submitted with this Form'. |  |  |  | I-ADD03-Q17-AP-CAPACITY | ai:workflow ADD-03-run-host-20261015T140902Z-ab89 | proposed | ADD-03
REL-AI-005 | limit_applies | proposed | proposed relationship | VOL-I-9.2-01 | ADD-03-3.2-01 |  | ADD-03:3.2 p1: “shall be addressed in the Technical Proposal narrative.” | ADD-03 3.2 places the Volume II Section 6 content 'in the Technical Proposal narrative'; VOL-I 9.2 limits that narrative to one hundred and fifty (150) pages of A4 and removes excess pages before evaluation. | Quoted from the text as amended (not as issued): VOL-I:9.2 p5: 'The Technical Proposal narrative shall not exceed one hundred and fifty (150) pages of A4, excluding the Form Sheets an…' |  |  |  | ai:workflow ADD-03-run-host-20261015T140902Z-ab89 | proposed | ADD-01; ADD-02
REL-AI-006 | depends_on | proposed | proposed relationship | ADD-03:cover/para3 | form-4a-prep |  | ADD-03:cover/para3 p1: “Bidders shall acknowledge receipt in Form 4-A.” | ADD-03:cover/para3 states 'Bidders shall acknowledge receipt in Form 4-A.' Activity form-4a-prep prepares the 'Addenda acknowledged (numbers):' field of the reissued Form 4-A, which must now include ADD-03. |  |  |  | I-F4A-FIELDS | ai:workflow ADD-03-run-host-20261015T140902Z-ab89 | proposed | ADD-03
REL-AI-007 | depends_on | proposed | proposed relationship | VOL-II-7.2-01 | VOL-II:2.1 |  | VOL-II:7.2 p4: “at not less than 90% of nominal capacity” | VOL-II 7.2 requires the reliability run 'at not less than 90% of nominal capacity'. VOL-II 2.1 sets the nominal treatment capacity, now 150,000 m³/day under op ADD-03/4.1(a). The run load therefore follows VOL-II 2.1. | Quoted from the text as amended (not as issued): VOL-II:2.1 p2: 'nominal treatment capacity of 150,000 m³/day average daily flow' |  |  |  | ai:workflow ADD-03-run-host-20261015T140902Z-ab89 | proposed | ADD-02; ADD-03
REL-AI-008 | depends_on | proposed | proposed relationship | VOL-II-2.3-01 | VOL-II:2.1 |  | VOL-II:2.3 p2: “a future expansion of 50% of nominal capacity” | VOL-II 2.3 requires space for 'a future expansion of 50% of nominal capacity'. VOL-II 2.1 sets the nominal treatment capacity, now 150,000 m³/day under op ADD-03/4.1(a). | Quoted from the text as amended (not as issued): VOL-II:2.1 p2: 'nominal treatment capacity of 150,000 m³/day average daily flow' |  |  |  | ai:workflow ADD-03-run-host-20261015T140902Z-ab89 | proposed
REL-AI-009 | depends_on | possible | possible impact | ADD-03:2.2 | CLARIFICATION-CUTOFF; BID-BOND-VALIDITY; PROPOSAL-VALIDITY; REFERENCE-LOOKBACK |  | ADD-03:2.2 p1: “Every period calculated by reference to the Proposal Due Date is adjusted accordingly.”; VOL-I:7.1 p4: “one hundred and fifty (150) days from the Proposal Due Date” | CONDITIONAL on disposition ADD-03/2.2-disp (unresolved) and issue ADD-03/2.2-issue (proposed). If ADD-03:2.2 is read as adjusting the periods ADD-01:2.2 listed (Reading A), or every PDD-referenced period (Reading B), these four date rules would be among them: each is worded by reference to the Proposal Due Date (VOL-I 5.2, 6.3, 7.1, 8.5 footnote 12). Not a confirmed link; a person decides. | CONDITIONAL on 2. AMENDMENT TO THE PROPOSAL DUE DATE (a change not applied): Quoted from the text as amended (not as issued): VOL-I:6.3 p3: 'valid for two hundred and ten (210) days from the Proposal Due Date' |  |  |  | ai:workflow ADD-03-run-host-20261015T140902Z-ab89 | proposed | ADD-03
REL-AI-010 | depends_on | possible | possible impact | ADD-03:6.1 | VOL-I-11.2-01 |  | ADD-03:6.1 p1: “Where, on completion of the combined evaluation, two or more Proposals are within two per cent (2%) of one another”; VOL-I:11.2 p5: “ranked on a combined score” | The new Clause 11.6 applies 'on completion of the combined evaluation', and VOL-I:11.2 states that Proposals 'will be ranked on a combined score'. The tie-break band therefore operates on the result of the evaluation in row VOL-I-11.2-01. | CONDITIONAL on 6. NEW VOLUME I CLAUSE 11.6 (a change not applied): CONDITIONAL on proposed issue ISS-ADD03-6.1 (basis of the 2% band). This is a possible link only, never confirmed. Which reading applies is a person's decision. |  |  | I-ADD03-11-6-BAND-COND | ai:workflow ADD-03-run-host-20261015T140902Z-ab89 | proposed | ADD-03
REL-AI-011 | depends_on | possible | possible impact | ADD-03:Q17 | VOL-I-10.2-01 |  | ADD-03:Q17 p2: “Bidders shall price the Project as amended by this Addendum.”; VOL-I:10.2 p5: “The Bidder shall quote a single Availability Payment expressed in Saudi Riyals per annum” | The Q17 question concerns 'the Availability Payment', and VOL-I:10.2 requires the Bidder to 'quote a single Availability Payment'. The response 'Bidders shall price the Project as amended by this Addendum.' governs what that quote prices. | CONDITIONAL on 8. RESPONSES TO CLARIFICATION REQUESTS 15 TO 18 (a change not applied): CONDITIONAL on proposed issue ADD-03/Q17-issue (reading A or B is a person's decision). This is a possible link only. |  |  | I-ADD03-Q17-PRICING-COND | ai:workflow ADD-03-run-host-20261015T140902Z-ab89 | proposed | ADD-03

## Stages
Stage | Addendum | Issued | Status | Ops | Invalid ops | Ops review | Provisions | Unresolved | Validated
BASE |  |  | BASE | 0 | 0 |  | 0 | 0 | TRUE
ADD-01 | ADD-01 | 2026-10-08 | APPLIED | 15 | 0 | accepted 15 | 36 | 0 | TRUE
ADD-02 | ADD-02 | 2026-10-22 | APPLIED | 23 | 0 | accepted 23 | 40 | 0 | TRUE
ADD-03 | ADD-03 | 2026-11-08 | PARTIAL | 13 | 0 | accepted 13 | 19 | 2 | FALSE

## Candidate statuses
Candidate status | Rows | Meaning
PROPOSED BY THE AI WORKFLOW | 0 | a new row or a reading re-made at ADD-03 by this run, validated by the controller; a person decides it (accept / reject)
UNRESOLVED | 5 | STALE at ADD-03 with no re-made reading, or (value in question) citing a unit an unresolved provision of ADD-03 names: the value shown may be superseded by that provision, which is named with its reason (never 'not changed by this run')
DECIDED | 205 | a named person's decision in the copied decisions file (none means nobody has decided yet)
proposed (existing row) | 0 | an existing row this run did not change; not reviewed